## Sheet1
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MS_ACCEPTED_WITH_EXCLUSION | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details remarks | Resposibility |  | Opening RFAI | CTA | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
DEL | FY20_21 | Q1 | Pratap Vihar, Khora Colony | Kh. No. 250, Pratap Vihar, Khora Colony, Ghaziabad U.P-201309 | 18046 | 18046 | 18046 | 18046 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | GTL | DEL/RTT/K/20149 | EXISTING | SHARING | RTT | 12 | 15 | 40/150/240/320 | SHARING |  | 3RD_PARTY | YES | >18HRS | No | 28.6215 | 77.3439 | 18046 | 2018-03-10 | 2018-03-17 | 2018-03-20 | 11109.MGBD.1843294 | 2018-07-11 | 2020-03-18 | 2018-07-12 | 2021-06-22 |  |  | 2018-07-06 | 2021-06-22 | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-06-24 |  |  |  | 2018-03-23 | 2018593523 | 2018593523 |  |  | 2018-03-28 | P/FVC/DEL/4751855/2018 | 2021-06-24 | 2021-06-25 | DL/04/5087/0053/0031/03/01/10037/NS/25062021 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-27 | 2021-06-25 | 2021-06-30 | 2021-07-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 672 | [5 empty] | 2018-07-12 | 2021-06-22 | [10 empty] | 404-10-618046-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+L_2100) RRU 2279 TD RRU 4418
DEL | FY20_21 | Q1 | Ajnara Homes | Ajnara Homes AppartmentTower K, Sec-16B Grather Noida UP-201009(K Block Flat No-K-2102,2105) | 17747 | 17747 | 17747 | 17747 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | NI_17747_Del | NEW | NEW_BUILT | RTP | 6 | 67 | 0/130/200/270/350 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.608 | 77.4467 | 17747 | 2019-05-27 | 2019-06-06 | 2019-06-07 | 11109.MNOI.1919126 | 2019-07-26 | 2020-03-02 | 2020-03-03 |  |  |  | 2019-07-28 | [8 empty] | 2019-10-22 | 2019665366 | 2019665366 |  |  | 2020-04-24 | P/FVC/DEL/5909925/2019 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Hold by Prince discussed on 12.04.22 | 3rd Party PRI | PRI_Without Material |  | PRI | TVI |  | M1 | 11653 | [5 empty] | 2019-07-27 |  | TOCO Issue//FMS Box required for BBU to RRU connection | [14 empty] | Hold by Prince discussed on 12.04.22 | 3rd Party PRI | 2G+FD+TD_Ericsson | 2G+FD(RRU 2219),TDD RRU 4412
DEL | FY20_21 | Q1 | MUSTAFABAD | 451,D-Block,Gali No-3, Nehru Vihar, Near Kuba Masjid, Mustafabad, Delhi-94 | 10987 | 10987 | 10987 | 10987 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_10987_DEL | Relocation | NEW_BUILT | RTP | 6 | 12 | Existing_3 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.7113 | 77.2683 | 10987 | 2015-01-09 | 2015-01-22 | 2015-01-25 | 111.MDIL.1392587 | 2017-05-02 | 2017-11-08 | 2017-05-03 | 2017-11-08 |  |  | 2017-05-04 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-11 | 2017-11-12 |  |  |  | 2016-04-13 | 2016584240 | 2016584240 |  | 2017-05-16 | 2019-05-28 | P/FBW/DEL/5623624/2019 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Owner/Legal Issue | Airtel | PRI_With Material |  |  | Indus |  | M1 | 611 | [5 empty] | 2017-05-03 |  | Owner Issue | [14 empty] | Owner/Legal Issue | Airtel | 2G+FD+TD_Ericsson | 2G+FD(RRU 2219),TDD RRU 4412
DEL | FY20_21 | Q1 | Mukherji Park(Relocation of 2908) | H. No-72-73, Chowkhandi, Tilak Nagar, New Delhi-110018 | 16844 | 16844 | 16844 | 16844 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1363150 | Relocation | NEW_BUILT | RTP | 9 | 13 | 60/180/350 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6466 | 77.0952 | R/NN-336545 | 2019-05-09 | 2019-06-24 | 2019-06-28 | 111.MDEL.1930829 | 2019-08-27 | 2019-08-28 | 2019-08-28 | 2021-12-20 |  |  | 2019-08-22 | 2021-12-21 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2021-12-23 |  |  |  | 2019-07-02 | 2019800302 | 2019800302 |  |  | 2019-07-25 | P/FVC/BBY/5736878/2019 | 2021-12-23 | 2021-12-24 | DL/01/5177/06474/0031/06/05/12865/NS/24122021 | 2021-12-24 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-04 | 2021-12-27 | 2022-01-04 | 2021-12-27 | 2022-01-10 | 2022-01-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4000 | [5 empty] | 2019-08-28 | 2021-12-23 | Material return on 15.10.20,Issue closed on 07.12.21 but Survey Rejected; 03M height deviation, Mains supply not available as on 07.12.21,Material Delivery Plan on 14.12.21 & Farend 4000 SR required,Issue closed on 20.12.21,Partial Installed-Power Issue as on 22.12.21,Issue closed on 23.12.21 | [9 empty] | 404-10-616844-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G+FD(RRU 2219),L_2100 (RRUS12B1) Available on parent Site,TDD RRU 4412,
DEL | FY20_21 | Q1 | Indirapuram Ghaziabad | GBM Location Near ATS Advantage Gate No-2,Indrapuram Gaziabad-201010 | 18023 | 18023 | 18023 | 18023 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1362318 | NEW | NEW_BUILT | GBM | 25 | 0 | 60/200/320 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.639 | 77.3654 | R/NN-334482 | 2019-04-27 | 2019-07-04 | 2019-07-23 | 11109.MGBD.1996344 | 2019-12-16 | 2021-07-06 | 2019-12-16 | 2021-07-06 |  |  | 2019-12-11 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-10 |  |  |  | 2019-07-31 | 2019843326 | 2019843326 |  |  | 2019-08-29 | P/FVC/DEL/5795842/2019 | 2021-07-10 | 2021-07-11 | DL/04/5177/0768/0031/04/01/00467/NS/11072021 | 2021-07-11 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-14 | 2021-07-12 | 2021-07-17 | 2021-07-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Airtel |  | M1 | 7147 | [5 empty] | 2019-12-16 | 2021-07-10 | GSM,BBU & GPS Kit Installed at site & Rest Material return from site,L2100 plates fixtures required according to L2100 RRU & fiber port is not up,Smart Pole Sites Issue resolved on 10.07.21 | [9 empty] | 404-10-918023-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+FD+TD+L2100 | 2G+FD RRU 2219 ,L_2100 RRUS 12B1, TD RRU 4418
DEL | FY20_21 | Q1 | Mahavir Nagar 1(Relocation of 7631) | Sri Gurudwara Singh Sabha, New Mahavir Nagar, New Delhi-110018 | 18167 | 18167 | 18167 | 18167 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1359616 | Relocation | NEW_BUILT | RTT | 15 | 7 | 0/120/250 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.6338 | 77.0839 | R/NN-325893 | 2019-03-12 | 2019-08-12 | 2019-09-04 | 111.MDEL.2019437 | 2020-01-28 | 2020-06-08 | 2020-01-29 | 2020-06-08 |  |  | 2020-01-30 | 2020-06-15 | 2020-06-16 | [6 empty] | 2019-09-18 | 2019613586 | 2019613586 |  |  | 2019-10-07 | P/FVC/DEL/5832682/2019 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 17.06.20 | Indus | PRI_Without Material |  |  | Indus |  | M1 | 929 | [5 empty] | 2020-01-29 |  | Material return on 17.06.20 | [14 empty] | Material return on 17.06.20 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 TD RRUS 4418
DEL | FY20_21 | Q1 | SSP hospital | SSP hospital | 25930 | 25930 | 25930 | 25930 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | SPACE_TELELINK | STIPL/DEL/045 | NEW | NEW_BUILT | IBS | 0 | 10 | IBS | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | No | 28.5764 | 77.3381 | 25930 | 2017-10-24 | 2017-11-13 | 2017-11-13 | 11109.MNOI.1639677 | 2017-12-28 | 2018-06-18 | 2017-12-29 | 2018-06-18 |  |  | 2017-12-30 | 2018-06-19 | 2018-06-20 | [30 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Installation Done_Infra Issue & LOS Blockage Issue(SRN Done_10 Oct 21) | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 769 | [5 empty] | 2017-12-29 |  | Installation Done_Infra Issue | [14 empty] | Installation Done_Infra Issue & LOS Blockage Issue(SRN Done_10 Oct 21) | 3rd Party PRI
DEL | FY20_21 | Q1 | Parsvnath Regalia | Parsvnath Regalia Appartment,Block T3,Lift Room,Near Raj Bagh Metro Raj Bagh sahibabad-201005 | 14422 | 14422 | 14422 | 14422 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NI_14422_Del | NEW | NEW_BUILT | RTP | 6 | 41 | 40/180/270 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.6787 | 77.3482 | 14422 | 2019-06-11 | 2019-12-24 | 2020-01-13 | 11109.MGBD.2041023 | 2020-03-11 | 2020-03-12 |  |  |  |  | 2020-03-13 | 2020-03-17 | 2020-03-18 | [6 empty] | 2020-01-16 | 2020331388 | 2020331388 |  |  | 2020-05-11 | P/FVC/DEL/6030319/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material Return . Nibar | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 4293 | [5 empty] | 2020-03-12 |  | Material Return . Nibar | [14 empty] | Material Return . Nibar | 3rd Party PRI | 2G+FD+TD_Ericsson | 2G RRU 2219 FD RRU 2219 TD RRUS 4412
DEL | FY20_21 | Q1 | Chauganpur, Gr.noida(Relocation of 7946) | Khasra NO-81,Plot NO-40,Chauganpur, Knowledge Park V, Greater Noida, Uttar Pradesh 201306 | 19891 | 19891 | 19891 | 19891 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3125491 | Relocation | NEW_BUILT | GBM | 30 | 0 | 40/140/210/290 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.5531 | 77.4645 | R/NN-647660 | 2019-11-19 | 2020-02-15 | 2020-02-17 | 11109.MNOI.2006748 | 2020-03-18 | 2020-03-18 |  |  |  |  | 2020-03-20 | 2020-03-20 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-06-17 |  |  |  | 2020-02-06 | 2020360470 | 2020360470 |  |  | 2020-03-04 | P/FVC/DEL/5984359/2020 | 2020-06-17 | 2020-06-18 | DL/03/0031/0276/0031/03/01/09211/NS/18062020 | 2020-06-18 | 2020-06-18 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-30 | 2022-03-26 | 2022-03-31 | 2022-03-26 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-25 |  | Indus |  | M0 | 4112 | [5 empty] | 2020-03-24 | 2022-03-25 | Integrated_Power Issue | [9 empty] | 404-10-619891-51 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 L-2100 RRU 12B1 TD RRUS 4412
Del | FY20_21 | Q1 | Shipra Krishna Vista | GBM Location Near Shipra Gate No-4,Ahinsa Khand-1,Indrapuram Gaziabad UP-201014 | 25001 | 25001 | 25001 | 25001 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1369326 | NEW | NEW_BUILT | GBM | 30 | 0 | 0/160/240 | INDUS_30M_GBT_OD_2T |  | LAST_AOP_SO | YES | >18HRS | No | 28.6397 | 77.3756 | R/NN-365792 | 2019-08-28 | 2019-09-20 | 2019-09-25 | 11109.MGBD.2067702 | 2020-06-18 | 2020-07-09 | 2020-06-19 | 2021-04-19 |  |  | 2020-06-13 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-08-05 |  |  |  | 2019-11-28 | 2019402529 | 2019402529 |  |  | 2020-05-30 | P/FVC/DEL/6074069/2020 | 2021-08-05 | 2021-08-06 | DL/04/5177/0770/0031/04/01/00473/NS/06082021 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-11 | 2021-08-06 | 2021-08-11 | 2021-08-06 | 2021-08-12 | 2021-08-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 813 | [5 empty] | 2020-06-19 | 2021-08-05 | Partially Installed_GSM & Jumper return due to Mount and Space Issue for Installation,Partially Material Requested for Media testing only/ Locator Issue for dispatch(1024337)_BBU Delivered for Media testing_Crane Planned on 5th Aug 21 | [9 empty] | 404-10-925001-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+FD+TD+L2100 | 2G+FD RRU 2219 ,L_2100 RRUS 12B1, TD RRU 4418
Del | FY20_21 | Q1 | Pahari wala Gurudwara(Relocation of 5003) | Smart Pole Location opp Pahari wala Gurudwara Medical store,Block B, Kailash Colony, Greater Kailash 1, New Delhi,110048 | 10816 | 10816 | 10816 | 10816 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1370705 | Relocation | NEW_BUILT | GBM | 21 | 0 | 0/130/270 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.5514 | 77.2385 | R/NN-364991 | 2019-08-23 07:31 | 2019-10-16 | 2019-10-23 | 111.MDEL.2072087 | 2020-06-29 | 2020-08-20 | 2020-06-30 | 2021-04-19 |  |  | 2020-06-27 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-07-24 |  |  |  | 2019-11-28 | 2019402522 | 2019402522 |  |  | 2020-05-30 | P/FVC/DEL/6074062/2020 | 2021-07-24 | 2021-07-25 | DL/01/5177/6314/0031/45/04/00964/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-08-03 | 2021-08-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 631 | [5 empty] | 2020-06-30 | 2021-07-27 | Partially Material Delivered/ HOLD By Indus due to MW Mount issue,SCFT & EMF Done_On Air Pending due to Power Issue resolved on 27.07.21 | [9 empty] | 404-10-910816-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+FD+TD+L2100 | 2G+FD RRU 2219 ,L_2100 RRUS 12B1, TD RRU 4418
DEL | FY20_21 | Q1 | US embassy network | Chatisgarh Bhawan, Chanakya Puri,In front of 2 Nyaya marg near Deutsche Schule New Delhi-110021 | 19325 | 19325 | 19325 | 19325 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | RJIO | I-DL-XXXX-COW-0059 | EXISTING | SHARING | Cow | 30 | 0 | 10, 140, 270 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.5994 | 77.1879 | 19325 | 2020-05-15 | 2020-06-20 | 2020-06-23 | 111.MDEL.2083057 | 2020-07-16 | 2020-07-17 | 2020-07-17 | 2020-09-16 |  |  | 2020-07-18 | 2020-09-16 | 2020-09-17 | [6 empty] | 2021-01-08 | ST202101005367 | S20210000384 |  |  | 2021-01-16 | P/FVC/DEL/1016292/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | One Sector GSM Mount Issue & BEE Issue_SRN Done as Per Kishore on 19.09.20 | 3rd Party PRI | PRI_Without Material |  |  | Indus |  | M1 | 10288 | [5 empty] | 2020-07-17 |  | One Sector GSM Mount Issue & BEE Issue_SRN Done as Per Kishore on 19.09.20 | [14 empty] | One Sector GSM Mount Issue & BEE Issue_SRN Done as Per Kishore on 19.09.20 | 3rd Party PRI | 2G+FD+TD_Ericsson | 2G RRU 2219 FD RRU 2219 TD RRUS 4418
Del | FY20_21 | Q1 | Amarpali Royal | GBM Location Vaibhav Park Roundabout Near amarpali Appartment Vaibhav Khand Indrapuram Gaziabad Uttar Pradesh-201010 | 25047 | 25047 | 25047 | 25047 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1362317 | NEW | NEW_BUILT | GBM | 30 | 0 | 0/120/240 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6375 | 77.3642 | R/NN-334480 | 2019-04-27 | 2019-05-04 | 2019-07-03 | 11109.MGBD.2087372 | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2021-07-21 |  |  | 2020-08-02 | 2021-07-21 | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-23 |  |  |  | 2020-08-12 | ST202008042488 | S20200002870 |  |  | 2020-08-20 | P/FVC/DEL/1004094/2020 | 2021-07-23 | 2021-07-24 | DL/04/5177/0769/0031/45/04/00963/NS/24072021 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-26 | 2021-07-24 | 2021-07-29 | 2021-07-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2020-08-07 | 2021-07-21 | Partially Material Requested for Media testing Ok/ Locator Issue for dispatch(1024282) | [9 empty] | 404-10-925047-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+FD+TD+L2100 | 2G+FD RRU 2219 ,L_2100 RRUS 12B1, TD RRU 4418
Del | FY20_21 | Q1 | Qutabplaza(Relocation of 5063) | Shahtoot_Marg, In front Of Silver Oaks Apartments,DLF Phase- I,Sector 26,Gurgaon Faridabad Road Gurgaon haryana-122002 | 17322 | 17322 | 17322 | 17322 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1369730 | Relocation | SHARING | GBM | 24 | 0 | 50/190/280 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.471 | 77.1039 | R/RES-426195 | 2020-06-11 | 2020-08-13 | 2020-08-18 | 11106.MGGN.2108817 | 2020-09-03 | 2020-09-04 | 2020-09-04 | 2021-04-19 |  |  | 2020-08-29 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-07-25 |  |  |  | 2020-08-21 | ST202008049421 | S20200003305 |  |  | 2020-08-27 | P/FVC/DEL/1004486/2020 | 2021-07-25 | 2021-07-25 | DL/05/5177/5288/0031/45/04/00965/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-26 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 325 | [5 empty] | 2020-09-04 | 2021-07-24 | Partially Installed_GSM & RRU Installation Pending at site_due to Mount and Space Issue for Installation,Partially Material Delivered/ FMS fiber cut at site & Access issue at far end for media patching | [9 empty] | 404-10-917322-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+FD+TD+L2100 | 2G+FD RRU 2219 ,L_2100 RRUS 12B1, TD RRU 4418
DEL | FY20_21 | Q1 | Jaitpur Ext,Badarpur | H No.- 178, Village Jaitpur, Near Bhagat Singh Chowk, Badarpur, New Delhi- 110044 | 18066 | 18066 | 18066 | 18066 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL021 | New | New_Built | RTP | 10 | 13 | 130/210/280 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.507 | 77.3285 | 18066 | 2019-03-26 | 2020-09-29 | 2020-10-04 | 111.MDEL.1994074 | 2020-10-26 | 2020-10-27 | 2020-10-27 | 2021-02-22 |  |  | 2020-10-28 | 2021-03-02 | 2021-03-03 | [6 empty] | 2020-10-07 | ST202010100603 | S20200005780 |  |  | 2020-10-17 | P/FVC/DEL/1008937/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | SRN Done_23.03.21 | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 842 | [5 empty] | 2020-10-27 |  | SRN Done_23.03.21 | [14 empty] | SRN Done_23.03.21 | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+L-2100) RRU 2279 TD RRUS 4418
DEL | FY20_21 | Q1 | NOD_Gulshan Homz | Logix Blossom County, Sector 137, Noida-201305 | 15853 | 15853 | 15853 | 15853 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1386522 | New | New_Built | Cow | 30 | 0 | 0/170/270 | COW |  |  | YES | >18HRS | No | 28.5099 | 77.4085 | R/NN-457814 | 2020-06-29 | 2020-08-07 | 2020-09-03 | 11109.MNOI.2140720 | 2020-10-26 | 2020-10-27 | 2020-10-27 | 2021-09-23 |  |  | 2020-10-21 | 2021-09-24 | 2021-09-26 | 2021-09-27 | 2021-09-27 | 2021-09-29 |  |  |  | 2021-03-13 | ST202103089551 | S20210004658 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033717/2021 | 2021-10-08 | 2021-10-08 | DL/03/5177/0909/0031/03/01/10199/NS/07102021 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-13 | 2021-10-08 | 2021-10-13 | 2021-10-08 | 2021-10-13 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 23687 | [5 empty] | 2020-10-27 | 2021-10-07 | Farend Not Feasible_23687(Non Indus),Issue closed on 9 Sep 21,Survey Rejected; MBTS has been dismantled and to be erected again as on 10 Sep 21,Issue Closed on 23 Sep 21,Locator Inactive Issue resolved on 24 Sep 21,GSM Mount required_Infra Not ready Issue closed on 28 Sep 21,Installed BBU Faulty on 29 Sep 21,SACFA Issue resolved on 7th Oct 21. | [9 empty] | 404-10-615853-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 L-2100 RRU 2219 TD RRUS 4418
Del | FY20_21 | Q2 | PATEL NAGAR GURGAON 6282 | Hno. 1100/5,Gali no. 13,Patel Nagar, Gurugram, Haryana 122001 | 19633 | 19633 | 19633 | 19633 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/AT/8122 | New | New_Built | RTT | 12 | 13 | 60/130/280 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | No | 28.4626 | 77.0382 | T19DL06078 | 2019-07-18 | 2019-07-28 | 2019-07-31 | 11106.MGGN.2154344 | 2020-11-15 | 2020-11-17 | 2020-11-17 | 2021-05-31 |  |  | 2020-11-13 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-02 | 2021-06-02 |  |  |  | 2019-08-08 | 2019851336 | 2019851336 |  |  | 2019-09-05 | P/FBC/DEL/5806177/2019 | 2021-06-02 | 2021-06-03 | DL/05/5126/0283/0031/03/01/10022/NS/03062021 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-04 | 2021-06-03 | 2021-06-05 | 2021-06-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4035 | [5 empty] | 2020-11-17 | 2021-05-31 | [10 empty] | 404-10-619633-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+L-2100) RRU 2279, TD RRUS 4418
Del | FY20_21 | Q1 | Village Tilpat | Hno.664,Near Nihal singh Farm,Amar nagar,Village Tilpat, Faridabad, Haryana 121003 | 20309 | 20309 | 20309 | 20309 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20309_DEL | New | New_Built | GBM | 30 | 0 | 0/80/240 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.463 | 77.3267 | 20309 | 2019-10-09 | 2020-11-12 | 2020-11-20 | 11106.MFAR.2002373 | 2020-11-20 | 2020-11-20 |  |  |  |  | 2020-11-21 | 2020-11-21 | 2020-11-25 | 2020-11-26 | 2020-11-26 | 2021-03-25 |  |  |  | 2020-01-30 | 2020349045 | 2020349045 |  |  | 2020-04-28 | P/FVC/DEL/6011026/2020 | 2021-03-26 | 2021-03-27 | DL/02/0031/0185/0031/345/04/08191/NS/27032021 | 2021-03-27 | 2021-03-27 | 2021-03-27 | 2021-03-27 | 2021-03-27 | 2021-03-28 | 2021-03-28 | 2021-03-29 | 2021-03-27 | 2021-03-31 | 2021-04-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 539 | [5 empty] | 2020-11-27 | 2021-03-25 | [10 empty] | 404-10-620309-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 L-2100 RRU 2219 TD RRUS 4418
Del | FY20_21 | Q3 | Brij Puri, New Mustafabad | House No.-C-427,Gali No.10,KH-1,Karawal Naagar,BrijPuri,Chand Bagh, Delhi-110094 | 21119 | 21119 | 21119 | 21119 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1432986 | New | New_Built | RTP | 9 | 14 | 0/120/240 | INDUS_LITE+ |  | LAST_AOP_SO | YES | >18HRS | No | 28.7066 | 77.2709 | R/NN-469477 | 2020-10-02 | 2020-10-14 | 2020-10-14 | 111.MDEL.2146041 | 2020-11-15 | 2021-07-05 | 2020-11-16 | 2021-07-05 |  |  | 2020-11-05 | 2021-07-05 | 2021-07-05 | 2021-07-06 | 2021-07-06 | 2021-07-07 |  |  |  | 2020-10-21 | ST202010117280 | S20200006523 |  |  | 2020-12-06 | P/FVC/DEL/1011035/2020 | 2021-07-08 | 2021-07-09 | DL/01/5177/6304/0031/03/01/10052/NS/09072021 | 2021-07-09 | 2021-07-10 | 2021-07-10 | 2021-07-10 | 2021-07-10 | 2021-07-10 | 2021-07-10 | 2021-07-12 | 2021-07-10 | 2021-07-15 | 2021-07-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8158 | [5 empty] | 2020-11-16 | 2021-07-05 | [10 empty] | 404-10-621119-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+L-2100) RRU 2279, TD RRUS 4418
Del | FY20_21 | Q2 | Model Town | House No-16,Block F-14,Model Town PH 2 Delhi-110009 | 23546 | 23546 | 23546 | 23546 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Alice | AT-DL-0014 | New | New_Built | RTP | 10 | 12 | 100/210/280 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.706 | 77.1905 | 23546 | 2020-09-02 | 2020-09-05 | 2020-09-11 | 111.MDIL.1559861 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-12 |  |  | 2020-12-03 | 2020-12-12 | 2020-12-13 | [6 empty] | 2020-09-17 | ST202009071397 | S20200004684 |  |  | 2020-09-22 | P/FVC/DEL/1006363/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Police Issue_SRN Done | 3rd Party PRI | PRI_Without Material |  |  | Indus |  | M1 | 4272 | [5 empty] | 2020-12-01 |  | Police Issue_SRN Done | [14 empty] | Police Issue_SRN Done | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRUS 4418
Del | FY20_21 | Q1 | DDA_Vasant Kunj | FRONT OF DESIGN MEDIATECH PVT LTD.,VASANT KUNJ MARG,BEHIND NOBLE HOUSE, LEVEL 1, CSC-6, POCKET 8, SECTOR C, VASANT KUNJ, NEW DELHI-110070 | 2924 | 2924 | 2924 | 2924 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1705613 | New | New_Built | GBM | 18 | 0 | 40/100/340 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.5352 | 77.1412 | R/NN-564553 | 2020-12-03 | 2020-12-17 | 2020-12-24 | 111.MDEL.52771411 | 2020-12-29 | 2020-12-30 | 2021-08-13 | 2021-08-13 |  |  | 2020-12-24 | 2021-08-14 | 2021-08-16 | 2021-08-17 | 2021-08-17 | 2021-08-19 |  |  |  | 2021-02-05 | ST202102039757 | S20210002332 |  |  | 2021-02-28 | P/FVC/DEL/1018780/2021 | 2021-08-20 | 2021-08-23 | DL/01/5177/6334/0031/03/01/10117/NS/23082021 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-24 | 2021-08-23 | 2021-08-24 | 2021-08-23 | 2021-08-31 | 2021-08-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 13094 | [5 empty] | 2020-12-30 | 2021-08-19 | Material return on 20.03.21,Clearance received on 7th Aug 21,1st sector and 2nd sectors pole mounts are not free for GSM installation,Issue closed on 13 Aug, 21,Partially Installed_Farend MW Mount required,MW Material short & Power Issue on 17th Aug 21 and resolved on 19 Aug 21 | [9 empty] | 404-10-602924-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 L-2100 RRU 2219 TD RRUS 4418
Del | FY20_21 | Q2 | Dhanwapur | Hno-121A,Khewat/Khata No. 231/285, Musktil/Khasra No. 30, Village Dhanwanpur, Tehsil and District Gurgaon-122006 | 21065 | 21065 | 21065 | 21065 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1466849 | New | New_Built | RTM | 11 | 12 | 90/180/320 | INDUS_LITE+ |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.4785 | 76.996 | R/NN-497373 | 2020-10-23 | 2020-10-27 | 2020-10-29 | 11106.MGGN.84769960 | 2020-12-29 | 2020-12-30 | 2020-12-30 | 2021-06-28 |  |  | 2020-12-03 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-06-30 | 2021-07-01 |  |  |  | 2020-11-04 | ST202011134636 | S20200007565 |  |  | 2020-12-13 | P/FVC/DEL/1012175/2020 | 2021-07-02 | 2021-07-02 | DL/05/5177/5276/0031/03/01/10045/NS/02072021 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-05 | 2021-07-03 | 2021-07-08 | 2021-07-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4665 | [5 empty] | 2020-12-30 | 2021-06-28 | [10 empty] | 404-10-621065-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+L-2100) RRU 2279 TD RRUS 4418
DEL | FY20_21 | Q3 | RAGHUBIR NAGAR | Hno.520,raghubir nagar near gurudwara road delhi-110027 | 21021 | 21021 | 21021 | 21021 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1403396 | New | New_Built | RTP | 9 | 17 | 70/180/270 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.6593 | 77.1123 | R/NN-467095 | 2020-09-21 | 2020-10-21 | 2020-11-26 | 111.MDEL.2184032 | 2020-12-28 | 2020-12-29 | 2020-12-29 |  |  |  | 2020-12-30 | [8 empty] | 2020-12-04 | ST202012165289 | S20200009127 |  |  | 2020-12-25 | P/FVC/DEL/1013611/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Owner Issue For SRN | Indus | PRI_Without Material |  | PRI | Non INDUS |  | M1 | 4070 | [5 empty] | 2020-12-29 |  | Owner Issue(SRN Done),Owner Issue for Survey | [14 empty] | Owner Issue For SRN | Indus | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4412
Del | FY20_21 | Q1 | F-Block,Malviya Nagar(Relocation of 11939) | Hno.268 MI/1, Haus Rani,near by malviya nagar metro New Delhi-110017 | 20979 | 20979 | 20979 | 20979 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | ID-1001742 | Relocation | Sharing | RTP | 6 | 16 | 0/80/180 | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | No | 28.5283 | 77.2074 | SR/SH/39454 | 2021-12-06 | 2020-11-07 | 2020-11-07 | 111.MDEL.2168605 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-07-28 |  |  | 2021-01-21 | 2021-08-03 | 2021-08-05 | [6 empty] | 2020-11-12 | ST202011145367 | S20200008117 |  |  | 2020-12-25 | P/FVC/DEL/1013818/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Public Issue_Plan for SRN & SRN Done on 08.04.22 by ATC Team | ATC | PRI_Without Material |  |  | Indus |  | M1 | 10667 | [5 empty] | 2021-01-19 |  | Material dispatch Plan on Night & Work on Morning(05:00 AM to 08:00 AM)_Approval Pending With Ritesh,MW Hardware MINI-LINK 6366 Outdoor Unit Not in Stock(25th July to 30th July 21),Material Delivered on 6th Aug 21,Hold By Sandeep,Near End - Public Issue & Far end Installed as on 15.03.22,Public Issue_Dropped/Material to be SRN as on 23.03.22 | [14 empty] | Public Issue_Plan for SRN | ATC | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 14B3 L_2100 RRU 12B1,Available On Parent Site TD RRUS 4418(New Required)
Del | FY20_21 | Q1 | Behrampur (relocation of 15017) | House No.5, Street No.B-26,Budha Bazar,BehramPur,Sector-63 Noida,Uttar Pradesh-201301 | 21157 | 21157 | 21157 | 21157 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/NO/AT/8662 | Relocation | New_Built | RTP | 6 | 15.6 | 0/70/170/240 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | No | 28.632 | 77.4018 | T20DL05211 | 2020-10-29 | 2020-11-26 | 2020-11-26 | 11109.MNOI.20774017 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-05-30 |  |  | 2021-01-14 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-01 | 2021-06-01 |  |  |  | 2020-11-30 | ST202011160630 | S20200008886 |  |  | 2020-12-23 | P/FVC/DEL/1013151/2020 | 2021-06-01 | 2021-06-02 | DL/03/5126/0348/0031/06/05/11568/NS/02062021 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-03 | 2021-06-02 | 2021-06-04 | 2021-06-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1313 | [5 empty] | 2021-01-19 | 2021-05-30 | [10 empty] | 404-10-621157-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A FD RRU 2219B3 L-2100 RRU 2219B1,12B1 TD RRUS 4412 available on parent site
Del | FY20_21 | Q3 | Uttam Nagar(Relocation of 1740) | House No. 17, Shyam Park, Village Nawada, New Delhi-110066 | 21230 | 21230 | 21230 | 21230 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1479806 | Relocation | New_Built | RTT | 12 | 10.5 | 90/210/330 | INDUS_LITE+ |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.6245 | 77.0463 | R/NN-522189 | 2020-10-29 | 2020-12-03 | 2020-12-10 | 111.MDEL.44770463 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-07-20 |  |  | 2021-01-06 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-25 |  |  |  | 2020-12-12 | ST202012172414 | S20200009536 |  |  | 2020-12-28 | P/FVC/DEL/1014699/2020 | 2021-07-25 | 2021-07-25 | DL/01/5177/6318/0031/345/04/08365/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 777 | [5 empty] | 2021-01-19 | 2021-07-20 | Parent Site Fiber POP & 30+ Technology running,Nearend MW Commisioned and Farend 777 Access Plan Today`s & Dismantaling WIP on 24.07.21 | [9 empty] | 404-10-621230-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A FD RRU 2219B3 L-2100 RRU 2219B1,TD RRUS 4412 Available on parent site
Del | FY20_21 | Q1 | Sector 3, RK Puram(Relocation of 27351) | Near IIT Bus stand & Poublic Toilet, ,Sector 3, Africa Avenue Road, Near DDA sports Complex, Opp. ITI Hostel, R K Puram,Delhi 110016 | 20695 | 20695 | 20695 | 20695 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1378584 | Relocation | New_Built | Cow | 30 | 0 | 0/160/260 | COW |  |  | YES | >18HRS | No | 28.5518 | 77.1849 | R/NN-395989 | 2020-02-11 | 2020-07-20 | 2020-08-10 | 111.MDEL.17771849 | 2021-01-19 | 2021-07-05 | 2021-01-19 | 2021-07-05 |  |  | 2021-01-14 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-07 | 2021-07-12 |  |  |  | 2020-08-12 | ST202008042357 | S20200002875 |  | 2021-07-22 | 2021-07-17 | P/FVC/DEL/1035689/2021 | 2021-07-22 | 2021-07-23 | DL/01/5177/6247/0031/03/01/10069/NS/23072021 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-24 | 2021-07-23 | 2021-07-28 | 2021-07-23 | 2021-07-29 | 2021-07-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1988 | [5 empty] | 2021-01-19 | 2021-07-22 | 7.07.21 Partially Installed_2G RRU Faulty_12.07.21 Installed SACFA Pending | [9 empty] | 404-10-620695-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A FD RRU 2219B3 L-2100 RRU 2219B1,TD RRUS 4412 Available on parent site
Del | FY20_21 | Q1 | Pusta-2, Soniya vihar (Relocation of 25566) | C 1/26, KH No-176, Sonia Vihar,2-1/2 Pusta,Main Service Road,Sonia vihar,New Delhi-110094 | 20971 | 20971 | 20971 | 20971 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388347 | Relocation | New_Built | RTM | 8 | 15 | 30/140/200 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.723 | 77.2445 | R/NN-464906 | 2020-08-11 | 2020-09-14 | 2020-09-22 | 111.MDEL.2184035 | 2021-01-18 | 2021-01-19 | 2021-01-19 | 2021-07-20 |  |  | 2021-01-16 | 2021-07-20 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-24 |  |  |  | 2020-09-26 | ST202009088916 | S20200005108 |  |  | 2020-10-06 | P/FVC/DEL/1007600/2020 | 2021-07-24 | 2021-07-25 | DL/01/5177/6315/0031/345/04/08361/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-31 | 2021-07-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1605 | [5 empty] | 2021-01-19 | 2021-07-20 | CATs Issue resolved on 12th July 21 againg Hold due to Parent site High Traffic | [9 empty] | 404-10-620971-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A FD RRU 2219B3 L-2100 RRU 2219B1,TD RRUS 4412 Available on parent site
Del | FY20_21 | Q2 | Mianwali Colony | HN. -258-P,Back Side of Ram Mandir and Berside ofApple Garden School, Miawali Colony Gurgaon. 122001 | 16817 | 16817 | 16817 | 16817 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVI | ATHAZGN0784 | New | New_Built | RTP | 9 | 19.5 | 320/130/220 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.4678 | 77.0306 | 16817 | 2019-10-17 | 2020-12-14 | 2020-12-19 | 11106.2846.78770305 | 2021-01-09 | 2021-01-09 | 2021-01-09 | 2021-09-16 |  |  | 2021-01-07 | 2021-09-17 | 2021-09-19 | 2021-09-20 | 2021-09-20 | 2021-09-21 |  |  |  | 2020-12-18 | ST202012177615 | S20200009806 |  |  | 2020-12-29 | P/FVC/DEL/1015002/2020 | 2021-09-21 | 2021-09-22 | DL/05/5113/0110/0031/03/01/10175/NS/22092021 | 2021-09-22 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-24 | 2021-09-23 | 2021-09-25 | 2021-09-23 | 2021-09-25 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4566 | [5 empty] | 2021-01-09 | 2021-09-16 | Survey rejected; AGL deviation issue,Approval received on 16 Sep 21 | [9 empty] | 404-10-616817-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q1 | TILAK NAGAR(Relocation of 4660) | Hno.22/37-A, near choudhary dairy Tilak nagar new delhi-110018 | 16681 | 16681 | 16681 | 16681 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL022 | Relocation | New_Built | RTP | 10 | 13 | 100/250/330 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6379 | 77.0901 | 16681 | 2020-08-27 | 2020-09-12 | 2020-09-12 | 111.MDEL.2154368 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-19 |  |  | 2021-01-28 | 2021-02-19 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-03-25 |  |  |  | 2020-09-17 | ST202009071400 | S20200004684 |  |  | 2020-09-22 | P/FVC/DEL/1006366/2020 | 2021-03-26 | 2021-03-26 | DL/01/0031/2613/0031/03/01/09947/NS/26032021 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-27 | 2021-03-27 | 2021-03-28 | 2021-03-26 | 2021-03-30 | 2021-04-01 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 882 | [5 empty] | 2021-02-02 | 2021-03-25 | [10 empty] | 404-10-616681-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q1 | SDMC_DDA Sarita Vihar | In front of 80 TO 90, near DDA Community Hall, Pocket-K and L, Sarita Vihar, New Delhi-110044 | 13037 | 13037 | 13037 | 13037 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1386207 | New | New_Built | Cow | 25 | 0 | 40/190/280 | COW |  |  | YES | >18HRS | No | 28.5369 | 77.2947 | R/NN-456550 | 2020-06-15 | 2020-10-20 | 2020-10-26 | 111.MDEL.68772947 | 2021-01-09 | 2021-06-25 | 2021-01-09 | 2021-06-25 |  |  | 2020-12-31 | 2021-06-25 | 2021-06-27 | 2021-06-28 | 2021-06-28 | 2021-06-28 |  |  |  | 2020-11-09 | ST202011141278 | S20200007855 |  |  | 2020-12-25 | P/FVC/DEL/1013760/2020 | 2021-06-30 | 2021-07-01 | DL/01/5177/6298/0031/03/01/10044/NS/01072021 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-03 | 2021-07-01 | 2021-07-06 | 2021-07-06 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 70 | [5 empty] | 2021-01-09 | 2021-06-25 | [10 empty] | 404-10-613037-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219, (FD+L_2100) RRU 2279,TD RRU 4418
Del | FY20_21 | Q1 | villege jharoda, mujra burari | KH No - 2/2, Street No 2/3, Sangam Vihar , Landmark Near Hathi Bala, Delhi - 84 | 21246 | 21246 | 21246 | 21246 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1560291 | New | New_Built | RTP | 6 | 16 | 30/130/300 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.7251 | 77.216 | R/NN-560233 | 2020-12-08 | 2020-12-10 | 2020-12-17 | 111.MDEL.51772159 | 2021-01-09 | 2021-06-22 | 2021-01-09 | 2021-06-21 |  |  | 2021-01-03 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-24 | 2021-07-02 |  |  |  | 2021-04-17 | ST202104151767 | S20210007098 |  | 2021-07-19 | 2021-06-09 | P/FVC/DEL/1028595/2021 | 2021-07-19 | 2021-07-20 | DL/01/5177/6309/0031/03/01/10058/NS/20072021 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-22 | 2021-07-20 | 2021-07-24 | 2021-07-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1605 | [5 empty] | 2021-01-09 | 2021-07-19 | SACFA_Pending_Issue resolved on 19.07.21 | [9 empty] | 404-10-621246-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Basantpur new | Khasra No. 165 Mustil No. 12, Killa No. 7(8-0), 8 (7-3), 13/1(1-9) ,Plot of land admeasuring 3 Kanal (1815 Sq. Yards) out of ¼ part of total land admeasuring 16 Kanal 12 Marla comprised insituated at Village Ishmailpur, Basantpur, Tehsil and District Faridabad, Haryana-121009 | 21369 | 21369 | 21369 | 21369 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6699 | New | New_Built | GBM | 30 | 0 | 0/170/270 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.502 | 77.3425 | T20DL05447 | 2020-12-08 | 2020-12-10 | 2021-01-11 | 11106.MDEL.19773425 | 2021-01-22 | 2021-01-23 | 2021-01-23 | 2021-04-13 |  |  | 2021-01-17 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-17 |  |  |  | 2020-12-25 | ST202012183688 | S20200010061 |  |  | 2020-12-30 | P/FVC/DEL/1015151/2020 | 2021-04-17 | 2021-04-18 | DL/02/5126/0047/0031/345/04/08229/NS/18042021 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-18 | 2021-04-22 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 17165 | [5 empty] | 2021-01-23 | 2021-04-13 | [10 empty] | 404-10-621369-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Jheel chowk(Relocation of 15314) | Kh No.94,Scooter Market,Jheel Chowk,Karawal Nagar,Delhi-110094 | 21045 | 21045 | 21045 | 21045 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1414227 | Relocation | New_Built | RTT | 12 | 11 | 0/120/240 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6592 | 77.2756 | R/NN-467861 | 2020-09-21 | 2020-12-15 | 2020-12-29 | 111.MDEL.91772756 | 2021-03-03 | 2021-03-04 | 2021-03-04 | 2021-07-20 |  |  | 2021-03-01 | 2021-07-20 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 |  |  |  | 2020-12-29 | ST202012187460 | S20200010276 |  |  | 2021-01-04 | P/FVC/DEL/1015247/2021 | 2021-07-25 | 2021-07-27 | DL/01/5177/6320/0031/03/01/10081/NS/27072021 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-08-04 | 2021-08-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 675 | [5 empty] | 2021-03-04 | 2021-07-24 | Relocation Site_Parent Site 15314 Rent Issue_Public Issue at Nearend_24.07.21 | [9 empty] | 404-10-621045-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRU 2219 B0 FD RRU RRUS 12 B3 L-2100 RRU RRUS12B1 TD RRUS 4418 Available on Parent site
Del | FY20_21 | Q4 | Joshi Colony(Relocation of 23921) | H No-B1/A,Joshi Colony,Mandawali Main Rd, I.P.Extension, Patparganj, Delhi-110092 | 21112 | 21112 | 21112 | 21112 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1436176 | Relocation | New_Built | RTM | 14 | 12 | 120/250/340 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6281 | 77.3021 | R/NN-469489 | 2020-10-03 | 2020-10-21 | 2020-11-09 | 111.2862.81773020 | 2021-03-03 | 2021-03-04 | 2021-03-04 | 2021-07-20 |  |  | 2021-03-01 | 2021-07-20 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-24 |  |  |  | 2020-11-12 | ST202011145410 | S20200008117 |  |  | 2020-12-25 | P/FVC/DEL/1013823/2020 | 2021-09-27 | 2021-09-27 | DL/01/5177/6373/0031/03/01/10189/NS/27092021 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-28 | 2021-09-27 | 2021-10-30 | 2021-09-27 | 2021-11-07 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 47 | [5 empty] | 2021-03-04 | 2021-09-27 | Owner Issue at Parent Site_23921_Power Issue at Nearend_24.07.21,Issue closed on 24 Sep 21,Installed_BBU Faulty and Media Issue resloved on 27 Sep 21 | [9 empty] | 404-10-621112-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRU 2219 B0 FD RRU RRUS 12 B3 L-2100 RRU RRUS12B1 TD RRUS 4418 Available on Parent site
Del | FY20_21 | Q4 | Vijay Vihar -I(Relocation of 5387) | I-125,Vijay Vihar, Phase-1,Sector-5,Rohini,Delhi-110085 | 20830 | 20830 | 20830 | 20830 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Alice | AT-DL-0024 | Relocation | NEW_BUILT | RTP | 9 | 16 | 40/140/280(With TB) | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.7134 | 77.0977 | 20830 | 2020-09-21 | 2020-11-01 | 2020-11-04 | 111.MDEL.2162159 | 2021-02-23 | 2021-02-24 | 2021-02-24 | 2021-07-20 |  |  | 2021-02-21 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-08-17 |  |  |  | 2020-11-07 | ST202011139511 | S20200007786 |  |  | 2020-12-22 | P/FVC/DEL/1012897/2020 | 2021-08-17 | 2021-08-18 | DL/01/0031/2793/0031/03/01/10115/NS/18082021 | 2021-08-18 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-05 | 2021-09-03 | 2021-09-09 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10959 | [5 empty] | 2021-02-24 | 2021-08-24 | 30+ sites dependency running from Parent site 5387,MW Material Delivered at Nearend & relocation Site Hold by Devender_23.07.21,Approval received on 05.08.21_CAM Done on 6th Aug but BB & Infra Material Theft from sites reported with Amit Sharma,Infra Material Punched on 11.08.21,Issue closed on 16 Aug 21,again PRI and issue closed on 24 aug 21 | [9 empty] | 404-10-620830-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD) RRU 2219 ,L_2100 (RRUS12B1) TD RRU 4412 available on parent site
Del | FY20_21 | Q4 | Dlf ph-1Bblock(Relocation of 928) | B-18/12,B-BlockDLF Phase-1,Gurgaon,haryana-122002 | 20828 | 20828 | 20828 | 20828 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/TT/1390 | Relocation | Sharing | RTT | 15 | 13 | 0/130/250 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.4696 | 77.0957 | T20DL02717 | 2020-07-09 | 2020-07-23 | 2020-08-01 | 11106.2846.95770956 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-07-20 |  |  | 2021-03-01 | 2021-07-20 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 |  |  |  | 2020-08-03 | ST202008035410 | S20200002462 |  |  | 2020-08-10 | P/FVC/DEL/1003610/2020 | 2021-07-25 | 2021-07-25 | DL/05/5126/0284/0031/345/04/08366/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-08-10 | 2021-08-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 940 | [5 empty] | 2021-03-05 | 2021-07-20 | Parent Site 928 POP Site_Need to Plan change discussed with Sindesh/Ankush | [9 empty] | 404-10-620828-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRU 2219 B0 FD RRU RRUS 12 B3 L-2100 RRU RRUS12B1 TD RRUS 4412 Available on Parent site
Del | FY20_21 | Q4 | Vishnu Garden West | Wz 283/352 Maddi Wali Gali No 11 Vishnu Garden West Delhi Delhi-110018 | 19866 | 19866 | 19866 | 19866 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Alice | AT-DL-0018 | New | New_Built | RTP | 6 | 16 | 40/110/300 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | No | 28.6511 | 77.0983 | 19866 | 2020-09-14 | 2020-12-14 | 2020-12-15 | 111.MDEL.11770982 | 2021-02-15 | 2021-02-16 | 2021-02-16 | 2022-03-09 |  |  | 2021-02-17 | 2022-03-10 | 2022-03-13 | [6 empty] | 2020-11-05 | ST202011135752 | S20200007597 |  |  | 2020-12-25 | P/FVC/DEL/1013731/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Police Issue_SRN Done on 22.03.22 | 3rd Party PRI | PRI_Without Material |  | PRI |  |  | M1 | 4000 |  |  | 1042190 | 2022-03-22 |  | 2021-02-16 |  | Public Issue(SRN Done),Issue closed on 09.03.22,74292_Locator Inactive Issue resloved on 11.03.22,Police Issue as on 14.03.22 | [14 empty] | Police Issue_SRN Done on 22.03.22 | 3rd Party PRI | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Inder Enclave 2 | House No. 181, Khasra No. 22/1, Village Kirari Suleman Nagar, Delhi-110086 | 21213 | 21213 | 21213 | 21213 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1503280 | New | New_Built | RTT | 12 | 8 | 90/180/270 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.7081 | 77.0477 | R/NN-558674 | 2020-11-11 | 2020-12-29 | 2021-01-22 | 111.MDEL.82770474 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-10-25 |  |  | 2021-03-03 | 2021-10-25 | 2021-10-26 | [6 empty] | 2021-01-23 | ST202101022173 | S20210001430 |  |  | 2021-02-25 | P/FVC/DEL/1017974/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 27.10.21 due to Public Issue | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 4175 | [5 empty] | 2021-03-01 |  | Public Issue(SRN Done),Issue closed on 21.10.21,Locator Inactive resolved on 25 Oct 21,Material return on 27.10.21 due to Public Issue | [14 empty] | Material return on 27.10.21 due to Public Issue | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | SDMC_Hudco Place, Andrews Ganj ext. area | MBTS Location,In Front Of Shop No-5,Near Ansal Plaza,Type-5,Opp Flat No-381,Andrews Ganj,New Delhi-110049 | 19875 | 19875 | 19875 | 19875 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3014236 | New | New_Built | Cow | 30 | 0 | 10/90/200 | COW |  |  | YES | >18HRS | No | 28.5622 | 77.2278 | R/NN-626787 | 2020-08-15 | 2020-09-10 | 2020-09-15 | 111-2867-55770259 | 2021-03-01 | 2021-03-02 | 2021-03-02 | 2021-08-09 |  |  | 2021-02-24 | 2021-08-10 | 2021-08-10 | 2021-08-11 | 2021-08-11 | 2021-08-12 |  |  |  | 2021-03-15 | ST202103091229 | S20210004773 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033395/2021 | 2021-08-26 | 2021-08-27 | DL/01/5177/6338/0031/345/04/08433/NS/27082021 | 2021-08-27 | 2021-08-28 | 2021-08-28 | 2021-08-28 | 2021-08-28 | 2021-08-28 | 2021-08-28 | 2021-09-01 | 2021-08-28 | 2021-09-02 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 502 | [5 empty] | 2021-03-02 | 2021-08-25 | Site Re-Release Required due to Drift,Site Re-Release Required due to Drift(Re SR SP Process),As Per Ashwani Site RFAI till 12 Aug 21,69419(RFAI expected till 12th Aug 21),Partially Installed_Farend Material return,Issue Closed on 25 Aug 21 | [7 empty] | 404-10-619875-51 |  | 404-10-619875-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Chhatterpur Pahadi | House No.-190,Gali No.-D 16 Chhatterpur Pahadi, Chhatterpur, New Delhi-110074 | 20295 | 20295 | 20295 | 20295 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1503524 | New | New_Built | RTM | 11 | 12 | 10/160/220 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.5083 | 77.1848 | R/NN-558709 | 2020-11-11 | 2020-11-14 | 2020-11-18 | 111.MDEL.82771847 | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-03-07 |  |  | 2021-03-05 | 2021-03-07 | 2021-03-08 | [6 empty] | 2020-11-22 | ST202011153110 | S20200008597 |  |  | 2020-12-22 | P/FVC/DEL/1012880/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Public Issue(SRN Done) | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 67 | [5 empty] | 2021-03-03 |  | Public Issue(Material SRN Done on 02 Aug 21) | [14 empty] | Public Issue(SRN Done) | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Rajouri Garden(Relocation of 5641) | SDMC Park opp A-31,Near Allahabad Bank & Rajori Garden Metro, Block A2, Block A, Rajouri Garden, New Delhi-110027 | 21264 | 21264 | 21264 | 21264 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1492993 | Relocation | New_Built | Cow | 30 | 0 | 0 deg with twin beam/100/230 | COW |  |  | YES | >18HRS | No | 28.6486 | 77.1245 | R/NN-545088 | 2020-11-06 | 2020-11-17 | 2020-12-01 | 111.MDEL.86771245 | 2021-02-23 | 2021-02-24 | 2021-02-24 | 2021-04-14 |  |  | 2021-02-18 | 2021-04-20 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | 2020-12-16 | ST202012174388 | S20200009628 |  |  | 2020-12-23 | P/FVC/DEL/1013375/2020 | 2021-04-25 | 2021-04-26 | DL/01/5177/6278/0031/345/04/08260/NS/26042021 | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-04-27 | 2021-04-28 | 2021-04-26 | 2021-04-30 | 2021-05-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 913 | [5 empty] | 2021-02-24 | 2021-04-25 | [10 empty] | 404-10-621264-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD) RRU 2219 ,L_2100 (RRUS12B1) TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | NEW SEELAMPUR | B-105,Fruit Market,New Seelampur,DELHI-110053 | 16534 | 16534 | 16534 | 16534 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Fine bunch | FB0017 | Relocation | New_Built | RTP | 9 | 16 | 350/60/200 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6747 | 77.267 | 16534 | 2020-10-01 | 2020-10-31 | 2020-11-03 | 111.MDIL.1719649 | 2021-03-10 | 2021-03-10 |  |  |  |  | 2021-02-19 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-13 | 2021-03-31 |  |  |  | 2020-11-05 | ST202011135756 | S20200007597 |  |  | 2020-12-25 | P/FVC/DEL/1013730/2020 | 2021-03-31 | 2021-04-06 | DL/01/0031/2625/0031/345/04/08201/NS/06042021 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-08 | 2021-04-06 | 2021-04-10 | 2021-04-14 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 284 | [5 empty] | 2021-03-13 | 2021-04-06 | [10 empty] | 404-10-616534-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Railway Officers Colony | House No-2 Block 3C Near Liberty cinema,Sarai Rohilla,New Delhi-110007 | 25570 | 25570 | 25570 | 25570 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | MTNL | MT_25570_Del | New | New_Built | RTT | 9 | 16 | 330/90/210 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6603 | 77.1886 | 25570 | 2021-01-04 | 2021-01-29 | 2021-01-29 | 111.MDEL.03771885 | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-31 |  |  | 2021-03-07 | 2021-04-01 | 2021-04-01 | 2021-04-03 | 2021-04-03 | 2021-04-05 |  |  |  | 2021-03-05 | ST202103080627 | S20210004229 |  |  | 2021-03-11 | P/FVC/DEL/1019879/2021 | 2021-04-05 | 2021-04-06 | DL/01/5165/0257/0031/345/04/08202/NS/06042021 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-08 | 2021-04-06 | 2021-04-10 | 2021-05-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 700 | [5 empty] | 2021-03-12 | 2021-04-05 | [10 empty] | 404-10-625570-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Qutab Road Ramnagar near ND railway station(Relocation of 2028) | HOTEL NEST S.J.S.Marg, Opp.Qutab Road, Ram Nagar, New Delhi-110055 | 20797 | 20797 | 20797 | 20797 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388613 | Relocation | New_Built | RTP | 9 | 12.5 | 110/210/300 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6449 | 77.2178 | R/NN-465198 | 2020-08-15 | 2020-08-22 | 2020-09-10 | 111.MDEL.2174431 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-04-27 |  |  | 2021-03-13 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-29 | 2021-05-01 |  |  |  | 2020-09-12 | ST202009066054 | S20200004361 |  |  | 2020-09-19 | P/FVC/DEL/1005959/2020 | 2021-05-01 | 2021-05-08 | DL/01/5177/6284/0031/06/05/11493/NS/08052021 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 | 2021-05-08 | 2021-05-12 | 2021-05-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4374 | [5 empty] | 2021-03-16 | 2021-05-08 | [10 empty] | 404-10-620797-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Gtb Enclave | H.No. 446 Janta flats gtb enclave,Nand Nagri, Delhi, 110093 | 19871 | 19871 | 19871 | 19871 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19871_DEL | New | New_Built | RTP | 9 | 13 | 80/150/300 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.6898 | 77.3119 | 19871 | 2020-08-03 | 2020-08-03 | 2020-08-03 | 111.MDEL.98773119 | 2021-03-22 | 2021-03-22 |  |  |  |  | 2021-03-13 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-04-01 |  |  |  | 2020-09-01 | ST202009057293 | S20200003755 |  |  | 2020-09-05 | P/FVC/DEL/1005095/2020 | 2021-04-02 | 2021-04-03 | DL/01/0031/2626/0031/06/05/11347/NS/03042021 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-04 | 2021-04-04 | 2021-04-05 | 2021-04-03 | 2021-04-07 | 2021-04-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 4949 | [5 empty] | 2021-03-22 | 2021-03-30 | [10 empty] | 404-10-619871-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q1 | NHAI Toll Gurgaon | NHAI Toll Gurgaon Near by Health insurance Office Gurgaon Haryana-122015 | 20689 | 20689 | 20689 | 20689 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | FCM_TOWER | NCR/24 | New | New_Built | GBM | 24 | 0 | 0/130/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.5083 | 77.0937 | 20689 | 2020-02-04 | 2020-08-29 | 2020-09-01 | 11106.MGGN.83770936 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-05-03 |  |  | 2021-03-13 | 2021-05-04 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-05-15 |  |  |  | 2021-03-26 | ST202103107524 | S20210005562 |  | 2021-04-15 | 2021-06-14 | P/FBC/DEL/1031316/2021 | 2021-05-15 | 2021-05-17 | DL/05/5410/0015/0031/345/04/08283/NS/16052021 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-18 | 2021-05-18 | 2021-05-19 | 2021-05-17 | 2021-05-21 | 2021-05-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4858 | [5 empty] | 2021-03-15 | 2021-05-14 | [10 empty] | 404-10-620689-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sec 8 Noida | Mr. Naveen Goyal,Simplex India,H.No. C 31,Sec 8, Noida,Uttar Pradesh 201301 | 19960 | 19960 | 19960 | 19960 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1900776 | New | New_Built | RTT | 9 | 15 | 40/170/270 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.5939 | 77.3271 | R/NN-568538 | 2019-10-17 | 2020-12-02 | 2020-12-17 | 11109.MNOI.45773272 | 2021-05-18 | 2021-05-18 |  |  |  |  | 2021-05-15 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-20 | 2021-05-21 |  |  |  | 2021-04-21 | ST202104161244 | S20210007316 |  | 2021-05-14 | 2021-07-22 | P/FVC/DEL/1036287/2021 | 2021-05-21 | 2021-05-22 | DL/03/5177/0895/0031/06/05/11532/NS/22052021 | 2021-05-22 | 2021-05-23 | 2021-05-23 | 2021-05-23 | 2021-05-23 | 2021-05-24 | 2021-05-24 | 2021-05-25 | 2021-05-23 | 2021-05-27 | 2021-05-28 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 538 | [17 empty] | 404-10-619960-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | Inder Enclave, Ph-2 | H.No.-317/2, Block-A, Village Kirari Suleman Nagar, Patti Nithari, Inder Enclave, Mubarikpur Road, Nangloi, Delhi-110086 | 20996 | 20996 | 20996 | 20996 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1389154 | New | New_Built | RTM | 10 | 12 | 120/240/350 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.7051 | 77.048 | R/NN-465861 | 2020-08-27 | 2020-09-14 | 2020-09-22 | 111.MDEL.50770479 | 2021-03-15 | 2021-03-16 | 2022-03-13 |  |  |  | 2021-03-17 | 2022-03-13 | 2022-03-14 | [6 empty] | 2020-09-26 | ST202009088911 | S20200005108 |  |  | 2020-10-06 | P/FVC/DEL/1007595/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material Delivered by Toco_SRN Done on 21.03.22 | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 8107 |  |  | 1042174 | 2022-03-20 | 2022-03-21 | 2021-03-18 |  | Delivered at Owner Shop By Indus(SRN Done_12.10.21),Material Delivered with Toco 15.03.22 | [14 empty] | Material Delivered by Toco_SRN Done on 21.03.22 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sector 21,Jalvayu Vihar,Noida | Near-Jal Vayu Vihar,Gate No.1,Sector-21 Gautam Buddha Nagar,Uttar Pradesh-201301 | 19114 | 19114 | 19114 | 19114 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Elite | ELDEL05 | New | New_Built | GBM | 30 | 0 | 0/110/200 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.5855 | 77.3341 | 19114 | 2020-08-04 | 2020-11-17 | 2020-11-24 | 11109.MNOI.55773340 | 2021-03-17 | 2021-03-17 |  |  |  |  | 2021-03-16 | 2021-03-18 | 2021-03-21 | 2021-03-22 | 2021-03-22 | 2021-03-24 |  |  |  | 2020-11-30 | ST202011160627 | S20200008886 |  |  | 2020-12-23 | P/FVC/DEL/1013149/2020 | 2021-03-24 | 2021-03-24 | DL/03/9073/0003/0031/03/01/09941/NS/24032021 | 2021-03-24 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-04-01 | 2021-03-30 | 2021-04-03 | 2021-04-06 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 180 | [5 empty] | 2021-03-18 | 2021-03-30 | [10 empty] | 404-10-619114-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q2 | Life care Hospital noida sec 61 | Life care Hospital E-1,noida sec 61 Near sai mandir U.P-201307 | 23021 | 23021 | 23021 | 23021 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_23021_DEL | New | New_Built | RTP | 9 | 16 | 0/110/180/300 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.5935 | 77.3703 | 23021 | 2021-01-29 | 2021-02-23 | 2021-02-26 | 11109.MNOI.34773703 | 2021-03-22 | 2021-03-22 |  |  |  |  | 2021-03-12 | 2021-04-02 | 2021-04-04 | 2021-04-05 | 2021-04-05 | 2021-04-06 |  |  |  | 2021-03-02 | ST202103075340 | S20210004046 |  |  | 2021-03-21 | P/FVC/DEL/1020361/2021 | 2021-04-06 | 2021-04-07 | DL/03/0031/0309/0031/345/04/08204/NS/07042021 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-09 | 2021-04-07 | 2021-04-11 | 2021-04-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 5338 | [5 empty] | 2021-03-22 | 2021-04-04 | [10 empty] | 404-10-623021-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q3 | Sector 1 Bawana Industrial Area | Plot no. H12 Sector 1 Bawana Industrial Area Delhi-39 | 20523 | 20523 | 20523 | 20523 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Lotus | LTIPL-DL-DLHI-0032 | New | New_Built | RTP | 9 | 12 | 0/100/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.7852 | 77.0435 | 20523 | 2020-02-27 | 2020-09-05 | 2021-02-20 | 111.2878.51770435 | 2021-03-26 | 2021-03-27 | 2021-03-27 | 2021-08-02 |  |  | 2021-03-24 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-05 | 2021-08-06 |  |  |  | 2021-02-18 | ST202102058252 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019518/2021 | 2021-08-06 | 2021-08-07 | DL/01/9071/0012/0031/03/01/10091/NS/07082021 | 2021-08-07 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-11 | 2021-08-09 | 2021-08-11 | 2021-08-09 | 2021-08-16 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5197 | [5 empty] | 2021-03-27 | 2021-08-02 | Farend PRI_5197/16189(Not Feasible_16189) Issue Closed on 02.08.21 | [9 empty] | 404-10-620523-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q3 | Greatornoida PI Eachachhar | Noida Authority, Inside Park,Near Electric Pole No 30749 TO 30752,First Cross Avenue Rd ,In Front Of Kushbu Apartment,Sec Pi I & II,Greater Noida ,Uttar Pradesh 201310 | 13241 | 13241 | 13241 | 13241 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1921180 | New | New_Built | GBM | 30 | 0 | 50/170/310 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.4638 | 77.5362 | R/NN-569156 | 2019-10-17 | 2020-01-10 | 2020-04-03 | 11109.2846.41775386 | 2021-06-29 | 2021-06-29 |  |  |  |  | 2021-06-26 | 2021-06-29 | 2021-07-01 | 2021-07-02 | 2021-07-02 | 2021-07-03 |  |  |  | 2021-04-17 | ST202104151770 | S20210007098 |  | 2021-05-10 | 2021-06-09 | P/FVC/DEL/1028600/2021 | 2021-07-05 | 2021-07-06 | DL/03/5177/0898/0031/03/01/10050/NS/06072021 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-08 | 2021-07-06 | 2021-07-11 | 2021-07-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [18 empty] | 404-10-613241-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | AILP Peaceful Homes | AILP The Peaceful Homes,Tower BLISS,Sector-70A,Gurgaon,Haryana 122101. | 19696 | 19696 | 19696 | 19696 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1352063 | EXISTING | Sharing | RTP | 6 | 103 | 320/80/220 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.3848 | 77.0169 | R/RES-434176 | 2021-02-17 | 2021-02-18 | 2021-03-01 | 11106.MGGN.48770168 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-05-03 |  |  | 2021-03-15 | 2021-05-04 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-05-07 |  |  |  | 2021-03-28 | ST202103109420 | S20210005642 |  | 2021-04-21 | 2021-07-08 | P/FVC/DEL/1033502/2021 | 2021-05-07 | 2021-05-08 | DL/05/5177/5198/0031/06/05/11495/NS/08052021 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 | 2021-05-08 | 2021-05-12 | 2021-05-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1962 | [5 empty] | 2021-03-26 | 2021-05-03 | [10 empty] | 404-10-619696-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | Nai Sarak(Relocation of 2491) | H No-4161, Om Jay Silk Co., Nai Sadak, New Delhi 110006 | 21263 | 21263 | 21263 | 21263 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1007724 | Relocation | Sharing | RTP | 6 | 13 | 40/180/250 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.6537 | 77.2283 | R/RES-431836 | 2020-11-27 | 2020-12-11 | 2020-12-23 | 111.MDEL.36772282 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-04-13 |  |  | 2021-02-11 | 2021-04-13 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-19 |  |  |  | 2021-03-18 | ST202103094632 | S20210004928 |  | 2021-04-09 | 2021-08-04 | P/FVC/DEL/1036722/2021 | 2021-04-19 | 2021-04-28 | DL/01/5177/3800/0031/03/01/10001/NS/28042021 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-04-28 | 2021-05-02 | 2021-05-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4899 | [5 empty] | 2021-03-16 | 2021-04-27 | [10 empty] | 404-10-621263-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Najafgarh Extn. | Solanki Cottage,Khasra No-153/19,Hno.C-91,Shiv Enclave, Dichaon Kalan, Delhi, 110043 | 21328 | 21328 | 21328 | 21328 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | ATDLNAJ0815 | New | New_Built | RTT | 6 | 18 | 0/90/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6228 | 76.9855 | 21328 | 2021-02-12 | 2021-02-18 | 2021-02-26 | 111.MDEL.27769854 | 2021-03-26 | 2021-03-26 |  |  |  |  | 2021-03-20 | 2021-03-30 | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-04-10 |  |  |  | 2021-02-23 | ST202102066896 | S20210003586 |  | 2021-03-17 | 2021-07-08 | P/FVC/DEL/1033766/2021 | 2021-04-10 | 2021-04-11 | DL/01/5113/0221/0031/03/01/09959/NS/11042021 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-11 | 2021-04-15 | 2021-04-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 263 | [5 empty] | 2021-03-26 | 2021-04-10 | [10 empty] | 404-10-621328-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q4 | RAMA VIHAR NEAR LEELU PEHLWAN | Property No. F-3/1, Khasra No. 24/23, Village Mohammedpur Majri, Rama Vihar, Delhi-110091 | 21352 | 21352 | 21352 | 21352 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1701190 | New | New_Built | GBM | 30 | 0 | 20/120/240 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.7225 | 77.0481 | R/NN-564611 | 2021-02-02 | 2021-02-05 | 2021-02-13 | 111.MDEL.24770481 | 2021-03-24 | 2021-03-25 |  |  |  |  | 2021-03-14 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-04-01 |  |  |  | 2021-02-18 | ST202102058258 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019525/2021 | 2021-04-01 | 2021-04-02 | DL/01/5177/6255/0031/06/05/11345/NS/02042021 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-03 | 2021-04-03 | 2021-04-04 | 2021-04-02 | 2021-04-06 | 2021-04-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 585 | [5 empty] | 2021-03-25 | 2021-03-30 | [10 empty] | 404-10-621352-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+) RRU 2219,L_2100 12B1 TD RRU 4418
Del | FY20_21 | Q4 | VILL-INDER GARHI MAZRA | H No 410 ,Vill-Inder Garhi Mazra,Dasna Dehat, Ghaziabad , Uttar Pradesh-201302 | 21351 | 21351 | 21351 | 21351 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1701171 | New | New_Built | RTP | 6 | 16.3 | 0/70/240 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6778 | 77.4945 | R/NN-564610 | 2021-02-02 | 2021-02-08 | 2021-02-13 | 11109.MGBD.77774945 | 2021-03-24 | 2021-03-25 |  |  |  |  | 2021-03-14 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-01 | 2021-04-01 |  |  |  | 2021-02-18 | ST202102058254 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019521/2021 | 2021-04-01 | 2021-04-02 | DL/04/5177/0758/0031/06/05/11344/NS/02042021 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-03 | 2021-04-03 | 2021-04-04 | 2021-04-02 | 2021-04-06 | 2021-04-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 5664 | [5 empty] | 2021-03-25 | 2021-03-30 | [10 empty] | 404-10-621351-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+) RRU 2219,L_2100 12B1 TD RRU 4418
Del | FY20_21 | Q1 | SDMC_Sec-8, R.K Puram, New Delhi | Sector 9 Road,Rama Krishna Puram,New Delhi,Pin-110022 | 7613 | 7613 | 7613 | 7613 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1705616 | New | New_Built | Cow | 30 | 0 | 350/90/190 | COW |  |  | YES | >18HRS | No | 28.571 | 77.1703 | R/NN-564596 | 2021-02-02 | 2021-02-08 | 2021-02-10 | 111.MDIL.1365950 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-05-13 |  |  | 2021-03-26 | 2021-05-14 | 2021-05-14 | 2021-05-15 | 2021-05-20 | 2021-05-20 |  |  |  | 2021-02-05 | ST202102039758 | S20210002332 |  |  | 2021-02-28 | P/FVC/DEL/1018781/2021 | 2021-05-20 | 2021-05-21 | DL/01/5177/6287/0031/345/04/08285/NS/21052021 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-22 | 2021-05-22 | 2021-05-23 | 2021-05-21 | 2021-05-25 | 2021-05-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8 | [5 empty] | 2021-03-31 | 2021-05-20 | [10 empty] | 404-10-607613-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q3 | Sec17,Ggn(Relocation of 9089) | Handbast No - 70, Khewat No - 43/41, Khatoni No - 48, Village Sarhaul , Tehsil and District Gurgaon - 122022 | 21581 | 21581 | 21581 | 21581 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1700665 | Relocation | Sharing | Cow | 30 | 0 | 0/130/280 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.4851 | 77.0612 | R/RES-433881 | 2021-02-17 | 2021-02-18 | 2021-03-02 | 11106.MGGN.50770611 | 2021-03-17 | 2021-03-17 |  |  |  |  | 2021-03-15 | 2021-03-20 | 2021-03-20 | 2021-03-21 | 2021-03-21 | 2021-03-22 |  |  |  | 2021-03-03 | ST202103077350 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020312/2021 | 2021-03-22 | 2021-03-23 | DL/05/5177/5264/0031/06/05/11266/NS/23032021 | 2021-03-23 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-27 | 2021-03-27 | 2021-03-28 | 2021-03-26 | 2021-03-30 | 2021-04-06 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 809 | [5 empty] | 2021-03-17 | 2021-03-26 | [10 empty] | 404-10-621581-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | Available on site Parent site
Del | FY20_21 | Q4 | Open Cinema Hall, CVD(Relocation of 17794) | NEAR WALL NO.7 GUARD POST NO.2 CVD DELHI CANTONMENT DELHI-110010 | 20636 | 20636 | 20636 | 20636 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1375786 | Relocation | Sharing | GBM | 30 | 0 | 40/150/250 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.5976 | 77.1121 | R/RES-433115 | 2021-01-12 | 2021-01-13 | 2021-02-13 | 111.MDEL.76771120 | 2021-03-17 | 2021-03-18 | 2021-03-18 | 2021-03-30 |  |  | 2021-03-07 | 2021-04-02 | 2021-04-04 | 2021-04-05 | 2021-04-05 | 2021-04-07 |  |  |  | 2021-01-14 | ST202101011207 | S20210000732 |  |  | 2021-01-20 | P/FVC/DEL/1016804/2021 | 2021-04-07 | 2021-04-08 | DL/01/5177/6031/0031/345/04/08206/NS/08042021 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-09 | 2021-04-09 | 2021-04-10 | 2021-04-08 | 2021-04-12 | 2021-04-14 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 4388 | [5 empty] | 2021-03-18 | 2021-04-07 | [10 empty] | 404-10-620636-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q4 | Village Ilaychipur | Khasra No.48,V.K.Enclave,Elaichipur Colony,Ram Park Extension,Post Office Loni,Loni Ghaziabad Uttar Pradesh-201102 | 18391 | 18391 | 18391 | 18391 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1306015 | EXISTING | Sharing | RTM | 11 | 12 | 80/160/300 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.7603 | 77.2436 | R/RES-433924 | 2021-02-17 | 2021-02-19 | 2021-03-01 | 11109.MGBD.02772435 | 2021-03-22 | 2021-03-23 | 2021-03-23 | 2021-03-30 |  |  | 2021-03-15 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-09 |  |  |  | 2021-03-02 | ST202103075341 | S20210004046 |  |  | 2021-03-21 | P/FVC/DEL/1020363/2021 | 2021-04-13 | 2021-04-14 | DL/04/5177/0682/0031/345/04/08216/NS/14042021 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-14 | 2021-04-18 | 2021-04-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4477 | [5 empty] | 2021-03-23 | 2021-04-12 | [10 empty] | 404-10-618391-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219B3+L_2100 RRU 12B1, TD RRU 4418
Del | FY20_21 | Q4 | EMCD_25_Near Indra Mkt. Trilok Puri | Nearby Shop no. 1 21/280 & Indra Market ,EMCD park,Pocket 2, Mayur Vihar,Trilokpuri,Delhi-110091 | 20861 | 20861 | 20861 | 20861 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1736331 | New | New_Built | GBM | 30 | 0 | 20/170/250 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6076 | 77.3033 | R/NN-565933 | 2021-02-16 | 2021-02-18 | 2021-02-26 | 111.MDEL.76773032 | 2021-03-24 | 2021-03-25 |  |  |  |  | 2021-03-19 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-25 |  |  |  | 2021-03-03 | ST202103077347 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020310/2021 | 2021-04-25 | 2021-04-27 | DL/01/5177/6280/0031/03/01/09999/NS/27042021 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-04-27 | 2021-05-01 | 2021-05-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4052 | [5 empty] | 2021-03-25 | 2021-04-25 | [10 empty] | 404-10-620861-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+) RRU 2219,L_2100 12B1 TD RRU 4418
Del | FY20_21 | Q4 | DDA_Block C, Adchini | Near PTS Bus Stop & kali mandir 30 , Lado Sarai, New Delhi-110016 | 19645 | 19645 | 19645 | 19645 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1754593 | New | New_Built | GBM | 25 | 0 | 90/210/330 | COW |  |  | YES | >18HRS | No | 28.5328 | 77.1953 | R/NN-565947 | 2021-02-16 | 2021-02-25 | 2021-03-04 | 111.MDEL.27771953 | 2021-03-24 | 2021-03-25 |  |  |  |  | 2021-03-22 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-21 | 2021-07-24 |  |  |  | 2021-02-16 | ST202102053954 | S20210002988 |  |  | 2021-03-07 | P/FVC/DEL/1019438/2021 | 2021-07-24 | 2021-07-25 | DL/01/5177/6317/0031/345/04/08362/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-26 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-31 | 2021-07-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 919 | [5 empty] | 2021-03-25 | 2021-07-23 | Power Issue | [9 empty] | 404-10-619645-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+L-2100) RRU 2279 TD RRUS 4418
Del | FY20_21 | Q4 | INDRAZ BHAWAN, BASAI CHOWK | House No. 128, Gali No. 1, Near BasaI Chowk, Bhawani Enclave, Gurgaon-122006 | 21348 | 21348 | 21348 | 21348 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1754592 | New | New_Built | RTT | 12 | 11.3 | 50/140/210 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.4599 | 76.9931 | R/NN-565939 | 2021-02-16 | 2021-02-25 | 2021-03-16 | 11106.MGGN.98769931 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-13 |  |  | 2021-03-21 | 2021-04-13 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-17 |  |  |  | 2020-12-21 | ST202012179476 | S20200009873 |  |  | 2020-12-30 | P/FVC/DEL/1015116/2020 | 2021-04-17 | 2021-04-19 | DL/05/5177/5265/0031/03/01/09979/NS/19042021 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-19 | 2021-04-23 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9129 | [5 empty] | 2021-03-31 | 2021-04-13 | [10 empty] | 404-10-621348-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q1 | candor IT- Tower 7 | Candor IT Park Tower 7, Sector 48, Gurgaon | 27597 | 27597 | 27597 | 27597 |  |  |  | G1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | IBUS | IBSHR008 | New | New_Built | IBS | 0 | 15 | IBS/IBS | PURE_IBS |  | 3RD_PARTY | YES | >18HRS | No | 28.4254 | 77.0325 | 27597 | 2020-01-03 | 2020-01-08 | 2020-01-15 | 11106.MGGN.1027597 | 2020-01-25 | 2021-04-10 | 2020-01-25 | 2021-04-22 |  |  | 2020-01-22 | 2021-04-23 | 2021-04-25 | 2021-04-26 | 2021-04-26 | 2021-05-23 | [10 empty] | 2021-05-23 |  | IBS | 2021-05-23 | 2021-05-23 | 2021-05-23 | 2021-05-23 | 2021-05-23 | 2021-05-24 | 2021-05-24 | 2021-05-25 | 2021-05-23 | 2021-05-27 | 2021-06-01 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8186 | [5 empty] | 2020-01-25 | 2021-05-23 | [10 empty] | 404-10-927597-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 TD RRUS 4418
Del | FY20_21 | Q1 | Gharoli(Relocation of 5724) | Kh No-992/67,House No.B-77,Kodli Sabji mandi ,Main road Gharoli , Gharoli, New Delhi-110096 | 21398 | 21398 | 21398 | 21398 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1362754 | Relocation | Sharing | RTP | 9 | 10 | 40/120/300 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.6154 | 77.3266 | R/RES-433540 | 2021-02-17 | 2021-02-18 | 2021-03-04 | 111.MDEL.53773265 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-05-24 |  |  | 2021-03-15 | 2021-05-30 | 2021-06-01 | 2021-06-02 | 2021-06-02 | 2021-06-02 |  |  |  | 2021-03-02 | ST202103075338 | S20210004046 |  |  | 2021-03-21 | P/FVC/DEL/1020388/2021 | 2021-06-02 | 2021-06-03 | DL/01/5177/5833/0031/06/05/11570/NS/03062021 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-04 | 2021-06-03 | 2021-06-05 | 2021-06-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 586 | [5 empty] | 2021-04-16 | 2021-05-30 | [10 empty] | 404-10-621398-12 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219,L_2100 RRU 12B1, TD RRU 4412, TD twin beam RRU 4418 Available on parent site
Del | FY20_21 | Q1 | I.P Collage(Relocation of 27434) | Indraprastha college for Women,Plot No.31,IP Collage,Near Football Ground,Sham Nath Marg,Civil Lines,Delhi, 110054 | 19731 | 19731 | 19731 | 19731 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept | PTIPL51 | Relocation | New_Built | GBM | 30 | 0 | 40/130/230/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6817 | 77.2246 | 19731 | 2021-02-19 | 2021-03-16 | 2021-03-19 | 111.2868.17772246 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-06-28 |  |  | 2021-04-17 | 2021-06-27 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-07-05 |  |  |  | 2021-03-18 | ST202103094623 | S20210004928 |  | 2021-04-09 | 2021-08-04 | P/FVC/DEL/1036726/2021 | 2021-07-05 | 2021-07-06 | DL/01/9052/0069/0031/03/01/10049/NS/06072021 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-08 | 2021-07-06 | 2021-07-11 | 2021-07-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10855 | [5 empty] | 2021-04-19 | 2021-06-28 | [10 empty] | 404-10-919731-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 TD RRU 4418 Available on Parenet Site L_2100 RRU 12B1
Del | FY20_21 | Q1 | Kotla Mubarakpur(Relocation of 2611) | SDMC, MBTS Locataion Kotla Mubarakpur, Near House No. G204, Opposite Toilet Block, New Delhi- 110003 | 20852 | 20852 | 20852 | 20852 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1799923 | Relocation | New_Built | Cow | 30 | 0 | 0/140/240 | COW |  |  | YES | >18HRS | No | 28.5784 | 77.2249 | R/NN-567119 | 2021-03-04 | 2021-03-10 | 2021-03-18 | 111.MDEL.62772266 | 2021-04-15 | 2021-04-15 |  |  |  |  | 2021-04-14 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-18 |  |  |  | 2021-03-26 | ST202103107522 | S20210005562 |  | 2021-04-15 | 2021-06-14 | P/FBC/DEL/1031315/2021 | 2021-04-19 | 2021-04-21 | DL/01/5177/6273/0031/345/04/08242/NS/21042021 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-22 | 2021-04-26 | 2021-04-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 2616 | [17 empty] | 404-10-620852-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | EMCD_83_Welocome(Relocation of 10668) | Near-East Delhi Municipal Corporation,Sahadara, North East Zone,Delhi-110053,(Near-Welcome Metro Station&HP Petrol Pump) | 20913 | 20913 | 20913 | 20913 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388168 | Relocation | New_Built | GBM | 30 | 0 | 60/130/240 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6731 | 77.2786 | R/NN-464242 | 2020-07-22 | 2020-09-10 | 2020-09-15 | 111.MDEL.31772786 | 2021-04-15 | 2021-04-16 | 2021-04-15 | 2021-04-16 |  |  | 2021-04-12 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-23 |  |  |  | 2020-10-07 | ST202010100601 | S20200005780 |  |  | 2020-10-17 | P/FVC/DEL/1008935/2020 | 2021-04-24 | 2021-04-25 | DL/01/5177/6279/0031/345/04/08255/NS/25042021 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-04-25 | 2021-04-29 | 2021-05-01 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10217 | [5 empty] | 2021-04-15 | 2021-04-16 | [10 empty] | 404-10-620913-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219,L_2100 RRU 12B1, TD RRU 4412, TD twin beam RRU 4418 Available on parent site
Del | FY20_21 | Q1 | Vikas Puri New Delhi | Near house A-238,Plot No AG1,New Delhi Public School,Block A - Vikas Puri, New Delhi- 110018 | 14442 | 14442 | 14442 | 14442 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Lotus | LTIPL-DL-DLHI-0066 | New | New_Built | RTP | 6 | 18 | 0/110/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6291 | 77.0666 | 14442 | 2020-12-28 | 2020-12-31 | 2021-01-25 | 111.MDEL.91770665 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-13 |  |  | 2021-03-22 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | 2021-04-17 |  |  |  | 2021-01-19 | ST202101017282 | S20210001143 |  |  | 2021-02-25 | P/FVC/DEL/1017925/2021 | 2021-04-17 | 2021-04-18 | DL/01/9071/0058/0031/06/05/11393/NS/18042021 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-19 | 2021-04-23 | 2021-04-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 617 | [5 empty] | 2021-04-01 | 2021-04-13 | [10 empty] | 404-10-614442-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Gk1Mblockmarket(Relocation of 2100) | M-71,GK 1,M block Market Kailash Greater,New Delhi 110048 | 19418 | 19418 | 19418 | 19418 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19418_DEL | Relocation | New_Built | RTP | 9 | 14 | 70/150/270 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.5509 | 77.234 | 19418 | 2019-07-15 | 2020-09-04 | 2020-09-14 | 111.MDEL.08772340 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-27 |  |  | 2021-04-09 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-04-30 | 2021-05-10 |  |  |  | 2020-09-17 | ST202009071336 | S20200004684 |  |  | 2020-09-22 | P/FVC/DEL/1006348/2020 | 2021-05-10 | 2021-05-11 | DL/01/0031/2660/0031/345/04/08277/NS/11052021 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-12 | 2021-05-12 | 2021-05-13 | 2021-05-11 | 2021-05-15 | 2021-05-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 616 | [5 empty] | 2021-04-20 | 2021-05-10 | [10 empty] | 404-10-619418-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Bhagirathi Vihar | House No.565,Gali No.22,Bhagirathi Vihar,Old Mustafabad,Delhi-110094 | 21120 | 21120 | 21120 | 21120 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1432993 | New | New_Built | RTP | 9 | 14 | 30/180/280 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.7116 | 77.2743 | R/NN-469478 | 2020-10-03 | 2020-10-27 | 2020-11-05 | 111.MDEL.15772743 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-06-15 |  |  | 2021-04-21 | 2021-06-15 | 2021-06-18 | [6 empty] | 2020-11-07 | ST202011139518 | S20200007786 |  |  | 2020-12-22 | P/FVC/DEL/1012904/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return due to Public issue_19.06.21 | Indus | PRI_Without Material |  |  | Indus |  | M1 | 1738 | [5 empty] | 2021-04-22 |  | Material return due to Public issue_19.06.21 | [14 empty] | Material return due to Public issue_19.06.21 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Ayanagar | Ch. Chimman,Plot No. 45, Khasra No. 1855/2, Village - Aaya Nagar, New Delhi - 110047 | 20541 | 20541 | 20541 | 20541 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762526 | New | New_Built | RTP | 6 | 18.5 | 40/110/220 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.4747 | 77.1317 | R/NN-566626 | 2021-02-25 | 2021-02-25 | 2021-03-24 | 111.MDEL.47771317 | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-04-06 |  |  | 2021-03-22 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-09 |  |  |  | 2021-03-03 | ST202103077356 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020318/2021 | 2021-04-09 | 2021-04-11 | DL/01/5177/6262/0031/06/05/11369/NS/11042021 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-11 | 2021-04-15 | 2021-04-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 4533 | [5 empty] | 2021-04-02 | 2021-04-06 | [10 empty] | 404-10-620541-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Hindu Rao Hospital, SabziMandi(Relocation of 27216) | Hindu Rao Hospital near by Out patient department Kamla nagar delhi-110007 | 11457 | 11457 | 11457 | 11457 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept | CM08 | Relocation | New_Built | Cow | 30 | 0 | 0/80/240 | COW |  | 3RD_PARTY | YES | >18HRS | No | 28.6755 | 77.2102 | 11457 | 2020-08-23 | 2020-08-24 | 2020-09-04 | 111.2867.55772102 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-08-09 |  |  | 2021-03-27 | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-10 | 2021-08-14 |  |  |  | 2020-09-11 | ST202009065532 | S20200004327 |  |  | 2020-09-18 | P/FVC/DEL/1005813/2020 | 2021-08-18 | 2021-08-18 | DL/01/9052/0070/0031/03/01/10111/NS/17082021 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-21 | 2021-08-18 | 2021-08-24 | 2021-08-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 513 | [5 empty] | 2021-04-01 | 2021-08-18 | Site Diamantled in Oct`20 & Material was Kept on Site(It was shifted alog with BTS),Consumable request on 5th Aug after Clearance,Site hold due to Locator,Locator Issue resolved on 09th Aug 21,Partially Installed_Power Issue Rectifier/Pole Mount crack on 11 Aug 21,Power issue resolved on 13 Aug 21,Installed_Earthing Issue 16 Aug 21,Earthing Issue resolved on 18 AUg 21 | [9 empty] | 404-10-611457-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 L_2100 RRU 12B1TD RRU 4418 Available on Parenet Site
Del | FY20_21 | Q1 | Geetanjali Vihar, Khora Colony | Plot No. 109,Khasra No. 432,New Ajanta Park,Village-Khora Colony,Ghaziabad,Uttar Pradesh-201309 | 18083 | 18083 | 18083 | 18083 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_18083_DEL | New | New_Built | RTP | 6 | 16 | 30/120/250/320 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.6197 | 77.3461 | 18083 | 2018-03-16 | 2020-10-19 | 2020-10-26 | 11109.MGBD.94773462 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-03-13 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-18 |  |  |  | 2021-03-13 | ST202103089555 | S20210004658 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033712/2021 | 2021-04-18 | 2021-04-18 | DL/04/0031/0195/0031/345/04/08228/NS/18042021 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-18 | 2021-04-22 | 2021-04-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 192 | [5 empty] | 2021-04-16 | 2021-04-18 | [10 empty] | 404-10-918083-44 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Barolla, Sector-49, Noida | Lokesh Sharma S/o Rajender Sharma,H.No 96 ,Baroula,Bharmano ke Baithak, Noida UP 201301 | 21027 | 21027 | 21027 | 21027 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21027_DEL | New | New_Built | RTP | 9 | 14 | 30/120/270 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.5643 | 77.3722 | 21027 | 2021-03-10 | 2021-03-16 | 2021-03-19 | 11109.MNOI.42773722 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-04-13 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-17 |  |  |  | 2021-03-24 | ST202103102273 | S20210005329 |  |  | 2021-04-10 | P/FVC/DEL/1021521/2021 | 2021-04-17 | 2021-04-18 | DL/03/0031/0312/0031/06/05/11394/NS/18042021 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-18 | 2021-04-22 | 2021-04-24 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5830 | [17 empty] | 404-10-621027-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | EMCD_22_Mayur Vihar, Ph-I | MBTS,Plot Just Behind Mayur Vihar Ph 1 Metro Station,Opp DDA Flat No-(107-130)Gate No 2, Pocket-4, Mayur Vihar, Phase-I, Delhi-110091 | 20858 | 20858 | 20858 | 20858 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762297 | New | New_Built | GBM | 30 | 0 | 60/150/330 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6042 | 77.2897 | R/NN-566594 | 2021-02-25 | 2021-02-25 | 2021-03-24 | 111.MDEL.42772896 | 2021-04-15 | 2021-04-15 |  |  |  |  | 2021-04-17 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-21 |  |  |  | 2021-03-03 | ST202103077351 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020313/2021 | 2021-04-21 | 2021-04-22 | DL/01/5177/6275/0031/03/01/09988/NS/22042021 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-22 | 2021-04-26 | 2021-04-30 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 902 | [17 empty] | 404-10-620858-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Madhu Vihar | Mr. Manish Kakkar,Plot No-278 (Old NoRZ-81 S/F F/S ),Gali no 2,Near Navjeevan School,Madhu Vihar,Uttam Nagar,New Delhi 110059 | 20444 | 20444 | 20444 | 20444 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Alice | AT-DL-0034 | New | New_Built | RTP | 6 | 16 | 0/90/220 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6028 | 77.0646 | 20444 | 2021-03-06 | 2021-03-16 | 2021-03-22 | 111.MDEL.2004781 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-13 |  |  | 2021-03-27 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | 2021-04-16 |  |  |  | 2019-12-20 | 2019452689 | 2019452689 |  |  | 2020-04-24 | P/FVC/DEL/5944650/2020 | 2021-04-16 | 2021-04-17 | DL/01/0031/2633/0031/03/01/09970/NS/17042021 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-17 | 2021-04-21 | 2021-04-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5189 | [5 empty] | 2021-04-06 | 2021-04-13 | [10 empty] | 404-10-620444-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | SDMC_Subhash Nagar, New Delhi | SDMC Plot,Near Gurudwara,Behind Sarvodaya Bal Vidyalaya,Opp Plot no-N51, Block 1, Ashok Nagar,Subhash Nagar,New Delhi-110027 | 19611 | 19611 | 19611 | 19611 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1629417 | New | New_Built | Cow | 30 | 0 | 30/210/330 | COW |  |  | YES | >18HRS | No | 28.6401 | 77.1097 | R/NN-562033 | 2021-01-05 | 2021-01-08 | 2021-01-22 | 111.MDEL.93771097 | 2021-04-15 | 2021-04-15 |  |  |  |  | 2021-04-14 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-19 |  |  |  | 2021-01-23 | ST202101022175 | S20210001430 |  |  | 2021-02-25 | P/FVC/DEL/1017976/2021 | 2021-04-19 | 2021-04-21 | DL/01/5177/6272/0031/345/04/08243/NS/21042021 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-22 | 2021-04-24 | 2021-04-24 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9137 | [17 empty] | 404-10-619611-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sec-9,Behind Sangam | Near SDMC Primary School,Sector-9,R K Puram,Behind-Sangam vihar,New Delhi-110022 | 17963 | 17963 | 17963 | 17963 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1386214 | New | New_Built | Cow | 30 | 0 | 0/120/250 | COW |  |  | YES | >18HRS | No | 28.5747 | 77.1713 | R/NN-456572 | 2020-06-15 | 2020-07-28 | 2020-08-05 | 111.MDEL.47771713 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-06 |  |  | 2021-03-29 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-09 |  |  |  | 2020-08-12 | ST202008042354 | S20210012735 |  |  | 2020-08-20 | P/FVC/DEL/1004124/2020 | 2021-04-10 | 2021-04-11 | DL/01/5177/6264/0031/06/05/11364/NS/11042021 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-11 | 2021-04-15 | 2021-04-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 607 | [5 empty] | 2021-04-01 | 2021-04-10 | [10 empty] | 404-10-917963-43 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Shiv Vihar,Karawal Nagar | H.No. 226-A/8,Khasra No.51/1&51/2,Gali No.8,Phase-7,Shiv Vihar ,Karawal Nagar,Delhi-110094 | 20520 | 20520 | 20520 | 20520 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20520_DEL | New | New_Built | RTP | 9 | 13 | 0/180/290 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.7188 | 77.2812 | 20520 | 2019-11-22 | 2020-09-07 | 2020-09-10 | 111.MDEL.2164383 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-04-13 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-19 |  |  |  | 2020-09-19 | ST202009081772 | S20200004801 |  |  | 2020-09-29 | P/FVC/DEL/1007061/2020 | 2021-04-19 | 2021-04-21 | DL/01/0031/2636/0031/345/04/08244/NS/21042021 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-22 | 2021-04-26 | 2021-05-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8068 | [5 empty] | 2021-04-16 | 2021-04-19 | [10 empty] | 404-10-620520-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Nehru nagar(Relocation of 9882) | Mr. Nahar Singh Yadav S/o Ramsurup ,H .No New No. A-18, Old No. A-12, Village Arya Nagar, Kotgaon, Dayanand Nagar, Ghaziabad-201001 | 16831 | 16831 | 16831 | 16831 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1733955 | Relocation | New_Built | GBM | 30 | 0 | 60/160/280 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6567 | 77.4422 | R/NN-565710 | 2021-02-15 | 2021-03-09 | 2021-03-15 | 11109.MGBD.66774421 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-21 |  |  | 2021-04-10 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-25 |  |  |  | 2021-03-15 | ST202103091226 | S20210004773 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033397/2021 | 2021-04-25 | 2021-04-25 | DL/04/5177/0763/0031/03/01/09993/NS/25042021 | 2021-04-25 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-25 | 2021-05-25 | 2021-05-26 | 2021-05-24 | 2021-05-28 | 2021-06-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4170 | [5 empty] | 2021-04-16 | 2021-05-24 | [10 empty] | 404-10-916831-2 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | ANAND PARWAT | Sachin Gandhi S/O - Keval Gandhi, Anand Parwat,Property Bearing No. PP-55-A, Gali No. 10, Anand Parbat Industrial Area, New Delhi-110005 | 20538 | 20538 | 20538 | 20538 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762296 | New | New_Built | RTT | 12 | 9 | 0/180/290 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6613 | 77.1727 | R/NN-566593 | 2021-02-25 | 2021-02-25 | 2021-03-24 | 111.MDEL.13771726 | 2021-04-07 | 2021-04-08 |  |  |  |  | 2021-03-28 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | 2021-04-16 |  |  |  | 2021-03-03 | ST202103077352 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020315/2021 | 2021-04-16 | 2021-04-17 | DL/01/5177/6270/0031/06/05/11386/NS/17042021 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-17 | 2021-04-21 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 11240 | [5 empty] | 2021-04-08 | 2021-04-13 | [10 empty] | 404-10-620538-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Ashok Nagar Mandoli | 200/201, Khasra No. 631, Gali No. 11, Ashok Nagar Mandoli, Shahdara, Delhi-110032 | 19628 | 19628 | 19628 | 19628 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1383073 | New | New_Built | RTP | 9 | 13 | 70/170/270 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6944 | 77.2975 | R/NN-420805 | 2020-04-08 | 2020-06-14 | 2020-06-20 | 111.MDEL.44772975 | 2021-04-20 | 2021-04-20 |  |  |  |  | 2021-04-17 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-23 |  |  |  | 2020-06-23 | ST202007018572 | S20200001310 |  |  | 2020-07-10 | P/FVC/DEL/1001739/2020 | 2021-04-23 | 2021-04-24 | DL/01/5177/6277/0031/03/01/09991/NS/24042021 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-24 | 2021-04-28 | 2021-05-03 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4751 | [17 empty] | 404-10-619628-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Ahinsa Khand Ii(Relocation of 5677) | GOVERNMENT LAND,GREEN BELT,GHAZIABAD AUTHORITY,GBM LOCATION,NEAR OF GATE NO.05,VASUNDHARA - INDIRAPURAM RD,NITI KHAND 3,MANOJ VIHAR,INDIRAPURAM,POLICE STATION -INDIRAPURAM,POST OFFICE - SHIPRA SUN CITY | 21690 | 21690 | 21690 | 21690 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3021580 | Relocation | New_Built | GBM | 30 | 0 | 40/140/260 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6433 | 77.3787 | R/NN-627124 | 2019-04-27 | 2019-05-04 | 2019-05-08 | 11109.MGBD.33773787 | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2021-04-19 |  |  | 2020-08-12 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-08-07 |  |  |  | 2019-05-16 | 2019931428 | 2019931428 |  |  | 2019-06-25 | P/FVC/DEL/5683068/2019 | 2021-08-07 | 2021-08-09 | DL/04/5177/0765/0031/03/01/10093/NS/09082021 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-09 | 2021-08-10 | 2021-08-09 | 2021-08-16 | 2021-08-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2020-08-17 | 2021-08-07 | 130 mtr Lat Long Drift,Azimuth & Tower Height Mismatch_HOLD By Bharti Planning (Dismantling Approval Required),GSM Rectification Plan on 24th July 21 & SACFA Reapplied as Per New Lat Long,SACFA approval received on 31 July 21,Smart Pole Site Plan on 7 Aug 21 Night. | [9 empty] | 404-10-621690-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | sector-9,old vijay nagar,Ghaziabad | Satpal Yadav,House No. 1257 & 1258 , Sector-09, Old Vijay Nagar, Sabzi Mandi, Mawai Road, Ghaziabad-201009 | 20674 | 20674 | 20674 | 20674 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1754581 | New | New_Built | RTM | 14 | 6 | 150/220/290 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6494 | 77.4257 | R/NN-565951 | 2021-02-16 | 2021-02-24 | 2021-03-24 | 11109.MGBD.94774257 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-12 |  |  | 2021-03-28 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-13 | 2021-04-14 |  |  |  | 2021-03-03 | ST202103077355 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020314/2021 | 2021-04-14 | 2021-04-15 | DL/04/5177/0761/0031/345/04/08218/NS/15042021 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-15 | 2021-04-19 | 2021-04-22 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 291 | [5 empty] | 2021-04-08 | 2021-04-12 | [10 empty] | 404-10-620674-53 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Subhash Colony, Sector 60, Faridabad | HOUSE NO-1431 HARI VIHAR, RAKESH GUJJAR PALACE ADARSH NAGAR, BALLABHGARH, FARIDABAD HARYANA-121004 | 21196 | 21196 | 21196 | 21196 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1799924 | New | New_Built | GBM | 30 | 0 | 0/130/240 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.3203 | 77.317 | R/NN-567121 | 2021-03-04 | 2021-03-11 | 2021-03-17 | 11106.MFBD.02773170 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-19 |  |  | 2021-04-11 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-22 |  |  |  | 2021-01-29 | ST202101028321 | S20210001789 |  |  | 2021-03-21 | P/FVC/DEL/1020284/2021 | 2021-04-22 | 2021-04-23 | DL/02/5177/5019/0031/03/01/09989/NS/23042021 | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-24 | 2021-04-25 | 2021-04-23 | 2021-04-27 | 2021-04-30 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4116 | [5 empty] | 2021-04-16 | 2021-04-19 | [10 empty] | 404-10-621196-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Shalimar Garden | Amandeep Kaur and Beant Singh ,H.No. S-15B, Block B, Shalimar Garden Extension 2,Shalimar Garden ,Ghaiabad ,Uttar Pradesh ,201005 | 20407 | 20407 | 20407 | 20407 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762589 | New | New_Built | RTP | 9 | 10 | 60/220/310 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6884 | 77.3443 | R/NN-566632 | 2021-02-25 | 2021-02-25 | 2021-03-16 | 11109.MGBD.87773441 | 2021-04-07 | 2021-04-08 |  |  |  |  | 2021-03-28 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  | 2021-03-05 | ST202103080625 | S20210004229 |  |  | 2021-03-11 | P/FVC/DEL/1019878/2021 | 2021-04-14 | 2021-04-15 | DL/04/5177/0760/0031/03/01/09966/NS/15042021 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-15 | 2021-04-19 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5617 | [5 empty] | 2021-04-08 | 2021-04-13 | [10 empty] | 404-10-620407-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | EMCD_1_Trilokpuri | PARK NEAR E-72, BHARAT GAS AGENCY, JANTA FLATS , CHILLA VILLAGE,NEW DELHI 110096 | 18012 | 18012 | 18012 | 18012 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1820514 | New | New_Built | GBM | 30 | 0 | 30/180/240 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.5977 | 77.3045 | R/NN-567567 | 2021-03-09 | 2021-03-17 | 2021-03-24 | 111.MDEL.77773040 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-04-13 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-19 |  |  |  | 2021-01-29 | ST202101028323 | S20210001789 |  |  | 2021-03-21 | P/FVC/DEL/1020281/2021 | 2021-04-20 | 2021-04-21 | DL/01/5177/6274/0031/345/04/08245/NS/21042021 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-22 | 2021-04-24 | 2021-04-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1047 | [5 empty] | 2021-04-17 | 2021-04-20 | [10 empty] | 404-10-618012-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Kundan Colony 2, Faridabad | H No-C/133, Bhatia Colony, Infrnit Of Ridhi Sidhi ClinicBallabhgarh, Faridabad 121004 | 21141 | 21141 | 21141 | 21141 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1548121 | New | New_Built | RTT | 9 | 11 | 90/210/280 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.3351 | 77.3327 | R/NN-560093 | 2020-12-03 | 2020-12-14 | 2021-01-22 | 11106.MFBD.55773324 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-13 |  |  | 2021-03-22 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-16 |  |  |  | 2021-01-23 | ST202101022172 | S20210001430 |  |  | 2021-02-25 | P/FVC/DEL/1017973/2021 | 2021-04-16 | 2021-04-17 | DL/02/5177/5018/0031/06/05/11382/NS/17042021 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-17 | 2021-04-21 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4101 | [5 empty] | 2021-04-01 | 2021-04-13 | [10 empty] | 404-10-621141-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | BPTP The Resort | Mr. Yadveer(Estate Manager),BPTP The Resort,Block G,Plot No. GH-3,Sector 75, Faridabad, Haryana 121002 | 17896 | 17896 | 17896 | 17896 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL/DEL/054 | New | New_Built | RTP | 6 | 61 | IBS (2G+TD),0/90(2G+FD+TD+L_2100+L_900) | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.3632 | 77.3498 | 17896 | 2019-11-13 | 2021-03-12 | 2021-03-13 | 11106.MFBD.32773498 | 2021-04-19 | 2021-04-20 |  |  |  |  | 2021-04-16 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-25 |  |  |  | 2021-03-13 | ST202103089549 | S20210004658 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033707/2021 | 2021-04-25 | 2021-04-25 | DL/02/5305/0111/0031/345/04/08254/NS/25042021 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-04-25 | 2021-04-29 | 2021-05-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9621 | [5 empty] | 2021-04-23 | 2021-04-24 | [10 empty] | 404-10-617896-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Dichaon Kalan (Relocation of 10071) | House No. 127,Dichaon Kalan,South West Delhi,Near-MTNL Tower,Delhi-110043 | 13792 | 13792 | 13792 | 13792 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/8410 | Relocation | New_Built | RTP | 9 | 12 | 100/170/220 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | No | 28.642 | 76.9826 | T20DL01269 | 2020-01-21 | 2020-10-02 | 2020-10-12 | 111.MDEL.2184029 | 2021-04-01 | 2021-04-03 | 2021-04-03 | 2021-10-13 |  |  | 2021-03-30 | 2021-10-14 | 2021-10-19 | 2021-10-20 | 2021-10-20 | 2021-10-22 |  |  |  | 2020-10-15 | ST202010108922 | S20200006167 |  |  | 2020-12-07 | P/FVC/DEL/1011210/2020 | 2021-10-22 | 2021-10-23 | DL/01/5126/1547/0031/03/01/10248/NS/23102021 | 2021-10-23 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4498 | [5 empty] | 2021-04-03 | 2021-10-18 | Site Diamantled & SRN Pending due to Parent Site Access Issue_10071(Reliance),Issue resolved on 13 Oct 21,10 Port Antenna Not in stock,Locator Inactive resolved on 18 Oct 21,Partially Installed_Cabinet Not Delivered as on 20 Oct 21,900 band 3rd sec disabled & service degraded alarm, 3rd RET Disabled(71072) as on 22 Oct 21 | [9 empty] | 404-10-613792-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219B3 L-2100 RRU 2219B1, Available on parent site TD RRUS 4418
Del | FY20_21 | Q1 | South City -2 | Infront of S 3, 4 & 5 B block commercial market, South City 2 Sec-49 GGN-122018 | 10795 | 10795 | 10795 | 10795 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1466152 | New | New_Built | GBM | 24 | 0 | 40/180/290 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.4167 | 77.0465 | R/NN-485620 | 2020-10-19 | 2020-10-26 | 2020-11-09 | 11106.MGGN.66770464 | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-04-19 |  |  | 2021-03-22 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-07-17 |  |  |  | 2020-11-12 | ST202011145344 | S20200008117 |  |  | 2020-12-25 | P/FVC/DEL/1013807/2020 | 2021-07-17 | 2021-07-18 | DL/05/5177/5281/0031/04/01/00468/NS/19072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-26 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 971 | [5 empty] | 2021-04-02 | 2021-07-24 | Partially Material Delivered/ Installation Planned on 15 July Nyt/ Crane & access approval required_TDD 2nd sector disable Issue resolved on 24 july 21 | [9 empty] | 404-10-910795-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+FD+TD+L2100 | 2G+FD RRU 2219 ,L_2100 RRUS 12B1, TD RRU 4418
Del | FY20_21 | Q1 | Vill:-Sikandar Pur Bada | Maya Devi W/O Satpal Singh, Khewat No. - 607, Khatoni No. – 610, Vill - Sikanderpur Badha, Gurgaon | 17095 | 17095 | 17095 | 17095 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | TVI | ATHAZGN0782 | New | New_Built | GBT | 30 | 0 | 20/90/260 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.4045 | 76.9495 | 17095 | 2020-05-26 | 2020-08-04 | 2020-08-16 | 11106.MGGN.44769494 | 2021-04-15 | 2021-04-16 |  |  |  |  | 2021-04-14 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-19 |  |  |  | 2020-08-27 | ST202008053876 | S20200003565 |  |  | 2020-09-01 | P/FVC/DEL/1004902/2020 | 2021-04-20 | 2021-04-21 | DL/05/5113/0107/0031/345/04/08241/NS/21042021 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-22 | 2021-04-24 | 2021-04-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4545 | [5 empty] | 2021-04-17 | 2021-04-20 | [10 empty] | 404-10-617095-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Piyawali Dadri | H No-89,Village-Piyawali Dadri,GB Nagar,U.P.201008 | 20849 | 20849 | 20849 | 20849 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20849_DEL | Relocation | New_Built | RTP | 9 | 11 | 0/120/240 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.611 | 77.5819 | 20849 | 2020-08-20 | 2020-09-25 | 2020-10-07 | 11109.MNOI.10775818 | 2021-04-06 | 2021-04-06 |  |  |  |  | 2021-03-27 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | 2021-04-16 |  |  |  | 2020-11-03 | ST202011133620 | S20200007510 |  |  | 2020-12-11 | P/FVC/DEL/1011946/2020 | 2021-04-16 | 2021-04-17 | DL/03/0031/0310/0031/06/05/11385/NS/17042021 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-17 | 2021-04-21 | 2021-04-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5770 | [5 empty] | 2021-04-06 | 2021-04-13 | [10 empty] | 404-10-620849-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | SECTOR 25,ROHINI | House No. 64/65, Pocket-9, Sec-25, Rohini, Delhi-110085 | 25253 | 25253 | 25253 | 25253 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388106 | New | New_Built | RTT | 12 | 13 | 0/90/240 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.7365 | 77.0895 | R/NN-464524 | 2020-08-07 | 2020-08-26 | 2020-08-26 | 111.MDIL.1593432 | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-04-08 |  |  | 2021-03-27 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-10 | 2021-04-10 |  |  |  | 2020-09-11 | ST202009065510 | S20200004327 |  |  | 2020-09-18 | P/FVC/DEL/1005808/2020 | 2021-04-10 | 2021-04-11 | DL/01/5177/6263/0031/06/05/11365/NS/11042021 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-12 | 2021-04-16 | 2021-04-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 9104 | [5 empty] | 2021-04-02 | 2021-04-12 | [10 empty] | 404-10-625253-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Phi Chi Extension | GBM Location,Behind Of Prateek Residency,Plot No.149,D-Block,Phase-3,Beta-2,Gereater Noida,Uttar Pradesh-201310 | 13259 | 13259 | 13259 | 13259 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1374576 | New | New_Built | GBM | 30 | 0 | 0/120/240 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.4482 | 77.5233 | R/RES-436548 | 2020-11-11 | 2020-12-02 | 2020-12-10 | 11109.MNOI.61775234 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-02 |  |  | 2021-05-02 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-04 | 2021-05-05 |  |  |  | 2021-04-08 | ST202104132992 | S20210006375 |  | 2021-04-29 | 2021-06-07 | P/FVC/DEL/1027989/2021 | 2021-05-05 | 2021-05-07 | DL/03/5177/0888/0031/06/05/11490/NS/07052021 | 2021-05-07 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 | 2021-05-08 | 2021-05-12 | 2021-05-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16081 | [5 empty] | 2021-05-01 | 2021-05-02 | [10 empty] | 404-10-613259-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Puri Pratham Sector-84 | Khewat No. 814/787, Khatoni No. 897, Near by english wine shop,Village Kheri Kalan, Tehsil and District Faridabad-121002, 121002 | 25475 | 25475 | 25475 | 25475 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1739757 | New | New_Built | GBM | 30 | 0 | 20/250/320 | COW |  |  | YES | >18HRS | No | 28.4081 | 77.3629 | R/NN-566086 | 2021-02-17 | 2021-03-03 | 2021-03-05 | 11106.MFBD.81773628 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-16 |  |  | 2021-03-27 | 2021-04-17 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-23 |  |  |  | 2021-02-18 | ST202102058255 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019522/2021 | 2021-04-23 | 2021-04-24 | DL/02/5177/5020/0031/03/01/09992/NS/24042021 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-24 | 2021-04-26 | 2021-04-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4528 | [5 empty] | 2021-04-01 | 2021-04-23 | [10 empty] | 404-10-625475-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Western green Rangpuri | Mr.Vikas, Khasra No. 764 Min., Village Rangpuri, New Delhi-110037 | 20995 | 20995 | 20995 | 20995 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1800135 | New | New_Built | GBM | 30 | 0 | 70/200/320 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.5282 | 77.1255 | R/NN-567569 | 2021-03-09 | 2021-03-11 | 2021-03-24 | 111.MDEL.81771254 | 2021-04-15 | 2021-04-15 |  |  |  |  | 2021-04-17 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-20 | 2021-04-23 |  |  |  | 2021-03-15 | ST202103091228 | S20210004773 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033392/2021 | 2021-04-23 | 2021-04-25 | DL/01/5177/6276/0031/06/05/11457/NS/25042021 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-04-25 | 2021-04-29 | 2021-05-01 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 600 | [5 empty] | 2021-04-20 | 2021-04-23 | [10 empty] | 404-10-620995-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Mahagun Mirabella | Plot No. 3,Florentia Tower, Mahagun Mirabella , Sec 79 ,Noida ,Uttar Pradesh 201305 | 13538 | 13538 | 13538 | 13538 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_13538_DEL | New | New_Built | RTP | 5 | 94.4 | 0/90/180/270 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.5638 | 77.3982 | 13538 | 2021-01-29 | 2021-03-01 | 2021-03-11 | 11109.MNOI.37773981 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-19 |  |  |  | 2021-03-13 | ST202103089557 | S20210004658 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033715/2021 | 2021-04-19 | 2021-04-20 | DL/03/0031/0314/0031/03/01/09982/NS/20042021 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-22 | 2021-04-20 | 2021-04-24 | 2021-05-21 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 18351 | [17 empty] | 404-10-613538-52 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | VILL FATHEPUR | Near Purana Kua & Khasra No.-375 ,Vill Rampur Fatehpur ,post Maincha ,G.B Nagar UP 201310 | 20281 | 20281 | 20281 | 20281 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1754570 | New | New_Built | GBM | 30 | 0 | 0/120/230 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.443 | 77.5892 | R/NN-565958 | 2021-02-16 | 2021-02-22 | 2021-02-25 | 11109.MGBD.35775876 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-16 |  |  | 2021-03-22 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-22 |  |  |  | 2021-03-03 | ST202103077348 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020311/2021 | 2021-04-22 | 2021-04-23 | DL/03/5177/0894/0031/06/05/11427/NS/23042021 | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-04-24 | 2021-04-24 | 2021-04-25 | 2021-04-23 | 2021-04-27 | 2021-04-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8005 | [5 empty] | 2021-04-01 | 2021-04-16 | [10 empty] | 404-10-620281-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | C12 Supertech Ecovillage-2 | Mr.Azeem(Estate Manager),Building Name-C12,Plot no. GH-01,Supertech Ecovillage-2,Sector 16 B,Greater Noida ,Uttar Pradesh-201310 | 18189 | 18189 | 18189 | 18189 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Fine bunch | FB0021 | New | New_Built | RTP | 6 | 64 | 330/90/220 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6114 | 77.4444 | 18189 | 2021-02-24 | 2021-02-26 | 2021-03-14 | 11109.MNOI.14774444 | 2021-04-19 | 2021-04-20 |  |  |  |  | 2021-04-18 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-24 |  |  |  | 2021-03-13 | ST202103089554 | S20210004658 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033708/2021 | 2021-04-24 | 2021-04-25 | DL/03/0031/0316/0031/03/01/09996/NS/25042021 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-25 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-04-25 | 2021-04-29 | 2021-05-05 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5809 | [17 empty] | 404-10-618189-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Rasid Gate, Loni | Saeed Kureshi S/o Rasid Kureshi Main Rashid Gate,House No. 120,Near Sunrise Pulic School ,Loni,Mohalla Jamalpura, Near Rashid Ali Gate, Pargana Loni, Tehsil and District Ghaziabad-201102 | 21279 | 21279 | 21279 | 21279 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762298 | New | New_Built | RTP | 9 | 12.6 | 40/160/270 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | No | 28.7524 | 77.2877 | R/NN-566597 | 2021-02-25 | 2021-02-25 | 2021-03-24 | 11109.MGBD.23772876 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-12-07 |  |  | 2021-04-03 | 2021-12-07 | 2021-12-12 | 2021-12-12 | 2021-12-13 |  |  |  |  | 2021-03-03 | ST202103077354 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020317/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Installed_MW Interference Issue_Plan after Id | Indus | PRI_With Material |  |  | Indus |  | M1 | 4477 | [5 empty] | 2021-04-01 |  | Public Issue_Work on Night,SRN Done,again Issue cleared on 07.12.21,Access Issue as on 13.12.21,Public Issue & Farend Installed as on 21.01.22,MW alignment WIP/Access required at Nearend as on 23.03.22 | [14 empty] | Installed_MW Interference Issue_Plan after Id | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Balram Nagar ext. , Loni | Hema Lata,House No.294,Khasra No.1/10,Min Vijay Vihar Colony,Village Ahmed Nagar,Nawada Pargana ,Police Chowki And Post Office -Loni ,Tehsil And District-Ghaziabad,Uttar Pradesh-201102 | 21378 | 21378 | 21378 | 21378 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1761172 | New | New_Built | RTP | 9 | 11 | 110/200/340 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.7453 | 77.2854 | R/NN-566595 | 2021-02-25 | 2021-02-25 | 2021-03-24 | 11109.MGBD.52772854 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-13 |  |  | 2021-03-28 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-16 |  |  |  | 2021-03-03 | ST202103077353 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020321/2021 | 2021-04-16 | 2021-04-18 | DL/04/5177/0762/0031/345/04/08226/NS/18042021 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-18 | 2021-04-22 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4477 | [5 empty] | 2021-04-07 | 2021-04-13 | [10 empty] | 404-10-621378-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | SHIV ENCLAVE, ISMAILPUR | Hno. B-56, Shiv Enclave, Faridabad Haryana- 121003 | 21321 | 21321 | 21321 | 21321 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1776887 | New | New_Built | RTT | 12 | 15 | 10/140/250 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.4978 | 77.3424 | R/NN-456275 | 2021-02-05 | 2021-03-03 | 2021-03-15 | 11106.MFBD.78773424 | 2021-04-01 | 2021-04-01 |  |  |  |  | 2021-04-03 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-05 | 2021-04-08 |  |  |  | 2021-01-08 | ST202101005368 | S20210000384 |  |  | 2021-01-16 | P/FVC/DEL/1016291/2021 | 2021-04-08 | 2021-04-09 | DL/02/5177/5017/0031/06/05/11362/NS/09042021 | 2021-04-09 | 2021-04-09 | 2021-04-09 | 2021-04-09 | 2021-04-09 | 2021-04-10 | 2021-04-10 | 2021-04-11 | 2021-04-09 | 2021-04-13 | 2021-04-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M0 | 17165 | [5 empty] | 2021-04-01 | 2021-04-08 | [10 empty] | 404-10-621321-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Garhii Chokhandi | Kh.no.26M,village,Garhi chokhandi,pargana and tehsil dadri district ghaziyabad U.P-201301 | 21176 | 21176 | 21176 | 21176 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1700931 | New | New_Built | GBM | 30 | 0 | 50/190/330 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.6076 | 77.4037 | R/NN-564581 | 2021-02-02 | 2021-02-14 | 2021-03-01 | 11109.MGBD.75774037 | 2021-04-01 | 2021-04-01 |  |  |  |  | 2021-03-28 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-05 | 2021-04-06 |  |  |  | 2021-03-02 | ST202103075345 | S20210004046 |  |  | 2021-03-21 | P/FVC/DEL/1020364/2021 | 2021-04-06 | 2021-04-07 | DL/04/5177/0759/0031/345/04/08205/NS/07042021 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-09 | 2021-04-09 | 2021-04-10 | 2021-04-08 | 2021-04-12 | 2021-04-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 11466 | [5 empty] | 2021-04-01 | 2021-04-04 | [10 empty] | 404-10-621176-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Binola Near Auto International | Khata No-628/753,Binola Near Auto international comapany, Tehsil - Pataudi, Distt. - Gurgaon. 122413 | 21297 | 21297 | 21297 | 21297 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | ATHAZGN0812 | New | New_Built | RTT | 15 | 10.5 | 0/90/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.314 | 76.8739 | 21297 | 2020-12-28 | 2021-02-18 | 2021-02-26 | 11106.MGGN.40768739 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-18 |  |  |  | 2021-02-23 | ST202102066894 | S20210003586 |  | 2021-03-17 | 2021-07-08 | P/FVC/DEL/1033738/2021 | 2021-04-19 | 2021-04-20 | DL/05/5113/0106/0031/03/01/09981/NS/20042021 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-22 | 2021-04-20 | 2021-04-24 | 2021-04-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4919 | [17 empty] | 404-10-621297-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | MILAN GARDEN | Property No. 10, Khasra No. 10/10/2, Village Mandoli, G-Block, Milan Garden, Illaqa Shahdara, Delhi-110093 | 21314 | 21314 | 21314 | 21314 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1669828 | New | New_Built | RTT | 15 | 8 | 70/260/320 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.7121 | 77.3197 | R/NN-563678 | 2021-01-20 | 2021-02-06 | 2021-02-13 | 111.MDEL.20773197 | 2021-04-01 | 2021-04-01 |  |  |  |  | 2021-04-01 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-05 | 2021-04-15 |  |  |  | 2021-02-16 | ST202102053961 | S20210002988 |  |  | 2021-03-07 | P/FVC/DEL/1019445/2021 | 2021-04-15 | 2021-04-16 | DL/01/5177/6269/0031/06/05/11380/NS/16042021 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-16 | 2021-04-20 | 2021-04-22 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4696 | [5 empty] | 2021-04-01 | 2021-04-14 | [10 empty] | 404-10-621314-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Krishan Vihar, S -Block | Mr.Vijay S/O Mr.Har Chand,House No.31B,Shop No.57 to 59,Khasra No.24/2,Block-G,Solanki Market,Krishan Vihar Near Dharam Market,Police Station Sultanpuri,Maharishi Valmiki Marg,Sultanpuri Post Office,Delhi-110086 | 21440 | 21440 | 21440 | 21440 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1763337 | New | New_Built | RTP | 9 | 13 | 80/180/280 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.7041 | 77.0807 | R/NN-566692 | 2021-02-24 | 2021-03-13 | 2021-03-18 | 111.MDEL.41770806 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-03 |  |  | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-05-06 |  |  |  | 2021-03-24 | ST202103102270 | S20210005329 |  |  | 2021-04-10 | P/FVC/DEL/1021534/2021 | 2021-05-06 | 2021-05-07 | DL/01/5177/6285/0031/03/01/10006/NS/07052021 | 2021-05-07 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 | 2021-05-08 | 2021-05-12 | 2021-05-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4936 | [5 empty] | 2021-05-01 | 2021-05-03 | [10 empty] | 404-10-621440-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Samsung india(Relocation of 27334) | SAMSUNG FACTORY, Block B, Sector 81, Noida, Uttar Pradesh 201305 NOIDA | 21400 | 21400 | 21400 | 21400 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21400_DEL | New | New_Built | RTP | 9 | 18 | 30/160/300/90/180 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.5517 | 77.3942 | 21400 | 2021-01-27 | 2021-03-01 | 2021-03-11 | 11109.MNOI.07773977 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-20 |  |  | 2021-04-18 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-09-13 |  |  |  | 2021-03-05 | ST202103080628 | S20210004229 |  |  | 2021-03-11 | P/FVC/DEL/1019882/2021 | 2021-09-13 | 2021-09-15 | DL/03/0031/0330/0031/06/05/12074/NS/15092021 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-11-25 | 2021-09-15 | 2021-09-20 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10824 | [5 empty] | 2021-04-16 | 2021-09-12 | Partially Installed_Power Issue_Team Planned on 16th July But Not resolved,Partially Installed_Infra/FMS Installation Pending(1024673) FMS done on 7th Sep 21,Site survey on 8th Sep 21 and Material req raise on 8 Sep 21,Access Issue at Saturday & Sunday,Plan on 12 Sep 21 | [9 empty] | 404-10-621400-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0,FD RRU 2219B3, L_2100 RRU 2219 B3, TD RRU 4412 Available on Parent Site one sector RRU material to be Sent
Del | FY20_21 | Q1 | B-Block, Kaushik Enclave | KH N0 - 36/7, 36/8, 36/9. B-Block, Kaushik EnclaveB Block, Gali No. 22, Main 25 Feet Road, Kaushik Enclave, Burari, Delhi-110086 | 21291 | 21291 | 21291 | 21291 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1721689 | New | New_Built | RTP | 9 | 14 | 10/160/250 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.7626 | 77.1909 | R/NN-565226 | 2021-02-10 | 2021-02-12 | 2021-03-01 | 111.MDEL.26771908 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-06 |  |  | 2021-03-29 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-10 |  |  |  | 2021-02-18 | ST202102058249 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019515/2021 | 2021-04-10 | 2021-04-11 | DL/01/5177/6261/0031/345/04/08213/NS/11042021 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-11 | 2021-04-15 | 2021-04-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M0 | 9354 | [5 empty] | 2021-04-01 | 2021-04-06 | [10 empty] | 404-10-621291-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | NEHRU NAGAR | House No. 502, Gali No. 11, Nehru Nagar, New Delhi-110008 | 21286 | 21286 | 21286 | 21286 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1721643 | New | New_Built | RTT | 12 | 12.5 | 40/160/270 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6638 | 77.1665 | R/NN-565203 | 2021-02-10 | 2021-02-12 | 2021-02-25 | 111.MDEL.37771664 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-06 |  |  | 2021-03-28 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-08 | 2021-04-10 |  |  |  | 2021-02-18 | ST202102058248 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019514/2021 | 2021-04-10 | 2021-04-16 | DL/01/5177/6260/0031/03/01/09967/NS/16042021 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-04-18 | 2021-04-16 | 2021-04-20 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M0 | 917 | [5 empty] | 2021-04-01 | 2021-04-16 | [10 empty] | 404-10-621286-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | DSIDC NARELA | Plot No- B-2598, DSIDC Industrial Area, Narela, Delhi-110040 | 21357 | 21357 | 21357 | 21357 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1721580 | New | New_Built | RTP | 9 | 14.5 | 0/120/260 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.8341 | 77.0968 | R/NN-565192 | 2021-02-10 | 2021-02-14 | 2021-02-26 | 111.MDEL.40770967 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-02 |  |  | 2021-03-28 | 2021-04-05 | 2021-04-05 | 2021-04-06 | 2021-04-06 | 2021-04-06 |  |  |  | 2021-02-23 | ST202102066891 | S20210003586 |  | 2021-03-17 | 2021-07-08 | P/FVC/DEL/1033737/2021 | 2021-04-13 | 2021-04-14 | DL/01/5177/6268/0031/03/01/09964/NS/14042021 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-14 | 2021-04-18 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9018 | [5 empty] | 2021-04-01 | 2021-04-12 | [10 empty] | 404-10-621357-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Iskcon temple(Relocation of 656) | Nearby 108/12 Amrit puri, Chandrawati Chaudhary Smarak Trust, Desh Raj Campus,Behind Krishna Dutt Health Centre C Block East Of Kailash New delhi-110066 | 21684 | 21684 | 21684 | 21684 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1736899 | Relocation | New_Built | Cow | 30 | 0 | 10/240/300 | COW |  |  | YES | >18HRS | No | 28.5565 | 77.2548 | R/NN-565735 | 2021-02-15 | 2021-02-17 | 2021-03-09 | 111.MDEL.65772547 | 2021-04-19 | 2021-04-19 |  |  |  |  | 2021-04-15 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-27 | 2021-04-29 |  |  |  | 2021-03-15 | ST202103091230 | S20210004773 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033410/2021 | 2021-04-29 | 2021-04-30 | DL/01/5177/6282/0031/03/01/10003/NS/30042021 | 2021-04-30 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 | 2021-05-08 | 2021-05-12 | 2021-05-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11014 | [5 empty] | 2021-04-19 | 2021-05-08 | [10 empty] | 404-10-621684-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0,FD RRU 2219 B3,L_2100 RRU 12B1, TD RRU 4412, Available on parent site
Del | FY20_21 | Q1 | Village Bada Gurgaon(Relocation of 5165) | I P Jain (Northex Estate Limited) GDITL Northex Tower, A-9, Opposite Ring Road,Netaji Subhash Place, Pitampura,Delhi-110034 | 21685 | 21685 | 21685 | 21685 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1739087 | Relocation | New_Built | RTP | 6 | 41 | 30/150/250 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6918 | 77.1523 | R/NN-565997 | 2021-02-16 | 2021-02-22 | 2021-03-04 | 111.MDEL.18771523 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-11 |  |  | 2021-04-09 | 2021-04-11 | 2021-04-11 | 2021-04-12 | 2021-04-12 | 2021-04-12 |  |  |  | 2021-03-05 | ST202103080631 | S20210004229 |  |  | 2021-03-11 | P/FVC/DEL/1019886/2021 | 2021-04-16 | 2021-04-18 | DL/01/5177/6271/0031/345/04/08227/NS/18042021 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-18 | 2021-04-22 | 2021-04-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5661 | [5 empty] | 2021-04-07 | 2021-04-16 | [10 empty] | 404-10-621685-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | (2G+FD+) RRU 2219,L_2100 12B1 TD RRU 4412
Del | FY20_21 | Q1 | Ranjit Vihar | B-43 Khasra No.15/22 , Ranjit Vihar,Nilothi Extension,New Delhi-110041 | 19702 | 19702 | 19702 | 19702 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | FCM_TOWER | NCR/27 | New | New_Built | RTP | 9 | 15.3 | 0/130/200 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6538 | 77.0713 | 19702 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 111.MDEL.38770713 | 2021-04-14 | 2021-04-14 | 2021-04-15 | 2021-04-19 |  |  | 2021-04-09 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-22 | 2021-04-26 |  |  |  | 2020-10-20 | ST202010115950 | S20200006476 |  |  | 2020-12-06 | P/FVC/DEL/1011018/2020 | 2021-04-26 | 2021-04-27 | DL/01/5410/0001/0031/345/04/08262/NS/27042021 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-04-27 | 2021-05-01 | 2021-05-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4180 | [5 empty] | 2021-04-15 | 2021-04-26 | [10 empty] | 404-10-619702-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | VILLAGE SURAJPUR | Khasra No.203,Surajpur,Behind Police Chowki Kasba Surajpur,Dadri,Gautam Buddha Nagar,Uttar Pradesh-201306 | 20250 | 20250 | 20250 | 20250 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20250_DEL | New | New_Built | RTM | 5 | 18 | 10/120/240 | STANDARD_PRODUCT |  | LAST_AOP_SO | YES | >18HRS | No | 28.5149 | 77.4831 | 20250 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 11109.MNOI.48774831 | 2021-04-14 | 2021-04-14 |  |  |  |  | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-16 | 2021-04-18 |  |  |  | 2020-12-07 | ST202012166278 | S20200009174 |  |  | 2020-12-23 | P/FVC/DEL/1013397/2020 | 2021-04-18 | 2021-04-20 | DL/03/0031/0313/0031/06/05/11396/NS/20042021 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | 2021-04-22 | 2021-04-20 | 2021-04-24 | 2021-04-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4809 | [5 empty] | 2021-04-16 | 2021-04-20 | [10 empty] | 404-10-620250-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sky Mark One | Skymark Building,Plot No. H-10, Sector 98, Noida, Uttar Pradesh-201303 | 27693 | 27693 | 27693 | 27693 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | SIS | UPSM422021 | New | New_Built | IBS | 0 | 20 | IBS/IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | No | 28.5321 | 77.3612 | 27693 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 11109.MNOI.21773612 | 2021-04-17 | 2021-04-18 | 2021-04-18 | 2021-04-20 |  |  | 2021-04-19 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-27 | [10 empty] | 2021-04-27 |  | IBS | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-04 | 2021-05-04 | 2021-05-05 | 2021-05-03 | 2021-05-07 | 2021-05-08 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4015 | [5 empty] | 2021-04-18 | 2021-05-03 | [10 empty] | 404-10-927693-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219, TD RRU 4418
Del | FY20_21 | Q1 | CWG Village,tower 24(Relocation of 7126) | Tower No 24 CWG Village,Behind Akshardham,Pandav Nagar,New Delhi-110092 | 21694 | 21694 | 21694 | 21694 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | AIPL | AIPLDLSZ21S0053 | Relocation | New_Built | RTP | 6 | 28 | 20/90/140 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6114 | 77.2721 | 21694 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 111.MDEL.14772720 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-27 |  |  | 2021-04-18 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-04-29 | 2021-05-20 |  |  |  | 2021-02-23 | ST202102067359 | S20210003587 |  |  | 2021-04-28 | P/FVC/DEL/1022238/2021 | 2021-05-20 | 2021-05-21 | DL/01/5404/0011/0031/345/04/08284/NS/21052021 | 2021-05-21 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-23 | 2021-05-22 | 2021-05-24 | 2021-05-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8042 | [5 empty] | 2021-04-22 | 2021-05-19 | [10 empty] | 404-10-621694-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | CWG Village,TOWER 2(Relocation of 7123) | Tower No 02 CWG Village,Behind Akshardham,Pandav Nagar,New Delhi-110092 | 21692 | 21692 | 21692 | 21692 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | AIPL | AIPLDLSZ21S0062 | Relocation | New_Built | RTP | 6 | 22 | 170/230/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6125 | 77.2738 | 21692 | 2021-02-05 | 2021-02-15 | 2021-02-19 | 111.2861.24772737 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-07-23 |  |  | 2021-04-17 | 2021-07-23 | 2021-07-24 | 2021-07-26 | 2021-07-27 | 2021-07-31 |  |  |  | 2021-02-23 | ST202102067360 | S20210003587 |  |  | 2021-04-28 | P/FVC/DEL/1022227/2021 | 2021-08-02 | 2021-08-03 | DL/01/5404/0012/0031/03/01/10085/NS/03082021 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-07 | 2021-08-03 | 2021-08-07 | 2021-08-03 | 2021-08-09 | 2021-08-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8042 | [5 empty] | 2021-04-22 | 2021-08-02 | Far end PRI (Site 8042) No access on the site due to covid Issue and no other Far end is Feasible,Consumable Material_69078(Material return on 25th July 21 & Consumable Delivered on 26.07.21)_again Farend PRI 8042 reported on 27th July 21 & Issue Closed on 31st July 21 & Media issue reported on 31st July21,Media Issue Closed on 02 Aug 21 | [9 empty] | 404-10-621692-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | FD RRU 2219, TD RRU 4418 Available On Parent Site ,(2G+L_2100) RRU 2219
Del | FY20_21 | Q1 | CWG Village,TOWER 15(Relocation of 7125) | Tower No 15 CWG Village,Behind Akshardham,Pandav Nagar,New Delhi-110092 | 21693 | 21693 | 21693 | 21693 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | AIPL | AIPLDLSZ21S0071 | Relocation | New_Built | RTP | 6 | 28 | 50/150/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.61 | 77.2731 | 21693 | 2021-02-05 | 2021-02-15 | 2021-02-19 | 111.2860.99772731 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-07-23 |  |  | 2021-04-20 | 2021-07-23 | 2021-07-24 | 2021-07-26 | 2021-07-27 | 2021-07-31 |  |  |  | 2021-02-23 | ST202102067361 | S20210003587 |  |  | 2021-04-28 | P/FVC/DEL/1022229/2021 | 2021-08-02 | 2021-08-03 | DL/01/5404/0013/0031/03/01/10086/NS/03082021 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-07 | 2021-08-03 | 2021-08-07 | 2021-08-03 | 2021-08-16 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8042 | [5 empty] | 2021-04-22 | 2021-07-31 | Far end PRI (Site 8042) No access on the site due to covid Issue and no other Far end is Feasible,Consumable Material_69081(Material return on 25th July 21 & Consumable delivered on 26th July 21)_again Farend PRI 8042 reported on 27th July 21 & Issue Closed on 31st July 21 | [9 empty] | 404-10-621693-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | FD RRU 2219 ,1*TD RRU 4412 Available On Parent Site ,(2G+L_2100) RRU 2219,2* TD RRU 4418
Del | FY20_21 | Q1 | DDA_Sec-6 Dwarka | GBM LOCATION DDA PAK DWARKA,INFROT OF PLOT NO 5 & 6, SECTOR 6, DWARKA | 18672 | 18672 | 18672 | 18672 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1820513 | New | New_Built | GBM | 30 | 0 | 90/180/320 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.5943 | 77.0626 | R/NN-567566 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 111.MDEL.41770634 | 2021-04-24 | 2021-04-24 |  |  |  |  | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-27 | 2021-05-01 |  |  |  | 2021-03-26 | ST202103107523 | S20210005562 |  | 2021-04-15 | 2021-06-14 | P/FBC/DEL/1031312/2021 | 2021-05-01 | 2021-05-01 | DL/01/5177/6283/0031/03/01/10004/NS/01052021 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-02 | 2021-05-02 | 2021-05-03 | 2021-05-01 | 2021-05-05 | 2021-05-07 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 615 | [17 empty] | 404-10-618672-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | GURDAYAL VIHAR | Mr. Rajveer Singh,Open Plot Of,Khasra No. 69/11,Near Fair Deal Properties,Chanchal Park,Ranhola Extesion,New Delhi-110041 | 20331 | 20331 | 20331 | 20331 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1872289 | New | New_Built | GBM | 30 | 0 | 90/180/340 | COW |  |  | YES | >18HRS | No | 28.6532 | 77.0224 | R/NN-569133 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 111.MDEL.31770224 | 2021-04-24 | 2021-04-24 |  |  |  |  | 2021-04-23 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-27 | 2021-04-28 |  |  |  | 2021-03-26 | ST202103107518 | S20210005562 |  | 2021-04-15 | 2021-06-14 | P/FBC/DEL/1031326/2021 | 2021-04-28 | 2021-04-29 | DL/01/5177/6281/0031/03/01/10002/NS/29042021 | 2021-04-29 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-02 | 2021-05-02 | 2021-05-03 | 2021-05-01 | 2021-05-05 | 2021-05-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4180 | [5 empty] | 2021-04-29 | 2021-05-01 | [10 empty] | 404-10-620331-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Kot Gaon,Ghaziabad | Mr. Raj Kumar S/o Sohan lal ,H.No 112,Old Arya Nagar,Old Arya Nagar Rd, Ghaziabad,Uttar Pradesh,201009 | 17089 | 17089 | 17089 | 17089 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1370204 | EXISTING | Sharing | RTP | 9 | 14 | 90/230/330 | SHARING |  | LAST_AOP_SO | YES | >18HRS | No | 28.6491 | 77.436 | R/RES-436472 | 2021-03-31 | 2021-04-12 | 2021-04-25 | 11109.MGBD.91774360 | 2021-05-01 | 2021-05-10 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-02 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-02 | 2021-06-03 |  |  |  | 2021-04-08 | ST202104132850 | S20210006373 |  | 2021-04-29 | 2021-06-08 | P/FVC/DEL/1028046/2021 | 2021-06-03 | 2021-06-04 | DL/04/5177/0752/0031/06/05/11575/NS/04062021 | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-06-05 | 2021-06-04 | 2021-06-06 | 2021-06-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 291 | [5 empty] | 2021-05-02 | 2021-05-31 | [10 empty] | 404-10-617089-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Amrapali Leisure Valley | Greater Noida Authority,Green Belt Area,Gbm Location, Near Plot No.(Villa)A-198,In Front Of Amrapali Leisure Valley And Cherry County Police Chowky,Bisrakh,Greater Noida,Uttar Pradesh-201009 | 20825 | 20825 | 20825 | 20825 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1363638 | EXISTING | Sharing | GBM | 30 | 0 | 110/190/350 | SHARING |  | SHARING | YES | >18HRS | No | 28.5895 | 77.4365 | R/RES-436551 | 2021-03-31 | 2021-04-12 | 2021-04-25 | 11109.MNOI.95774364 | 2021-05-01 | 2021-05-02 | 2021-05-02 | 2021-05-03 |  |  | 2021-05-01 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-05-07 |  |  |  | 2021-04-08 | ST202104132993 | S20210006375 |  | 2021-04-29 | 2021-06-07 | P/FVC/DEL/1027998/2021 | 2021-05-07 | 2021-05-08 | DL/03/5177/0813/0031/345/04/08273/NS/08052021 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 | 2021-05-08 | 2021-05-12 | 2021-06-01 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 17265 | [5 empty] | 2021-05-02 | 2021-05-03 | [10 empty] | 404-10-620825-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Satin Creditcare Network Ltd | Satin Creditcare Network Ltd, Plot No.492, Udyog Vihar Phase-3, Gurgaon . | 27682 | 27682 | 27682 | 27682 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FNL-IBS-004 | New | New_Built | IBS | 0 | 21 | IBS/IBS | PURE_IBS |  |  | YES | >18HRS | No | 28.5121 | 77.0883 | 27682 | 2021-03-31 | 2021-04-12 | 2021-04-25 | 11106.MGGN.21770882 | 2021-05-01 | 2021-05-02 | 2021-05-02 | 2021-05-03 |  |  | 2021-05-03 | 2021-05-04 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-05-06 | [10 empty] | 2021-05-06 |  | IBS | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-08 | 2021-05-08 | 2021-05-09 | 2021-05-07 | 2021-05-11 | 2021-05-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 119 | [5 empty] | 2021-05-02 | 2021-05-03 | [10 empty] | 404-10-927682-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219,TD RRU 4418
Del | FY20_21 | Q4 | TRIL Commercial Center | KILLA NO. 12/2,13/1,13/2,14/1,TATA INTELLION EDGE TOWERB,SOUTHERN PERPHERAL ROAD,VILL FAZIRPUR,JHARSA,SEC-72 GURGAON HARYANA-122103 | 27672 | 27672 | 27672 | 27672 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS+Macro | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1373218 | New | New_Built | RTP | 6 | 16 | 30/300(VBW)/IBS/IBS/IBS | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.4023 | 77.0385 | IBSR/NN-1942 | 2020-12-14 | 2020-12-25 | 2020-12-26 | 11106-2840-23770385 | 2021-07-06 | 2021-07-07 | 2021-07-07 | 2021-09-02 |  |  | 2021-07-04 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-09-13 |  |  |  | 2021-05-19 | ST202105272211 | S20210009709 |  |  | 2021-06-17 | P/FVC/DEL/1031569/2021 | 2021-09-13 | 2021-09-14 | DL/05/5177/5203/0031/03/01/10151/NS/14092021 | 2021-09-14 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-19 | 2021-09-16 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4265 | [5 empty] | 2021-07-07 | 2021-09-07 | Survey Rejected; OD location is not ready,Survey Rejected_Supply for OD Sector Not avl_(SP Pending from Indus) issue closed on 19 Aug 21,again MO Punching hold due to 200 Mtr OFC Not in stock,Issue closed on 2 sep 21, again Site Hold due to Access Issue,Issue closed on 7 sep 21 | [9 empty] | 404-10-627672-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SSP office surajpur | House No.159, Near SSP office Surajpur Gautam Budh Nagar U.P-201306 | 20275 | 20275 | 20275 | 20275 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-GRGN-176 | New | New_Built | RTP | 6 | 16 | 80/210/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.5092 | 77.4787 | 20275 | 2021-02-08 | 2021-02-18 | 2021-04-19 | 11109.MNOI.91774786 | 2021-05-11 | 2021-05-12 | 2021-05-12 | 2021-07-02 |  |  | 2021-05-09 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-05 | 2021-07-06 |  |  |  | 2021-02-23 | ST202102067362 | S20210003587 |  |  | 2021-04-28 | P/FVC/DEL/1022234/2021 | 2021-07-06 | 2021-07-08 | DL/03/0031/0319/0031/03/01/10051/NS/07072021 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-10 | 2021-07-08 | 2021-07-13 | 2021-07-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 368 | [5 empty] | 2021-05-12 | 2021-07-02 | [10 empty] | 404-10-620275-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | R.K.Puram | MBTS_OPP-CENTRAL GOVT RESIDENT COMPLEX GATE NO 4,AND NEAR FLAT NO- 97,SOUTH DELHI MUNICIPAL CORPORATION AREA,R K PURAM, SECTOR 5 NEW DELHI-110022 | 15601 | 15601 | 15601 | 15601 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1373241 | EXISTING | Sharing | Cow | 30 | 0 | 30/170/270 | SHARING |  | COW_SITE | YES | >18HRS | No | 28.5635 | 77.1716 | R/RES-436630 | 2021-04-09 | 2021-04-09 | 2021-04-14 | 111.MDEL.35771716 | 2021-06-23 | 2021-06-23 |  |  |  |  | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-26 | 2021-06-26 |  |  |  | 2021-04-10 | ST202104138218 | S20210006550 |  | 2021-05-07 | 2021-07-22 | P/FVC/DEL/1036261/2021 | 2021-06-28 | 2021-06-29 | DL/01/5177/5994/0031/03/01/10041/NS/29062021 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-07-01 | 2021-06-29 | 2021-07-04 | 2021-07-06 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5464 | [17 empty] | 404-10-615601-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Iffcosaket | SDMC,GBM Location Front of Ahluwalias(Building)M-1,M-Block,Iffco Saket,Saket Sports Complex Road & Police Station,Saket, New Delhi-110017 | 19988 | 19988 | 19988 | 19988 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1806939 | New | New_Built | GBM | 30 | 0 | 50/140/220 | COW |  |  | YES | >18HRS | No | 28.5258 | 77.2156 | R/NN-567868 | 2020-06-15 | 2021-03-13 | 2021-03-18 | 111-2852-58772155 | 2021-06-29 | 2021-06-30 | 2021-06-30 | 2021-07-13 |  |  | 2021-06-19 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-16 | 2021-07-17 |  |  |  | 2021-03-24 | ST202103102275 | S20210005329 |  |  | 2021-04-10 | P/FVC/DEL/1021531/2021 | 2021-07-17 | 2021-07-20 | DL/01/5177/6308/0031/03/01/10059/NS/20072021 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | 2021-07-21 | 2021-07-24 | 2021-07-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 806 | [5 empty] | 2021-06-30 | 2021-07-13 | Survey rejected; Mains or DG supply not available_PRI Clearance received on 13.07.21_Installed_RRU Faulty_17.07.21 | [9 empty] | 404-10-619988-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sihi village(Relocation of 27403) | Municipal Corporation of Faridabad,GBM Location Near Pocket-1, Opposite Khatushyam Mandir(5657, 36 GUJ Colony), Sector 3, Faridabad, Haryana 121001 | 17561 | 17561 | 17561 | 17561 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Protel Telepower Infrastructure Pvt Ltd. | PTIPL50 | Relocation | New_Built | GBM | 30 | 0 | 0/120/190/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.3545 | 77.3352 | 17561 | 2021-02-14 | 2021-03-16 | 2021-03-19 | 11106-2835-45773352 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-06 |  |  | 2021-06-23 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-10 | 2021-07-14 |  |  |  | 2021-03-18 | ST202103094628 | S20210004928 |  | 2021-04-09 | 2021-08-04 | P/FVC/DEL/1036718/2021 | 2021-07-14 | 2021-07-15 | DL/02/0031/0204/0031/03/01/10054/NS/15072021 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-17 | 2021-07-15 | 2021-07-20 | 2021-07-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1351 | [5 empty] | 2021-07-03 | 2021-07-12 | Installed_L2100 HW Faulty on 12.07.21 | [9 empty] | 404-10-617561-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A,FD RRU 2219B3, TD RRU 4418 available on Parent Site L_2100 RRU 2219
Del | FY20_21 | Q4 | Metro Hospital | Opp- Metro Heart & Multyspacialty Hospital, Sector-16 A- Faridabad- 121002 | 19241 | 19241 | 19241 | 19241 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1395983 | New | New_Built | Cow | 30 | 0 | 0/120/240 | COW |  |  | YES | >18HRS | No | 28.4056 | 77.3184 | R/NN-466907 | 2020-09-12 | 2020-09-24 | 2020-09-25 | 11106.MDEL.56773184 | 2021-06-15 | 2021-06-16 | 2021-06-16 | 2021-06-21 |  |  | 2021-06-05 | 2021-06-22 | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-06-24 |  |  |  | 2020-09-29 | ST202009092454 | S20200005308 |  |  | 2020-10-06 | P/FVC/DEL/1007766/2020 | 2021-06-24 | 2021-06-25 | DL/02/5177/5025/0031/03/01/10038/NS/25062021 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-27 | 2021-06-25 | 2021-06-30 | 2021-07-01 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 564 | [17 empty] | 404-10-619241-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | RAMA GARDEN | A-290,Gali No.2,Rama Garden,Karawal nagar,Near-Navdeepak Public School,Delhi-110094 | 21182 | 21182 | 21182 | 21182 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/8638 | New | New_Built | RTT | 12 | 11 | 40/200/310 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | No | 28.723 | 77.2729 | T20DL05059 | 2020-10-14 | 2020-12-14 | 2020-12-19 | 111.MDEL.30772728 | 2021-06-23 | 2021-06-23 |  |  |  |  | 2021-06-20 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-25 | 2021-06-26 |  |  |  | 2020-12-21 | ST202012179473 | S20200009873 |  |  | 2020-12-30 | P/FVC/DEL/1015110/2020 | 2021-06-28 | 2021-06-29 | DL/01/5126/1525/0031/03/01/10040/NS/29062021 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-07-01 | 2021-06-29 | 2021-07-04 | 2021-07-06 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 694 | [17 empty] | 404-10-621182-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Ward 3 Mehrauli(Relocation of 4038) | H.No. - 173c/3, ward No. 3, Near Vikash Hospital , Mehrauli, New Delhi | 21258 | 21258 | 21258 | 21258 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/TT/3084 | Relocation | Sharing | RTP | 9 | 13 | 30/110/220 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.5193 | 77.1742 | T20DL05234 | 2020-11-05 | 2020-11-19 | 2021-02-09 | 111.MDEL.92771741 | 2021-05-21 | 2021-05-22 |  |  |  |  | 2021-05-23 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-25 | 2021-05-26 |  |  |  | 2021-01-29 | ST202101028327 | S20210001789 |  |  | 2021-03-21 | P/FVC/DEL/1020291/2021 | 2021-05-31 | 2021-06-01 | DL/01/5126/1523/0031/345/04/08290/NS/01062021 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-02 | 2021-06-01 | 2021-06-03 | 2021-06-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 227 | [5 empty] | 2021-05-26 | 2021-05-31 | [10 empty] | 404-10-621258-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD+L_2100 (RRU 2279), TD RRU 4418
Del | FY20_21 | Q4 | Kundan Colony Ballabhgarh | Hno.3,Near Ghantaghr Chock Kundan Colony Ballabhgarh Faridabad-121004 | 21140 | 21140 | 21140 | 21140 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21140_DEL | New | New_Built | RTM | 7 | 15 | 0/120/190/270 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.3358 | 77.3281 | 21140 | 2020-11-12 | 2020-12-25 | 2020-12-28 | 11106.2833.58773280 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-07-18 |  |  | 2021-06-06 | 2021-07-18 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-23 |  |  |  | 2021-06-16 | ST202106346574 | S20210011619 |  | 2021-07-08 | 2021-07-10 | P/FVC/DEL/1034035/2021 | 2021-07-23 | 2021-07-25 | DL/02/0031/0208/0031/345/04/08360/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-27 | 2021-07-25 | 2021-07-29 | 2021-07-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 544 | [5 empty] | 2021-06-11 | 2021-07-19 | Survey rejected; AGL deviation issue_SACFA Reapplied | [9 empty] | 404-10-621140-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | DEFFENCE COLONY | Mr.Ravi Kasana S/O Mr.Gyaan Chand,House No.B-17/2,Defence Colony,Bhopura,Ghaziabad,Uttar Pradesh-201102 | 20267 | 20267 | 20267 | 20267 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20267_DEL | New | New_Built | RTP | 12 | 10.5 | 90/180/270 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.6984 | 77.3367 | 20267 | 2019-10-09 | 2021-05-24 | 2021-05-26 | 11109.MGBD.83773367 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-09 |  |  | 2021-06-07 | 2021-06-09 | 2021-06-11 | 2021-06-12 | 2021-06-12 | 2021-06-26 |  |  |  | 2021-05-28 | ST202105303942 | S20210010398 |  | 2021-06-24 | 2021-07-22 | P/FVC/DEL/1036102/2021 | 2021-06-26 | 2021-08-05 | DL/04/0031/0216/0031/03/01/10088/NS/05082021 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-07 | 2021-08-05 | 2021-08-07 | 2021-08-05 | 2021-08-09 | 2021-08-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4942 | [5 empty] | 2021-06-12 | 2021-08-05 | Public Issue | [9 empty] | 404-10-620267-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | ALI VIHAR GALI NUMBER-1 | Vivek S/O Dham Singh,H.No D-5,Gali Number 10, Ali Vihar, Sarita Vihar, Ali, New Delhi, Delhi 110076 | 20551 | 20551 | 20551 | 20551 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1637865 | New | New_Built | RTT | 12 | 11.3 | 140/210/330 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.5229 | 77.3058 | R/RES-502519 | 2021-06-04 | 2021-06-07 | 2021-06-12 | 111.MDEL.20773061 | 2021-06-29 | 2021-06-29 |  |  |  |  | 2021-06-28 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-02 | 2021-07-12 |  |  |  | 2021-06-16 | ST202106346572 | S20210011619 |  | 2021-07-12 | 2021-07-10 | P/FVC/DEL/1034048/2021 | 2021-07-12 | 2021-07-13 | DL/01/5177/6305/0031/03/01/10053/NS/13072021 | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-15 | 2021-07-13 | 2021-07-18 | 2021-07-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 139 | [5 empty] | 2021-07-03 | 2021-07-12 | SACFA Issue resolved on 12.07.21 | [9 empty] | 404-10-620551-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | 337_DDA_SEC-13,ROHINI | GOVERNMENT LAND-GBM LOCATION DDA PARK NEAR PLOT NO. 10 PATEL APPARTMENTS POCKET-10, SECTOR-13, ROHINI DELHI-110085 | 13114 | 13114 | 13114 | 13114 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1736628 | New | New_Built | GBM | 30 | 0 | 10/130/250 | COW |  |  | YES | >18HRS | No | 28.7197 | 77.1344 | R/NN-565962 | 2021-02-16 | 2021-02-18 | 2021-03-15 | 111.MDEL.97771344 | 2021-06-21 | 2021-06-22 |  |  |  |  | 2021-06-20 | 2021-06-22 | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-06-24 |  |  |  | 2021-03-15 | ST202103091227 | S20210004773 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033393/2021 | 2021-06-24 | 2021-06-25 | DL/01/5177/6294/0031/03/01/10036/NS/25062021 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-27 | 2021-06-25 | 2021-06-30 | 2021-07-06 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 112 | [17 empty] | 404-10-613114-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | HAPUR BORDER | Mr. Mohit Singh S/O Rajesh Singh,Khasra no. 159,Village Indergarhi,Pragna Dasna,Near Tyagi Hostel,Main Market Akash Nagar,Govindpuram,Ghaziabad,Uttar Pradesh-201015 | 23422 | 23422 | 23422 | 23422 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_23422_DEL | New | New_Built | RTM | 12 | 10 | 310/90/220 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.6849 | 77.5015 | 23422 | 2019-04-05 | 2021-06-18 | 2021-06-18 | 11109-2868-53775025 | 2021-07-08 | 2021-07-09 | 2021-07-09 | 2021-07-18 |  |  | 2021-06-28 | 2021-07-18 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-22 |  |  |  | 2021-06-26 | ST202106362823 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034616/2021 | 2021-07-22 | 2021-07-23 | DL/04/0031/0226/0031/03/01/10067/NS/23072021 | 2021-07-23 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-31 | 2021-07-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 599 | [5 empty] | 2021-07-09 | 2021-07-19 | Survey Rejected; Mains supply not available_Issue resolved on 19.07.21,Faulty(1024398 2279 HW Material delivered on 24.07.21) | [9 empty] | 404-10-623422-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | PARVATIA COLONY, FARIDABAD | House No-666, Nagla Road, ParvatyaColony, Sec-22, Faridabaad-121005 | 21204 | 21204 | 21204 | 21204 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Alice | AT-FDB-0005 | New | New_Built | RTP | 9 | 12.6 | 20/140/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.3628 | 77.2797 | 21204 | 2021-01-02 | 2021-01-12 | 2021-03-22 | 11106-2836-27772797 | 2021-07-05 | 2021-07-06 | 2021-07-06 | 2021-07-07 |  |  | 2021-06-08 | 2021-07-08 | 2021-07-11 | 2021-07-12 | 2021-07-12 | 2021-07-17 |  |  |  | 2021-01-19 | ST202101017284 | S20210001143 |  |  | 2021-02-25 | P/FVC/DEL/1017927/2021 | 2021-07-17 | 2021-07-20 | DL/02/0031/0206/0031/03/01/10057/NS/20072021 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-22 | 2021-07-20 | 2021-07-24 | 2021-07-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9146 | [5 empty] | 2021-07-06 | 2021-07-13 | Partially Installed_Infra Material under Dispatch(16650837) | [9 empty] | 404-10-621204-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Inland Container Depot, Garhi Harsaru | Manoj Kumar Parmar,Khasra no. 323/294,khatoni no. 394,Near- House No.1483,Tower Wali Gali,Village-Garhi Harsaru,Kherki Daula Police Station,Garhi Harsaru Post Office,Gurugram,Haryana-122505 | 21146 | 21146 | 21146 | 21146 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762866 | New | New_Built | GBM | 30 | 0 | 60/160/250 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.4373 | 76.9262 | R/NN-566656 | 2021-02-24 | 2021-03-19 | 2021-04-05 | 11106.MGGN.73769261 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-24 |  |  | 2021-06-24 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-26 | 2021-06-28 |  |  |  | 2021-04-07 | ST202104131183 | S20210006313 |  | 2021-04-29 | 2021-07-08 | P/FVC/DEL/1033424/2021 | 2021-06-28 | 2021-06-29 | DL/05/5177/5275/0031/03/01/10042/NS/29062021 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-07-01 | 2021-06-29 | 2021-07-04 | 2021-07-06 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5157 | [17 empty] | 404-10-621146-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Makhanpur Colony_1 | Mr. Balvir Singh ,Plot No. 19,Block-B, Khasra No. 1018,Subhash Park-I,Village Makanpur,Pargana Loni,Tehsil and District Ghaziabad-201014 | 21311 | 21311 | 21311 | 21311 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1550405 | New | New_Built | RTP | 6 | 15.4 | 90/210/310 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6279 | 77.3411 | R/NN-560228 | 2020-12-04 | 2021-03-16 | 2021-03-24 | 11109.MGBD.35775876 | 2021-05-18 | 2021-05-18 |  |  |  |  | 2021-05-15 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-20 | 2021-05-21 |  |  |  | 2021-03-26 | ST202103107525 | S20210005562 |  | 2021-04-15 | 2021-06-14 | P/FBC/DEL/1031320/2021 | 2021-05-21 | 2021-05-22 | DL/04/5177/0764/0031/345/04/08286/NS/22052021 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-23 | 2021-05-23 | 2021-05-24 | 2021-05-22 | 2021-05-26 | 2021-06-01 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4173 | [17 empty] | 404-10-621311-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Doulat Ram Colony, Noida | Mr. Rajesh Singh,N.S. Inter college,Hno. 365G,Doulat Ram Colony,Gautampuri, Pink City Colony, Dadri, Uttar Pradesh 203207 | 21375 | 21375 | 21375 | 21375 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | ID-1011028 | New | Sharing | RTP | 6 | 14 | 40/180/300 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.5434 | 77.5358 | T20DL05571 | 2020-12-11 | 2021-03-16 | 2021-03-19 | 11109-2854-33775357 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-07-16 |  |  | 2021-06-21 | 2021-07-17 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 |  |  |  | 2021-03-18 | ST202103095675 | S20210004955 |  | 2021-04-09 | 2021-06-06 | P/FVC/DEL/1027944/2021 | 2021-07-23 | 2021-07-24 | DL/03/5126/0102/0031/03/01/10072/NS/24072021 | 2021-07-24 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-27 | 2021-07-25 | 2021-07-29 | 2021-07-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5160 | [5 empty] | 2021-06-23 | 2021-07-16 | Pole Required at Farend_5160_Indus TSP team Plan on 17.07.07.21 | [9 empty] | 404-10-621375-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Chattarpur(Relocation of 7783) | Plot no.2&3,khasra no.619/8,Sunshine Apartment Opp.Tivoli Garden Chattarpur New Delhi-110074 | 21442 | 21442 | 21442 | 21442 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1577540 | Relocation | New_Built | RTP | 6 | 19 | 70/210/300 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.4967 | 77.1844 | R/NN-560935 | 2020-12-15 | 2021-01-14 | 2021-03-04 | 111.MDEL.67771844 | 2021-05-03 | 2021-05-04 |  |  |  |  | 2021-04-29 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-08 | 2021-05-10 |  |  |  | 2021-02-16 | ST202102053958 | S20210002988 |  |  | 2021-03-07 | P/FVC/DEL/1019442/2021 | 2021-05-10 | 2021-05-11 | DL/01/5177/6286/0031/345/04/08276/NS/11052021 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-12 | 2021-05-12 | 2021-05-13 | 2021-05-11 | 2021-05-15 | 2021-05-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11380 | [5 empty] | 2021-05-04 | 2021-05-05 | [10 empty] | 404-10-621442-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Mundka Warehouse(Relocation of 23683) | HOUSE NEAR POLE NO 103, MUNDKA KH NO - 803/1, NEW DELHI - 110041 | 21580 | 21580 | 21580 | 21580 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3014228 | Relocation | New_Built | RTT | 12 | 10 | 50/230/300 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6755 | 77.0259 | R/NN-626544 | 2021-01-07 | 2021-01-27 | 2021-03-04 | 111-2867-55770259 | 2021-07-09 | 2021-07-10 | 2021-07-10 | 2021-08-28 |  |  | 2021-07-04 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-30 | 2021-09-02 |  |  |  | 2021-02-16 | ST202102053959 | S20210002988 |  |  | 2021-03-07 | P/FVC/DEL/1019443/2021 | 2021-09-02 | 2021-09-03 | DL/01/5177/6342/0031/345/04/08439/NS/03092021 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-04 | 2021-09-03 | 2021-09-05 | 2021-09-03 | 2021-09-10 | 2021-09-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4180 | [5 empty] | 2021-07-10 | 2021-08-28 | Survey Rejected; Actual AGL is 3M greater than planned AGL( Re SR SP Process),Issue closed on 25 Aug 21,Re RFAI Pending,Issue closed on 28.08.21,Partially Installed_MCB Required at Farend | [9 empty] | 404-10-621580-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Tukmirpur Extention | HOUSE NO.T-125 PLOT NO.- B6, KHASRA NO.-477,TUKMIRPUR EXTENTION, KHAJOORI KHAS, NEW DELHI-110094 | 21596 | 21596 | 21596 | 21596 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-4267 | New | Sharing | GBM | 25 | 0 | 0/180/240 | SHARING |  | 3RD_PARTY | YES | >18HRS | No | 28.7167 | 77.2618 | SR-DL000131 | 2021-01-08 | 2021-02-09 | 2021-02-18 | 111.MDEL.66772617 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-10-19 |  |  | 2021-04-29 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-22 | 2021-10-23 |  |  |  | 2021-02-10 | ST202102048372 | S20210002677 |  |  | 2021-03-05 | P/FVC/DEL/1019256/2021 | 2021-10-24 | 2021-10-25 | DL/01/5370/2867/0031/03/01/10257/NS/25102021 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 906 | [5 empty] | 2021-05-07 | 2021-10-19 | Material return on 07.05.21,Issue closed on 19.10.21,Installed_Link Interference as on 23rd Oct 21 | [9 empty] | 404-10-621596-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Sector 15 Part-II | Smt Omwati W/o Sh Deshraj,Plot No.-910, Sector-15 Part-II, Gurgaon, Haryana-122007 | 21705 | 21705 | 21705 | 21705 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21705_DEL | New | New_Built | RTP | 9 | 10 | 50/170/340 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.4601 | 77.042 | 21705 | 2021-03-17 | 2021-04-01 | 2021-04-10 | 11106.2846.00770420 | 2021-06-14 | 2021-06-15 |  |  |  |  | 2021-06-13 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-17 | 2021-07-29 |  |  |  | 2021-04-10 | ST202104138216 | S20210006550 |  | 2021-05-07 | 2021-07-22 | P/FVC/DEL/1036266/2021 | 2021-08-05 | 2021-08-06 | DL/05/0031/0536/0031/03/01/10089/NS/06082021 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-11 | 2021-08-06 | 2021-08-11 | 2021-08-06 | 2021-08-12 | 2021-08-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 17291 | [5 empty] | 2021-06-17 | 2021-08-05 | Owner Issue_Issue resolved on 26th July 21,Partially Installed_Limited Access & MW Antenna Faulty on 27th July21,Installed_Water Logging Issue at Farend on 29th July21_Issue resolved on 04.08.21 as per Deepak Luthra | [9 empty] | 404-10-621705-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | CP Flower valley | Mr Neeraj Gupta,Infront of house D-01 To D-07, Central Park Flower Valley Village Dhunella Sohna Near GD Goenka University pin code 122103 | 21712 | 21712 | 21712 | 21712 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21712_DEL | New | New_Built | RTP | 9 | 14 | 30/100/270 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.2845 | 77.0748 | 21712 | 2021-04-01 | 2021-04-02 | 2021-04-10 | 11106.MDEL.47770787 | 2021-05-08 | 2021-05-09 | 2021-05-09 | 2021-05-10 |  |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-11 | 2021-05-11 | 2021-05-14 |  |  |  | 2021-04-10 | ST202104138217 | S20210006550 |  | 2021-05-07 | 2021-07-22 | P/FVC/DEL/1036262/2021 | 2021-05-14 | 2021-05-15 | DL/05/0031/0516/0031/345/04/08282/NS/15052021 | 2021-05-15 | 2021-05-15 | 2021-05-15 | 2021-05-15 | 2021-05-15 | 2021-05-16 | 2021-05-16 | 2021-05-17 | 2021-05-15 | 2021-05-19 | 2021-05-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8106 | [5 empty] | 2021-05-09 | 2021-05-13 | [10 empty] | 404-10-621712-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Plumeria Garden Estate | GBM Location,Infront of Plumeria Garden Estate,Omicron III Service Lane,Greater Noida, Uttar Pradesh 201310 | 18032 | 18032 | 18032 | 18032 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1857392 | New | New_Built | GBM | 30 | 0 | 20/120/270 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | No | 28.4761 | 77.5495 | R/NN-569154 | 2020-09-14 | 2021-04-01 | 2021-04-10 | 11109.MNOI.60775494 | 2021-05-18 | 2021-05-18 |  |  |  |  | 2021-05-15 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-20 | 2021-05-21 |  |  |  | 2021-03-15 | ST202103091231 | S20210004773 |  | 2021-04-09 | 2021-07-08 | P/FVC/DEL/1033394/2021 | 2021-05-26 | 2021-05-27 | DL/03/5177/0896/0031/06/05/11552/NS/27052021 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-28 | 2021-05-27 | 2021-05-29 | 2021-06-03 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5033 | [5 empty] | 2021-05-21 | 2021-05-25 | [10 empty] | 404-10-618032-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Supertech Astralis | Plot no-3,Supertech Astralis Commercial, Sector 94, Noida, Utter Pradesh 201313. | 27691 | 27691 | 27691 | 27691 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | SIS | SI_27691_DEL | New | New_Built | IBS | 0 | 24 | IBS | PURE_IBS |  |  | YES | >18HRS | No | 28.5506 | 77.3252 | 27691 | 2020-09-14 | 2021-04-01 | 2021-04-10 | 11109.MNOI.05773251 | 2021-05-31 | 2021-06-01 | 2021-06-01 | 2021-06-23 |  |  | 2021-05-29 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-25 | 2021-06-26 | [10 empty] | 2021-06-26 |  | IBS | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-30 | 2021-06-28 | 2021-07-03 | 2021-07-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 639 | [5 empty] | 2021-06-01 | 2021-06-23 | [10 empty] | 404-10-927691-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219,TD RRU 4418
Del | FY20_21 | Q1 | Model Town(Relocation of 25759) | D-55/SF,D-Block,Near-Police Booth,Mahendra Enclave,Delhi-110009 | 20809 | 20809 | 20809 | 20809 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept | PTIPL40 | Relocation | New_Built | RTP | 9 | 17 | 60/180/330 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.7056 | 77.1847 | 20809 | 2020-09-01 | 2020-09-10 | 2020-09-10 | 111.MDEL.55771846 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-06-13 |  |  | 2021-02-06 | 2021-06-13 | 2021-06-13 | 2021-06-13 | 2021-06-14 | 2021-06-14 |  |  |  | 2020-09-12 | ST202009066049 | S20200004361 |  |  | 2020-09-19 | P/FVC/DEL/1005954/2020 | 2021-06-14 | 2021-06-15 | DL/01/9052/0068/0031/03/01/10031/NS/15062021 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-17 | 2021-06-15 | 2021-06-20 | 2021-06-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 209 | [5 empty] | 2021-02-10 | 2021-06-13 | [10 empty] | 404-10-620809-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRUS 2219 B0A+FD RRUS 2219B3+L_2100 RRUS 2219B1, TD RRU 4418
Del | FY20_21 | Q4 | PARVATIA COLONY, PART-2 | Khasra No. 25/10/2, Plot No. 461, Village- Gauchi, Tehsil- Ballabhgarh, Faridabad, Haryana-121001 | 18616 | 18616 | 18616 | 18616 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1682507 | New | New_Built | RTP | 9 | 10.5 | 60/210/320 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.3552 | 77.2821 | R/NN-564087 | 2021-01-26 | 2021-01-27 | 2021-02-04 | 11106.DEL.58772821 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-06-15 |  |  | 2021-02-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-17 | 2021-06-18 |  |  |  | 2021-01-29 | ST202101028328 | S20210001789 |  | 2021-02-22 | 2021-03-21 | P/FVC/DEL/1020285/2021 | 2021-06-18 | 2021-06-19 | DL/02/5177/5024/0031/03/01/10035/NS/19062021 | 2021-06-19 | 2021-06-19 | 2021-06-19 | 2021-06-19 | 2021-06-19 | 2021-06-19 | 2021-06-19 | 2021-06-21 | 2021-06-19 | 2021-06-24 | 2021-06-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 542 | [5 empty] | 2021-02-16 | 2021-06-15 | [10 empty] | 404-10-618616-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Seemapuri(Relocation of 2684) | H.No. C-206/207,Old Seemapuri,Near-Hanuman Mandir,Sahadara,Dehi-110095 | 21007 | 21007 | 21007 | 21007 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1476949 | Relocation | New_Built | RTM | 11 | 12 | 0/120/240 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6804 | 77.3302 | R/NN-466201 | 2020-09-02 | 2020-11-10 | 2020-11-17 | 111.MDEL.03773301 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-27 |  |  | 2021-04-10 | 2021-05-04 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-06-08 |  |  |  | 2020-11-22 | ST202011153063 | S20200008589 |  |  | 2020-12-16 | P/FVC/DEL/1012677/2020 | 2021-06-12 | 2021-06-13 | DL/01/5177/6291/0031/06/05/11604/NS/13062021 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-16 | 2021-06-14 | 2021-06-19 | 2021-06-22 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 625 | [5 empty] | 2021-04-20 | 2021-06-09 | [10 empty] | 404-10-621007-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219,L_2100 RRU 2299, TD RRU 4418 Available On Parent site
Del | FY20_21 | Q1 | RD Block, Najafgarh | RD Block, Najafgarh,Khasra No. 34/5/2, Dharampura Extension, Najafgarh, New Delhi-110043 | 17917 | 17917 | 17917 | 17917 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1381097 | New | New_Built | RTT | 15 | 9 | 50/150/270 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.6084 | 76.9935 | R/NN-405026 | 2020-03-11 | 2020-06-09 | 2020-08-12 | 111.MDEL.84769935 | 2021-04-19 | 2021-04-20 |  |  |  |  | 2021-04-16 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | 2020-09-11 | ST202009065368 | S20200004327 |  |  | 2020-09-18 | P/FVC/DEL/1005778/2020 | 2021-06-17 | 2021-06-18 | DL/01/5177/6292/0031/03/01/10034/NS/18062021 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-20 | 2021-06-18 | 2021-06-23 | 2021-06-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10981 | [5 empty] | 2021-04-23 | 2021-06-17 | [10 empty] | 404-10-617917-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Maruti Plant GGN | Building Machine Shop-3, Opposite Of KSEG Plant, Old Palam Gurgaon Road, Maruti Udyog, Sector 18, Gurgaon, Haryana 122022 | 19927 | 19927 | 19927 | 19927 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1471395 | New | New_Built | RTT | 15 | 5.5 | 40/190/300 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.4953 | 77.0718 | R/NN-506210 | 2020-10-26 | 2020-10-27 | 2020-10-29 | 11106.MGGN.52770718 | 2021-04-01 | 2021-05-28 | 2021-04-01 | 2021-05-28 |  |  | 2021-03-30 | 2021-05-28 | 2021-05-31 | 2021-06-01 | 2021-06-01 | 2021-06-05 |  |  |  | 2020-11-04 | ST202011134635 | S20200007565 |  |  | 2020-12-13 | P/FVC/DEL/1012171/2020 | 2021-06-05 | 2021-06-07 | DL/05/5177/5273/0031/06/05/11583/NS/07062021 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-10 | 2021-06-17 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 17653 | [5 empty] | 2021-04-01 | 2021-06-03 | [10 empty] | 404-10-619927-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sec-83 Noida | Mr. Dharambir Singh S/O Bhup Singh,property bearing No. 47,Village -Yakubpur,Sec 83,Tehsil- Dadri, Dist- Gautam budh Nagar, Noida,Uttar Pradesh 201305 | 21428 | 21428 | 21428 | 21428 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | TVI | RJUPZNO0254 | EXISTING | Sharing | RTT | 15 | 8 | 30/110/320 | SHARING |  | 3RD_PARTY | YES | >18HRS | No | 28.5228 | 77.4023 | 21428 | 2021-01-12 | 2021-03-14 | 2021-03-19 | 11109.MNOI.28774022 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-03 |  |  | 2021-05-02 | 2021-05-04 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-06-09 |  |  |  | 2021-03-18 | ST202103094631 | S20210004928 |  | 2021-04-09 | 2021-08-04 | P/FVC/DEL/1036719/2021 | 2021-06-09 | 2021-06-10 | DL/03/5113/0071/0031/345/04/08301/NS/10062021 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-11 | 2021-06-10 | 2021-06-12 | 2021-06-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 983 | [5 empty] | 2021-05-01 | 2021-06-08 | [10 empty] | 404-10-621428-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sec-03,Faridabad (Relocation of 2555) | SHO- 44, Huda Market, Sector 3,Near By- Sarva Haryana Gramin Bank,Ballabhgarh, Faridabad, Haryana-121001 | 21604 | 21604 | 21604 | 21604 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1008473 | Relocation | Sharing | RTT | 18 | 8 | 0/120/240 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | No | 28.3505 | 77.3356 | R/RES-433088 | 2021-01-12 | 2021-01-28 | 2021-03-04 | 11106.MFBD.05773355 | 2021-04-19 | 2021-04-19 | 2021-04-20 | 2021-04-23 |  |  | 2021-04-14 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-10 |  |  |  | 2021-03-24 | ST202103102274 | S20210005329 |  |  | 2021-04-10 | P/FVC/DEL/1021523/2021 | 2021-06-10 | 2021-06-11 | DL/02/5177/0398/0031/345/04/08302/NS/11062021 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-12 | 2021-06-11 | 2021-06-13 | 2021-06-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4262 | [5 empty] | 2021-04-20 | 2021-06-08 | [10 empty] | 404-10-621604-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRU 2219,L_2100 RRU 12B1, TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | JAWAHAR COLONY, NIT, FARIDABAD | Khasra No. 557/2, Jawahar Colony, Sec-22, Tehsil and District Faridabad-121005 | 21203 | 21203 | 21203 | 21203 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1479031 | New | New_Built | RTT | 15 | 8 | 0/120/240 | INDUS_LITE+ |  |  | YES | >18HRS | No | 28.3669 | 77.2888 | R/NN-520941 | 2020-10-29 | 2020-11-20 | 2020-12-01 | 11106.MFBD.69772888 | 2021-06-11 | 2021-06-11 |  |  |  |  | 2021-06-10 | 2021-06-12 | 2021-06-15 | 2021-06-16 | 2021-06-16 | 2021-06-17 |  |  |  | 2020-12-16 | ST202012174392 | S20200009628 |  |  | 2020-12-23 | P/FVC/DEL/1013378/2020 | 2021-06-17 | 2021-06-18 | DL/02/5177/5023/0031/03/01/10033/NS/18062021 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-20 | 2021-06-18 | 2021-06-23 | 2021-06-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 800 | [5 empty] | 2021-06-12 | 2021-06-15 | [10 empty] | 404-10-621203-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Sec-4,Gurgaon | NEAR HOUSE NO - 1063,WARD NO -10,MCG GREEN BELT,URBAN ESTATE, SEC-4, GURGAON HARYANA-122001 | 10096 | 10096 | 10096 | 10096 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | TVI | RJHAZGN0473 | New | New_Built | GBM | 30 | 0 | 40/170/290 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.4733 | 77.0144 | 10096 | 2020-05-26 | 2021-02-02 | 2021-02-26 | 11106.MGGN.32770144 | 2021-06-03 | 2021-06-03 |  |  |  |  | 2021-06-02 | 2021-06-04 | 2021-06-04 | 2021-06-05 | 2021-06-05 | 2021-06-05 |  |  |  | 2020-12-18 | ST202012177616 | S20200009806 |  |  | 2020-12-29 | P/FVC/DEL/1015007/2020 | 2021-06-10 | 2021-06-11 | DL/05/5113/0108/0031/06/05/11595/NS/11062021 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-12 | 2021-06-11 | 2021-06-13 | 2021-06-21 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5220 | [5 empty] | 2021-06-05 | 2021-06-09 | [10 empty] | 404-10-610096-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Kasa Isles 2 | Mr Subhash Chand Tyagi S/o Sh Surjan Sing, Khata Khatoni No.-1618, Khasra No.- 957m, Village-Sihani, Paragna-Loni, Ghaziabad, UP-201001 | 21591 | 21591 | 21591 | 21591 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-GZBD-ENB-3760 | New | Sharing | GBT | 30 | 0 | 60/200/300 | SHARING |  | 3RD_PARTY | YES | >18HRS | No | 28.6871 | 77.4202 | SR-DL000135 | 2021-01-08 | 2021-02-09 | 2021-02-18 | 11109.MGBD.71774201 | 2021-05-11 | 2021-05-12 | 2021-05-12 | 2021-06-09 |  |  | 2021-05-09 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-11 | 2021-06-12 |  |  |  | 2021-02-10 | ST202102048373 | S20210002677 |  |  | 2021-03-05 | P/FVC/DEL/1019257/2021 | 2021-06-12 | 2021-06-13 | DL/04/0031/0210/0031/03/01/10029/NS/13062021 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-16 | 2021-06-14 | 2021-06-19 | 2021-06-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1589 | [5 empty] | 2021-05-12 | 2021-06-09 | [10 empty] | 404-10-621591-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Sec 60,Noida(Relocation of 25656) | Noida Authority ,GBM Location,Near Amarnath design LLP( B-7),B Block,Sector 59,Noida,Uttar Pradesh 201307 | 21152 | 21152 | 21152 | 21152 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | RJUPZNO0751 | New | New_Built | GBM | 30 | 0 | 50/120/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.6064 | 77.3627 | 21152 | 2020-09-14 | 2021-04-01 | 2021-04-10 | 11109.MNOI.64773627 | 2021-06-03 | 2021-06-03 |  |  |  |  | 2021-06-05 | 2021-06-04 | 2021-06-04 | 2021-06-05 | 2021-06-05 | 2021-06-07 |  |  |  | 2021-04-22 | ST202104166425 | S20210007457 |  | 2021-05-14 | 2021-07-22 | P/FVC/DEL/1036053/2021 | 2021-06-07 | 2021-06-08 | DL/03/5113/0134/0031/06/05/11584/NS/08062021 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-10 | 2021-06-21 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 50 | [17 empty] | 404-10-621152-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
DEL | FY20_21 | Q1 | Rectangle One Saket | MBTS Location,South Delhi Municipal Corporation Parking, Gupta Market,Near Quarter No. 145 to 176, Sector 5,Pushp vihar,New Delhi- 110017 | 21148 | 21148 | 21148 | 21148 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1900792 | New | New_Built | Cow | 30 | 0 | 10/90/240 | COW |  |  | YES | >18HRS | NO | 28.5265 | 77.2221 | R/NN-569132 | 2021-03-26 | 2021-04-21 | 2021-04-27 | 111.MDEL.65772220 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-30 |  |  | 2021-06-28 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-02 | 2021-07-03 |  |  |  | 2021-03-28 | ST202103109418 | S20210005642 |  | 2021-04-21 | 2021-07-08 | P/FVC/DEL/1033501/2021 | 2021-07-03 | 2021-07-05 | DL/01/5177/6302/0031/03/01/10047/NS/05072021 | 2021-07-05 | 2021-07-05 | 2021-07-05 | 2021-07-05 | 2021-07-05 | 2021-07-05 | 2021-07-05 | 2021-07-07 | 2021-07-05 | 2021-07-10 | 2021-07-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4974 | [17 empty] | 404-10-621148-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
DEL | FY20_21 | Q4 | Grand Forte,sigma 4 | Noida Authority(Green Belt),GBM Location,in Front of Electricity Pole No.42741,Near Royal Apartment,Grand Forte,Sigma IV, Greater Noida, Uttar Pradesh 201310 | 13258 | 13258 | 13258 | 13258 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1901744 | New | New_Built | GBM | 30 | 0 | 50/260/330 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4493 | 77.5607 | R/NN-570064 | 2021-04-07 | 2021-04-16 | 2021-04-27 | 11109.MNOI.93775606 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-07-02 |  |  | 2021-06-24 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-05 | 2021-07-05 |  |  |  | 2021-04-27 | ST202104194588 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028816/2021 | 2021-07-20 | 2021-07-21 | DL/03/5177/0899/0031/03/01/10061/NS/21072021 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | 2021-07-21 | 2021-07-26 | 2021-07-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1540 | [5 empty] | 2021-07-05 | 2021-07-19 | Installed_2G Media Issue_Issue resolved on 19.07.21 | [9 empty] | 404-10-613258-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
DEL | FY20_21 | Q1 | Gaur City, Ghaziabad | Mr.Bobby(Mr.Satish) S/O Shri Satpal Singh,House No.K-48,Khasra No.1142,Mahendra Enclave,Near-M Block Tikona Park,Ghaziabad,Uttar Pradesh-201002 | 20260 | 20260 | 20260 | 20260 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20260_DEL | New | New_Built | RTP | 6 | 16 | 0/150/270 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6683 | 77.4646 | 20260 | 2019-11-26 | 2021-05-24 | 2021-05-26 | 11109.MGBD.83774646 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-10 |  |  | 2021-06-06 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-12 | 2021-07-01 |  |  |  | 2021-05-28 | ST202105303941 | S20210010398 |  | 2021-06-24 | 2021-07-22 | P/FVC/DEL/1036077/2021 | 2021-07-01 | 2021-07-03 | DL/04/0031/0218/0031/03/01/10046/NS/03072021 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-05 | 2021-07-03 | 2021-07-08 | 2021-07-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 289 | [17 empty] | 404-10-620260-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
DEL | FY20_21 | Q1 | APRON AREA OF INTERNATIONAL PIER, NEAR PLANE PARKING AREA, T-3 | Building Name Fire Station 2,Terminal-3,international airport pior,apperal area,IGI Airport,New Delhi-110037 | 19314 | 19314 | 19314 | 19314 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1374475 | New | Sharing | RTP | 6 | 8 | 90/210/320 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.5591 | 77.0765 | R/RES-502281 | 2021-05-20 | 2021-05-25 | 2021-06-07 | 111.MDEL.91770765 | 2021-06-11 | 2021-06-21 | 2021-06-11 | 2021-06-21 |  |  | 2021-06-06 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-06-29 |  |  |  | 2021-06-04 | ST202106322612 | S20210010900 |  |  | 2021-06-27 | P/FVC/DEL/1032881/2021 | 2021-06-29 | 2021-06-30 | DL/01/5177/6224/0031/03/01/10043/NS/30062021 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-07-02 | 2021-06-30 | 2021-07-05 | 2021-07-06 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5105 | [17 empty] | 404-10-619314-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
DEL | FY20_21 | Q1 | Sec-58,Gurgaon(Relocation of 17219) | INFRON OF IREO GRAND HYATT ,GREEN BELT, SECTOR-58,RAJESH PILOT ROAD GURGAON HARYANA-122005 | 20446 | 20446 | 20446 | 20446 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1856734 | New | New_Built | Cow | 30 | 0 | 60/180/270 | COW |  |  | YES | >18HRS | NO | 28.4175 | 77.1015 | R/NN-569146 | 2021-03-26 | 2021-04-13 | 2021-04-29 | 11106-2841-75771014 | 2021-06-25 | 2021-06-26 | 2021-06-26 | 2021-07-22 |  |  | 2021-06-23 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-24 | 2021-07-25 |  |  |  | 2021-05-01 | ST202105213663 | S20210008457 |  |  | 2021-06-12 | P/FVC/DEL/1031146/2021 | 2021-07-25 | 2021-07-25 | DL/05/5177/5290/0031/345/04/08364/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1850 | [5 empty] | 2021-06-26 | 2021-07-22 | Survey Rejected; 46M Lat-Long deviation found | [9 empty] | 404-10-620446-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
DEL | FY20_21 | Q1 | SDMC_Dwarka Sec-5(Relocation of 1361) | Government Land,South Delhi Municipal Corporation(SDMC)Park No.5,In Betwwen Plot No 5(The New Jai Bharat Apartment) & Plot No6(Aakriti Apartment Civil Supplies),Police Station-Sector 1 Dwarka,Post Office -Sector 4 Dwarka,Sec 4,Dwarka, New Delhi-110078 | 17330 | 17330 | 17330 | 17330 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016762 | New | New_Built | GBM | 30 | 0 | 0/120/270 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6016 | 77.054 | R/NN-627100 | 2021-04-29 | 2021-05-03 | 2021-05-18 | 111-2860-16770540 | 2021-08-13 | 2021-08-14 | 2021-08-14 | 2021-08-20 |  |  | 2021-08-08 | 2021-08-20 | 2021-08-22 | 2021-08-23 | 2021-08-23 | 2021-08-25 |  |  |  | 2021-04-27 | ST202104194581 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028812/2021 | 2021-08-25 | 2021-08-26 | DL/01/5177/6337/0031/06/05/11933/NS/26082021 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-27 | 2021-08-26 | 2021-08-27 | 2021-08-26 | 2021-09-01 | 2021-09-01 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | INDUS |  | M1 | 750 | [5 empty] | 2021-08-14 | 2021-08-25 | Survey Rejected; 106M Lat-Long deviation found, Mains supply not available but DG available and Blockage issue at 150 and 270 degree_SACFA Issue resolved on 27.07.21 but Blockage Issue not resolved,Site Re-released on 13 Aug 21,Blockage & Still Mains or DG not available at site,Issue resolved on 20 Aug 21 Site on fiber,Partially Installed_Media Issue(Fiber Team Working),Issue closed on 25 Aug 21 | [9 empty] | 404-10-617330-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
DEL | FY20_21 | Q3 | Badusarai, Delhi | SH.RAJ SINGH S/O SH.RAGHU NATH SINGH,HOUSE NEAR ELECTRICITY POLE NO. 11,VILLAGE BADUSARAI DELHI-110071 | 20477 | 20477 | 20477 | 20477 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1909757 | New | New_Built | GBM | 25 | 0 | 50/120/210 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.53 | 76.9858 | R/NN-570184 | 2021-04-09 | 2021-04-20 | 2021-04-30 | 111.MDEL.00769858 | 2021-06-23 | 2021-06-23 |  |  |  |  | 2021-06-20 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-25 | 2021-07-24 |  |  |  | 2021-05-01 | ST202105213667 | S20210008457 |  |  | 2021-06-12 | P/FVC/DEL/1031150/2021 | 2021-07-24 | 2021-07-31 | DL/01/5177/6316/0031/03/01/10083/NS/31072021 | 2021-07-31 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-07 | 2021-08-02 | 2021-08-09 | 2021-08-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 966 | [5 empty] | 2021-06-25 | 2021-07-31 | Partially Installed_Police Issue,Access Issue for SCFT & EMF,Access Issue resolved on 31st July 21 & HW faulty | [9 empty] | 404-10-620477-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
DEL | FY20_21 | Q4 | Surajpur industrial area | Mr.Sri krishan Sharma S/o Ved Prakash Sharma,Khasra No. 35K,Khata No. 49, 50 and 91,Near Chaudhary Keshram Inter College ,Vill Habibpur, Ecotech III,Greater Noida,Goutam Buddh Nagar ,Uttar Pradesh,201306 | 21345 | 21345 | 21345 | 21345 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1906015 | New | New_Built | RTP | 12 | 11 | 0/90/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5368 | 77.4519 | R/NN-570152 | 2021-03-12 | 2021-05-21 | 2021-06-03 | 11109.MNOI.67774519 | 2021-06-21 | 2021-06-22 |  |  |  |  | 2021-06-20 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-24 | 2021-06-25 |  |  |  | 2021-04-07 | ST202104131180 | S20210006313 |  | 2021-04-29 | 2021-07-08 | P/FVC/DEL/1033422/2021 | 2021-06-25 | 2021-06-26 | DL/03/5177/0897/0031/03/01/10039/NS/26062021 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-03 | 2021-07-01 | 2021-07-06 | 2021-07-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4112 | [17 empty] | 404-10-621345-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
DEL | FY21_22 | Q1 | Sharifabad Rajapur | Smt Chandravati w/o Mr Ram Charan Mishra,Plot No.-31, Village sharifabad Rajapur,Pargana Loni,Tehsil and district ghaziabad -201003 | 21710 | 21710 | 21710 | 21710 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1845692 | New | New_Built | RTT | 9 | 13 | 110/230/310 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7373 | 77.3572 | R/NN-568968 | 2021-03-23 | 2021-04-20 | 2021-04-26 | 11109.MGBD.73773572 | 2021-06-29 | 2021-06-30 | 2021-06-30 | 2021-07-02 |  |  | 2021-07-01 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-05 | 2021-07-05 |  |  |  | 2021-04-27 | ST202104194452 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028814/2021 | 2021-07-05 | 2021-07-06 | DL/04/5177/0767/0031/03/01/10048/NS/06072021 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-08 | 2021-07-06 | 2021-07-11 | 2021-07-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 25414 | [17 empty] | 404-10-621710-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
DEL | FY21_22 | Q1 | REC Limited | Plot no. I-4 behind iffco chock Metro station sector 29 gurgoan | 27681 | 27681 | 27681 | 27681 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | SIS | HRRL562021 | New | New_Built | IBS | 0 | 36 | IBS/IBS | PURE_IBS |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4677 | 77.0719 | 27681 | 2021-02-18 | 2021-03-09 | 2021-03-09 | 11106-2846-77770719 | 2021-07-06 | 2021-07-07 | 2021-07-07 | 2021-07-09 |  |  | 2021-07-08 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-12 | 2021-07-17 | [10 empty] | 2021-07-17 |  |  | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-20 | 2021-07-18 | 2021-07-23 | 2021-07-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 138 | [5 empty] | 2021-07-07 | 2021-07-16 | Partially Installed_IF routing Issue(Link Pending) under discussion with Toco & gaurav_12.07.21,Issue resolved on 16.07.21 & L2100 RRU Faulty at site(16688359) | [9 empty] | 404-10-927681-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 TD RRU 4418
DEL | FY21_22 | Q1 | Sabzi Mandi(Relocation of 17257) | Usha Dhingra S/O Rajeev Dhingra,Bearing No. 5013-14 (New), Ward No. XII, Roshanara Road, Subzi Mandi, Delhi-110007 | 21686 | 21686 | 21686 | 21686 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1953975 | New | New_Built | RTP | 6 | 16 | 40/100/200 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6715 | 77.2009 | R/NN-618365 | 2021-04-23 | 2021-06-03 | 2021-06-14 | 111-2867-14772008 | 2021-07-03 | 2021-07-03 | 2021-07-03 | 2021-07-13 |  |  | 2021-06-23 | 2021-07-13 | 2021-07-13 | 2021-07-14 | 2021-07-14 | 2021-07-17 |  |  |  | 2021-06-18 | ST202106351959 | S20210011842 |  |  | 2021-07-22 | P/FVC/DEL/1036138/2021 | 2021-07-17 | 2021-07-18 | DL/01/5177/6307/0031/03/01/10055/NS/19072021 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-20 | 2021-07-18 | 2021-07-23 | 2021-07-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 513 | [5 empty] | 2021-07-03 | 2021-07-13 | CAT Issue resolved on 13.07.21,Partially Installed_Link Pending MMU Faulty_16.07.21 | [9 empty] | 404-10-621686-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A,FD RRU 2219B3, L_2100 RRU 2219, TD RRU 4418 available on Parent Site
DEL | FY21_22 | Q1 | Ankur Enclave | Mr Dhram Prakash S/o Mani Ram , House number A-186/6, Khasra number 7/14,Sukkar Bazar Road,Prakash Vihar,Karawal Nagar,Delhi - 110094 | 21223 | 21223 | 21223 | 21223 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | ID-1011125 | New | New_Built | RTP | 6 | 16 | 60/180/320 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.7341 | 77.2696 | 13732216 | 2021-05-11 | 2021-05-31 | 2021-06-13 | 111-2873-41772696 | 2021-07-08 | 2021-07-09 | 2021-07-09 | 2021-08-09 |  |  | 2021-07-06 | 2021-08-10 | 2021-08-10 | 2021-08-11 | 2021-08-11 | 2021-08-12 |  |  |  | 2021-06-04 | ST202106322526 | S20210010898 |  |  | 2021-06-27 | P/FVC/DEL/1032899/2021 | 2021-08-13 | 2021-09-22 | DL/01/5126/1201/0031/03/01/10176/NS/22092021 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-10-05 | 2021-09-22 | 2021-10-05 | 2021-10-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 694 | [5 empty] | 2021-07-09 | 2021-09-21 | Survey Rejected; Planned 3rd sector 320 degree not available, Mains supply with single phase only and 6nos 32Amp MCB required,approval received from Amit,Power issue closed on 21 sep 21 Sikka for Material dispatch on 09th Aug 21,69401(EB Upgradation Pending till 25th Aug 21) | [9 empty] | 404-10-621223-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | SEC-78 NOIDA(Relocation of 23434) | Infront of GH-005B SunShine Helios Apartment,Green belt, Sector-78 Noida,Uttar Pradesh-201306 | 20787 | 20787 | 20787 | 20787 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1529075 | New | New_Built | GBM | 30 | 0 | 60/120/350 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5598 | 77.3844 | R/NN-559021 | 2020-11-11 | 2020-11-26 | 2020-12-01 | 11109-2855-98773844 | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-10-13 |  |  | 2021-07-14 | 2021-10-13 | 2021-10-15 | 2021-10-16 | 2021-10-16 | 2021-10-17 |  |  |  | 2020-12-17 | ST202012176920 | S20200009775 |  |  | 2020-12-29 | P/FVC/DEL/1014968/2020 | 2021-10-21 | 2021-10-22 | DL/03/5177/0913/0031/03/01/10244/NS/22102021 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-30 | 2021-10-22 | 2021-10-30 | 2021-10-22 | 2021-11-07 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 556 | [5 empty] | 2021-07-17 | 2021-10-17 | MW Mount & MCB Required at Farend_556 & Parent Site Shutdown, Planning support required_Issue Closed on 19.07.21_Access Issue at site 23434 discuused with Kushabh,Issue closed on 13 Oct 21,Partial Installed_Farend mcb req_media not provisioned as on 16 oct 21,Issue closed on 17 Oct 21,Installed_Farend MW Radio Faulty(1025207)_Delivered on 20.10.21 | [9 empty] | 404-10-620787-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219, TD RRU 4418 available on parent Site , new RRU to be send (FD+L_2100) RRU 2279
Del | FY20_21 | Q2 | Mohan garden II(Relocation of 23431) | Hno.40, block R5 Mohan garden near uttam nagar delhi-110059 | 21009 | 21009 | 21009 | 21009 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1389309 | New | New_Built | RTP | 9 | 14 | 50/160/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6366 | 77.0384 | R/NN-466199 | 2020-09-01 | 2020-11-06 | 2020-11-17 | 111-MDEL-2174434 | 2021-07-16 | 2021-07-17 | 2021-07-17 | 2021-10-11 |  |  | 2021-07-14 | 2021-10-16 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 |  |  |  | 2020-11-22 | ST202011153062 | S20200008589 |  |  | 2020-12-16 | P/FVC/DEL/1012679/2020 | 2021-10-20 | 2021-10-21 | DL/01/5177/6409/0031/03/01/10239/NS/21102021 | 2021-10-21 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 740 | [5 empty] | 2021-07-17 | 2021-10-11 | Only FD+TD avlbl at parent site, Planning support required_Issue Closed on 19.07.21_Again Hold by Anoop on 20.07.21,Issue closed on 11 oct 21,MW Requested_Locator Inactive resolved on 16 Oct 21,Antenna Port Faulty_SCFT Done(71095) | [9 empty] | 404-10-621009-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | TD RRU 4418 available on parent Site ,New RRU to be send on site 2G RRU 2219, FD+L-2100 RRU 2279
Del | FY20_21 | Q1 | Narela DSIDC(Relocation of 10074) | Mrs.Anita Goel W/O Mr.Priyavrat Goel,Plot Bearing No.A-219,Block-A,Narela DSIIDC Industrial Area,Delhi-110040 | 20845 | 20845 | 20845 | 20845 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388253 | New | New_Built | RTT | 12 | 14 | 60/170/280 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.8353 | 77.1015 | R/NN-461832 | 2020-07-21 | 2021-04-07 | 2021-04-29 | 111-2883-53771015 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-15 |  |  | 2021-07-10 | 2021-07-17 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-25 |  |  |  | 2021-05-01 | ST202105213661 | S20210008457 |  |  | 2021-06-12 | P/FVC/DEL/1031141/2021 | 2021-07-25 | 2021-07-27 | DL/01/5177/6319/0031/03/01/10080/NS/27072021 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-08-04 | 2021-08-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 43 | [5 empty] | 2021-07-12 | 2021-07-15 | Survey Rejected; 100M Lat-Long deviation found_Issue resolved on 15.07.21,Installed_Link Done WAN Down(MMU+Radio Faulty Delivered on 24.07.21) | [9 empty] | 404-10-620845-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 , TD RRU RRU4412 available on parent site, new FD +L-2100 RRU 2279 to be send
Del | FY20_21 | Q2 | NAND RAM PARK UTTAM NAGAR | Plot A 216 , Nand Ram Park ,Bindarpur Delhi 110059 | 25460 | 25460 | 25460 | 25460 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-173 | New | New_Built | RTP | 6 | 16 | 20/180/290 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6154 | 77.0657 | 25460 | 2020-03-22 | 2021-01-20 | 2021-02-01 | 111-2861-53770656 | 2021-07-31 | 2021-07-31 |  |  |  |  | 2021-08-01 | 2021-08-03 | 2021-08-03 | 2021-08-04 | 2021-08-04 | 2021-08-05 |  |  |  | 2019-11-21 | 2019694190 | 2019694190 |  | 2021-08-09 | 2020-04-24 | P/FVC/DEL/5911014/2019 | 2021-08-09 | 2021-08-10 | DL/01/0031/2783/0031/03/01/10095/NS/10082021 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-11 | 2021-08-10 | 2021-08-11 | 2021-08-10 | 2021-08-16 | 2021-08-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4254 | [5 empty] | 2021-08-05 | 2021-08-09 | L2100 SACFA Pending,Approval received on 09th Aug for Site On Air Without l2100 | [9 empty] | 404-10-625460-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Sec 28,Chakkarpur,Gurgaon(Relocation of 16801) | HUDA LAND,PARK,Roadside,near Proposed Shopping Centre, Chakkarpur,Sec-28, Gurgaon-122002 | 20832 | 20832 | 20832 | 20832 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1514617 | New | New_Built | GBM | 30 | 0 | 80/190/300 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4688 | 77.0902 | R/NN-559017 | 2020-11-11 | 2020-12-08 | 2020-12-17 | 11106-2846-88770902 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-16 |  |  | 2021-07-14 | 2021-07-16 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 |  |  |  | 2020-12-17 | ST202012176918 | S20200009775 |  |  | 2020-12-29 | P/FVC/DEL/1014965/2020 | 2021-07-24 | 2021-07-25 | DL/05/5177/5289/0031/345/04/08363/NS/25072021 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-27 | 2021-07-25 | 2021-07-28 | 2021-07-25 | 2021-07-31 | 2021-07-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 940 | [5 empty] | 2021-07-12 | 2021-07-16 | TND Issue Resolved on 16.07.21,Farend Owner Issue at 1829(Farend Changed 940_TND received) | [9 empty] | 404-10-620832-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,FD RRUS12B3, L_2100 RRUS12B1, TD RRU RRU4412 available on parent site
Del | FY20_21 | Q2 | Kakrola Patel garden(Relocation 15988) | Smt. Sunil Kumari W/O Sh. Ramesh Chand,Plot No.47-B,Khasra No.17/12,Village Kakrola,Tara Nagar,Delhi, 110078 | 21005 | 21005 | 21005 | 21005 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1953882 | New | New_Built | RTP | 12 | 14 | 0/110/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6145 | 77.0274 | R/NN-618362 | 2021-04-23 | 2021-04-29 | 2021-05-04 | 111-2861-45770273 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-22 |  |  | 2021-07-21 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-25 | 2021-07-29 |  |  |  | 2021-04-17 | ST202104151764 | S20210007098 |  |  | 2021-06-09 | P/FVC/DEL/1028599/2021 | 2021-07-29 | 2021-07-30 | DL/01/5177/6322/0031/03/01/10082/NS/30072021 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-05 | 2021-07-30 | 2021-08-05 | 2021-07-30 | 2021-08-05 | 2021-08-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 642 | [5 empty] | 2021-07-20 | 2021-07-22 | MW Mount required at Farend_642,Installed_HW Faulty(TDD) | [9 empty] | 404-10-621005-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | Gaur atulyam,omnicron ,greater Noida | Ajay Bhati(Estate Manager)Plot No. GH-02,Nicolas Tower - 3, Supertech CZAR, Near Omicron Circle, Greater Noida, Uttar Pradesh-201310 | 19156 | 19156 | 19156 | 19156 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Fine bunch | FB0022 | New | New_Built | RTP | 6 | 70 | 30/100/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4594 | 77.5609 | 19156 | 2021-03-17 | 2021-05-25 | 2021-06-09 | 11109-2845-94775609 | 2021-07-13 | 2021-07-14 | 2021-07-14 | 2021-07-22 |  |  | 2021-07-08 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-25 | 2021-07-31 |  |  |  | 2021-05-28 | ST202105303944 | S20210010398 |  | 2021-06-24 | 2021-07-22 | P/FVC/DEL/1036078/2021 | 2021-07-31 | 2021-08-02 | DL/03/0031/0324/0031/03/01/10084/NS/02082021 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-07 | 2021-08-02 | 2021-08-07 | 2021-08-02 | 2021-08-09 | 2021-08-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1540 | [5 empty] | 2021-07-14 | 2021-07-22 | Pole Required at Farend_11643_Revised TND received from 1540 on 16.07.21_Hold By WH 16th July to 22 July 21,MW Hardware MINI-LINK 6366 Outdoor Unit New Configuration(Partially Delivered by WH on 25th July 21) | [9 empty] | 404-10-619156-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | TRIPATHI ENCLAVE | Mr. Anil Mishra S/O Rama Kant Mishra,House No.D-321,Plot No.2A/2,Khasra No.333,D-Block,Tripathi Enclave,Prem Nagar-2,Village Mundka,Delhi-110081 | 21214 | 21214 | 21214 | 21214 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1956434 | New | New_Built | RTP | 6 | 13.5 | 110/220/320 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6886 | 77.047 | R/NN-618372 | 2021-04-23 | 2021-05-03 | 2021-05-04 | 111-2868-85770470 | 2021-07-16 | 2021-07-16 |  |  |  |  | 2021-07-13 | 2021-07-16 | 2021-07-19 | 2021-07-20 | 2021-07-20 | 2021-07-21 |  |  |  | 2021-04-21 | ST202104161246 | S20210007316 |  | 2021-05-14 | 2021-07-22 | P/FVC/DEL/1036290/2021 | 2021-07-21 | 2021-07-22 | DL/01/5177/6310/0031/03/01/10065/NS/22072021 | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-24 | 2021-07-22 | 2021-07-27 | 2021-07-29 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19251 | [17 empty] | 404-10-621214-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Pulpehladpur | MR.KASIM-HOUSE NO.RZF-46,MEETHAPUR EXTENSION BADARPUR THANA PULPEHLADPUR DELHI-110044 | 19967 | 19967 | 19967 | 19967 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL73 | New | New_Built | RTP | 9 | 16 | 20/130/250 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4963 | 77.2977 | 19967 | 2021-05-13 | 2021-06-02 | 2021-06-16 | 111-2849-63772977 | 2021-07-16 | 2021-07-17 | 2021-07-17 | 2021-08-07 |  |  | 2021-07-11 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-10 | 2021-08-11 |  |  |  | 2021-06-26 | ST202106362822 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034598/2021 | 2021-08-11 | 2021-08-12 | DL/01/0031/2786/0031/03/01/10099/NS/12082021 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-13 | 2021-08-12 | 2021-08-13 | 2021-08-12 | 2021-08-18 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 683 | [5 empty] | 2021-07-17 | 2021-08-07 | Survey Rejected; Mains or DG supply not available and MCD permission not available for Work_Material Delivered required on 23rd July 21_Material return on 23rd July 21,Clearance received on 7th Aug 21 | [9 empty] | 404-10-619967-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Gaur saundaryam,sec-4 | Mr. Sunder Singh S/o Mathura Singh.Bhukhand Number 132,Village Itehara,Near Adhimal Dham,Police Station - Bisrakh,Post Office - Bisrakh,Gautam Buddh Nagar,Uttar Pradesh-201009. | 17853 | 17853 | 17853 | 17853 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_17853_Del | New | New_Built | GBM | 30 | 0 | 10/240/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6034 | 77.4358 | 17853 | 2021-01-11 | 2021-06-29 | 2021-08-10 | 11109-2860-33774358 | 2021-09-23 | 2021-09-24 | 2021-09-24 | 2021-09-25 |  |  | 2021-09-13 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-01 |  |  |  | 2021-06-30 | ST202106367451 | S20210012477 |  |  | 2021-07-14 | P/FVC/DEL/1035025/2021 | 2021-10-01 | 2021-10-04 | DL/03/5417/0002/0031/03/01/10195/NS/04102021 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-18 | 2021-10-04 | 2021-10-20 | 2021-10-04 | 2021-10-20 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 17265 | [5 empty] | 2021-09-24 | 2021-09-28 | Survey rejected; 165M Lat-Long deviation and Tower not erected yet and Mains supply not available (DG Available),Site Released on 23rd Sep 21,MW Mount required at farend_17265,Issue closed on 25 Sep 21,HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21,BB & SMPS,Cable Tray, 1 Sector Pole Mount(Approval required) as on 30 Sep 21 | [9 empty] | 404-10-617853-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q2 | Village-Sarfarabad | Infront Of Jal Board,Near-Prateek Laurel Apartment,Sector-120 Noida,Uttar Pradesh-201306 | 27381 | 27381 | 27381 | 27381 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1797731 | New | New_Built | GBM | 30 | 0 | 30/90/150 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5853 | 77.3946 | R/NN-567587 | 2021-03-09 | 2021-03-09 | 2021-03-24 | 111-MDEL-2174434 | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-07-23 |  |  | 2021-07-06 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-06 |  |  |  | 2021-02-16 | ST202102053955 | S20210002988 |  |  | 2021-03-07 | P/FVC/DEL/1019439/2021 | 2021-08-06 | 2021-08-07 | DL/03/5177/0900/0031/03/01/10090/NS/07082021 | 2021-08-07 | 2021-08-07 | 2021-08-07 | 2021-08-07 | 2021-08-07 | 2021-08-10 | 2021-08-07 | 2021-08-10 | 2021-08-07 | 2021-08-12 | 2021-08-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10526 | [5 empty] | 2021-07-17 | 2021-08-06 | Survey Rejected; Mains or DG supply not available and DCDB not installed(Hold By Ashwani K),MW Hardware MINI-LINK 6366 Outdoor Unit Not in Stock(25th July to 30th July 21),Partially Installed_DCDB Required(2 Aug),Installed_2G Media Issue(3 Aug 21),Media Issue resolved on 06th Aug 21 | [9 empty] | 404-10-627381-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | SHIV VIHAR | Smt Babita w/o Mukesh Bashit,Property No. 86-A,Khasra No. 49/2/1 Min.,Gali No. 6,Devi Nagar,Shiv Vihar,VIllage Karawal Nagar,Illaqa Shahdara, Delhi-110094 | 21191 | 21191 | 21191 | 21191 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3000616 | New | New_Built | RTT | 12 | 10 | 140/240/350 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7215 | 77.2785 | R/NN-619005 | 2021-05-03 | 2021-07-01 | 2021-07-01 | 111-2872-14772784 | 2021-07-16 | 2021-07-17 |  |  |  |  | 2021-07-15 | 2021-07-17 | 2021-07-19 | 2021-07-20 | 2021-07-20 | 2021-07-21 |  |  |  | 2021-04-21 | ST202104161243 | S20210007316 |  | 2021-05-14 | 2021-07-22 | P/FVC/DEL/1036291/2021 | 2021-07-21 | 2021-07-23 | DL/01/5177/6311/0031/03/01/10066/NS/23072021 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-25 | 2021-07-23 | 2021-07-28 | 2021-07-28 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 591 | [17 empty] | 404-10-621191-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | SDMC_GREATER KAILASH III | MBTS Location,South Delhi Municipal Corporation Park,Infront of H.No. E-29, Masjid Moth,Greater Kailash,New Delhi- 110048 | 2800 | 2800 | 2800 | 2800 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1823512 | New | New_Built | cow | 30 | 0 | 40/190/300 | COW |  |  | YES | >18HRS | NO | 28.5395 | 77.2365 | R/NN-568463 | 2021-03-17 | 2021-03-18 | 2021-05-05 | 111-2853-94772364 | 2021-07-16 | 2021-07-16 |  |  |  |  | 2021-07-18 | 2021-07-20 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-22 |  |  |  | 2021-05-10 | ST202105243480 | S20210009050 |  | 2021-06-09 | 2021-07-08 | P/FVC/DEL/1033867/2021 | 2021-07-22 | 2021-07-23 | DL/01/5177/6312/0031/03/01/10068/NS/23072021 | 2021-07-23 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-28 | 2021-07-24 | 2021-08-03 | 2021-08-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9282 | [5 empty] | 2021-07-16 | 2021-07-20 | Hold due to 40 OFC Not in Stock | [9 empty] | 404-10-602800-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Ace city society | GOVERNMENT LAND--GBM LOCATION,GREEN BELT NOIDA AUTHORITY,IN FRONT OF CH-604 MODICARE DP,NEAR STELLAR JEEVAN, AIMNABAD Gautam Buddha Nagar(NOIDA) Uttar Pradesh-203207 | 27221 | 27221 | 27221 | 27221 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1363639 | New | Sharing | GBM | 30 | 0 | 170/250/320 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.5659 | 77.4509 | R/RES-502486 | 2021-06-03 | 2021-06-07 | 2021-06-12 | 11109-2856-58774509 | 2021-07-16 | 2021-07-16 |  |  |  |  | 2021-07-15 | 2021-07-17 | 2021-07-19 | 2021-07-20 | 2021-07-20 | 2021-07-21 |  |  |  | 2021-06-18 | ST202106351955 | S20210011842 |  |  | 2021-07-22 | P/FVC/DEL/1036145/2021 | 2021-07-21 | 2021-07-22 | DL/03/5177/0800/0031/03/01/10064/NS/22072021 | 2021-07-22 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-25 | 2021-07-23 | 2021-07-28 | 2021-07-28 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5223 | [17 empty] | 404-10-627221-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | Omax Mall, Gr. Noida | Mrs.Neeraj Devi W/o Bijender Bhati,H.No G 255,Gali No. 9,Block G, Sector Beta II,Greater Noida,Rampur Jagir,Goutam Buddha Nagar,Uttar Pradesh,201306 | 19685 | 19685 | 19685 | 19685 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-NODA-163 | New | New_Built | RTP | 6 | 14 | 0/90/190 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4868 | 77.5109 | 19685 | 2020-11-20 | 2021-06-02 | 2021-06-05 | 11109-2848-57775099 | 2021-07-13 | 2021-07-13 |  |  |  |  | 2021-07-11 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-16 | 2021-07-17 |  |  |  | 2021-06-04 | ST202106322528 | S20210010898 |  |  | 2021-06-27 | P/FVC/DEL/1032891/2021 | 2021-07-17 | 2021-07-18 | DL/03/0031/0320/0031/03/01/10056/NS/19072021 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-18 | 2021-07-20 | 2021-07-18 | 2021-07-23 | 2021-07-24 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11782 | [17 empty] | 404-10-619685-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Ave, Block G, Gamma II, Greater Noida | Mr. Sukhvir singh s/o Naryan singh. House Number I 027 Gamma 2,Police Station Kasna,Post Office Gamma 2,greater noida,Uttar Pradesh 201307 | 19596 | 19596 | 19596 | 19596 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001958 | New | New_Built | GBM | 30 | 10.2 | 0/120/250 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4922 | 77.5091 | R/NN-625318 | 2019-08-09 | 2019-09-06 | 2019-09-10 | 11109-2849-17775109 | 2021-07-27 | 2021-07-28 | 2021-07-28 | 2021-07-29 |  |  | 2021-07-29 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-02 | 2021-08-11 |  |  |  | 2019-10-22 | 2019665339 | 2019665339 |  |  | 2019-12-18 | P/FVC/DEL/5909897/2019 | 2021-08-12 | 2021-08-12 | DL/03/5177/0901/0031/03/01/10101/NS/12082021 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-13 | 2021-08-12 | 2021-08-18 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 646 | [5 empty] | 2021-07-28 | 2021-08-11 | MW Hardware MINI-LINK 6366 Outdoor Unit Not in Stock(25th July to 30th July 21),Material Delivered at Owner House at 02 Aug 21,Public Issue_Team Plan on Night as Per Indus Team,Public Issue_Installed TDD Fiber Faulty on 11 Aug 21 | [9 empty] | 404-10-619596-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q1 | Rail Vihar, Sector 57, Gurugram | Gurugram Huda Park, Opposite Of H.NO-3444,Rail Vihar, ,Sec-57, Gurgaon Haryana-122003 | 19608 | 19608 | 19608 | 19608 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3002045 | New | New_Built | GBM | 30 | 0 | 120/220/340 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4248 | 77.0782 | R/NN-625321 | 2020-09-21 | 2020-10-20 | 2020-10-26 | 11106-2842-48770781 | 2021-07-16 | 2021-07-16 |  |  |  |  | 2021-07-13 | 2021-07-16 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 |  |  |  | 2020-11-09 | ST202011141382 | S20200007857 |  |  | 2020-12-13 | P/FVC/DEL/1012222/2020 | 2021-07-23 | 2021-07-24 | DL/05/5177/5287/0031/03/01/10071/NS/24072021 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-07-26 | 2021-07-24 | 2021-07-29 | 2021-07-29 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1985 | [17 empty] | 404-10-619608-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | OM SAI ENCLAVE | Mrs.Usha Rani W/o Mr.Bijender Singh,H.No. 59,Om Sai Enclave,Chipyana Buzurg, Ghaziabad,Uttar Pradesh,201009 | 21349 | 21349 | 21349 | 21349 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL63 | New | New_Built | RTP | 6 | 16 | 310/80/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.619 | 77.4503 | 21349 | 2021-05-15 | 2021-06-02 | 2021-06-14 | 11109-2855-98773844 | 2021-07-16 | 2021-07-17 |  |  |  |  | 2021-07-15 | 2021-07-17 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-22 |  |  |  | 2021-06-16 | ST202106346589 | S20210011619 |  | 2021-07-08 | 2021-07-10 | P/FVC/DEL/1034046/2021 | 2021-07-22 | 2021-07-23 | DL/04/0031/0228/0031/03/01/10070/NS/23072021 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-25 | 2021-07-23 | 2021-07-28 | 2021-07-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5809 | [5 empty] | 2021-07-16 | 2021-07-17 | [10 empty] | 404-10-621349-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector 37C, Gurugram | Mrs Soni Kumari,Plot No.1,Khevat/Khata No.255/303,Khasra No.412/2,KD Hospital Village Basai,Near Narayan School,Tehsil-Kadipur,Gurugram Haryana-1222001 | 21295 | 21295 | 21295 | 21295 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/AT/8744 | New | New_Built | RTP | 6 | 16 | 30/130/220 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.4497 | 76.9829 | T21DL00432 | 2021-02-25 | 2021-04-05 | 2021-04-19 | 11106-2844-96769828 | 2021-07-28 | 2021-07-29 | 2021-07-29 | 2021-08-18 |  |  | 2021-07-26 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-24 |  |  |  | 2021-04-17 | ST202104151766 | S20210007098 |  |  | 2021-06-09 | P/FVC/DEL/1028596/2021 | 2021-08-24 | 2021-08-25 | DL/05/5126/0286/0031/345/04/08428/NS/25082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-26 | 2021-08-25 | 2021-08-31 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 18606 | [5 empty] | 2021-07-29 | 2021-08-24 | Survey Rejected; Mains not connected (Meter Available),MW Hardware MINI-LINK 6366 Outdoor Unit Not in Stock(25th July to 30th July 21),Material return due to Public Issue_02.08.21,Issue closed on 18 Aug 21,Partial Installed_Power Issue-EB not connected/Farend owner Issue 20 Aug 21,Farend Changed 17024 to 18606(TND awaited),Issue closed on 24 Aug 21 | [9 empty] | 404-10-621295-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY21_22 | Q1 | Balram Nagar | Mr Joginder Singh S/o Sh Jai Singh, Khasra No.-431, Village-Ali Pur, Near Tata Dharm Kanta, Delhi-110040 | 21382 | 21382 | 21382 | 21382 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_21382_Del | New | New_Built | RTP | 6 | 16 | 350/90/190/280 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.8009 | 77.1283 | 21382 | 2021-05-04 | 2021-06-02 | 2021-06-14 | 111-2880-09771283 | 2021-07-13 | 2021-07-14 |  |  |  |  | 2021-07-11 | 2021-07-14 | 2021-07-19 | 2021-07-20 | 2021-07-20 | 2021-07-21 |  |  |  | 2021-06-18 | ST202106351956 | S20210011842 |  |  | 2021-07-22 | P/FVC/DEL/1036137/2021 | 2021-07-21 | 2021-07-22 | DL/01/5417/0001/0031/03/01/10063/NS/22072021 | 2021-07-22 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-25 | 2021-07-23 | 2021-07-28 | 2021-07-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4502 | [5 empty] | 2021-07-14 | 2021-07-18 | Material Dispatch Hold due to Oracle Issue | [9 empty] | 404-10-621382-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Kalyanpur | Dinesh Garg S/O Jagjeet Garg,Hno.4/250,Block no 4,Near Red Rose Saloon Khichripur delhi -110091 | 21282 | 21282 | 21282 | 21282 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/7499 | New | Sharing | RTP | 6 | 16 | 180/270/330 | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.6202 | 77.3192 | T21DL00444 | 2022-02-23 | 2021-04-20 | 2021-06-25 | 111-2862-01773192 | 2021-07-13 | 2021-07-14 |  |  |  |  | 2021-07-15 | 2021-07-14 | 2021-07-15 | [6 empty] | 2021-04-22 | ST202104166420 | S20210007457 |  | 2021-05-14 | 2021-07-22 | P/FVC/DEL/1036048/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material Handover With ATC Team & Canopy Return_Clearance received for Parsawa dispatch on Night at 11:30 PM on 30 July 2021 & return due to Public Issue on 30 july 2021 (69194),again dispatch on 20 Sep 21,Again return on 21 Sep 21,SRN Done_19.12.21 | ATC | PRI_Without Material |  |  | Indus |  | M1 | 968 | [5 empty] | 2021-07-16 |  | Material Handover With ATC Team & Canopy Return_Clearance received for Parsawa dispatch on Night,SRN Done_19.12.21 | [14 empty] | Material Handover With ATC Team & Canopy Return_Clearance received for Parsawa dispatch on Night at 11:30 PM on 30 July 2021 & return due to Public Issue on 30 july 2021 (69194),again dispatch on 20 Sep 21,Again return on 21 Sep 21,SRN Done_19.12.21 | ATC | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | District Government Multi Speciality Hospital- Noida | Mr.Mukesh Kumar S/O Dayanand, House No.350,Naharpur Kasan,Lakhnaula,Gurgaon,Haryana-122004 | 21592 | 21592 | 21592 | 21592 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II_21592_DEL | New | New_Built | RTP | 6 | 19 | 30/150/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3791 | 76.9378 | 21592 | 2021-05-06 | 2021-05-26 | 2021-05-26 | 11106-2837-91769378 | 2021-07-13 | 2021-07-14 |  |  |  |  | 2021-07-11 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-16 | 2021-07-20 |  |  |  | 2021-05-28 | ST202105304055 | S20210010398 |  | 2021-06-24 | 2021-07-22 | P/FVC/DEL/1036079/2021 | 2021-07-20 | 2021-07-21 | DL/05/0031/0527/0031/03/01/10062/NS/21072021 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | 2021-07-21 | 2021-07-26 | 2021-07-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16207 | [5 empty] | 2021-07-16 | 2021-07-20 | L2100 HW Faulty | [9 empty] | 404-10-621592-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q1 | Migsun Wynne, Omicron | Mr. Surender Arora (Ex. Director),Migsun Wynne,Tower No A, Infront of electric pole no - 36359,ETA II,Greater Noida,Uttar pradesh - 201310 | 21711 | 21711 | 21711 | 21711 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21711_DEL | New | New_Built | RTP | 6 | 82 | 70/180/240/330 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4951 | 77.5385 | 21711 | 2021-04-15 | 2021-04-20 | 2021-04-22 | 11109-2849-50775385 | 2021-07-13 | 2021-07-14 |  |  |  |  | 2021-07-10 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-16 | 2021-07-17 |  |  |  | 2021-04-22 | ST202104166424 | S20210007457 |  | 2021-05-14 | 2021-07-22 | P/FVC/DEL/1036050/2021 | 2021-07-19 | 2021-07-20 | DL/03/0031/0321/0031/03/01/10060/NS/20072021 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-22 | 2021-07-20 | 2021-07-25 | 2021-07-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-07-17 | 2021-07-19 | Installed_Media Issue_Issue resolved on 19.07.21 | [9 empty] | 404-10-621711-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q1 | Teesta Urja Limited | Teesta Urja Limited Ground Floor (Unit – A) Plot no.58, Sector – 44 GURGAON – 122 002 (Haryana) | 27689 | 27689 | 27689 | 27689 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27689_DEL | New | New_Built | IBS | 0 | 21 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4525 | 77.0681 | 27689 | 2021-03-27 | 2021-04-14 | 2021-04-18 | 11106-2845-25770681 | 2021-07-31 | 2021-08-02 |  |  |  |  | 2021-08-01 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-05 | 2021-08-09 | [10 empty] | 2021-08-10 |  |  | 2021-08-10 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-16 | 2021-08-13 | 2021-08-18 | 2021-08-13 | 2021-08-18 | 2021-08-18 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-08-05 | 2021-08-06 | Weekend Access Only reported on 5th Aug 21 | [9 empty] | 404-10-927689-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY21_22 | Q1 | India Bulls Centrum Park | Mr. Gajinder Singh,(RWA)Resident Welfare Association,Khasra no-52/19/1/1 ,Indiabulls Centrum Park,Sector 103,Post Office Daulatabad,Police Station, Sector - 9A,Dwarka link road,Gurgaon-122006 | 27699 | 27699 | 27699 | 27699 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001520 | New | New_Built | RTT | 12 | 10 | 170/270/350 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.497 | 76.9839 | R/NN-620818 | 2021-06-28 | 2021-07-02 | 2021-07-05 | 11106-2849-70769838 | 2021-07-31 | 2021-07-31 |  |  |  |  | 2021-08-01 | 2021-08-03 | 2021-08-03 | 2021-08-04 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-07-26 | ST202107397091 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036567/2021 | 2021-08-05 | 2022-03-03 | DL/05/5177/5292/0031/03/01/10413/NS/03032022 | 2022-03-04 | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-03-09 |  | 2022-03-09 | 2022-03-13 | 2022-03-09 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 15856 | [5 empty] | 2021-08-06 | 2022-03-03 | Access Issue reported on 6th Aug 21 & Issue resolution timeline on 8th Aug 21,Site on Air Plan as Per KPI_03.03.22,BBU Faulty(Locator Inactive) & Access Issue as on 05.03.22 | [9 empty] | 404-10-627699-51 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q1 | DLF mall of india(Relocation of 15422) | DLF MALL OF INDIA OPPOSITE HOTEL RADISSON BLUE SEC-18 NOIDA UTTAR PRADESH-201301 | 27711 | 27711 | 27711 | 27711 |  |  |  | G900_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | SC-27711-Del | New | New_Built | IBS | 0 | 20 | IBS/IBS/IBS/IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.567 | 77.3209 | 27711 | 2021-06-21 | 2021-06-29 | 2021-06-29 | 11109.MNOI.1518456 | 2021-07-15 | 2021-07-15 |  |  |  |  | 2021-07-12 | 2021-07-15 | 2021-07-18 | 2021-07-19 | 2021-07-19 | 2021-07-26 | [10 empty] | 2021-07-26 |  |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-28 | 2021-07-26 | 2021-07-28 | 2021-07-26 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-07-15 | 2021-07-18 | Material dispatch Hold due to Oracle issue 3 Days,L210 RRU Clamp,Patch chord & Combining Material Required(Dispatch Done on 23.07.21) | [9 empty] | 404-10-927711-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD+L_2100 | 2G RRU 2219 ,L_2100 RRU (2219B1/12B1) TD RRU 4418
Del | FY21_22 | Q1 | DLF mall of india(Relocation of 15423) | DLF MALL OF INDIA OPPOSITE HOTEL RADISSON BLUE SEC-18 NOIDA UTTAR PRADESH-201301 | 27712 | 27712 | 27712 | 27712 |  |  |  | G900_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | SC-27712-Del | New | New_Built | IBS | 0 | 19 | IBS/IBS/IBS/IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5676 | 77.3209 | 27712 | 2021-06-21 | 2021-06-29 | 2021-06-29 | 11109.MNOI.1518456 | 2021-07-15 | 2021-07-15 |  |  |  |  | 2021-07-12 | 2021-07-15 | 2021-07-18 | 2021-07-19 | 2021-07-19 | 2021-07-24 | [10 empty] | 2021-07-24 |  |  | 2021-07-25 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-28 | 2021-07-26 | 2021-07-28 | 2021-07-26 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-07-15 | 2021-07-18 | Material dispatch Hold due to Oracle issue 3 Days,L210 RRU Clamp,Patch chord & Combining Material Required(Dispatch Done) | [9 empty] | 404-10-927712-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD+L_2100 | 2G RRU 2219 ,L_2100 RRU (2219B1/12B1) TD RRU 4418
Del | FY21_22 | Q1 | DLF mall of india | DLF MALL OF INDIA OPPOSITE HOTEL RADISSON BLUE SEC-18 NOIDA UTTAR PRADESH-201301 | 27713 | 27713 | 27713 | 27713 |  |  |  | G900_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | SC-27713-Del | New | New_Built | IBS | 0 | 18 | IBS/IBS/IBS/IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.567 | 77.3209 | 27713 | 2021-06-21 | 2021-06-29 | 2021-06-29 | 11109.MNOI.1518456 | 2021-07-15 | 2021-07-15 |  |  |  |  | 2021-07-12 | 2021-07-15 | 2021-07-18 | 2021-07-19 | 2021-07-19 | 2021-07-25 | [10 empty] | 2021-07-25 |  |  | 2021-07-25 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-28 | 2021-07-26 | 2021-07-28 | 2021-07-26 | 2021-08-02 | 2021-08-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-07-15 | 2021-07-18 | Material dispatch Hold due to Oracle issue 3 Days,L210 RRU Clamp,Patch chord & Combining Material Required(Dispatch Done on 23.07.21) | [9 empty] | 404-10-927713-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD+L_2100 | 2G RRU 2219 ,L_2100 RRU (2219B1/12B1) TD RRU 4418
Del | FY21_22 | Q1 | COPERATE PARK D-21 | D-21 Corporate Park. 301,3rd floor, Manikarnan Power Limited, Sector 21, Dwarka, Near Sector 8 Metro station Dwarka, New Delhi 110077 | 27714 | 27714 | 27714 | 27714 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | DIPPL/DEL/001 | New | New_Built | IBS | 0 | 17 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5621 | 77.0673 | 27714 | 2021-06-21 | 2021-06-29 | 2021-06-29 | 111-2856-20770672 | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-08-02 |  |  | 2021-07-14 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-07 | 2021-08-12 | [10 empty] | 2021-08-12 |  |  | 2021-08-12 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-14 | 2021-08-13 | 2021-08-14 | 2021-08-13 | 2021-08-19 | 2021-08-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 238 | [5 empty] | 2021-07-24 | 2021-08-12 | Pole Mount required at Farend 238 Issue closed on 02.08.21,Hold due to Adapter Din(m)-N(f),BBU & Antenna,Infra Material return_MW Pole Mount required at Farend on 7th Aug 21,Issue closed on 12.08.21 | [9 empty] | 404-10-927714-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 TD RRU 4418
Del | FY21_22 | Q1 | Sector 6 Dwarka | Government land,GBM Location,Open Plot Of South Delhi Municipal Corporation(SDMC) Area,In front of Plot No- 28 Kamakshi Apartment,And Behind Plot No- 27 Param Puneet Apartment,Police Station Sec 1 Dwarka,Post Office Sector 6 Dwarka,Sector 6 Dwarka, New Delhi-110075 | 17183 | 17183 | 17183 | 17183 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001887 | New | New_Built | GBM | 30 | 0 | 80/220/320 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5909 | 77.0664 | R/NN-621205 | 2021-06-21 | 2021-06-29 | 2021-06-29 | 111.2859.09770664.CWIP-CL | 2021-07-28 | 2021-07-29 | 2021-07-29 | 2021-07-29 |  |  | 2021-07-27 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-02 | 2021-08-04 |  |  |  | 2021-07-19 | ST202107388722 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036217/2021 | 2021-08-04 | 2021-08-06 | DL/01/5177/6324/0031/03/01/10087/NS/06082021 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-08 | 2021-08-08 | 2021-08-09 | 2021-08-08 | 2021-08-10 | 2021-08-08 | 2021-08-16 | 2021-08-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 615 | [5 empty] | 2021-07-29 | 2021-07-29 | Survey Rejected; Mains or DG supply not available,MW Hardware MINI-LINK 6366 Outdoor Unit Not in Stock(25th July to 30th July 21)_Power Issue reported after Integration on 5th Aug 21 & Issue resolved on 6th Aug 21 | [9 empty] | 404-10-617183-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q1 | EMCD_8_Nalanda chowk | Mr. Anil And Arun Gaur S/O Lt A.S. Gaur,Property Bearing No. D-436/D-1,2,Khasra No. 797,Police Station Mandawli,Post Office Mandawli,Village Mandwali Fazalpur,West Vinod Nagar,Delhi-110092 | 19904 | 19904 | 19904 | 19904 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001991 | New | New_Built | RTM | 12 | 10.6 | 0/180/250 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6263 | 77.3025 | R/NN-625365 | 2021-07-05 | 2021-07-14 | 2021-07-15 | 111-2862-63773025 | 2021-08-10 | 2021-08-10 |  |  |  |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-12 | 2021-09-02 |  |  |  | 2021-07-19 | ST202107388712 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036224/2021 | 2021-09-02 | 2021-09-03 | DL/01/5177/6340/0031/06/05/11959/NS/03092021 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-04 | 2021-09-03 | 2021-09-05 | 2021-09-03 | 2021-09-07 | 2021-09-10 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 136 | [5 empty] | 2021-08-12 | 2021-08-30 | Installed_Fiber faulty 2 nos & Public Issue, Issue resolved on 30 Aug 21 | [9 empty] | 404-10-619904-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Vidhan Sabha(Relocation of 5469) | Delhi Legistative Assembly,Behind Vidhan sabha Metro Gate No 2,New Delhi-110054 | 19802 | 19802 | 19802 | 19802 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Protel Telepower Infrastructure Pvt Ltd. | PO_19802_Del | Relocation | New_Built | GBM | 30 | 0 | 0,120,240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6891 | 77.2217 | 19802 | 2020-05-26 | 2020-09-28 | 2020-09-28 | 111-2868-78772222 | 2021-08-05 | 2021-08-05 |  |  |  |  | 2021-08-02 | 2021-08-05 | 2021-08-05 | 2021-08-06 | 2021-08-06 | 2021-08-07 |  |  |  | 2020-10-05 | ST202010098577 | S20200005636 |  |  | 2020-10-15 | P/FVC/DEL/1008856/2020 | 2021-08-09 | 2021-08-10 | DL/01/0031/2785/0031/03/01/10094/NS/10082021 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-11 | 2021-08-10 | 2021-08-14 | 2021-08-10 | 2021-08-14 | 2021-08-16 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 13049 | [17 empty] | 404-10-619802-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Sector 45 Faridabad | Municipal Corporation Faridabad(MCF),GBM Location andNear of Pole No.29069,Sector 45, Faridabad, Haryana 121003 | 14183 | 14183 | 14183 | 14183 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1884296 | New | New_Built | GBM | 30 | 0 | 50/160/290 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4518 | 77.3001 | R/NN-569828 | 2021-04-02 | 2021-05-03 | 2021-07-01 | 11106-2845-16773000 | 2021-08-27 | 2021-08-28 | 2021-08-28 | 2021-09-01 |  |  | 2021-08-17 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-09-07 |  |  |  | 2021-07-05 | ST202107374643 | S20210012735 |  |  | 2021-07-15 | P/FVC/DEL/1035196/2021 | 2021-09-08 | 2021-09-09 | DL/02/5177/5032/0031/345/04/08456/NS/09092021 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-10 | 2021-09-09 | 2021-09-10 | 2021-09-09 | 2021-09-14 | 2021-09-14 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9893 | [5 empty] | 2021-08-28 | 2021-09-01 | Pole Mount required at Farend Issue closed on 1 Sep 21,Installed BBU faulty on 6th Sep 21,BBU recvd on 8th Sep 21 | [9 empty] | 404-10-614183-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | Sector 11 Rohini | Mr Prabhakar Pandey S/o Shri Ganga Prasad Pandey,House Number - 32,Block - G,Pocket 6,Sector 11 Rohini,New Delhi - 110085, | 17347 | 17347 | 17347 | 17347 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II_17347_DEL | New | New_Built | RTP | 11 | 13 | 0/120/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7335 | 77.108 | 17347 | 2020-09-14 | 2021-05-26 | 2021-05-26 | 111-2873-34771079 | 2021-08-26 | 2021-08-27 |  |  |  |  | 2021-08-27 | 2021-08-27 | 2021-08-29 | 2021-08-30 | 2021-08-30 | 2021-09-03 |  |  |  | 2021-05-28 | ST202105304054 | S20210010398 |  |  | 2021-07-22 | P/FVC/DEL/1036094/2021 | 2021-09-03 | 2021-09-07 | DL/01/0031/2810/0031/03/01/10139/NS/07092021 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-15 | 2021-09-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11812 | [5 empty] | 2021-08-30 | 2021-09-07 | Partially Installed_Media Issue resolved,Partially Installed_EB Connection Pending resolved on 2 sep 21,Publis Issue reported on 4 Sep 21,Issue closed on 7 Sep 21 | [9 empty] | 404-10-617347-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Shalimar Bagh_X (Relocation of569) | Ram Lila Ground, Behind Delhi Jal Borad,In Front of House No - AG-576, A.F.Block, Shalimar Garden,Veer Bazaar Road,Delhi-110088 | 19347 | 19347 | 19347 | 19347 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1739779 | Relocation | New_Built | Cow | 30 | 0 | 30/250/310 | COW |  |  | YES | >18HRS | NO | 28.7043 | 77.1663 | R/NN-566088 | 2021-02-17 | 2021-02-18 | 2021-02-26 | 111-2870-42771663 | 2021-08-26 | 2021-08-28 | 2021-08-28 | 2021-09-06 |  |  | 2021-08-12 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-09 | 2021-09-10 |  |  |  | 2021-03-03 | ST202103077349 | S20210004126 |  |  | 2021-03-21 | P/FVC/DEL/1020327/2021 | 2021-09-10 | 2021-09-11 | DL/01/5177/6347/0031/345/04/08459/NS/11092021 | 2021-09-11 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-16 | 2021-09-14 | 2021-09-21 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5122 | [5 empty] | 2021-08-28 | 2021-09-06 | Material return on 31.08.21,Issue closed on 6 Sep 21,DG Issue on 13th Sep 21 | [9 empty] | 404-10-619347-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | BRPL Sec-3,Pushp Vihar | GBM Location,South Delhi Municipal Corporation Park(SDMC),Opp. Radha Krishan Vidya Niketen,Sec 5,and Near Falt 1931/1,Gurudwara Rd, Sector 3,Pushp Vihar,New Delhi 110017 | 17567 | 17567 | 17567 | 17567 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001965 | New | New_Built | RTT | 30 | 0 | 50/150/250 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5216 | 77.2253 | R/NN-625327 | 2021-07-05 | 2021-07-17 | 2021-07-25 | 111-2852-11772253 | 2021-08-26 | 2021-08-27 | 2021-08-27 | 2021-12-09 |  |  | 2021-07-26 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-11 | 2021-12-13 |  |  |  | 2021-07-29 | ST202107401819 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037075/2021 | 2021-12-13 | 2021-12-14 | DL/01/5177/6465/0031/345/04/08663/NS/14122021 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-21 | 2021-12-14 | 2021-12-18 | 2021-12-14 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16 | [5 empty] | 2021-08-27 | 2021-12-09 | Survey Rejected; 46M Lat-Long deviation found,Issue closed on 09.12.21,Partially Installed_MW pole issue nearend as on 11.12.11 | [9 empty] | 404-10-617567-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | ANAND VIHAR | Mr Naveen Kumar S/O Kartar Singh , Plot number B-86, Block - B, Anand Vihar , Uttam Nagar, New Delhi - 110059 | 20339 | 20339 | 20339 | 20339 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL041 | New | New_Built | RTM | 12 | 13 | 80/210/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6242 | 77.0542 | 20339 | 2019-11-11 | 2021-06-17 | 2021-06-18 | 111-2862-42770542 | 2021-08-10 | 2021-08-11 |  |  |  |  | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-13 | 2021-08-18 |  |  |  | 2021-07-09 | ST202107379565 | S20210012929 |  |  | 2021-07-16 | P/FVC/DEL/1035537/2021 | 2021-08-18 | 2021-08-19 | DL/01/0031/2795/0031/03/01/10116/NS/19082021 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-21 | 2021-08-19 | 2021-08-21 | 2021-08-19 | 2021-08-26 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5999 | [5 empty] | 2021-08-13 | 2021-08-17 | Public issue,Material Handover with toco in Night,Issue closed on 17th Aug 21 | [9 empty] | 404-10-620339-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | MAHAVIR ENCLAVE, GALI NO-6 | Plot Numver-36-C,Khasra Number-7/18/2,Village-Mirzapur,Colony Tamilar Enclave,Police Station-Sagar pur,Post Office -Dabri,Dabri Palam Road,New Delhi-110045 | 20415 | 20415 | 20415 | 20415 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1357277 | New | New_Built | RTP | 6 | 18.3 | 0/150/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6061 | 77.0739 | R/RES-503981 | 2021-07-26 | 2021-07-26 | 2021-08-05 | 111-2860-57770744 | 2021-08-13 | 2021-08-14 | 2021-08-14 | 2022-03-21 |  |  | 2021-08-11 | 2022-03-21 | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-23 |  |  |  | 2021-07-29 | ST202107401852 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037086/2021 | 2022-03-23 | 2022-03-24 | DL/01/5177/06590/0031/03/01/10462/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-04-14 | 2022-03-24 | 2022-03-26 | 2022-03-24 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1618 | [5 empty] | 2021-08-14 | 2022-03-23 | MW Mount required at Farend,Material return on 19.08.21,Issue closed on 16.03.22 & Material Delivery Plan on 21.03.22,Public Issue_17.03.22,Partial Installed_Power Issue battery bank Isnt req/Farend Installed as on 22.03.22 | [9 empty] | 404-10-620415-11 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Prem Nagar-III | Mr Raju S/O Sh Suraj Yadav , Plot number F-89, Khsara number 102, Astha Vihar , Mangal bazar road , Prem Nagar-3, Kirari , Police Station - Prem Nagar, New Delhi 110086 | 21184 | 21184 | 21184 | 21184 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1765513 | New | New_Built | RTT | 12 | 11 | 80/230/310 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6966 | 77.0465 | R/NN-566740 | 2021-02-24 | 2021-07-13 | 2021-07-17 | 111-2869-66770464 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-23 |  |  | 2021-08-21 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-25 | 2021-08-27 |  |  |  | 2021-07-27 | ST202107398492 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036779/2021 | 2021-08-27 | 2021-08-28 | DL/01/5177/6339/0031/03/01/10128/NS/28082021 | 2021-08-28 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-09-03 | 2021-08-31 | 2021-09-07 | 2021-09-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19251 | [5 empty] | 2021-08-20 | 2021-08-27 | Pole Mount required at Farend,Issue closed on 23 Aug 21,again Installed Farend Access Issue reported on 26 Aug 21 and Closed on 27 Aug 21 | [7 empty] | 404-10-621184-51 |  | 404-10-621184-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | SDMC_RBI COLONY ,POORVI MARG | Government Land,South Delhi Municipal Corporation(Park),GBM Location,in Frount House Number- D8/1,SDMC RBI Colony,Delhi, Police Station Vasant vihar ,Post office Vasant Vihar, Delhi-110057 | 17190 | 17190 | 17190 | 17190 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001987 | New | New_Built | Cow | 30 | 0 | 160/290/350 | COW |  |  | YES | >18HRS | NO | 28.5601 | 77.1534 | R/NN-625363 | 2020-03-31 | 2020-07-20 | 2021-07-19 | 111-2855-99771536 | 2021-08-04 | 2021-08-05 |  |  |  |  | 2021-08-03 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-07 | 2021-08-13 |  |  |  | 2021-07-27 | ST202107398506 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036783/2021 | 2021-08-13 | 2021-08-14 | DL/01/5177/6330/0031/03/01/10103/NS/14082021 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-16 | 2021-08-14 | 2021-08-17 | 2021-08-14 | 2021-08-24 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 257 | [5 empty] | 2021-08-07 | 2021-08-11 | Survey Rejected ; Mains supply not available but DG available,Material Delivered on 7 Aug 21,Public Issue Site Hold by Ashwani K,Public Issue resolved 11 Aug 21 | [9 empty] | 404-10-617190-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | EMCD_52_Ghazipur Dairy Farm Near SBI Bank | Property Bearing No. C-62,Road No. 3, Gazipur Dairy Farm, Delhi-110096 | 20888 | 20888 | 20888 | 20888 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001799 | New | New_Built | RTT | 12 | 7.5 | 0/130/200 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6246 | 77.3219 | R/NN-621215 | 2021-06-30 | 2021-07-02 | 2021-07-19 | 111-2862-46773218 | 2021-08-10 | 2021-08-11 |  |  |  |  | 2021-08-09 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-13 | 2021-08-14 |  |  |  | 2021-07-27 | ST202107398489 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036778/2021 | 2021-08-14 | 2021-08-16 | DL/01/5177/6331/0031/03/01/10109/NS/16082021 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-17 | 2021-08-16 | 2021-08-18 | 2021-08-16 | 2021-09-06 | 2021-09-06 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1559 | [7 empty] | Partially Installed_SFP Short | [9 empty] | 404-10-620888-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | TRIPATHI ENCLAVE 2 | H No-2C-86, Gauri Shankar Enclave Nagar-3, Kirari Suleman Nagar, Delhi-110086 | 21215 | 21215 | 21215 | 21215 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1503258 | New | New_Built | RTT | 12 | 11 | 90/220/320 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6881 | 77.0451 | R/NN-558666 | 2020-11-11 | 2020-12-04 | 2020-12-10 | 111-2868-81770450 | 2021-08-26 | 2021-08-27 |  |  |  |  | 2021-08-27 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-08-31 | 2021-09-03 |  |  |  | 2021-05-19 | ST202105272209 | S20210009709 |  |  | 2021-06-17 | P/FVC/DEL/1031572/2021 | 2021-09-06 | 2021-09-07 | DL/01/5177/6345/0031/03/01/10141/NS/07092021 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-14 | 2021-09-14 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19251 | [5 empty] | 2021-09-01 | 2021-09-06 | MCB Burnt,Farend Pole Mount required Issue closed on 3 Sep 21.,SACFA Pending issue resolved on 6 sep 21 | [9 empty] | 404-10-621215-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Chander puri, Hapur road, Ghaziabad | Mrs. Savita Rani W/o Mr. Vinod Kumar Garg,House Number 53,Chanderpuri,Police Station Navyug Markrt Richalpuri Gaziabad,Post Office Chanderpuri,Tehsil & District- Ghaziabad U.P 201001 | 21251 | 21251 | 21251 | 21251 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | AM-21251-Del | New | New_Built | RTP | 9 | 14 | 30/130/230/310 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.6672 | 77.4243 | T21DL01584 | 2020-10-29 | 2021-07-11 | 2021-07-11 | 11109-2866-72774242 | 2021-08-19 | 2021-08-20 |  |  |  |  | 2021-07-30 | 2021-08-20 | 2021-08-22 | 2021-08-23 | 2021-08-23 | 2021-08-24 |  |  |  | 2021-07-13 | ST202107382797 | S20210013039 |  |  | 2021-07-17 | P/FVC/DEL/1035690/2021 | 2021-08-24 | 2021-08-25 | DL/04/5126/0255/0031/345/04/08426/NS/25082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-26 | 2021-08-25 | 2021-08-26 | 2021-08-25 | 2021-08-31 | 2021-09-02 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 781 | [17 empty] | 404-10-621251-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | shashi garden | MCD TOILET, Raam prasad, bismil camp, patparganj, behind india post office, infront of house no 161,Mayur Vihar, Delhi, 110091 | 17260 | 17260 | 17260 | 17260 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL013 | New | New_Built | Cow | 30 | 0 | 100/190/260 | COW |  | 3RD_PARTY | YES | >18HRS | NO | 28.6134 | 77.2926 | 17260 | 2020-07-14 | 2020-07-23 | 2021-07-16 | 111-2861-34772926 | 2021-08-03 | 2021-08-04 | 2021-08-04 | 2021-09-17 |  |  | 2021-08-01 | 2021-09-17 | 2021-09-19 | 2021-09-20 | 2021-09-20 | 2021-09-23 |  |  |  | 2020-08-03 | ST202008035405 | S20200002462 |  |  | 2020-08-10 | P/FVC/DEL/1003605/2020 | 2021-09-23 | 2021-09-23 | DL/01/0031/2874/0031/03/01/10182/NS/23092021 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-24 | 2021-09-23 | 2021-09-29 | 2021-09-23 | 2021-09-29 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1448 | [5 empty] | 2021-08-06 | 2021-09-23 | Material return due to Public Issue_06.08.21,Issue closed on 17 Sep 21,Partially Installed_GSM 2G Port Faulty(70356) on 21 Sep 21 and Delivered on 23 Sep 21 | [9 empty] | 404-10-617260-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | NANDNI ENCLAVE, NAND GRAM, GAZIABAD | Mrs kusum s/o Mr surender pal, h. No R 11 Nandi enclave, nandgram, 201003 | 20191 | 20191 | 20191 | 20191 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001977 | New | New_Built | RTP | 9 | 13.5 | 90/230/330 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6881 | 77.4112 | R/NN-625351 | 2021-01-20 | 2021-07-14 | 2021-07-19 | 11109-2868-80774112 | 2021-08-10 | 2021-08-11 |  |  |  |  | 2021-08-09 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-13 | 2021-08-14 |  |  |  | 2021-07-27 | ST202107398488 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036782/2021 | 2021-08-14 | 2021-08-14 | DL/04/5177/0771/0031/03/01/10105/NS/14082021 | 2021-08-14 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-20 | 2021-08-19 | 2021-08-24 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4764 | [5 empty] | 2021-08-13 | 2021-08-18 | Installation WIP/Eb Connection Pending Close by 5 pm,Power Issue resolved on 18 Aug 21 | [9 empty] | 404-10-620191-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Sharma Nursing home | Khushal Arora S/o Surender Arora, House No. 128, Bhagat Singh Colony, Near Banke Bihari Mandir, NIT-5, Faridabad, Haryana, 121001 | 21677 | 21677 | 21677 | 21677 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1853175 | New | New_Built | RTP | 6 | 13 | 10/170/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4006 | 77.3068 | R/NN-569038 | 2021-03-25 | 2021-04-20 | 2021-04-26 | 11106-2840-06773067 | 2021-08-13 | 2021-08-14 |  |  |  |  | 2021-08-14 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-03-15 | ST202103091234 | S20210004773 |  |  | 2021-07-08 | P/FVC/DEL/1033400/2021 | 2021-08-24 | 2021-08-25 | DL/02/5177/5027/0031/06/05/11922/NS/25082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-27 | 2021-08-25 | 2021-08-31 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 587 | [5 empty] | 2021-08-19 | 2021-08-22 | Installed_2G Media Issue & GSM Port Faulty on 19 Aug 21,Media Issue resolved 22 Aug 21 | [9 empty] | 404-10-621677-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | B Block Vasant Vihar(Relocation of 7234) | Government Land,South Delhi Municipal Corporation(Park),GBM Location,opposite B-3/15,Delhi, Police Station Vasant vihar ,Post office Vasant Vihar, Delhi-110057 | 13182 | 13182 | 13182 | 13182 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001797 | Relocation | New_Built | Cow | 30 | 0 | 120/240/340 | COW |  |  | YES | >18HRS | NO | 28.568 | 77.1624 | R/NN-621213 | 2021-06-30 | 2021-07-02 | 2021-07-19 | 111-2856-79771624 | 2021-08-04 | 2021-08-05 |  |  |  |  | 2021-08-04 | 2021-08-06 | 2021-08-06 | 2021-08-07 | 2021-08-07 | 2021-08-09 |  |  |  | 2021-07-27 | ST202107398505 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036784/2021 | 2021-08-10 | 2021-08-11 | DL/01/5177/6327/0031/03/01/10097/NS/11082021 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-11 | 2021-08-12 | 2021-08-11 | 2021-08-14 | 2021-08-16 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 671 | [7 empty] | Survey Rejected ; Mains supply not available but DG available | [9 empty] | 404-10-613182-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | SHIV VIHAR | Sh. Deepak Mathur s/o Sh. Ajit Singh,Plot No. J-158A,Khasra No. 93/6/7,Shiv Vihar Colony,Delhi-110081 | 19776 | 19776 | 19776 | 19776 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1777009 | New | New_Built | GBM | 30 | 0 | 50/120/290 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.7295 | 77.0262 | R/NN-566963 | 2021-02-24 | 2021-05-03 | 2021-06-21 | 111.2872.95770261.CWIP-CL | 2021-08-26 | 2021-08-27 |  |  |  |  | 2021-08-25 | 2021-08-27 | 2021-08-29 | 2021-08-30 | 2021-08-30 | 2021-09-02 |  |  |  | 2021-06-26 | ST202106362827 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034601/2021 | 2021-09-02 | 2021-09-03 | DL/01/5177/6341/0031/03/01/10134/NS/03092021 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-08 | 2021-09-04 | 2021-09-08 | 2021-09-08 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 585 | [17 empty] | 404-10-619776-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | Lakshmi Garden, Gzb | Mr.Krishan Kumar Tyagi S/O Shri Balvir Tyagi,House No.A-245,Block-A,Vikas Kunj Pal Vihar,Loni,Ghaziabad,Uttar Pradesh-201102 | 20992 | 20992 | 20992 | 20992 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Infinite | II_20992_DEL | New | New_Built | RTP | 9 | 10 | 0/120/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7257 | 77.2922 | 20992 | 2021-02-24 | 2021-05-04 | 2021-07-08 | 11109-2872-56772922 | 2021-08-03 | 2021-08-04 |  |  |  |  | 2021-08-04 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-06 | 2021-08-09 |  |  |  | 2020-12-25 | ST202012183707 | S20200010062 |  |  | 2020-12-30 | P/FVC/DEL/1015145/2020 | 2021-08-13 | 2021-08-16 | DL/04/0031/0236/0031/03/01/10107/NS/16082021 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-18 | 2021-08-16 | 2021-08-24 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5408 | [5 empty] | 2021-08-09 | 2021-08-12 | Installed_Farend Access Issue,Installed 2G Media Issue,Issue closed on 12 Aug 21 | [9 empty] | 404-10-620992-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Shakti Khand III, Indirapuram, Ghaziabad | Mr. Surender,Plot No 50/1,Shakti Plaza, Shakti khand III, Indirapuram ,Vasundhara police Station,Shipra Sun City Post Office,Ghaziabad, Uttar Pradesh - 201014 | 20124 | 20124 | 20124 | 20124 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTPL058 | New | New_Built | RTP | 6 | 16 | 100/180/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6504 | 77.3655 | 20124 | 2021-04-17 | 2021-06-30 | 2021-06-30 | 11109-2865-04773655 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-17 |  |  | 2021-07-26 | 2021-08-17 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-21 |  |  |  | 2021-07-02 | ST202107370631 | S20210012660 |  |  | 2021-07-15 | P/FVC/DEL/1035084/2021 | 2021-08-24 | 2021-08-25 | DL/04/5414/0001/0031/03/01/10122/NS/25082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-31 | 2021-08-25 | 2021-08-31 | 2021-08-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 826 | [5 empty] | 2021-08-05 | 2021-08-24 | Survey Rejected; 3M Height deviation found,approval received from Manoj on 17th Aug 21,Installed_Media Issue reported on 23 Aug 21 and closed on 24 Aug 21 | [9 empty] | 404-10-620124-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Palm Drive Gurgaon | Rakesh kumar(Estate Manager),Emaar Palm Terraces Select,Tower-10,Badshahpur, Sector 66, Gurugram, Haryana 122102 | 23342 | 23342 | 23342 | 23342 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1373169 | New | Sharing | RTP | 6 | 43 | 40/200/280 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4011 | 77.055 | R/RES-435940 | 2021-03-13 | 2021-03-15 | 2021-03-17 | 11106-2840-11770549 | 2021-08-10 | 2021-08-11 | 2021-08-11 | 2021-08-13 |  |  | 2021-08-12 | 2021-08-14 | 2021-08-16 | 2021-08-17 | 2021-08-17 | 2021-09-03 |  |  |  | 2021-03-15 | ST202103091235 | S20210004773 |  |  | 2021-07-08 | P/FVC/DEL/1033399/2021 | 2021-09-03 | 2021-09-04 | DL/05/5177/5200/0031/06/05/11985/NS/04092021 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-06 | 2021-09-04 | 2021-09-06 | 2021-09-04 | 2021-09-09 | 2021-09-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4735 | [5 empty] | 2021-08-11 | 2021-09-02 | Owner Issue at Farend,Material Delivery Plan on Monday,Material dippatch hold 14th Aug to 15th Aug 21,Partially Installed_Farend MW Mount required on 17th Aug,Partially Installed Work Stop by Building Authority,Issue closed on 2 sep 21 | [9 empty] | 404-10-623342-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q1 | Sar Group | Plot No. 221 Udyog Vihar Phase-1 Gurgaon | 27688 | 27688 | 27688 | 27688 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27688_DEL | New | New_Built | IBS | 0 | 29 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5086 | 77.0834 | 27688 | 2021-03-22 | 2021-07-06 | 2021-07-06 | 11106-2850-83770830 | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-07-18 |  |  | 2021-07-06 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-05 | 2021-08-11 | [10 empty] | 2021-08-11 |  |  | 2021-08-11 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-16 | 2021-08-13 | 2021-08-18 | 2021-08-13 | 2021-08-18 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5374 | [5 empty] | 2021-07-16 | 2021-08-06 | Infra_Ladder for routing of Media cables for TN on priority_Issue Closed on 18.07.21,Weekend Access Only reported on 5th Aug 21 | [9 empty] | 404-10-927688-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q1 | DMRC depot SamayPur Badli | Mr.Bijender Kumar S/O Mr.Hari Ram, Khasra No.756/2,Village-Siraspur,Near Hanuman Mandir Wali Gali & Barat Ghar,Swaroop Nagar Police Station,Post office siraspur,Delhi-110042 | 20703 | 20703 | 20703 | 20703 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_20703_DEL | New | New_Built | RTP | 6 | 16 | 340/90/170 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7582 | 77.1281 | 20703 | 2021-05-21 | 2021-06-29 | 2021-06-29 | 111-2875-81771280 | 2021-08-10 | 2021-08-10 |  |  |  |  | 2021-08-09 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-12 | 2021-08-14 |  |  |  | 2021-06-30 | ST202106367452 | S20210012477 |  |  | 2021-07-14 | P/FVC/DEL/1035029/2021 | 2021-08-14 | 2021-08-16 | DL/01/5417/0002/0031/03/01/10106/NS/16082021 | 2021-08-16 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-24 | 2021-08-18 | 2021-08-24 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1596 | [5 empty] | 2021-08-13 | 2021-08-17 | Installation WIP/Eb Connection Pending /Close Today As per Toco,Partally Installed_MW Mount req at Farend,Issue resolved on 14 Aug 21,Azimuth revised on 16th Aug and field activity completed on 17th Aug | [9 empty] | 404-10-620703-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Ganga Yamuna Appartment,Sec-7 Sidharth Vihar Gaziabad | Mr. Sudhakar Yadav,Plot No.1,Ganga Yamuna Apartment,Tower Number Y1, Sector-7,Siddharth Vihar,Police Station Siddhart Vihar,Ghaziabad,Post Office Vijay Nagar,Ghaziabad,Uttar Pradesh-201009 | 20784 | 20784 | 20784 | 20784 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1638009 | New | New_Built | RTP | 6 | 67 | 40/130/240 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6559 | 77.4022 | R/NN-562519 | 2021-01-08 | 2021-07-12 | 2021-07-14 | 11109-2865-58774022 | 2021-08-02 | 2021-08-03 | 2021-08-03 |  |  |  | 2021-08-04 | [8 empty] | 2021-07-19 | ST202107388719 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036212/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Authority Issue | Indus | PRI_Without Material |  |  | Indus |  | M1 | 781 | [5 empty] | 2021-08-03 |  | Survey Rejected; Access Issue | [14 empty] | Authority Issue | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Model Town, Delhi | Mr.Sudhir Kumar S/O K.R.Maini,House No.540,Parmanand Colony,Model Town,Tagore Park,Police Station Mukherjee Nagar,Post Office Mukharjee Nagar,North West,Delhi-110009 | 21206 | 21206 | 21206 | 21206 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL61 | EXISTING | Sharing | RTP | 9 | 13 | 0/90/210 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.7084 | 77.2012 | 21206 | 2021-05-11 | 2021-06-02 | 2021-07-10 | 111-2870-83772011 | 2021-08-10 | 2021-08-10 |  |  |  |  | 2021-08-07 | 2021-08-10 | 2021-08-10 | 2021-08-11 | 2021-08-11 | 2021-08-16 |  |  |  | 2021-07-13 | ST202107382776 | S20210013039 |  |  | 2021-07-17 | P/FVC/DEL/1035688/2021 | 2021-08-17 | 2021-08-18 | DL/01/0031/2794/0031/03/01/10113/NS/18082021 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-20 | 2021-08-18 | 2021-08-20 | 2021-08-18 | 2021-08-24 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4836 | [5 empty] | 2021-08-11 | 2021-08-16 | Material delivered with Toco as Discussed with Amit Sikka,Issue resolved on 16 Aug 21,Installed Link Done | [9 empty] | 404-10-621206-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Sec-84, Noida | Opp Motherson Sumi System Ltd. Gate No. A3 , Mandi Marg , C Block ,Noida Phase 2, Yakubpur Sec 84 , Noida ,Uttar pradesh 201305 | 16752 | 16752 | 16752 | 16752 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1640203 | New | New_Built | GBM | 30 | 0 | 140/240/350 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5301 | 77.4067 | R/NN-562575 | 2021-01-08 | 2021-01-22 | 2021-02-08 | 11109-2853-00774066 | 2021-08-19 | 2021-08-20 |  |  |  |  | 2021-07-28 | 2021-08-20 | 2021-08-22 | 2021-08-23 | 2021-08-23 | 2021-08-28 |  |  |  | 2021-02-16 | ST202102053952 | S20210002988 |  |  | 2021-03-07 | P/FVC/DEL/1019436/2021 | 2021-08-30 | 2021-08-31 | DL/03/5177/0902/0031/345/04/08436/NS/31082021 | 2021-08-31 | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-09-03 | 2021-09-02 | 2021-09-08 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5693 | [5 empty] | 2021-08-23 | 2021-08-27 | Delivered with Short RRU by TPT,Shortage RRU Delivered on 27 Aug 21(After 4 Days of Material Delivery) | [9 empty] | 404-10-616752-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Sahibabad | Mr Vijender Kumar S/o Sh Chandra Pal Singh, House Number C-194, Prahlad garhi, Vasundhara ,Vasundhra police Station,Vasundhra Post Office ,Ghaziabad, Uttar Pradesh - 201012 | 21283 | 21283 | 21283 | 21283 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II_21283_DEL | New | New_Built | RTP | 7 | 14 | 40/130/290 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6568 | 77.3544 | 21283 | 2021-04-30 | 2021-06-29 | 2021-07-16 | 11109-2865-68773543 | 2021-08-03 | 2021-08-04 |  |  |  |  | 2021-08-01 | 2021-08-06 | 2021-08-09 | 2021-08-10 | 2021-08-10 | 2021-08-13 |  |  |  | 2021-06-30 | ST202106367454 | S20210012477 |  |  | 2021-07-14 | P/FVC/DEL/1035031/2021 | 2021-08-13 | 2021-08-14 | DL/04/0031/0237/0031/03/01/10102/NS/14082021 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-16 | 2021-08-14 | 2021-08-17 | 2021-08-14 | 2021-08-24 | 2021-08-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4142 | [5 empty] | 2021-08-06 | 2021-08-12 | Hold by WH 6th Aug to till 8 aug 21,Partially Installed_Neighbor issue & Link Pending on 11 Aug 21,Partially installed_2G Media Issue on 12 Aug 21,Issue closed on 12 Aug 21 | [9 empty] | 404-10-621283-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q1 | OZONE SECUTECH PRIVATE LIMITED | 1/122 WHS Kirti Nagar near Fire Station Delhi, 110015 | 27706 | 27706 | 27706 | 27706 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27706_DEL | New | New_Built | IBS | 0 | 38 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6392 | 77.1344 | 27706 | 2021-06-26 | 2021-07-06 | 2021-07-06 | 111-2863-92771344 | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-07-22 |  |  | 2021-07-13 | 2021-07-22 | 2021-07-24 | 2021-07-25 | 2021-07-25 | 2021-08-02 | [10 empty] | 2021-08-02 |  |  | 2021-08-02 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-16 | 2021-08-14 | 2021-08-18 | 2021-08-14 | 2021-08-19 | 2021-08-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9183 | [5 empty] | 2021-07-16 | 2021-08-13 | Survey Rejected; Mains not available, SMPS_BB required, Climbing ladder required, PARSWA PAD Required_Approval received for Material dispatch on 17th July 21,Access Available only on Weekend Only,Issue closed on 02.08.21,SGW Issue after Integration,Issue resolved on 13 Aug 21 | [9 empty] | 404-10-927706-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q1 | Sec-108, Noida(Relocation of 23135) | Noida sec 108 near by oyo 9341 mascot pentazz hotel noida U.P-201304 | 20893 | 20893 | 20893 | 20893 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1505433 | Relocation | New_Built | GBM | 30 | 0 | 20/140/270 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5281 | 77.3727 | R/NN-558847 | 2020-11-11 | 2020-11-24 | 2020-11-26 | 11109-2852-81773727 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-26 |  |  | 2021-08-09 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-28 | 2021-09-02 |  |  |  | 2020-11-30 | ST202011160634 | S20200008886 |  |  | 2020-12-23 | P/FVC/DEL/1013155/2020 | 2021-09-02 | 2021-09-04 | DL/03/5177/0903/0031/06/05/11970/NS/04092021 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-08 | 2021-09-04 | 2021-09-08 | 2021-09-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4015 | [5 empty] | 2021-08-20 | 2021-08-26 | CATS Issue | [9 empty] | 404-10-620893-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY20_21 | Q4 | Shahbad dairy | Mr. Vinod Kumar S/O Sh. Ramdin ,Juggi number A-2/449 & A-2/250, Landmark JJ Colony, Shahbad Dairy, Police Station - Prahladpur Shahbad Dairy, Post Office - Prahladpur Shahbad Dairy, New Delhi - 110042, | 21275 | 21275 | 21275 | 21275 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1548007 | New | New_Built | RTT | 12 | 10 | 60/130/210 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7448 | 77.091 | R/NN-560079 | 2020-12-03 | 2021-07-05 | 2021-07-14 | 111-2874-47770910 | 2021-08-10 | 2021-08-11 |  |  |  |  | 2021-08-09 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-13 | 2021-08-14 |  |  |  | 2021-07-19 | ST202107388713 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036214/2021 | 2021-08-17 | 2021-08-18 | DL/01/5177/6333/0031/03/01/10114/NS/18082021 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-08-20 | 2021-08-18 | 2021-08-24 | 2021-08-25 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1880 | [17 empty] | 404-10-621275-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Agar Nagar | House No. 3/90, Plot No 40, Khasra No.25/25, Agar Nagar, New Delhi 110081 | 21268 | 21268 | 21268 | 21268 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3059207 | New | New_Built | RTT | 12 | 12 | 30/130/260 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7059 | 77.0393 | R/NN-633364 | 2020-12-03 | 2020-12-14 | 2020-12-29 | 111-2870-59770393 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-11-02 |  |  | 2021-08-17 | 2021-11-03 | 2021-11-07 | 2021-11-08 | 2021-11-08 | 2021-11-10 |  |  |  | 2020-12-29 | ST202012187462 | S20200010276 |  |  | 2021-01-04 | P/FVC/DEL/1015249/2021 | 2021-11-27 | 2021-11-29 | DL/01/5177/6451/0031/03/01/10305/NS/29112021 | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2021-12-10 | 2021-11-29 | 2021-12-05 | 2021-11-29 | 2021-12-06 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4175 | [5 empty] | 2021-08-20 | 2021-11-25 | Survey Rejected ; 02M Height deviation found,Issue resolved on 2.11.21,Partial Installed_Farend Water loggin Issue as on 08.11.21,Issue closed on 18.11.21,Installed/Farend water logging not clear as on 18.11.21,Issue closed on 20.11.21,Installed_Farend Water loggin Issue,New Farend TND awaited as on 23.11.21,Issue closed on 25.11.21 | [9 empty] | 404-10-621268-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | JAGRITI VIHAR, SEC-23 | Mr.Yogesh Tyagi S/O Kalu Ram Tyagi,Plot No.45,Sector-23,Sanjay Nagar,Jagriti Vihar,Sec 23 Police Chowki,Ghaziabad,Uttar Pradesh-201002 | 21555 | 21555 | 21555 | 21555 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/8853 | New | New_Built | RTP | 6 | 16 | 30/110/190 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.6981 | 77.4538 | T21DL01663 | 2021-01-04 | 2021-05-31 | 2021-06-13 | 11109-2869-81774537 | 2021-08-10 | 2021-08-10 |  |  |  |  | 2021-08-09 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-12 | 2021-08-13 |  |  |  | 2021-06-16 | ST202106346578 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034037/2021 | 2021-08-14 | 2021-08-14 | DL/04/5126/0254/0031/03/01/10104/NS/14082021 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-16 | 2021-08-14 | 2021-08-17 | 2021-08-14 | 2021-08-23 | 2021-08-25 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 776 | [17 empty] | 404-10-621555-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | CRPF Camp, Bawana | Mr. Shiv Ram Yadav S/O Harpal Yadav,Khasra Number. 203,Chotpur Colony, Chhajarsi Colony,Post Office - Chhajarasi,Police Station - Bahlolpur, Noida, Uttar Pradesh 201307 | 21589 | 21589 | 21589 | 21589 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL65 | New | New_Built | RTP | 6 | 16 | 350/60/200 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6262 | 77.3963 | 21589 | 2021-05-13 | 2021-06-02 | 2021-06-14 | 11109-2862-59773964 | 2021-08-17 | 2021-08-18 |  |  |  |  | 2021-08-15 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-21 |  |  |  | 2021-06-16 | ST202106346580 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034040/2021 | 2021-08-23 | 2021-08-23 | DL/03/0031/0327/0031/345/04/08422/NS/23082021 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-24 | 2021-08-23 | 2021-08-25 | 2021-08-23 | 2021-09-23 | 2021-09-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8004 | [5 empty] | 2021-08-20 | 2021-08-21 | Partial Installed_Power Issue-EB not connected,Issue Closed on 21 Aug 21 | [9 empty] | 404-10-621589-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Vasant Kunj D Blk(Relocation of 5167) | MBTS Location MCD Park Near Plot No. D-10, Near UGR DJB office, Vasant Kunj, New Delhi-110070 | 19994 | 19994 | 19994 | 19994 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1376793 | Relocation | New_Built | Cow | 30 | 0 | 10/110/240 | COW |  |  | YES | >18HRS | NO | 28.5263 | 77.1391 | R/NN-391657 | 2020-01-29 | 2020-02-04 | 2020-02-13 | 111.2852.63771390.CWIP-CL | 2021-08-17 | 2021-08-17 |  |  |  |  | 2021-08-19 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-21 | 2021-08-25 |  |  |  | 2020-02-21 | 2020383373 | 2020383373 |  |  | 2020-05-29 | P/FVC/DEL/6069869/2020 | 2021-08-25 | 2021-08-25 | DL/01/5177/6335/0031/345/04/08430/NS/25082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-26 | 2021-08-25 | 2021-08-27 | 2021-08-25 | 2021-08-31 | 2021-08-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19048 | [5 empty] | 2021-08-23 | 2021-08-24 | Partially Installed_1 GSM Short Delivered_Media Issue closed on 24 Aug 21. | [9 empty] | 404-10-619994-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,FD RRUS12B3, L_2100 RRUS12B1, TD RRU RRU4412 available on parent site
Del | FY20_21 | Q4 | NOOR NAGAR ,SIHANI | Mr.Vishal Tyagi S/o Mr. Vinay Tyagi,H.No. 336,Noor Nagar,Sihani,Ghaziabad,Uttar Pradesh,201003 | 21421 | 21421 | 21421 | 21421 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_21421_Del | New | New_Built | RTP | 6 | 16 | 350/100/180/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6968 | 77.4186 | 21421 | 2021-05-13 | 2021-06-02 | 2021-06-14 | 11109-2869-67774185 | 2021-08-04 | 2021-08-05 |  |  |  |  | 2021-08-04 | 2021-08-06 | 2021-08-08 | 2021-08-09 | 2021-08-09 | 2021-08-11 |  |  |  | 2021-06-18 | ST202106351941 | S20210011840 |  |  | 2021-07-11 | P/FVC/DEL/1034186/2021 | 2021-08-11 | 2021-08-12 | DL/04/5417/0001/0031/03/01/10100/NS/12082021 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-13 | 2021-08-12 | 2021-08-18 | 2021-08-12 | 2021-08-18 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5521 | [5 empty] | 2021-08-09 | 2021-08-10 | Partially Installed_Infra Issue(Cable Tray) | [9 empty] | 404-10-621421-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Uttam Nagar | Mst Kamla Devi W/O Surender Singh,Plot No. A-1/292,Khasra No. 69/23,Village Hastsal, Uttam Nagar,New Delhi-110059 | 21179 | 21179 | 21179 | 21179 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1777020 | New | New_Built | RTP | 9 | 13 | 80/180/300 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.627 | 77.0576 | R/NN-566964 | 2021-02-24 | 2021-04-07 | 2021-04-15 | 111-2862-70770576 | 2021-08-03 | 2021-08-04 |  |  |  |  | 2021-08-01 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-06 | 2021-08-07 |  |  |  | 2021-04-17 | ST202104151765 | S20210007098 |  |  | 2021-06-09 | P/FVC/DEL/1028597/2021 | 2021-08-07 | 2021-08-09 | DL/01/5177/6325/0031/03/01/10092/NS/09082021 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-09 | 2021-08-10 | 2021-08-09 | 2021-08-16 | 2021-08-16 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 573 | [17 empty] | 404-10-621179-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Sec 16,Rohini | Mr. Satish Kumar Pahwa S/O Rattan Singh Pahwa, House - Janta Flat Number 157, Pocket Number - 6, Block-F, Sector-16 Rohini, Police Station - KN Katju Marg, Sector 16 Rohini , Post Office - Sector 16 Rohini, Delhi-110085 | 19532 | 19532 | 19532 | 19532 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001903 | New | New_Built | RTT | 9 | 10 | 10/90/160 | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.734 | 77.1227 | R/NN-403856 | 2020-03-06 | 2021-07-12 | 2021-07-15 | 111-2873-39771227 | 2021-08-03 | 2021-08-04 |  |  |  |  | 2021-08-05 | 2021-08-05 | 2021-08-05 | [6 empty] | 2021-07-19 | ST202107388717 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036211/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Partially Material Delivered(Shortage 1 Qty RRU,MW & BBU due to MCD Issue)_Closer timeline 17th Aug 21_Material Pick up on 21 Sep 21 | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 318 | [5 empty] | 2021-08-06 |  | Partially Material Delivered(Shortage 1 Qty RRU,MW & BBU due to MCD Issue) | [14 empty] | Partially Material Delivered(Shortage 1 Qty RRU,MW & BBU due to MCD Issue)_Closer timeline 17th Aug 21_Material Pick up on 21 Sep 21 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Laxmi Nagar(Relocation of 4574) | Mr. Arvind S/O P. L Guota,Property Bearing No. D-211-A,Khasra No. 38, Gali No. 10, Post office laxmi Nagar thana sahdra,Laxmi Nagar, Village Shakarpur Khas, Illaqa Shahdara, Delhi-110092 | 21700 | 21700 | 21700 | 21700 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1987982 | Relocation | New_Built | RTP | 9 | 16 | 80/210/280 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6316 | 77.2763 | R/NN-567511 | 2021-03-08 | 2021-07-14 | 2021-07-19 | 111-2863-15772763 | 2021-08-19 | 2021-08-20 |  |  |  |  | 2021-07-30 | 2021-08-20 | 2021-08-22 | 2021-08-23 | 2021-08-23 | 2021-08-25 |  |  |  | 2021-07-27 | ST202107398487 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036780/2021 | 2021-08-25 | 2021-08-25 | DL/01/5177/6336/0031/03/01/10124/NS/25082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-27 | 2021-08-25 | 2021-09-01 | 2021-08-25 | 2021-09-02 | 2021-09-10 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 193 | [17 empty] | 404-10-621700-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRUS 2219 B0A,FD RRU RRUS 2219 B3, L_2100 RRU RRUS2219B1, TD RRU 4412 available on parent site
Del | FY20_21 | Q1 | NANDGRAM ,GHAZIABAD | Mrs.Poonam Tyagi W/O Umesh Tyagi, Plot No.10,Khasra No.119,Adarsh Nagar,Nandgram,Ghaziabad,Uttar Pradesh-201003 | 21249 | 21249 | 21249 | 21249 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_21249_DEL | New | New_Built | RTT | 12 | 10 | 30/130/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6865 | 77.407 | 21249 | 2021-05-06 | 2021-06-02 | 2021-06-14 | 11109-2868-64774069 | 2021-08-02 | 2021-08-03 | 2021-08-03 | 2021-08-09 |  |  | 2021-07-28 | 2021-08-10 | 2021-08-10 | 2021-08-12 | 2021-08-12 | 2021-12-05 |  |  |  | 2021-06-18 | ST202106351957 | S20210011842 |  |  | 2021-07-22 | P/FVC/DEL/1036140/2021 | 2021-12-07 | 2021-12-07 | DL/04/5417/0002/0031/06/05/12682/NS/07122021 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-10 | 2021-12-07 | 2021-12-10 | 2021-12-07 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 290 | [5 empty] | 2021-08-03 | 2021-12-06 | Survey Rejected; Planned GSM height not available (3M AGL deviation)_approval received on 6th Aug 21,Site hols on 6th Aug due to Pole Mount required at farend,Issue resolved on 09th Aug 21,Public Issue & power Issue-BB Not Installed on 12 Aug 21,Public Issue & power Issue-BB Not Installed_Plan on Saturday & Sunday(14.08.21),Partially Installed_Work Stop By GDA on 13 Aug 21,Issce clearance received on 04.12.21,Mux Port Issue as on 05.12.21,Media Issue resolved on 06.12.21 | [9 empty] | 404-10-621249-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Yamaha Motor India Ltd | Mr. Lalit,Khata Number -11,Khet Number - 74,Rakba Number - 0.7936/Khet Number - 78,Rakba Number - 0.1328/Khet Number - 79,Rakba Number - 0.9187,UPSIDC Site A,Surajpur,Greater Noida,Police Station - Surajpur,Post Office - Surajpur,Dist - Gautam Budh Nagar,Uttar Pradesh-201306 | 19158 | 19158 | 19158 | 19158 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_19158_DEL | New | New_Built | GBM | 30 | 0 | 310/100/220 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5193 | 77.4727 | 19158 | 2021-05-21 | 2021-06-29 | 2021-06-29 | 11109-2851-96774762 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-16 |  |  | 2021-07-31 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-19 | 2021-08-21 |  |  |  | 2021-07-29 | ST202107401822 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037072/2021 | 2021-08-25 | 2021-08-25 | DL/03/5417/0001/0031/06/05/11918/NS/23082021 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-26 | 2021-08-25 | 2021-08-27 | 2021-08-25 | 2021-08-31 | 2021-09-03 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 368 | [5 empty] | 2021-08-10 | 2021-08-21 | Survey Rejected; Pole mounts required and Mains or DG not available,Partial Installed_Power Issue-SMPS,Issue Closed on 21 Aug 21 | [9 empty] | 404-10-619158-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Village-Kirari Suleman Naga | Mr.Bhisham Bhardwaj,Plot No.120,Khasra No.2/17(8-0),Ravi Nagar,Basai Road,Village&Tehsil-Kadipur,Drona Public School,Gurugram,Haryana-122001 | 21594 | 21594 | 21594 | 21594 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001118 | New | New_Built | GBM | 30 | 0 | 40/160/320 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4602 | 77.0045 | R/NN-620043 | 2021-06-09 | 2021-06-14 | 2021-06-23 | 11106-2846-02770045 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-09-16 |  |  | 2021-07-29 | 2021-09-17 | 2021-09-19 | 2021-09-20 | 2021-09-20 | 2021-09-21 |  |  |  | 2021-05-28 | ST202105304056 | S20210010398 |  |  | 2021-07-22 | P/FVC/DEL/1036083/2021 | 2021-09-21 | 2021-09-22 | DL/05/5177/5297/0031/03/01/10177/NS/22092021 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-23 | 2021-09-22 | 2021-09-26 | 2021-09-22 | 2021-09-26 | 2021-09-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4726 | [5 empty] | 2021-08-05 | 2021-09-16 | Survey Rejected; 54M Lat-Long Deviation found,Re-RFAI Approval received on 16 Sep 21 | [9 empty] | 404-10-621594-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q1 | 7th Avenue,H-Tower | Mr.Rahul Tyagi(AGM Facility),7th Avenue,H-Tower,Near - Shop No.2,High Street Market,7 th Avenue ,Gaur City-1,Noida,G B Nagar,Uttar Pradesh-201301 | 21731 | 21731 | 21731 | 21731 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21731_Del | New | New_Built | RTT | 12 | 10 | 30/90/200/290 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6081 | 77.4262 | 21731 | 2021-04-23 | 2021-06-14 | 2021-06-14 | 11109-2860-81774261 | 2021-08-03 | 2021-08-04 |  |  |  |  | 2021-08-04 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-06 | 2021-08-11 |  |  |  | 2021-06-16 | ST202106346585 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034047/2021 | 2021-08-14 | 2021-08-16 | DL/03/0031/0325/0031/03/01/10108/NS/16082021 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-18 | 2021-08-16 | 2021-08-24 | 2021-09-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11466 | [5 empty] | 2021-08-06 | 2021-08-13 | Installed_GSM Faulty on 06 Aug 21,Faulty GSM Delivered on 13 Aug 21 | [9 empty] | 404-10-621731-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q1 | Client Office Terminal 1 | Client Office, Near Terminal 1 IGIA airport, Delhi 110037 | 21714 | 21714 | 21714 | 21714 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3000902 | New | New_Built | IBS | 0 | 29 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5679 | 77.1211 | R/NN-620171 | 2021-06-10 | 2021-06-14 | 2021-06-26 | 111-2856-77771211 | 2021-08-26 | 2021-08-27 |  |  |  |  | 2021-08-23 | 2021-08-27 | 2021-08-29 | 2021-08-30 | 2021-08-30 | 2021-08-31 |  |  |  | 2021-06-16 | ST202106346587 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034043/2021 | 2021-08-31 |  |  | 2021-08-31 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-02 | 2021-09-01 | 2021-09-02 | 2021-09-01 | 2021-09-15 | 2021-09-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-08-30 | 2021-08-30 | Partially Installed_Media Issue resolved on 30 Aug 21 | [9 empty] | 404-10-921714-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219, TD RRU 4418
Del | FY21_22 | Q1 | Lalpur,Faridabad | Mr.Mangay Raam S/O Yajram,Khasra No.5,Village Mahawatpur Bhaskola,Police Station Bhupani,Post Office Greater Faridabad,Tehsil&District Faridabad,Haryana-121002 | 21745 | 21745 | 21745 | 21745 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001235 | New | New_Built | RTT | 30 | 0 | 60/120/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.433 | 77.4081 | R/NN-620476 | 2021-06-17 | 2021-07-15 | 2021-07-15 | 11106-2843-30774080 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-23 |  |  | 2021-08-17 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-26 | 2021-08-27 |  |  |  | 2021-07-27 | ST202107398491 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036777/2021 | 2021-09-02 | 2021-09-03 | DL/02/5177/5031/0031/03/01/10132/NS/03092021 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-04 | 2021-09-03 | 2021-09-04 | 2021-09-03 | 2021-09-08 | 2021-09-08 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 14181 | [5 empty] | 2021-08-20 | 2021-08-23 | TND awaited | [9 empty] | 404-10-621745-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q1 | Narela(Relocation of 23365) | Mr. Pradeep Kumar S/O Sh. Kanhya Lal, Plot number - 684,Delhi State Industrial and Infrastructure Development Corporation Ltd. (DSIIDC) Narela, Police Station - Narela ,Post Office - Narela,Narela,New Delhi-110040 | 21748 | 21748 | 21748 | 21748 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/TT/1566 | Relocation | New_Built | RTT | 15 | 14 | 0/110/240 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.8305 | 77.1027 | T21DL02389 | 2021-06-25 | 2021-06-29 | 2021-07-21 | 111-2883-04771027 | 2021-08-05 | 2021-08-05 |  |  |  |  | 2021-08-04 | 2021-08-06 | 2021-08-06 | 2021-08-07 | 2021-08-07 | 2021-08-09 |  |  |  | 2021-07-26 | ST202107397094 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036564/2021 | 2021-08-10 | 2021-08-11 | DL/01/5126/1531/0031/03/01/10098/NS/11082021 | 2021-08-11 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-16 | 2021-08-13 | 2021-08-16 | 2021-08-13 | 2021-08-16 | 2021-08-25 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 43 | [17 empty] | 404-10-621748-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,FD RRU 12B0,L_2100 RRU 12B1 TD RRU 4412
Del | FY20_21 | Q4 | CK Birla Hospital | Plot No 57/41, Road No. 41, near baba nattha singh vatika, West Punjabi Bagh, New Delhi | 27709 | 27709 | 27709 | 27709 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27709_DEL | New | New_Built | IBS | 0 | 25 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6674 | 77.1316 | 27709 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 111-2866-75771319 | 2021-08-02 | 2021-08-08 | 2021-08-02 | 2021-08-08 |  |  | 2021-07-23 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-12 | 2021-08-19 |  |  |  | 2021-10-11 | ST202110556903 | S20210031490 |  |  | 2021-10-27 | P/FVC/DEL/1044006/2021 | 2021-08-19 |  |  | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-20 | 2021-08-19 | 2021-08-24 | 2021-08-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5686 | [5 empty] | 2021-08-02 | 2021-08-18 | TND awaited,TND received on 08 Aug 21,MW Farend PRI resolved on 10 Aug 21,Partially Installed_Ping Ok DAS WIP(13 Aug to 18 Aug 21) | [9 empty] | 404-10-927709-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Sector-60, Gurgaon(Relocation of 18133) | Mr Sanjeev,Rect no 31 killa No 5 (1-8),EWS Skyon Apartment Sector-60 Gurugram,Police Station Badshahpur,Post office Badshahpur,Gurugram Haryana 122102 | 21738 | 21738 | 21738 | 21738 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Alice | AC_21738_Del | Relocation | New_Built | RTP | 6 | 31.4 | 150/210/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4016 | 77.0969 | 21738 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 11106-2840-15770968 | 2021-08-03 | 2021-08-04 |  |  |  |  | 2021-08-04 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-06 | 2021-08-07 |  |  |  | 2021-07-26 | ST202107397130 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036562/2021 | 2021-08-10 | 2021-08-10 | DL/05/0031/0539/0031/03/01/10096/NS/10082021 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-11 | 2021-08-12 | 2021-08-11 | 2021-08-16 | 2021-08-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11110 | [5 empty] | 2021-08-06 | 2021-08-09 | Consumable Request(16819431)_Consumable Delivered on 07th Aug 21 and LOS Issue reported on 7th Aug 21_TND revised on 7th Aug 21,RA received on 9th Aug 21 | [9 empty] | 404-10-621738-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on Parent site
Del | FY20_21 | Q4 | Lodhi Hotel 1 | Hotel lodhi Near JLN stadium lodhi road new delhi-110003 | 21778 | 21778 | 21778 | 21778 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/PR/7451 | New | New_Built | RTP | 6 | 27 | 60/180/280 | ATC_LITE_POLE_SITE |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.5914 | 77.2379 | T20DL03698 | 2020-10-01 | 2020-11-17 | 2020-11-18 | 111-2859-14772379 | 2021-08-10 | 2021-08-11 | 2021-08-11 | 2021-10-11 |  |  | 2021-07-30 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-13 | 2021-10-20 |  |  |  | 2020-12-07 | ST202012166272 | S20200009174 |  |  | 2020-12-31 | P/FVC/DEL/1015185/2020 | 2021-10-20 | 2021-10-21 | DL/01/5126/1358/0031/03/01/10238/NS/21102021 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-23 | 2021-10-21 | 2021-10-23 | 2021-10-21 | 2021-11-02 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4850 | [5 empty] | 2021-08-11 | 2021-10-19 | Team details shared with Sandeep,Access Confirmation Pending,Issue closed on 11 Oct 21,DCDB Connection Pending,MCB Req 32 4 nos as on 13 Oct 21,Partially Installed_Power Issue as on 14 Oct 21,Issue closed on 19.10.21,RET Disable on 21.10.21 | [9 empty] | 404-10-621778-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Najafgarh Metro Station | Najafgarh metro station,Najafgarh Extension, Delhi- 110043 | 27724 | 27724 | 27724 | 27724 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL/DEL/100 | New | New_Built | IBS | 0 | 24 | IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6125 | 76.9861 | 27724 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 111-2861-25769861 | 2021-08-13 | 2021-08-14 |  |  |  |  | 2021-08-12 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-09-06 | [10 empty] | 2021-09-06 |  |  | 2021-09-07 | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-15 | 2021-09-08 | 2021-09-15 | 2021-09-08 | 2021-09-15 | 2021-09-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10981 | [5 empty] | 2021-08-20 | 2021-09-03 | Partial Installed_Media planning issue & Permission required for GPS Cabling,Media Plan required,Issue Closed on 26 Aug 21,Installed_Combining Plan Changed on 27 Aug 21,Installed_Combining Plan Changed(FDD & L2100 RRU to be dispatch) Issue resolved on 3 sep 21 | [9 empty] | 404-10-627724-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | I Energizer | I energizer A 37 , Sec 60 Noida | 27731 | 27731 | 27731 | 27731 |  |  |  | G900_L1800 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27731_Del | New | New_Built | IBS | 0 | 32 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6045 | 77.3654 | 27731 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 11109.MNOI.1753999.CWIP-CL | 2021-08-13 | 2021-08-16 |  |  |  |  | 2021-08-15 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-19 | 2021-08-20 | [10 empty] | 2021-08-20 |  |  | 2021-08-20 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-24 | 2021-08-21 | 2021-08-24 | 2021-08-21 | 2021-10-05 | 2021-10-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-08-13 | 2021-08-16 | Access Issue(14 to 16 Aug 21) | [9 empty] | 404-10-627731-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(900+1800) | 2G RRU 2219
Del | FY20_21 | Q4 | Police Station, DLF PH-1(Relocation of 19641) | Ms. Avneet Kaur,House Number G-10/11,DLF Phase-1,Police Station - DLF Phase-1,Post Office - DLF Phase-1,Sector 26,Gurugram,Haryana 122002 | 21750 | 21750 | 21750 | 21750 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | FCM_TOWER | FC_21750_Del | New | New_Built | RTP | 6 | 14 | 130/200/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4756 | 77.1048 | 21750 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 11106-2847-55771048 | 2021-08-16 | 2021-08-16 |  |  |  |  | 2021-08-13 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 | 2021-08-16 |  |  |  | 2021-08-03 | ST202108406430 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037552/2021 | 2021-08-16 | 2021-08-17 | DL/05/5410/0016/0031/03/01/10110/NS/17082021 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-24 | 2021-08-17 | 2021-08-24 | 2021-09-02 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 18546 | [17 empty] | 404-10-621750-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4418 Available on Parent site
Del | FY20_21 | Q4 | Mukundpur 1 | Mr. Safi Alam S/O Sh. Mohd Irfan ,House Number - 217-A,Khasra number - 319/216, Block - B,Veer bazar road,Village Mukundpur,Post Office - Samaypur Badli,Police Station - Bhalswa Dairy, Mukundpur , Delhi - 110042, | 21741 | 21741 | 21741 | 21741 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II-21741-Del | New | New_Built | RTP | 9 | 10.6 | 10/140/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7376 | 77.1804 | 21741 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 111.2873.76771804.CWIP-CL | 2021-08-17 | 2021-08-18 | 2021-08-18 | 2021-08-27 |  |  | 2021-08-07 | 2021-08-27 | 2021-08-30 | 2021-08-31 | 2021-08-31 | 2021-09-03 |  |  |  | 2021-07-29 | ST202107401835 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037081/2021 | 2021-09-03 | 2021-09-04 | DL/01/0031/2811/0031/06/05/11974/NS/04092021 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-06 | 2021-09-04 | 2021-09-06 | 2021-09-04 | 2021-09-09 | 2021-09-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 933 | [5 empty] | 2021-08-20 | 2021-09-03 | Material return on 20.08.21,Issue closed on 27 Aug 21,Partially Installed/Link Pending_EB Connection Pending on 2 sep 21 and resolved on 3 sep 21 | [9 empty] | 404-10-621741-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Frankfinn Aviation Services Pvt. Ltd | Plot No- 21a, Sector 18, Near Genpact Building, Gurgaon 122015 | 27710 | 27710 | 27710 | 27710 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27710_DEL | New | New_Built | IBS | 0 | 16 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.487 | 77.0749 | 27710 | 2021-07-15 | 2021-07-19 | 2021-07-21 | 11106.2804.87770749.CWIP-CL | 2021-08-17 | 2021-08-18 |  |  |  |  | 2021-08-10 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2021-08-28 | [10 empty] | 2021-08-28 |  |  | 2021-08-28 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 2021-08-31 | 2021-09-07 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 138 | [5 empty] | 2021-08-20 | 2021-08-28 | BTS Pad Required,DAS Permission Issue resolved on 28 Aug 21 | [7 empty] | 404-10-627710-51 |  | 404-10-927710-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q4 | Village.Saran | Mrs Soniya W/O Mr.Sonu,Khasra Mustkil Number.62/14/4,14/5,Plat Number 193A,Village Saran Jawahar Colony ,Police Station Parvatiya colony,Post Office Saran,Tehsil Badkal ,Faridabad Haryana-121001 | 13764 | 13764 | 13764 | 13764 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3010014 | New | New_Built | RTT | 12 | 8 | 40/160/290 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.3642 | 77.2851 | R/NN-626504 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11106-2836-42772850 | 2021-08-26 | 2021-08-27 |  |  |  |  | 2021-08-25 | 2021-08-27 | 2021-08-29 | 2021-08-30 | 2021-08-30 | 2021-09-02 |  |  |  | 2021-07-19 | ST202107388723 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036215/2021 | 2021-09-02 | 2021-09-04 | DL/02/5177/5030/0031/03/01/10135/NS/04092021 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-06 | 2021-09-04 | 2021-09-06 | 2021-09-04 | 2021-09-09 | 2021-09-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 800 | [5 empty] | 2021-08-30 | 2021-08-31 | Partially Installed_MCB Required at Farend | [9 empty] | 404-10-613764-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Kailash Hospital_Noida | Kailash Healthcare Ltd. Plot No 1 A, NH-1, Sec-71, Noida, Uttar Pradesh- 201307 | 27720 | 27720 | 27720 | 27720 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | IBUSUP028 | New | New_Built | IBS | 0 | 19 | IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6001 | 77.3764 | 27720 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11109.2860.01773763.CWIP-CL | 2021-08-26 | 2021-08-27 |  |  |  |  | 2021-08-10 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-30 | 2021-08-31 | [10 empty] | 2021-08-31 |  |  | 2021-08-31 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-02 | 2021-09-01 | 2021-09-02 | 2021-09-01 | 2021-09-07 | 2021-09-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4508 | [17 empty] | 404-10-927720-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Vasant Kunj(Relocation of 23681) | Mr. HS Pannu,Farm House Number -29, Sundervan Farms, Church Road,Police Station - Vasant Kunj,Post-Vasant Kunj, New Delhi- 110070 | 21765 | 21765 | 21765 | 21765 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | L10013 | New | New_Built | GBM | 30 | 0 | 60/220/330 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5123 | 77.132 | 21765 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 111-2851-22771319 | 2021-08-27 | 2021-08-28 | 2021-08-28 | 2021-09-05 |  |  | 2021-08-22 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-08 | 2021-09-09 |  |  |  | 2021-08-03 | ST202108406431 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037554/2021 | 2021-09-14 | 2021-09-15 | DL/01/0031/2849/0031/06/05/12065/NS/15092021 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-23 | 2021-09-15 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4521 | [5 empty] | 2021-08-28 | 2021-09-14 | Material return on 31.08.21,issue reslved on 5 sep 21,Partially Installed_SMPS Not connected_Media Issue as on 8 Sep 21,Issue closed on 9 Sep 21,Installed_2G Media Issue reported on 10 sep 21 and closed on 14 Sep 21 | [9 empty] | 404-10-621765-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRUS 2219 B0A,FD RRU RRUS 2219 B3, L_2100 RRU RRUS12 B1, TD RRU 4412
Del | FY20_21 | Q4 | Village-Chotpur | Mr. Chaman Yadav S/o Virpal Yadav Vill Chotpur,Khata No. 00185,Khasra No. 505,Near AAs Tower( New Parivartan Mission school) Noida,Uttar Pradesh 201307 | 21226 | 21226 | 21226 | 21226 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3008970 | New | New_Built | GBM | 30 | 0 | 90/210/350 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6234 | 77.4079 | R/NN-626310 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11109-2862-33774079 | 2021-08-27 | 2021-08-28 |  |  |  |  | 2021-08-20 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-08-31 | 2021-09-03 |  |  |  | 2021-04-17 | ST202104151771 | S20210007098 |  |  | 2021-06-09 | P/FVC/DEL/1028601/2021 | 2021-09-07 | 2021-09-08 | DL/03/5177/0906/0031/345/04/08454/NS/08092021 | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-09 | 2021-09-08 | 2021-09-09 | 2021-09-08 | 2021-09-14 | 2021-09-14 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8004 | [7 empty] | Installed_HW Faulty on 3 Sep 21_Material reached on site 7th Sep 21 | [9 empty] | 404-10-621226-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Village Kadarpur,Behind CRPF Camp resident,Gurgaon(Relocation of 13708) | Mr Prem Prakash (Senior Guy CRFP),MBTS Location,Plot Number - 308,Open Park At CRPF Camp At Seavage Traetment Plant Ground,Near Pole Number 10A,Near Type 1/14 Block And DIG Bunglaw And Nursery,Village-Kadarpur,Police Station - Badshahpur,Post Office - Badshahpur,CRPF Camp,Gurgaon, Haryana 122101 | 21716 | 21716 | 21716 | 21716 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3013694 | New | New_Built | Cow | 30 | 0 | 30/250/330 | COW |  |  | YES | >18HRS | NO | 28.3845 | 77.1055 | R/NN-626795 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11106-2838-45771055 | 2021-08-27 | 2021-08-28 | 2021-08-28 | 2021-08-30 |  |  | 2021-08-28 | 2021-08-30 | 2021-09-01 | 2021-09-02 | 2021-09-02 | 2021-09-06 |  |  |  | 2021-08-04 | ST202108408429 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037396/2021 | 2021-09-06 | 2021-09-07 | DL/05/5177/5295/0031/06/05/12001/NS/07092021 | 2021-09-07 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-12 | 2021-09-09 | 2021-09-12 | 2021-09-09 | 2021-09-14 | 2021-09-14 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16291 | [5 empty] | 2021-08-28 | 2021-08-30 | Pole Mount required at Near & Far end | [9 empty] | 404-10-621716-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | VVIP RESIDENCY AREA RAJ NAGAR EXTN | Mr. Gaurav,Plot No-826,Tower-O,VVIP Addreses,Raj Nagar Extention,Police Station Sihani Chungi,Post Office Raj Nagar Extension,Ghaziabad,Uttar Pradesh-201017 | 21498 | 21498 | 21498 | 21498 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPL018 | New | New_Built | RTP | 6 | 49 | 0/150/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6994 | 77.4296 | 21498 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11109-2869-94774296 | 2021-09-01 | 2021-09-02 | 2021-09-02 | 2021-09-03 |  |  | 2021-09-01 | 2021-09-03 | 2021-09-05 | 2021-09-06 | 2021-09-06 | 2021-09-08 |  |  |  | 2021-07-13 | ST202107382774 | S20210013039 |  |  | 2021-07-17 | P/FVC/DEL/1035694/2021 | 2021-09-09 | 2021-09-10 | DL/04/5414/0002/0031/345/04/08457/NS/10092021 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-16 | 2021-09-10 | 2021-09-16 | 2021-09-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4764 | [5 empty] | 2021-09-02 | 2021-09-08 | Access Not avl at farend due to Owner Not avl,Partially Installed,Cable Tray Wrong Installed,Far End Pole Mount Required/Mcb Required as on 6 Sep 21,Nearend Closed on 8th Sep 21 but Farend Mount required | [9 empty] | 404-10-621498-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Sec-31,Noida(Relocation of 15335) | Behind Of Smart Bharat Mall,Sector-25A,Noida Road,Uttar Pradesh-201301 | 16862 | 16862 | 16862 | 16862 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1637447 | New | New_Built | GBM | 30 | 0 | 70/180/280 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5829 | 77.3438 | R/NN-562469 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11109-2858-28773438 | 2021-09-01 | 2021-09-02 |  |  |  |  | 2021-08-30 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-09-06 |  |  |  | 2021-02-18 | ST202102058260 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019527/2021 | 2021-09-07 | 2021-09-08 | DL/03/5177/0905/0031/03/01/10143/NS/08092021 | 2021-09-08 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-10 | 2021-09-09 | 2021-09-10 | 2021-09-09 | 2021-09-15 | 2021-09-15 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 180 | [17 empty] | 404-10-616862-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Ravi Nagar Gurgaon | Mr. Vipin Kumar S/O Sh. Shiv Charan Singh,House Number - 499/28,Jyoti Park, Sector 7 Guragon ,Post Office - Sadar Bazar,Police Station - New Colony, Gurgaon - 122001 | 13715 | 13715 | 13715 | 13715 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1371742 | New | New_Built | RTP | 9 | 13 | 0/90/210 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4626 | 77.0108 | R/RES-504665 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11106-2846-25770107 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-03 |  |  | 2021-08-31 | 2021-09-04 | 2021-09-06 | 2021-09-07 | 2021-09-07 | 2021-09-08 |  |  |  | 2016-10-22 | 2016672618 | 2016672618 |  |  | 2016-11-15 | P/FVC/DEL/3630911/2016 | 2021-09-10 | 2021-09-11 | DL/05/5177/5250/0031/03/01/10150/NS/11092021 | 2021-09-11 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-16 | 2021-09-13 | 2021-09-16 | 2021-09-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4726 | [5 empty] | 2021-09-01 | 2021-09-09 | MW Mount required at Farend issue closed on 3 sep 21,But Issue not closed team Planned for Join visit on 8 Sep 21,Installed_2G Media Issue & TDD RRU Faulty on 8th Sep 21_Media Issue resolved on 09 Sep 21 | [9 empty] | 404-10-613715-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | CRPF Jharoda Kalan | Mr. Sanjeev Vohra,Government land,GBM Location,CRPF Jharoda Kalan,Near Football Stadium,Post Office - CRPF Jharoda Kalan,Police Station - Baba Haridass Najafgarh,New Delhi-110072 | 21850 | 21850 | 21850 | 21850 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3019824 | New | New_Built | GBM | 30 | 0 | 330/130/220 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6396 | 76.9557 | R/NN-627412 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 111-2863-95769557 | 2021-09-01 | 2021-09-02 |  |  |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-09-07 |  |  |  | 2021-08-31 | ST202108499280 | S20210028828 |  |  | 2021-09-17 | P/FVC/DEL/1039774/2021 | 2021-09-20 | 2021-09-21 | DL/01/5177/6367/0031/06/05/12138/NS/21092021 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-24 | 2021-09-21 | 2021-09-24 | 2021-09-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 660 | [5 empty] | 2021-09-07 | 2021-09-20 | Partially Installed(MW Material Wrong Delivered) on 4 Sep 21,again Fiber Faulty on 6th Sep 21,Installed_2G Media & SACFA Issue on 7th Sep 21,SACFA received on 20 Sep 21 | [9 empty] | 404-10-621850-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Sector 1 Ballabhgarh | Mr. Sunil S/O Ompal,Khasra No. 191,192,193,in Front Of Pole Number.245,Atali, Baniawada, Sector 1, Ballabhgarh,Post Office - Ballabhgarh,Police Station - Ballabhgarh, Faridabad, Haryana 121004 | 21799 | 21799 | 21799 | 21799 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1635657 | New | New_Built | RTT | 9 | 15 | 340/150/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.339 | 77.3237 | R/RES-504985 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 11106-2833-90773236 | 2021-09-01 | 2021-09-01 |  |  |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-09-06 |  |  |  | 2021-08-21 | ST202108486036 | S20210028308 |  |  | 2021-09-05 | P/FVC/DEL/1039101/2021 | 2021-09-17 | 2021-09-18 | DL/02/5177/5026/0031/03/01/10164/NS/18092021 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-23 | 2021-09-18 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 764 | [5 empty] | 2021-09-07 | 2021-09-16 | Owner Issue,Issue closed on 16 Sep 21 | [9 empty] | 404-10-621799-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Block-C,Sec 3, Rohini | Mrs. Usha Chawla,House Number - C-11/34,Block-C,Sec 3,Rohini,police station - Rohini sector 3,Post office - Rohini sector 7, district north west delhi, new delhi-110085 | 21826 | 21826 | 21826 | 21826 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1008032 | New | New_Built | RTP | 6 | 14 | 50/230/310 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7034 | 77.1134 | R/RES-504989 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 111-2870-34771134 | 2021-09-01 | 2021-09-01 |  |  |  |  | 2021-09-01 | 2021-09-03 | 2021-09-05 | 2021-09-06 | 2021-09-06 | 2021-09-07 |  |  |  | 2021-08-31 | ST202108499259 | S20210028828 |  |  | 2021-09-17 | P/FVC/DEL/1039771/2021 | 2021-09-20 | 2021-09-21 | DL/01/5177/3076/0031/06/05/12126/NS/21092021 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-25 | 2021-09-21 | 2021-09-25 | 2021-09-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15214 | [5 empty] | 2021-09-01 | 2021-09-20 | HOLD DUE TO 0.3 & 0.6 23ghz ANTENNA ISUUE,Installed 2G Media & SACFA Pending on 7th Sep 21,SACFA received on 20 Sep 21 | [9 empty] | 404-10-621826-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Nabi Karim | T-490, 6494 Factory Road Nabi Karim New Delhi-110055 | 17366 | 17366 | 17366 | 17366 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | lotus | LO_17366_DEL | New | New_Built | RTP | 6 | 16 | 30/120/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6519 | 77.2157 | 17366 | 2021-07-21 | 2021-08-09 | 2021-08-17 | 111-2865-19772157 | 2021-09-01 | 2021-09-02 |  |  |  |  | 2021-08-31 | 2021-09-03 | 2021-09-05 | 2021-09-06 | 2021-09-06 | 2021-09-08 |  |  |  | 2021-02-23 | ST202102067363 | S20210003587 |  |  | 2021-04-28 | P/FVC/DEL/1022228/2021 | 2021-09-09 | 2021-09-10 | DL/01/9071/0059/0031/345/04/08458/NS/10092021 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2021-09-10 | 2021-09-16 | 2021-09-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9136 | [5 empty] | 2021-09-02 | 2021-09-09 | HOLD DUE TO 0.3 & 0.6 23ghz ANTENNA ISUUE,Installed_LOS Issue as on 8 Sep 21,Issue closed on 9 sep 21 | [9 empty] | 404-10-617366-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | CLASSIC RESIDENCY | Mr Tapan (Manager),Plot Number 1125/1-3,Tower A,K.W Shristhey,C Block ,Raj Nagar Extension,Police Station - Sihani Gate,Post Office - Chungi,Ghaziabad,Uttar Pradesh 201017 | 17887 | 17887 | 17887 | 17887 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_17887_DEL | New | New_Built | GBM | 30 | 0 | 0/90/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7029 | 77.4292 | 17887 | 2021-05-06 | 2021-06-29 | 2021-08-10 | 11109-2870-28774292 | 2021-10-27 | 2021-10-28 | 2021-10-28 | 2021-12-16 |  |  | 2021-10-25 | 2021-12-17 | 2021-12-19 | 2021-12-20 | 2021-12-20 | 2021-12-23 |  |  |  | 2021-08-16 | ST202108425945 | S20210018615 |  |  | 2021-09-02 | P/FVC/DEL/1038899/2021 | 2021-12-23 | 2021-12-24 | DL/04/5417/00003/0031/06/05/12863/NS/24122021 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2022-01-01 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 776 | [5 empty] | 2021-10-28 | 2021-12-23 | Survey Rejected; 62M lat-long deviation and planned AGL is less that actual AGL and Mains supply not available,Site Re released on 27.10.21,Survey Rejected; 03M height deviation and Climbing ladder and safety railing required at Mumty as on 28.10.21,Issue closed on 16.12.21 as discussed with Amit S and Manoj,Partial Installed_Ladder & BB req as on 20.12.21,Issue closed on 23.12.21 | [9 empty] | 404-10-617887-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Budh nagar Inderpuri(Relocation of 7704) | F-444/445, J J Colony, Inderpuri, Delhi-110012 | 21111 | 21111 | 21111 | 21111 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1436159 | Relocation | New_Built | RTP | 9 | 13.8 | 20/120/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6308 | 77.1446 | R/NN-469433 | 2020-10-02 | 2020-10-31 | 2020-11-09 | 111-2863-08771445 | 2021-09-09 | 2021-09-10 | 2021-09-10 | 2021-10-13 |  |  | 2021-09-07 | 2021-10-13 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-21 |  |  |  | 2020-11-12 | ST202011145363 | S20200008117 |  |  | 2020-12-25 | P/FVC/DEL/1013814/2020 | 2021-10-21 | 2021-10-22 | DL/01/5177/6361/0031/03/01/10243/NS/22102021 | 2021-10-22 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 165 | [5 empty] | 2021-09-10 | 2021-10-21 | Parent site MIMO Running,Pole mount required for MIMO,SR received on 17 Sep 21,Consumable request raised(70255)_18 Sep 21_Consumable Delivered on 20 Sep 21,Parent Site Owner Issue,Issue closed on 13 Oct 21,Partial Installed_Link Done-Power Plant Faulty as on 20 Oct 21,Issue closed on 21.10,21,Calibration alarm on MIMO | [9 empty] | 404-10-621111-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY20_21 | Q3 | Anand prabat,Indestrial Area(Relocation of 11232) | Mr.Mukesh Kumar,Plot No. 19A/1,Gali No.13,Anand Parvat Industrial Area,Near Alka Steel,New Delhi-110005 | 21237 | 21237 | 21237 | 21237 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1805625 | Relocation | New_Built | RTT | 12 | 13 | 30/140/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6658 | 77.1722 | R/NN-511878 | 2020-10-29 | 2021-05-20 | 2021-06-21 | 111-2866-58771721 | 2021-09-02 | 2021-09-03 |  |  |  |  | 2021-09-02 | 2021-09-04 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-10 |  |  |  | 2021-06-26 | ST202106362824 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034612/2021 | 2021-09-14 | 2021-09-15 | DL/01/5177/6353/0031/03/01/10155/NS/15092021 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-11-19 | 2021-09-15 | 2021-09-20 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 21 | [5 empty] | 2021-09-09 | 2021-09-10 | Installed_Link Done Owner & Power Issue,Installed_BBU Faulty 13 sep 21 | [9 empty] | 404-10-621237-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY20_21 | Q1 | Vrindavan Garden(Relocation of 1445) | Mohd.Mukin S/O Deen Mohammad,House Number 892,Khata/Khatauni No.02048 ,Vrindavan Garden,Police Station Shaheed Nagar,Post Office Chikambarpur,Sahibabad,Ghaziabad,Uttar Pradesh-201005 | 20794 | 20794 | 20794 | 20794 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1806556 | Relocation | New_Built | RTT | 12 | 10 | 10/130/210 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6818 | 77.3458 | R/NN-567839 | 2021-03-12 | 2021-06-28 | 2021-07-05 | 11109-2868-18773458 | 2021-09-02 | 2021-09-03 |  |  |  |  | 2021-08-28 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-07 |  |  |  | 2020-06-23 | ST202007018529 | S20200001310 |  |  | 2020-07-10 | P/FVC/DEL/1001716/2020 | 2021-10-08 | 2021-10-09 | DL/04/5177/0775/0031/03/01/10201/NS/09102021 | 2021-10-09 | 2021-10-09 | 2021-10-09 | 2021-10-09 | 2021-10-09 | 2021-10-15 | 2021-10-09 | 2021-10-15 | 2021-10-09 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 288 | [5 empty] | 2021-09-03 | 2021-10-06 | Parent Site Rent Issue_1445,Issue resloved on 6 Oct 21,Consumable Delivered on 09.09.21_Parent Site Owner Issue(Indus),Partial Installed-TDD TB releasing pending/Link pending as on 6th Oct 21 | [9 empty] | 404-10-620794-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219, TD RRU 4412 Available on Parent SIte, New RRU(FD+L_2100) RRU 2279 to be sent
Del | FY20_21 | Q1 | EMCD_61_Raghubarpura Gandhi Nagar | Mr. Amarjit Singh S/o Hunsraj Singh, House Number- X/437,Ramnagar Market,Gandhi Nagar,Police Station GandhiNagar,Post office Gandhi nagar,Delhi- 110031 | 16809 | 16809 | 16809 | 16809 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PR_16809_Del | New | New_Built | RTP | 16 | 9 | 0/120/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6621 | 77.2671 | R/NN-569806 | 2021-08-24 | 2021-09-02 | 2021-09-12 | 111-2866-20772670 | 2021-09-16 | 2021-09-17 |  |  |  |  | 2021-09-16 | 2021-09-18 | 2021-09-21 | 2021-09-22 | 2021-09-22 | 2021-09-23 |  |  |  | 2020-01-30 | 2020349081 | 2020349081 |  |  | 2020-04-28 | P/FVC/DEL/6011062/2020 | 2021-09-23 | 2021-09-24 | DL/01/0031/2879/0031/03/01/10185/NS/24092021 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-25 | 2021-09-24 | 2021-10-05 | 2021-09-24 | 2021-10-05 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 675 | [5 empty] | 2021-09-22 | 2021-09-23 | Partially Installed_Cable tray Confirmation Pending | [9 empty] | 404-10-616809-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | EMCD_64_Ram Nagar Krishna Nagar(Relocation of 1016) | Mrs. Sudha Bhati W/O Mr. Surender Singh,House number - 133,Ram Nagar,Ghandhi Nagar,Post Office - Krishna Nagar,Police Station - Krishna Nagar,Delhi - 110051 | 20894 | 20894 | 20894 | 20894 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3023442 | Relocation | New_Built | GBM | 30 | 0 | 340/100/230 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6557 | 77.2858 | R/NN-627531 | 2020-07-22 | 2020-09-07 | 2021-08-27 | 111-2865-51772853 | 2021-09-19 | 2021-09-19 | 2021-09-20 | 2021-10-09 |  |  | 2021-09-09 | 2021-10-09 | 2021-10-11 | 2021-10-12 | 2021-10-12 | 2021-10-23 |  |  |  | 2020-10-09 | ST202010102178 | S20200005874 |  |  | 2020-10-20 | P/FVC/DEL/1009265/2020 | 2021-10-23 | 2021-10-24 | DL/01/5177/6412/0031/03/01/10254/NS/24102021 | 2021-10-24 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 667 | [5 empty] | 2021-09-20 | 2021-10-21 | Consumable request raised(70302)_20 Sep 21,Consumable Delivered on 21 Sep 21_Owner Issue at Parent Site,Issue closed on 09 oct 21,Delivered by Indus Team as on 12 Oct 21,issue closed on 21.10.21,Partial Installed-MW Power Connector Theft as on 22.10.21,Sector Mismatch in L2100 with Parent Site | [9 empty] | 404-10-620894-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 14B3 TD RRU 4412 , L_2100 RRU 12B1 Available on Parenet Site
Del | FY20_21 | Q1 | N Block -Mangolpuri | Mr. Rajesh s/o Ram kishor,Property Bearing Number. P-8/154, JJ Colony,Police Station Raj Park Sultanpuri,Post Office Mangolpuri S Block,Mangolpuri Delhi-110083 | 20554 | 20554 | 20554 | 20554 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001798 | New | New_Built | RTP | 9 | 14.5 | 350/100/230 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6909 | 77.0871 | R/NN-621209 | 2021-06-30 | 2021-07-12 | 2021-07-14 | 111-2869-08770871 | 2021-09-23 | 2021-09-23 |  |  |  |  | 2021-09-13 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-01 |  |  |  | 2021-07-19 | ST202107388714 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036209/2021 | 2021-10-06 | 2021-10-07 | DL/01/5177/6383/0031/03/01/10196/NS/07102021 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-12 | 2021-10-07 | 2021-10-12 | 2021-10-07 | 2021-10-12 | 2021-11-20 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1155 | [7 empty] | HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21,BBU Faulty on 01 Oct 21 | [9 empty] | 404-10-620554-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q1 | Tigri Market | Shri Devendra Gupta S/o Shri Ram Niwas Gupta,House Number - A-220,Block A,Tigri Colony,Police Station - Sangam Vihar,Post Office - STS Tigri BSF Camp,Delhi-110080 | 19640 | 19640 | 19640 | 19640 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-1714 | EXISTING | Sharing | RTT | 12 | 13 | 350/200/270 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.5109 | 77.2377 | SR-DL000163 | 2021-01-11 | 2021-08-05 | 2021-08-08 | 111-2851-09772377 | 2021-09-21 | 2021-09-21 |  |  |  |  | 2021-09-20 | 2021-09-22 | 2021-09-22 | 2021-09-23 | 2021-09-23 | 2021-09-29 |  |  |  | 2021-08-17 | ST202108430905 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038096/2021 | 2021-09-29 | 2021-09-30 | DL/01/5370/2493/0031/03/01/10191/NS/30092021 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 2021-09-30 | 2021-10-06 | 2021-10-06 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4992 | [5 empty] | 2021-09-23 | 2021-09-24 | Partially Installed_Owner Issue,Issue closed on 24 Sep 21,Farend Radio Faulty | [9 empty] | 404-10-619640-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | EMCD_35_Madhuban | Mr. Ishan S/O B.K.Garg,House Number - C 184,Block C,Delhi Officers Co-Operative House Building Society Limited, Madhuban,Police Station - Preet Vihar,Post Office - Nirman Vihar, Delhi-110092 | 20871 | 20871 | 20871 | 20871 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3021757 | New | New_Built | GBM | 30 | 0 | 40/120/260 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.63 | 77.2875 | R/NN-627529 | 2020-07-20 | 2020-09-07 | 2020-09-11 | 111.2863.05772863.CWIP-CL | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-17 |  |  | 2021-09-06 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-21 | 2021-09-22 |  |  |  | 2020-09-23 | ST202009086450 | S20200004981 |  |  | 2020-10-01 | P/FVC/DEL/1007206/2020 | 2021-09-24 | 2021-09-25 | DL/01/5177/6371/0031/03/01/10187/NS/25092021 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-26 | 2021-09-25 | 2021-10-06 | 2021-09-25 | 2021-10-23 | 2021-10-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1023 | [5 empty] | 2021-09-11 | 2021-09-24 | Pole Mount required at Farend,Issue closed on parallel as Per Ashwani K_17.09.21,Installed_LOS Issue_New IP Plan Required due to Farend change(4425 to 1031) as on 22 Sep 21.Media Issue closed on 24.09.21 | [9 empty] | 404-10-620871-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | SAINIK ENCLAVE SEC.3 | H.No-12&13, Sanik enclave, Mohan garden, Uttam nagar, delhi, Pin-110059 | 20317 | 20317 | 20317 | 20317 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20317_DEL | New | New_Built | RTM | 12 | 10 | 30/100/280 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6362 | 77.0326 | 20317 | 2019-10-09 | 2021-04-25 | 2021-05-03 | 111-MDEL-2105173 | 2021-09-09 | 2021-09-10 |  |  |  |  | 2021-09-08 | 2021-09-10 | 2021-09-12 | 2021-09-13 | 2021-09-13 | 2021-09-15 |  |  |  | 2020-07-12 | ST202007023115 | S20200001647 |  |  | 2020-07-18 | P/FVC/DEL/1002346/2020 | 2021-09-16 | 2021-09-17 | DL/01/0031/2856/0031/345/04/08472/NS/17092021 | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-09-19 | 2021-09-17 | 2021-09-19 | 2021-09-17 | 2021-09-22 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 740 | [5 empty] | 2021-09-13 | 2021-09-14 | Fall arrester Hang Issue,Issue closed on 14 Sep 21,Installed_Freq required | [9 empty] | 404-10-620317-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | DDA_Vasant Kunj 5(Relocation of 23867) | Mr. Kapil Chauhan S/o Badri Lal Chauhan,Khasra Number 1330,Vill Malikpur,Near SDMC Primary School,Police Station Vasant Kunj Pocket 4,Sector C,Post Office Mahipalpur L Block,Rangpuri Pahadi,Delhi-110037 | 20649 | 20649 | 20649 | 20649 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL15 | Relocation | New_Built | GBM | 27 | 0 | 0/70/170 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5356 | 77.132 | 20649 | 2021-03-28 | 2021-07-06 | 2021-07-06 | 111-2853-56771319 | 2021-09-03 | 2021-09-04 | 2021-09-04 | 2021-10-13 |  |  | 2021-09-01 | 2021-10-14 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-11-02 |  |  |  | 2021-04-21 | ST202104161247 | S20210007316 |  |  | 2021-07-22 | P/FVC/DEL/1036292/2021 | 2021-11-02 | 2021-11-03 | DL/01/0031/2948/0031/03/01/10270/NS/03112021 | 2021-11-03 | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2021-12-09 | 2021-11-29 | 2021-12-06 | 2021-11-29 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4164 | [5 empty] | 2021-09-04 | 2021-10-30 | Mains Supply Not available at site,Alternate Farend Required,Revise TND awaited from Birender/New Far-end shared,revised TND received on 08th Oct 21,70760(Wrong Address) Locator Issue resolved on 13 Oct 21,Delivered under Toco custody_Public Issue(70982) as on 19,10,21,Public Issue_BB+SMPS Infra Work pending as on 28.10.21,Partially Installed_Farend Access Issue as on 29.10.21,Issue closed on 30.10.21,L2100 TB Material required,Partially Installed_Link Done_L2100 TB Material Under dispatch(71261) and Delivered on 02.11.21,RSSI High on FDD Sector | [9 empty] | 404-10-620649-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY20_21 | Q1 | ND_KaushalCinema | Mohd Idrish S/O Mohd Sikdhik ,House Number - C-62,63 Jahangirpuri,Post Office - Jahangirpuri,Police Station - Jahangirpuri,Delhi 110034 | 20141 | 20141 | 20141 | 20141 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1010805 | New | New_Built | RTT | 9 | 11 | 110/250/340 | INDUS_LITE+ | Indus_Lite+ | Sharing available | YES | >18HRS | NO | 28.728 | 77.173 | R/RES-504972 | 2021-08-18 | 2021-08-23 | 2021-09-10 | 111-2872-71771723 | 2021-09-24 | 2021-09-24 |  |  |  |  | 2021-09-26 | 2021-09-28 | 2021-09-30 | [6 empty] | 2019-12-20 | 2019452695 | 2019452695 |  |  | 2020-01-14 | P/FVC/DEL/5944656/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 01.10.21 | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 575 | [5 empty] | 2021-10-01 |  | HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21 | [14 empty] | Material return on 01.10.21 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Sector 105, Gurugram | Khata No. - 1612/2282 - 2303, Kewat No. - 65, Vishnu Garden Hadud Nagar, Gurgaon, Haryana 122001 | 19695 | 19695 | 19695 | 19695 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | TVI | ATHAZGN0805 | New | New_Built | RTT | 15 | 10.6 | 60 /180/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4963 | 77.0084 | 19695 | 2020-11-05 | 2021-01-28 | 2021-02-09 | 11106-2849-63770084 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-23 |  |  | 2021-09-05 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-25 | 2021-09-27 |  |  |  | 2021-02-05 | ST202102039761 | S20210002332 |  |  | 2021-02-28 | P/FVC/DEL/1018784/2021 | 2021-09-27 | 2021-09-28 | DL/05/5113/0111/0031/03/01/10190/NS/28092021 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 2021-09-28 |  | 2021-09-28 | 2021-10-03 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11757 | [5 empty] | 2021-09-16 | 2021-09-27 | Survey Rejected; Mains supply not availble,Issue Closed on 23 Sep 21,Partially Installed_Pole Mount Issue resolved on 27th Sep 21 | [9 empty] | 404-10-619695-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | BHIM SINGH COLONY, WAZIRABAD | Mrs. Kamla W/O Mr. Roshan Lal, House number - 826, Near Sayed Baba,Village Wazirabad, Police Station Wazirabad, Post Office - Wazirabad Village,Gurugram Haryana - 122001 | 19705 | 19705 | 19705 | 19705 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3013664 | New | New_Built | GBM | 30 | 0 | 0/120/250 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4306 | 77.0822 | R/NN-626782 | 2021-08-04 | 2021-08-05 | 2021-08-09 | 11106-2843-06770821 | 2021-09-09 | 2021-09-10 | 2021-09-10 | 2021-09-15 |  |  | 2021-08-30 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-17 | 2021-09-20 |  |  |  | 2021-07-19 | ST202107388725 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036219/2021 | 2021-09-20 | 2021-09-21 | DL/05/5177/5296/0031/345/04/08487/NS/21092021 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-25 | 2021-09-21 | 2021-09-25 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1689 | [5 empty] | 2021-09-10 | 2021-09-19 | Pole mount required at farend,Issue closed on 15 Sep 21,Partially Installed_Farend Mount Required on 18 Sep 21,Issue closed on 19 Sep 21 | [9 empty] | 404-10-619705-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Mohan Garden | Hno-57C, Sai Enclave, Gali no. 05, Mohan Garden, Uttam Nagar, New Delhi, Pin-110059 | 17664 | 17664 | 17664 | 17664 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_17664_DEL | New | New_Built | RTP | 9 | 13 | 350/80/190/280 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.641 | 77.0347 | 17664 | 2019-10-17 | 2020-02-11 | 2020-02-14 | 111-MDEL-2057350 | 2021-09-14 | 2021-09-14 |  |  |  |  | 2021-09-13 | 2021-09-15 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-20 |  |  |  | 2020-02-06 | 2020360479 | 2020360479 |  |  | 2020-03-04 | P/FVC/DEL/5984368/2020 | 2021-09-20 | 2021-09-21 | DL/01/0031/2867/0031/03/01/10173/NS/21092021 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-10-05 | 2021-09-21 | 2021-10-05 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4955 | [5 empty] | 2021-09-14 | 2021-09-18 | Locator Inactive,Infra Not ready after Material Delivery,issue cleared on 18 sep 21,Installed_2G & TDD RRU Faulty | [9 empty] | 404-10-617664-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | Sukkar Bazar Uttam Nagar | Mr. Omvir singh,House Number - RZ New - T -13, OmVihar,Uttam Nagar,Police Station - Uttam Nagar East,Post Office - Subhash Park ,Delhi-110059 | 20012 | 20012 | 20012 | 20012 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_20012_Del | EXISTING | Sharing | RTP | 9 | 14 | 0/130/250 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.6151 | 77.0522 | 20012 | 2021-01-11 | 2021-08-10 | 2021-08-10 | 111-2861-50770522 | 2021-09-15 | 2021-09-16 |  |  |  |  | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-18 | 2021-09-19 |  |  |  | 2021-08-16 | ST202108425944 | S20210018615 |  |  | 2021-09-02 | P/FVC/DEL/1038917/2021 | 2021-09-19 | 2021-09-20 | DL/01/5417/0003/0031/345/04/08484/NS/20092021 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-25 | 2021-09-20 | 2021-09-25 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5999 | [5 empty] | 2021-09-18 | 2021-09-19 | Partially Installed_Infra Pending(cable Tray) on 18 sep 21,Issue closed on 19 Sep 21 | [9 empty] | 404-10-620012-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | LSC, Kalkaji | Plot no - 207, Vikas Plaza, 2 Logistics Sector Skill Council(LSC), Delhi Development Authority(DDA) Commercial Shopping Complex, Guru RavIdas Marg, Kalkaji , New Delhi-110019 | 20087 | 20087 | 20087 | 20087 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1008100 | New | Sharing | RTT | 14 | 15 | 0/100/210 | SHARING |  | SHARING | YES | >18HRS | NO | 28.5399 | 77.2617 | R/RES-504973 | 2021-08-18 | 2021-08-24 | 2021-09-05 | 111-2853-98772616 | 2021-09-11 | 2021-09-12 |  |  |  |  | 2021-09-07 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-18 |  |  |  | 2021-05-10 | ST202105243403 | S20210009047 |  |  | 2021-07-08 | P/FVC/DEL/1033865/2021 | 2021-09-18 | 2021-09-20 | DL/01/5177/3888/0031/03/01/10166/NS/20092021 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-21 | 2021-09-20 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 688 | [5 empty] | 2021-09-12 | 2021-09-14 | Locator Pending | [9 empty] | 404-10-620087-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418/4412
Del | FY20_21 | Q3 | ESCORT COLONY, DADRI | Mr. Bintu Singh Bhati S/o Mr. Harsawroop Bhati,Jild Number - 6117,Main Railway Rd ,Escort Colony,Police Station Dadri,Post Office Dadri,Goutam Buddh Nagar,Uttar Pradesh,203207 | 20277 | 20277 | 20277 | 20277 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPL016 | New | New_Built | RTP | 9 | 14 | 60/180/280 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5448 | 77.5419 | 20277 | 2021-05-02 | 2021-07-20 | 2021-07-26 | 11109-2854-48775418 | 2021-09-09 | 2021-09-10 |  |  |  |  | 2021-08-30 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-18 |  |  |  | 2021-07-29 | ST202107401836 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037076/2021 | 2021-09-18 | 2021-09-20 | DL/03/5414/0002/0031/345/04/08485/NS/20092021 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-23 | 2021-09-20 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5160 | [5 empty] | 2021-09-10 | 2021-09-14 | Locator address mismatch with releasing address | [9 empty] | 404-10-620277-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q3 | Mukundpur | Plot No. 2, Khasra No. 251/276, Street No. 1,Radha Vihar,Mukundpur, Delhi-110042 | 21131 | 21131 | 21131 | 21131 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1436184 | New | New_Built | RTT | 12 | 11 | 0/90/180 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7405 | 77.1827 | R/NN-469634 | 2020-10-02 | 2020-11-26 | 2020-12-01 | 111-2874-04771826 | 2021-09-19 | 2021-09-19 |  |  |  |  | 2021-09-15 | 2021-09-20 | 2021-09-20 | 2021-09-21 | 2021-09-21 | 2021-09-23 |  |  |  | 2020-12-17 | ST202012176923 | S20200009775 |  |  | 2020-12-29 | P/FVC/DEL/1014969/2020 | 2021-09-24 | 2021-09-25 | DL/01/5177/6372/0031/03/01/10186/NS/25092021 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-26 | 2021-09-25 |  | 2021-09-25 | 2021-09-30 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4656 | [5 empty] | 2021-09-21 | 2021-09-24 | Partially Installed_Farend Owner Issue_New IP Plan Required due to Farend change & .6 Antenna to be delivered,Media Issue closed on 24.09.21 | [9 empty] | 404-10-621131-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Chatterpur Extension 1 | Shri Sanjay Kumar Nagpal S/O Late Shri Hardwari Lal Nagpal , Plot No.F 171-C,Khasra No.561/2,Near-Chattarpur Mandir 60 Futa Road,Chattarpur Extn.,New Delhi-110074 | 20460 | 20460 | 20460 | 20460 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-0182 | EXISTING | Sharing | GBT | 30 | 0 | 50/120/190 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.4957 | 77.1782 | SR-DL000132 | 2021-01-11 | 2021-02-09 | 2021-02-18 | 111-MDEL-2105459 | 2021-09-09 | 2021-09-10 |  |  |  |  | 2021-08-30 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-18 |  |  |  | 2021-02-10 | ST202102048375 | S20210002677 |  |  | 2021-03-05 | P/FVC/DEL/1019260/2021 | 2021-09-18 | 2021-09-20 | DL/01/5370/3309/0031/345/04/08480/NS/20092021 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-21 | 2021-09-20 | 2021-09-24 | 2021-09-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 899 | [5 empty] | 2021-09-10 | 2021-09-14 | Locator inactive | [9 empty] | 404-10-620460-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | VILL-BARWALA | Mr. Sanjay S/O Sh. Sube Singh, Infront of Electrical Pole Number - HT 516-3/14, Khasra number - 87/55, Near Gyan Ganga School , Village Barwala, Post Office - Barwala, Police Station - Shahabad Dairy, New Delhi - 110042 | 20318 | 20318 | 20318 | 20318 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3878 | EXISTING | Sharing | RTT | 12 | 10 | 340/130/270 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.7611 | 77.065 | SR-DL000161 | 2021-01-11 | 2021-08-05 | 2021-08-08 | 111-MDEL-2004784 | 2021-09-09 | 2021-09-10 |  |  |  |  | 2021-08-30 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-18 |  |  |  | 2021-08-17 | ST202108430904 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038095/2021 | 2021-09-21 | 2021-09-23 | DL/01/5370/3244/0031/03/01/10180/NS/23092021 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-24 | 2021-09-23 | 2021-09-25 | 2021-09-23 | 2021-09-25 | 2021-09-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 585 | [5 empty] | 2021-09-10 | 2021-09-21 | Locator inactive,3 MCB Required & Media Issue resolved on 17 Sep 21,Not resolved Installed_Media Issue on 18 Sep 21,Media resolved on 21 sep 21 | [9 empty] | 404-10-620318-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Panchsheel Green | Mr. Ajay Tyagi S/o Late Kishan Chand Tyagi,Khasra No. 360,Opp. Primary School,Gas agency Rd,Vill Roza Yakubpur,Police Station Bisrakh ,Post Office Dadri,Goutam Buddh Nagar,Uttar Pradesh,201009 | 13815 | 13815 | 13815 | 13815 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPLS0052 | New | New_Built | RTT | 12 | 10.7 | 10/180/280(VBW) | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6079 | 77.4612 | 13815 | 2021-07-01 | 2021-07-11 | 2021-07-12 | 11109-2860-79774611 | 2021-09-06 | 2021-09-07 | 2021-09-07 | 2021-10-22 |  |  | 2021-09-02 | 2021-10-23 | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-27 |  |  |  | 2021-07-13 | ST202107382799 | S20210013039 |  |  | 2021-07-17 | P/FVC/DEL/1035695/2021 | 2021-10-27 | 2021-10-28 | DL/03/5414/0003/0031/03/01/10264/NS/28102021 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8082 | [5 empty] | 2021-09-07 | 2021-10-22 | Survey Rejected; Mains supply not availble,Issue closed on 22.10.21 | [9 empty] | 404-10-613815-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | HIND VIHAR, PREM NAGAR-3 | Mr. Samatul Bishwash S/O Sh. Navo Bishwash,Plot Number - 68 (OLD),House number - A-3/147, (2),Hind Vihar,Prem Nagar - III,Kirari Suleman Nagar,Nagloi,Post Office - Prem Nagar - III,Police Station - Prem Nagar,Delhi - 110086 | 20347 | 20347 | 20347 | 20347 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9461 | EXISTING | Sharing | RTT | 9 | 10 | 30/160/260 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.6893 | 77.0387 | SR-DL000164 | 2021-07-11 | 2021-08-10 | 2021-08-16 | 111-2868-92770387 | 2021-09-15 | 2021-09-16 |  |  |  |  | 2021-09-16 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-18 | 2021-09-18 |  |  |  | 2021-08-18 | ST202108483263 | S20210028126 |  |  | 2021-09-01 | P/FVC/DEL/1038765/2021 | 2021-09-20 | 2021-09-21 | DL/01/5370/4248/0031/345/04/08488/NS/21092021 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-25 | 2021-09-21 | 2021-09-25 | 2021-09-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8175 | [5 empty] | 2021-09-18 | 2021-09-19 | Installed_Link Pending DCDB Req,Installed_Link pending(ETU card pending-20P) | [9 empty] | 404-10-620347-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Hari Nagar-2 | Mr Amar Singh S/o Sh Harkesh Meena ,House number - B-40,Gali number - 8,Hari nagar,Part 2, Jaitpur,South Delhi - 110044, | 19668 | 19668 | 19668 | 19668 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-185 | New | New_Built | RTP | 6 | 14 | 30/120/180 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5024 | 77.3174 | 19668 | 2021-07-25 | 2021-08-05 | 2021-08-08 | 111-2850-35773160 | 2021-09-09 | 2021-09-10 |  |  |  |  | 2021-09-08 | 2021-09-10 | 2021-09-13 | 2021-09-14 | 2021-09-14 | 2021-09-15 |  |  |  | 2021-06-04 | ST202106322611 | S20210010900 |  |  | 2021-06-27 | P/FVC/DEL/1032888/2021 | 2021-09-17 | 2021-09-18 | DL/01/0031/2861/0031/03/01/10163/NS/18092021 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-24 | 2021-09-18 | 2021-09-24 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 842 | [5 empty] | 2021-09-14 | 2021-09-17 | Partial installed-EB connection pending on 14sep21,Media Issue reported on 15th Sep 21,Media Issue resolved on 17 Sep 21 | [9 empty] | 404-10-619668-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Abhay Khand Indrapuram(Relocation of 5296) | Government Land,Ghaziabad Authority,Green Belt,MBTS Location,in Front of Electricity Pole No.18,Block E, Sector 2,Abhay Khand Indirapuram,Near Abhay Khand Krishna Colony Police Chowki,Post Office Old Seemapuri,Ghaziabad, Uttar Pradesh 201014 | 18599 | 18599 | 18599 | 18599 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | NIBAR CREATIONS | NBGC-18599 | Relocation | New_Built | Cow | 30 | 0 | 310/90/180 | COW |  | 3RD_PARTY | YES | >18HRS | NO | 28.6373 | 77.3431 | 18599 | 2021-04-18 | 2021-06-29 | 2021-06-29 | 11109-2863-73773431 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-10-04 |  |  | 2021-09-24 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-14 |  |  |  | 2021-06-30 | ST202106367462 | S20210012477 |  |  | 2021-07-14 | P/FVC/DEL/1035030/2021 | 2021-10-14 | 2021-10-16 | DL/04/9035/0004/0031/03/01/10218/NS/16102021 | 2021-10-16 | 2021-10-16 | 2021-10-16 | 2021-10-16 | 2021-10-16 | 2021-10-21 | 2021-10-16 | 2021-10-21 | 2021-10-16 | 2021-10-21 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10052 | [5 empty] | 2021-09-23 | 2021-10-14 | Survey Rejected; Pole mounts not installed,Issue closed on 4th Oct 21,HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP & 40 mtr optical Not In Stock,Partially Installed_Infra Pending(cable Tray,Power) & Work Stop by GDA as on 7th Oct 21,Partial Installed_Mains not available, cabe tray earthing pendin(Monday)/Link Done as on 08 Oct 21,Issue closed on 14 Oct 21 | [9 empty] | 404-10-618599-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Budena Village, Sector 86, Faridabad | Mr.Kalyan Singh S/O Late Shri Karan Singh,Plot Number-21,Khasra Number-215,Budena Village, Sector 86,Police Station - Sector 11 Faridabad,Post Office - Sector 15 Faridabad,Sector-86,Faridabad-121004 | 20999 | 20999 | 20999 | 20999 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3010066 | New | New_Built | GBM | 30 | 0 | 30/130/260 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.3998 | 77.3458 | R/NN-626517 | 2021-07-29 | 2021-08-12 | 2021-08-18 | 11106-2839-99773458 | 2021-09-24 | 2021-09-24 |  |  |  |  | 2021-09-22 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-01 |  |  |  | 2021-09-09 | ST202109513823 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040666/2021 | 2021-10-01 | 2021-10-04 | DL/02/5177/5039/0031/03/01/10193/NS/04102021 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-15 | 2021-10-04 | 2021-10-15 | 2021-10-04 | 2021-11-11 | 2021-11-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15195 | [7 empty] | HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21 | [9 empty] | 404-10-620999-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | BHAGYA VIHAR | Mr. Babu Lal Gupta S/O Sh. Churaman Singh, House number - B-320,Bhagya Vihar,Jain Colony, Near Kali Mandir,Post office - Prem Nagar - 3,Kirari Suleman Nagar,Police Station - Kirari Suleman Nagar, Delhi - 110081. | 20355 | 20355 | 20355 | 20355 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9526 | EXISTING | Sharing | RTT | 12 | 7 | 20/160/300 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.7064 | 77.0306 | SR-DL000170 | 2021-07-11 | 2021-08-10 | 2021-08-16 | 111-MDEL-2057347 | 2021-09-15 | 2021-09-16 | 2021-09-16 | 2021-09-17 |  |  | 2021-09-10 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-23 | 2021-09-24 |  |  |  | 2021-08-17 | ST202108430897 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038092/2021 | 2021-09-25 | 2021-09-27 | DL/01/5370/4012/0031/03/01/10188/NS/27092021 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-28 | 2021-09-27 | 2021-10-06 | 2021-09-27 | 2021-10-06 | 2021-10-06 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 585 | [5 empty] | 2021-09-16 | 2021-09-24 | Pole Mount required at Farend,Issue closed on parallel as Per Ashwani K_17.09.21,Locator Inactive Issue resolved on 21 Sep 21,Partially Installed_Link Done_Media Provisioning Issue,Media Issue closed on 24.09.21 | [9 empty] | 404-10-620355-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q1 | Sec-17,Faridabad | Mr. Rajiv Kumar Arora -Plot No. 1278 , Sec-16, Faridabad haryana-121002 | 16680 | 16680 | 16680 | 16680 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-FRBD-150 | Relocation | New_Built | RTT | 6 | 12 | 30/130/230/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4056 | 77.3225 | 16680 | 2020-02-04 | 2020-10-23 | 2020-10-23 | 11106-2840-55773226 | 2021-09-17 | 2021-09-18 |  |  |  |  | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-20 | 2021-09-22 |  |  |  | 2020-10-29 | ST202010125952 | S20200007048 |  |  | 2020-12-08 | P/FVC/DEL/1011454/2020 | 2021-09-22 | 2021-09-23 | DL/02/0031/0224/0031/03/01/10181/NS/23092021 | 2021-09-23 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-25 | 2021-09-24 | 2021-09-26 | 2021-09-24 | 2021-09-26 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 564 | [5 empty] | 2021-09-20 | 2021-09-21 | Partially Installed_Infra Pending | [9 empty] | 404-10-616680-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Sector 81 Faridabad | Government Land,Faridabad Authority,MBTS Location,In Front of Hno.01,Sector 81,Police Station Sector-14,Post OfficeSector 15,Faridabad, Haryana 121002 | 19672 | 19672 | 19672 | 19672 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | NIBAR CREATIONS | NI_19672_DEL | New | New_Built | Cow | 30 | 0 | 130/210/280 | COW |  | 3RD_PARTY | YES | >18HRS | NO | 28.3933 | 77.3474 | 19672 | 2021-05-18 | 2021-06-29 | 2021-06-29 | 11106-2839-32773474 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-10-20 |  |  | 2021-09-17 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-23 | 2021-10-26 |  |  |  | 2021-06-30 | ST202106367463 | S20210012477 |  |  | 2021-07-14 | P/FVC/DEL/1035026/2021 | 2021-10-26 | 2021-10-27 | DL/02/9035/0003/0031/03/01/10261/NS/27102021 | 2021-10-27 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15195 | [5 empty] | 2021-09-19 | 2021-10-26 | Survey Rejected; 63M Lat-Long deviation, Pole mounts not installed and Mains supply not available (DG Available),Issue closed on 20 Oct 21,Hold due to 2G RRU Not in Stock,Assembled-BB Power WIP/Infra WIP_Media Issue as on 23rd Oct 21,Issue closed on 24 Oct 21,Installed_MW Pole Mount Issue - On DG as on 25.10.21,Issue closed on 26 Oct 21 | [9 empty] | 404-10-619672-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | SDMC_LANE W-7A WESTERN AVENUE | Mr.Varun Singh,Plot No. W-15K/7,Old No.J-Block MID No.1541,Mustatil No.13 Killa No.14 Min,Western Avenue ,Village Devli,Delhi-110062 | 27036 | 27036 | 27036 | 27036 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3013676 | New | New_Built | GBM | 30 | 0 | 0/110/280 | COW |  |  | YES | >18HRS | NO | 28.5031 | 77.2207 | R/NN-626790 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 111-2850-31772206 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-20 |  |  | 2021-09-19 | 2021-09-21 | 2021-09-21 | 2021-09-22 | 2021-09-22 | 2021-09-23 |  |  |  | 2021-08-16 | ST202108425946 | S20210018615 |  |  | 2021-09-02 | P/FVC/DEL/1038900/2021 | 2021-09-23 | 2021-09-24 | DL/01/5177/6369/0031/03/01/10184/NS/24092021 | 2021-09-24 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-25 | 2021-09-26 | 2021-09-25 | 2021-10-08 | 2021-09-25 | 2021-10-08 | 2021-10-08 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 7777 | [5 empty] | 2021-09-19 | 2021-09-23 | Owner Issue at Farend,Partially Installed_Mains and DG Not avl_Farend Owner Issue at 7777,Farend change 712,Issue Closed on 23 Sep 21 | [9 empty] | 404-10-627036-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Casa Royale | Mr.Paras Deepa Bhati S/o Late jaideep bhati,Khasra No.617,Opposite Sanskriti Apartment,Vill Bisrakh,Police Station Bisrakh,Post Office Bisrakh,Greater Noida ,Uttar Pradesh,201306 | 16163 | 16163 | 16163 | 16163 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STSPL053 | New | New_Built | GBM | 30 | 0 | 330(VBW)/120/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5746 | 77.4366 | 16163 | 2021-06-21 | 2021-07-11 | 2021-07-12 | 11109-2857-46774366 | 2021-09-06 | 2021-09-07 |  |  |  |  | 2021-09-02 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-11 | 2021-09-14 |  |  |  | 2021-07-19 | ST202107388720 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036213/2021 | 2021-09-14 | 2021-09-15 | DL/03/5414/0001/0031/06/05/12067/NS/15092021 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-20 | 2021-09-15 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10867 | [5 empty] | 2021-09-07 | 2021-09-09 | Hold due to 10 port Vertical beam antenna stuck in reserved kitty | [9 empty] | 404-10-616163-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Bhalaswa Dairy | Mr. Ashok Bhati S/O Late Sh. Shiv Singh, House number F-17/2, Khasra Number - 740,(Rajeev Nagar),Street number - 10,Block - F,Swami Shardha Nand Colony,Village Bhalswa Jahangirpur,Post Office - Samaipur Badli,Police Station - Bhalswa Dairy,New Delhi - 110042, | 21298 | 21298 | 21298 | 21298 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762845 | New | New_Built | RTT | 12 | 10 | 0/90/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7461 | 77.1629 | R/NN-566654 | 2021-02-24 | 2021-08-01 | 2021-08-01 | 111-2874-60771629 | 2021-09-16 | 2021-09-17 | 2021-09-17 | 2021-10-07 |  |  | 2021-09-11 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-09 |  |  |  | 2021-08-16 | ST202108425947 | S20210018615 |  |  | 2021-09-02 | P/FVC/DEL/1038911/2021 | 2021-10-12 | 2021-10-13 | DL/01/5177/6393/0031/03/01/10213/NS/13102021 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-15 | 2021-10-14 | 2021-10-15 | 2021-10-14 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5621 | [5 empty] | 2021-09-17 | 2021-10-11 | Pole mount required at Farend,Revise TND req. or 23Ghz 0.6 Mw req,Partial Installed_Link done,2 TDD RRU Faulty_2G Media Issue resolved on 11 oct 21 | [9 empty] | 404-10-621298-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | HASTSAL | Smt Saroj Yadav W/O Shri Anil Kumar Yadav,Plot No. 324/4,Khasra No-107/1,Village Hastsal,Uttam Nagar,New Delhi-110059 | 21397 | 21397 | 21397 | 21397 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-4141 | EXISTING | Sharing | RTT | 9 | 16 | 320/70/220 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.6329 | 77.0549 | SR-DL000105 | 2021-01-11 | 2021-07-27 | 2021-07-30 | 111-2863-29770548 | 2021-09-15 | 2021-09-16 |  |  |  |  | 2021-09-14 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-18 | 2021-09-21 |  |  |  | 2021-07-30 | ST202107402572 | S20210013993 |  |  | 2021-08-04 | P/FVC/DEL/1037096/2021 | 2021-09-21 | 2021-09-22 | DL/01/5370/2556/0031/03/01/10179/NS/22092021 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-23 | 2021-09-22 | 2021-09-25 | 2021-09-22 | 2021-09-25 | 2021-09-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 740 | [5 empty] | 2021-09-20 | 2021-09-21 | Partial Installed_Media Issue | [9 empty] | 404-10-621397-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q4 | Sultanpuri | Mr.Pradeep Kumar Mittal S/O Mr.Mahavir Pradad Mittal, House No.328,Block-F-6,Sultanpuri,Near-Railway Crossing Sultanpuri,New Delhi-110041 | 21437 | 21437 | 21437 | 21437 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_21437_DEL | New | New_Built | RTT | 12 | 10 | 60/240/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.688 | 77.07 | 21437 | 2021-05-21 | 2021-06-02 | 2021-06-14 | 111-2868-79770699 | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-24 |  |  | 2021-09-11 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-06-16 | ST202106346591 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034049/2021 | 2021-10-01 | 2021-10-01 | DL/01/5417/0004/0031/03/01/10192/NS/01102021 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-15 | 2021-10-01 | 2021-10-15 | 2021-10-01 | 2021-11-11 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1154 | [5 empty] | 2021-09-23 | 2021-09-28 | MW Mount required at farend_1154 Issue resolved & Locator Issue,HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21,BB & SMPS Installation Pending on 29 Sep 21 & Installed RSL Issue on 30 Sep 21 | [9 empty] | 404-10-621437-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q3 | Nand Vatika Colony, Wave City, Ghaziabad | Mr.Rakesh Gupta S/O Raghuvar Dayal Gupta ,House Number B-98/1,Khasra No.27/22,B-Block,Gali No.7&4,25 Futa Road,Sushila Garden,Mandoli,Police Station Nand Nagri,Post Office Nand Nagri,Delhi-110093 | 21586 | 21586 | 21586 | 21586 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Nettel | NE_21586_DEL | New | New_Built | RTP | 9 | 14.7 | 0/120/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7049 | 77.3054 | 21586 | 2021-05-23 | 2021-06-02 | 2021-07-10 | 111-2870-48773053 | 2021-09-24 | 2021-09-25 | 2021-09-25 | 2021-09-28 |  |  | 2021-09-19 | 2021-09-29 | 2021-09-29 | 2021-09-30 | 2021-09-30 | 2021-10-01 |  |  |  | 2021-07-13 | ST202107382775 | S20210013039 |  |  | 2021-07-17 | P/FVC/DEL/1035693/2021 | 2021-10-12 | 2021-10-13 | DL/01/9037/0001/0031/03/01/10211/NS/13102021 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-11-10 | 2021-10-14 | 2021-11-29 | 2021-10-14 | 2021-10-19 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 277 | [5 empty] | 2021-09-25 | 2021-10-09 | Survey Rejected; Infra not ready and Mains supply not avl,Issue closed on 28 Sep 21,Partially Installed_BB Team required & BBU Short as on 30 Sep 21,Installed_Link Done BBU Short(70547)_Delivered & Media Issue as on 1 Oct 21,Media Issue resolved on 9th Oct 21,Installed_Link Done(2279 HW Faulty_70762) | [9 empty] | 404-10-621586-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | village kherki dhaula(Relocation of 17584) | Ms. Babli W/O Sh. Mahabir Singh,Khewat/Jamabandi No. 662 //587, Khatauni No. 697,Village Kherki Daula,Sikanderpur Road Near Shani Mandir, Police Station - Kherki Daula Post Office - Kherki Daula,Gurugram Haryana 122004 | 21699 | 21699 | 21699 | 21699 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3021736 | Relocation | New_Built | GBM | 30 | 19 | 80/210/280 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4052 | 76.9875 | R/NN-627523 | 2021-03-06 | 2021-03-09 | 2021-03-18 | 11106.2840.49769872.CWIP-CL | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-16 |  |  | 2021-09-01 | 2021-09-17 | 2021-09-19 | 2021-09-20 | 2021-09-20 | 2021-09-21 |  |  |  | 2021-03-18 | ST202103094627 | S20210004928 |  |  | 2021-08-04 | P/FVC/DEL/1036724/2021 | 2021-09-21 | 2021-09-22 | DL/05/5177/5298/0031/03/01/10178/NS/22092021 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-23 | 2021-09-22 | 2021-09-25 | 2021-09-22 | 2021-09-25 | 2021-10-25 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 200 | [5 empty] | 2021-09-11 | 2021-09-16 | Relocation Site Material dispatch hold | [9 empty] | 404-10-621699-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q1 | BE Block Hari Nagar(Relocation of 5957) | Mr. Parvinder,General Secretary Ramgaria,Ramgaria Sabha,H.No. BE-51,Khasra No. 2008, Hari Nagar, Clock Tower, Village Tihar,Mayapuri Police Station ,P.O Hari Nagar,New Delhi-110043 | 21707 | 21707 | 21707 | 21707 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3003264 | Relocation | New_Built | RTP | 9 | 15 | 0/80/200 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.628 | 77.1172 | R/NN-625589 | 2021-07-14 | 2021-07-28 | 2021-07-31 | 111-2862-79771171 | 2021-09-09 | 2021-09-10 | 2021-09-10 | 2021-09-13 |  |  | 2021-08-10 | 2021-09-13 | 2021-09-13 | 2021-09-14 | 2021-09-14 | 2021-09-17 |  |  |  | 2021-07-30 | ST202107402571 | S20210013993 |  |  | 2021-08-04 | P/FVC/DEL/1037100/2021 | 2021-09-17 | 2021-09-18 | DL/01/5177/6361/0031/03/01/10162/NS/18092021 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-19 | 2021-09-18 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 820 | [5 empty] | 2021-09-10 | 2021-09-16 | Near end Survey Rejected due to pole mounts required and Parent site already dismantled,Issue closed on 13 Sep 21,Partial installed/Farend access issue on 14 sep 21,Farend Access Issue,Issue closed on 16 Sep 21 | [9 empty] | 404-10-621707-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4418 Available on Parent site
Del | FY21_22 | Q1 | Microtek International | Microtek International H-57 Udhyog Nagar, Delhi | 27692 | 27692 | 27692 | 27692 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27692_DEL | New | New_Built | IBS | 0 | 20 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6826 | 77.093 | 27692 | 2021-03-31 | 2021-04-26 | 2021-04-26 | 111-2868-26770929 | 2021-09-08 | 2021-09-09 |  |  |  |  | 2021-09-07 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-11 | 2021-09-18 | [10 empty] | 2021-09-18 |  |  | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-19 | 2021-09-22 | 2021-09-19 | 2021-10-02 | 2021-10-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 839 | [5 empty] | 2021-09-13 | 2021-09-18 | MS Pad Req_POP Team req_Partially Installed,POP team arranged on 18 sep 21 | [9 empty] | 404-10-927692-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY21_22 | Q1 | Basant enclave(Relocation of 671) | Mr.Som Dutt S/O Sh.Madan Lal,House No.86,Khasra No.32/1/1,Old Lal Dora Of 1908-09,Basant Gaon Vasant Vihar,Near Basant Apartment,New Delhi-110057 | 21718 | 21718 | 21718 | 21718 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1927461 | Relocation | New_Built | RTT | 12 | 13 | 80/180/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5739 | 77.1578 | R/NN-617438 | 2021-04-13 | 2021-04-20 | 2021-04-26 | 111-2857-38771577 | 2021-09-02 | 2021-09-03 |  |  |  |  | 2021-08-20 | 2021-09-04 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-10 |  |  |  | 2021-04-27 | ST202104194455 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028798/2021 | 2021-09-18 | 2021-09-20 | DL/01/5177/6362/0031/03/01/10165/NS/20092021 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 |  | 2021-09-20 | 2021-09-25 | 2021-11-26 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 962 | [7 empty] | Installed_Link Done(AMM Faulty),Again AMM Faulty | [9 empty] | 404-10-621718-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY21_22 | Q1 | Sector- 1 Rohini(Relocation of 13141) | Mrs Geeta W/O Mr. Virender, & Mrs Kavita W/O Mr. Manoj,House Number - 358, Block - B, Sector 1 Rohini,Police Station - Vijay Vihar,Post office - Mangolpuri I Block ,Rohini - Delhi 110085 | 21735 | 21735 | 21735 | 21735 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3000369 | Relocation | New_Built | RTP | 6 | 16 | 50/110/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7011 | 77.0963 | R/NN-619596 | 2021-05-20 | 2021-07-17 | 2021-07-25 | 111-2870-11770963 | 2021-09-02 | 2021-09-03 |  |  |  |  | 2021-09-02 | 2021-09-04 | 2021-09-05 | 2021-09-07 | 2021-09-08 | 2021-09-15 |  |  |  | 2021-07-27 | ST202107398490 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036776/2021 | 2021-09-15 | 2021-09-16 | DL/01/5177/6356/0031/06/05/12081/NS/16092021 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-21 | 2021-09-16 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15234 | [5 empty] | 2021-09-07 | 2021-09-12 | RFS Done_CATS Issue,Consumable Delivered on 07.09.21_CAM Plan done on 14 Sep 21 | [9 empty] | 404-10-621735-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY21_22 | Q1 | DARCL Logistics Limited | Mr.Bhem Singh Yadav,DARCL Logistics Limited,Plot No.55P,Sector-44,Near-Hotel Taj Vivanta,Gurugram,Haryana-122003 | 27701 | 27701 | 27701 | 27701 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS+Macro | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27701_DEL | New | New_Built | RTP | 6 | 32 | 260/320/IBS | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.4527 | 77.0698 | 27701 | 2021-05-10 | 2021-07-19 | 2021-08-16 | 11106-2845-27770698 | 2021-09-06 | 2021-09-07 | 2021-09-07 | 2021-09-14 |  |  | 2021-08-27 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-17 | 2021-10-10 |  |  |  | 2021-05-28 | ST202105303943 | S20210010398 |  |  | 2021-07-22 | P/FVC/DEL/1036090/2021 | 2021-10-10 | 2021-10-11 | DL/05/0031/0558/0031/03/01/10206/NS/11102021 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-16 | 2021-10-11 | 2021-10-16 | 2021-10-11 | 2021-10-16 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5919 | [5 empty] | 2021-09-07 | 2021-10-10 | Farend Mount Required/SR Required,Issue closed on 14 Sep 21,Partially Installed_IBS Pending 1200 mtr,Access avl on Saturday & Sunday on 17 Sep 21,Issue closed on 24 Sep 21,again Issue open on 25th Sep 21,Plan on 09th Oct 21,Partially Installed_Access Issue on Floor Issue closed on 10th oct 21 | [9 empty] | 404-10-627701-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q1 | Fortis Hospital Noida | Fortis hospital,Block D, Industrial Area, Surajpur Site 4, Greater Noida, Uttar Pradesh 201310 | 27703 | 27703 | 27703 | 27703 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL-DEL-531 | New | New_Built | IBS | 0 | 33 | IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.449 | 77.5322 | 44333 | 2021-08-11 | 2021-08-16 | 2021-08-16 | 11109-2844-90775321 | 2021-09-21 | 2021-09-22 | 2021-09-22 | 2021-09-28 |  |  | 2021-09-11 | 2021-09-29 | 2021-09-29 | 2021-09-30 | 2021-09-30 | 2021-10-12 | [10 empty] | 2021-10-12 |  |  | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-11-11 | 2021-10-23 | 2021-11-19 | 2021-10-23 | 2021-10-28 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1540 | [5 empty] | 2021-09-22 | 2021-10-23 | LOS Blocked by Fancing wall,Issue closed on 28 Sep 21,Partially Installed_Infra Pending & BBU short as on 30 Sep 21,Partially Installed_Infra Pending & MCB required at Farend as on 6th Oct 21,Installed_VSWRas on 9th Oct 21,Issue closed on 11 oct 21,DAS Work Not Completed till 16th Oct 21,Issue resolved on 23rd Oct 21 | [9 empty] | 404-10-627703-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219, TD RRU 4418
Del | FY21_22 | Q1 | Gopinath Bardolai Marg Chankayapuri(Relocation of 92) | Government Land,New Delhi Municipal Committee(NDMC)Park,GBM Location,Near 27 Bihar Bhawan Kautilya Marg,Gopinath Bardolai Marg ,Diplomatic Enclave,Police Station Chanakyapuri,Post Office Chanakyapuri Malcha Marg, New Delhi-110011 | 21742 | 21742 | 21742 | 21742 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001433 | Relocation | New_Built | GBM | 30 | 0 | 10/150/250 | COW |  |  | YES | >18HRS | NO | 28.6009 | 77.1966 | R/NN-620475 | 2021-06-17 | 2021-06-23 | 2021-07-27 | 111-2860-08771966 | 2021-09-03 | 2021-09-03 |  |  |  |  | 2021-09-02 | 2021-09-04 | 2021-09-06 | 2021-09-07 | 2021-09-07 | 2021-09-08 |  |  |  | 2021-07-30 | ST202107402579 | S20210013993 |  |  | 2021-08-04 | P/FVC/DEL/1037094/2021 | 2021-09-10 | 2021-09-11 | DL/01/5177/6346/0031/345/04/08461/NS/11092021 | 2021-09-11 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-25 | 2021-09-22 | 2021-09-25 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10288 | [5 empty] | 2021-09-08 | 2021-09-21 | Installed_2G Media Issue as on 8 sep 21,Issue closed on 10 sep 21.Latency Issue 11 sep 21 to 21 Sep 21 | [9 empty] | 404-10-621742-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY21_22 | Q1 | Vill-Nawada(Relocation of 11446) | Mr. Raj singh Gahlot S/O Nafe Gahlot,House Number. 7-B,Khasra No. 485 and 486,Village Nawada,Rama Park, Block-C 2,Police Station Mohan Garden,Post Office Mohan Garden,New Delhi-110059 | 21744 | 21744 | 21744 | 21744 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3009412 | Relocation | New_Built | RTP | 6 | 16 | 0/190/260 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6239 | 77.0339 | R/NN-626322 | 2021-07-27 | 2021-07-30 | 2021-07-30 | 111-2862-39770339 | 2021-09-02 | 2021-09-03 |  |  |  |  | 2021-09-02 | 2021-09-04 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-16 |  |  |  | 2021-08-03 | ST202108406434 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037559/2021 | 2021-09-17 | 2021-09-18 | DL/01/5177/6357/0031/345/04/08473/NS/18092021 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2021-09-23 | 2021-09-18 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 642 | [5 empty] | 2021-09-08 | 2021-09-17 | RFS Pending due to Material Not showing in CATS as on 08 sep 21,Farend Material requested raised due to Owner Issue at farend 4484,CAM Material delivered on 13 Sep 21,(MW_70086),Farend Radio Faulty,Installed_TDD SACFA Pending,SACFA approval received without TDD | [9 empty] | 404-10-621744-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY21_22 | Q1 | Tilak Nagar Krishnapuri(Relocation of 1461) | Mr. shudarshan kumar S/o bhola singh mehta, Khasra Number. 1,Property Bearing No. WZ-13-A,Gali No. 16 and 17,Village Nangli Jalib tilak nagar Krishnapuri,police station -krishnapuri,post office - tilak Nagar,New Delhi-110018 | 21753 | 21753 | 21753 | 21753 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3002613 | Relocation | New_Built | RTP | 9 | 17 | 30/180/250 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6407 | 77.0836 | R/NN-625641 | 2021-07-08 | 2021-08-01 | 2021-08-09 | 111-2864-06770836 | 2021-09-02 | 2021-09-03 |  |  |  |  | 2021-09-04 | 2021-09-06 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 |  |  |  | 2021-08-16 | ST202108428695 | S20210018615 |  |  | 2021-09-02 | P/FVC/DEL/1038901/2021 | 2021-09-11 | 2021-09-14 | DL/01/5177/6351/0031/03/01/10152/NS/14092021 | 2021-09-14 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-16 | 2021-09-15 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 270 | [5 empty] | 2021-09-03 | 2021-09-06 | CATS Issue,Installed_Link Pending(RAU Faulty),AMM Faulty on 13 Sep 21 | [9 empty] | 404-10-621753-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, L_2100 RRU 12B1, TD RRU 4412 Available on Parent site
Del | FY21_22 | Q1 | RBM House | 38, Amrita Shergill Marg, New Delhi | 27715 | 27715 | 27715 | 27715 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27715_DEL | New | New_Built | IBS | 0 | 22 | IBS | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5978 | 77.2211 | 27715 | 2021-07-19 | 2021-07-19 | 2021-09-08 | 111-2859-77772210 | 2021-09-08 | 2021-09-09 |  |  |  |  | 2021-09-10 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-11 | [28 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Infra Not Ready | Airtel | PRI_With Material |  |  |  |  | M1 | [6 empty] | 2021-09-11 |  | Hold by Praveen Tokas | [14 empty] | Infra Not Ready | Airtel | 2G+TD | 2G RRU 2219,TD RRU 4418
Del | FY21_22 | Q2 | Zamrudpur GK(Relocation of 23977) | Government Land,South Delhi Municipal Corporation,MBTS Location,Near By House Number.27/D,Post Office - Greater Kailash,Police Station - Greater Kailash,Block J, Kailash Colony,Greater Kailash, New Delhi 110048 | 21771 | 21771 | 21771 | 21771 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1368576 | Relocation | Sharing | Cow | 30 | 0 | 20/150/220 | SHARING |  | SHARING | YES | >18HRS | NO | 28.5552 | 77.2384 | R/RES-504436 | 2021-08-05 | 2021-08-05 | 2021-08-17 | 111-2855-52772387 | 2021-09-24 | 2021-09-25 |  |  |  |  | 2021-09-20 | 2021-09-30 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-04 |  |  |  | 2021-08-17 | ST202108430896 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038090/2021 | 2021-10-06 | 2021-10-07 | DL/01/5177/5986/0031/03/01/10197/NS/07102021 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-23 | 2021-10-07 | 2021-10-23 | 2021-10-07 | 2021-11-11 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 631 | [5 empty] | 2021-09-25 | 2021-10-06 | HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,CAM Plan,Fresh Material approval received on 30 Sep 21,Media Issue reported on 4th Oct 21,Media Issue resolved on 6 Oct 21 | [9 empty] | 404-10-621771-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,FD RRUS12B3,L_2100 RRU RRUS12B1, TD RRU 4412 Available on Parent Site
Del | FY21_22 | Q2 | C Block, Rajiv Nagar,Bhalaswa Dairy | Mr.Bittoo S/O Mr.Basir Khan,House Number- C-273,Plot Number-6,Khasra Number-560,Village Bhalswa Jahangirpur, Rajiv Nagar Extension,Police Station - Bhalaswa Dairy,Post Office - Bhalaswa Dairy,Delhi-110042 | 21776 | 21776 | 21776 | 21776 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016666 | New | New_Built | RTT | 14 | 9 | 0/100/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7462 | 77.1659 | R/NN-627058 | 2020-08-07 | 2020-09-07 | 2020-09-11 | 111-2874-65771655 | 2021-09-19 | 2021-09-19 |  |  |  |  | 2021-09-16 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-21 | 2021-09-22 |  |  |  | 2021-09-02 | ST202109505866 | S20210029004 |  |  | 2021-09-19 | P/FVC/DEL/1040616/2021 | 2021-09-23 | 2021-09-24 | DL/01/5177/6368/0031/03/01/10183/NS/24092021 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2021-09-25 | 2021-09-24 |  | 2021-09-24 | 2021-09-29 | 2021-11-26 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5621 | [5 empty] | 2021-09-22 | 2021-09-23 | Installed_Link Done Media Issue,Issue Closed on 23 Sep 21 | [9 empty] | 404-10-621776-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q2 | STP PLANT DLF-5,Gurugram | Mr.Jai Bhagwan,Khewat/Khata No. 942/998, Khasra No. 303/2/3/60 0-0-12, Siwana Mouja Wazirabad,Sec 43,Near By Dlf apartment,Police Station - Sector 43 ,Post Office - Sector 45,Tehsil and District Gurgaon,Haryana 122003 | 21796 | 21796 | 21796 | 21796 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1355180 | EXISTING | Sharing | RTT | 13 | 9 | 20(VBW)/170/290 | SHARING |  | SHARING | YES | >18HRS | NO | 28.451 | 77.0932 | R/RES-504977 | 2021-08-18 | 2021-08-20 | 2021-09-05 | 11106-2845-11770932 | 2021-09-19 | 2021-09-19 |  |  |  |  | 2021-09-18 | 2021-09-20 | 2021-09-20 | 2021-09-21 | 2021-09-21 | 2021-10-13 |  |  |  | 2021-08-21 | ST202108486035 | S20210028308 |  |  | 2021-09-05 | P/FVC/DEL/1039100/2021 | 2021-10-14 | 2021-10-16 | DL/05/5177/5187/0031/03/01/10219/NS/16102021 | 2021-10-16 | 2021-10-16 | 2021-10-16 | 2021-10-16 | 2021-10-16 | 2021-10-23 | 2021-10-16 | 2021-10-23 | 2021-10-16 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5639 | [5 empty] | 2021-09-21 | 2021-10-14 | Owner Issue,Issue closed on 11 Oct 21,Installed-2G Media Issue,Issue closed on 14 Oct 21 | [9 empty] | 404-10-621796-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q2 | Krishna garden colony | Mr.Abhishek Upadhyay S/O Mr.Ram Mohan Upadhyaya,House Number-F-75,Block-F,Balaji Enclave,Govindpuram,Police Station - Govindpuram,Post Office - Govindpuram,Ghaziabad,Uttar Pradesh-201013 | 21841 | 21841 | 21841 | 21841 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1706170 | EXISTING | Sharing | RTP | 6 | 15 | 100/180/330 | SHARING |  | SHARING | YES | >18HRS | NO | 28.6928 | 77.4761 | R/RES-504991 | 2021-08-18 | 2021-08-21 | 2021-09-02 | 11109-2869-40774769 | 2021-09-06 | 2021-09-06 | 2021-09-06 | 2021-09-08 |  |  | 2021-09-04 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-11 | 2021-09-14 |  |  |  | 2021-08-21 | ST202108486034 | S20210028308 |  |  | 2021-09-05 | P/FVC/DEL/1039099/2021 | 2021-09-15 | 2021-09-16 | DL/04/5177/0772/0031/03/01/10158/NS/16092021 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-09-17 | 2021-09-16 | 2021-09-23 | 2021-09-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 18180 | [5 empty] | 2021-09-06 | 2021-09-08 | TND received on 8 sep 21,Partially Installed_BBU Short 13 Sep 21 | [9 empty] | 404-10-621841-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q2 | New, Jaffarpur Kalan | Mr. Suresh Yadav,Khasra Number 334, ITI Road Jaffarpur,Police Station - Jaffarpur,Post Office - Jaffarpur New Delhi 110073 | 21843 | 21843 | 21843 | 21843 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016759 | New | Sharing | GBM | 30 | 0 | 20/90/260 | SHARING |  | SHARING | YES | >18HRS | NO | 28.5948 | 76.9142 | R/NN-627099 | 2021-08-27 | 2021-08-30 | 2021-09-05 | 111-2859-33769134 | 2021-09-24 | 2021-09-24 |  |  |  |  | 2021-09-22 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-09-30 | 2021-10-01 |  |  |  | 2021-09-09 | ST202109513807 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040665/2021 | 2021-10-01 | 2021-10-04 | DL/01/5177/6376/0031/03/01/10194/NS/04102021 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-18 | 2021-10-04 | 2021-10-18 | 2021-10-04 | 2021-11-11 | 2021-11-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4485 | [7 empty] | HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21,Partially Installed_Mains Not avl as on 30 Sep 21 | [9 empty] | 404-10-621843-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY21_22 | Q2 | Paramount Golfforest(Relocation of 18430) | GOVERNMENT LAND-GBM LOCATION,NOIDA AUTHORITY,IN FRONT OF HOUSE NO. A.336,PARAMOUNT GOLFFORESTE,UPSIDC SITE C,GULISTANPUR,POLICE STATION - KASNA,POST OFFICE - GAMMA II | 21849 | 21849 | 21849 | 21849 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | NA | Relocation | New_Built | GBM | 30 | 0 | 190/270/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.517 | 77.5327 | 21849 | 2021-08-10 | 2021-08-14 | 2021-08-14 | 11109-2851-69775326 | 2021-09-06 | 2021-09-06 |  |  |  |  | 2021-09-03 | 2021-09-06 | 2021-09-06 | 2021-09-07 | 2021-09-07 | 2021-09-09 |  |  |  | 2021-08-17 | ST202108430892 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038098/2021 | 2021-09-10 | 2021-09-11 | DL/03/0031/0333/0031/03/01/10148/NS/11092021 | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-13 | 2021-09-11 | 2021-09-16 | 2021-09-16 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5033 | [17 empty] | 404-10-621849-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRUS 2219 B0A,FD RRU RRUS 2219 B3, TD RRU 4412, new L_2100 RRU 2219 to be send on site
Del | FY21_22 | Q2 | Atlas Shipping Services Private Limited | A – 25, Sector - 136, Noida 201 305.UP | 27719 | 27719 | 27719 | 27719 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27719_Del | New | New_Built | IBS | 0 | 32 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.505 | 77.4029 | 27719 | 2021-04-21 | 2021-06-28 | 2021-06-28 | 11109-2850-49774028 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2022-03-09 |  |  | 2021-07-02 | 2022-03-10 | 2022-03-13 | 2022-03-14 | 2022-03-14 | 2022-03-21 | [10 empty] | 2022-03-21 |  |  | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-26 | 2022-03-22 | 2022-03-29 | 2022-03-22 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 27292 | [5 empty] | 2021-06-30 | 2022-03-21 | Media_Pending,Issue closed on 20 Oct 21,Pole Mount required at Farend & Nearend Infra Issue as on 21 Oct 21,Issue closed on 28.10.21,MW Mount req at Farend as on 29.10.21,IBS/N-male connector 1/2",TDD Jumper{ (4.3.10) male N(m)} Comnet068 as on 09.03.22,74292_Locator Inactive Issue resloved on 11.03.22,Partial Installed/farend pole issue/nxt fared mcb req./DAS 800 mtr work access Sunday/media issue as on 14.03.22,DAS inst wip-27719 link between 27292 done and 27292 to 983 power issue DCDB Req.-port req as on 17.03.22 | [9 empty] | 404-10-627719-11 |  |  |  |  | KPI Accepted/Infra AT pending | MAPA_&_ON_AIR_(MS2)_PENDING | TD | TD RRU 4418
Del | FY21_22 | Q2 | Dhansa Metro Station | Dhansa Metro Station, Najafgarh Village, Najafgarh, Delhi, 110043 | 27725 | 27725 | 27725 | 27725 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL/DEL/101 | New | New_Built | IBS | 0 | 23 | IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6119 | 76.9776 | 27725 | 2021-08-05 | 2021-08-21 | 2021-09-02 | 111-2861-18769776 | 2021-09-06 | 2021-09-07 |  |  |  |  | 2021-08-12 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-10 | 2021-09-13 | [10 empty] | 2021-09-13 |  |  | 2021-09-13 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-09-20 | 2021-09-14 | 2021-09-23 | 2021-09-23 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [8 empty] | Hold due to Quadruplexer stuck in reserved kitty on 7 Sep 21,Partially Installed Jumper Short_10 Sep 21 | [9 empty] | 404-10-627725-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2219, TD RRU 4418
Del | FY21_22 | Q2 | BUSINESS EYE | 40 DLF 1ST FLOOR KIRTI NAGAR NEW DELHI New Delhi 110015 | 27728 | 27728 | 27728 | 27728 |  |  |  | G900 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27728 | New | New_Built | IBS | 0 | 12 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6557 | 77.1421 | 27728 | 2021-08-10 | 2021-08-24 | 2021-09-05 | 111-2865-57771421 | 2021-09-11 | 2021-09-12 |  |  |  |  | 2021-09-11 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-15 | 2021-09-19 | [10 empty] | 2021-09-19 |  |  | 2021-09-19 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-10-19 | 2021-09-20 | 2021-11-07 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 24 | [5 empty] | 2021-09-12 | 2021-09-19 | Locator,Infra Request late received,Infra Not ready_discussed Kushabh With Kushabh,Issue closed on 19 Sep 21 | [9 empty] | 404-10-627728-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G | 2G RRU 2219
Del | FY21_22 | Q2 | Godrej Summit Tower-3,Sector 104, Gurugram | Mr. Randhir Singh Dahiya S/O Sh. Pyare Lal Surat Khasara Number- 14/21/3,Khatoni Number- 5108,Near Godrej Summit Appartment,Sector-104 Police Station- Rajendra Park Post Office- Daultabad, Dhanwapur Gurugram Haryana 122006 | 21831 | 21831 | 21831 | 21831 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3017259 | New | New_Built | RTT | 30 | 0 | 70/150/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4834 | 76.9998 | R/NN-627138 | 2021-08-10 | 2021-09-10 | 2021-09-16 | 11106-2848-31769993 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-04 |  |  | 2021-09-29 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-07 |  |  |  | 2021-09-21 | ST202109526839 | S20210030073 |  |  | 2021-09-27 | P/FVC/DEL/1042148/2021 | 2021-10-08 | 2021-10-09 | DL/05/5177/5299/0031/03/01/10202/NS/09102021 | 2021-10-09 | 2021-10-09 | 2021-10-09 | 2021-10-09 | 2021-10-09 | 2021-10-15 | 2021-10-09 | 2021-10-15 | 2021-10-09 | 2021-11-11 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4779 | [5 empty] | 2021-09-29 | 2021-10-08 | 40 Mtr Full Axs Armoured Optical Cable between RRUS / AIR with Full Axs connector and MU,HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock,Installed_Media Issue reported on 7th Oct 21,Media Issue resolved on 8 Oct 21. | [9 empty] | 404-10-621831-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | SURAJ PUR G.B NAGAR | Mr.Deepak Bhati S/o Mr.Omveer, Khasra No.526,Village Devala,Police Station Surajpur,Post Office surajpur,Tehsil-Dadri, District-Gautam Budh Nagar,Greater Noida,Uttar Pradesh,201306 | 19921 | 19921 | 19921 | 19921 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | AM_19921_DEL | New | New_Built | GBM | 30 | 0 | 20/120/250 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.5199 | 77.5024 | T21DL01588 | 2021-05-13 | 2021-06-29 | 2021-07-21 | 11109-2851-99775024 | 2021-09-27 | 2021-09-29 | 2021-09-29 | 2021-10-07 |  |  | 2021-09-17 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-11 |  |  |  | 2021-07-26 | ST202107397095 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036563/2021 | 2021-10-11 | 2021-10-12 | DL/03/5126/0349/0031/03/01/10208/NS/12102021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16193 | [5 empty] | 2021-09-29 | 2021-10-11 | 40 Mtr Full Axs Armoured Optical Cable between RRUS /Approval req. for dispatch Dual Pol. Mw Antenna,Revise TND req. or 15Ghz 0.6 Mw req.,Partial Installed/Link Pending_MCB Required as on 09th Oct 21,Issue closed on 11 oct 21 | [9 empty] | 404-10-619921-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VIJAY NAGAR, GHAZIABAD | H No. 484 , Krishna Nagar, Baghu, Gali No 4 , Vijay Nagar , Ghaziabad , Uttar Pradesh 201009 | 21354 | 21354 | 21354 | 21354 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-GZBD-ENB-4097 | New | Sharing | RTT | 15 | 10.4 | 0/160/280 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.6397 | 77.4177 | SR-DL000102 | 2021-01-12 | 2021-06-17 | 2021-07-29 | 11109-2863-96774176 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-29 |  |  | 2021-09-23 | 2021-10-01 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-08 |  |  |  | 2021-07-30 | ST202107402573 | S20210013993 |  |  | 2021-08-04 | P/FVC/DEL/1037095/2021 | 2021-10-08 | 2021-10-09 | DL/04/5370/3943/0031/03/01/10203/NS/09102021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-11-11 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5227 | [5 empty] | 2021-09-27 | 2021-10-08 | Pole mount required at Farend,Issue closed on 29 Sep 21,40 Mtr Full Axs Armoured Optical Cable between RRUS / AIR with Full Axs connector and MU,HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock,Partially Installed_Far-end Material Delivered at nearend after discussion with ashwani k as on 8 Oct 21,BBU Faulty(1025110) | [9 empty] | 404-10-621354-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Sector 76 to 78, Noida (Relocation of 23851) | GBM Location,Noida Authiority,Near-NBCC (India) LTD. And Shop No.14 Amrapali Princely Estate,Sector-76 Noida,Noida , Uttar Pradesh-201306 | 17015 | 17015 | 17015 | 17015 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1845600 | Relocation | New_Built | Cow | 30 | 0 | 0/70(VBW)/120 | COW |  |  | YES | >18HRS | NO | 28.5663 | 77.38 | R/NN-568493 | 2021-03-17 | 2021-03-24 | 2021-04-05 | 11109-2856-63773799 | 2021-09-27 | 2021-09-28 | 2021-09-28 | 2021-10-07 |  |  | 2021-09-17 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-11 |  |  |  | 2021-04-08 | ST202104132853 | S20210006373 |  |  | 2021-06-08 | P/FVC/DEL/1028033/2021 | 2021-10-12 | 2021-10-13 | DL/03/5177/0910/0031/03/01/10212/NS/13102021 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5830 | [5 empty] | 2021-09-28 | 2021-10-12 | Pole mount required at Farend,TND req. in 15Ghz 0.3 or with 0.6 XPIC Antenna,Partially Installed_Farend Pole Mount Required as on 09th Oct 21,Installed_Site on DG and DG Falty as on 11 oct 21,Issue closed on 12 Oct 21 | [9 empty] | 404-10-617015-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | SILICON CITY | Noida Authority,GBM Location Green Belt,near Sector 50 Link Road,in front of Amarpali Silicon Citytower No. V-Block, Near by noida sector 76 metro,Noida U.P-201304 | 25051 | 25051 | 25051 | 25051 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1640092 | New | New_Built | GBM | 30 | 0 | 80(VBW)/170/340 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5688 | 77.3796 | R/NN-562564 | 2021-01-09 | 2021-02-14 | 2021-03-04 | 11109-2856-87773796 | 2021-09-27 | 2021-09-28 |  |  |  |  | 2021-09-27 | 2021-09-29 | 2021-09-29 | 2021-09-30 | 2021-09-30 | 2021-10-01 |  |  |  | 2021-03-05 | ST202103080630 | S20210004229 |  |  | 2021-03-11 | P/FVC/DEL/1019881/2021 | 2021-10-13 | 2021-10-14 | DL/03/5177/0912/0031/03/01/10215/NS/14102021 | 2021-10-14 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-11-10 | 2021-10-18 | 2021-11-10 | 2021-10-18 | 2021-11-10 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 18739 | [5 empty] | 2021-10-01 | 2021-10-18 | Partially Installed_BBU & MDU Connector short(Site on DG) as on 30 sep 21,MW Mount required & Owner Issue closed on 4 oct 21,Installed_MW Pending & BBU Short(1025030) as on 6 Oct 21,Installed_MW Pending & BBU Short(1025030)_Delivered on 7th Oct 21,Installed_TDD RRU faulty and LOS Issue as on 7th Oct 21,New TND received on 11 Oct 21,DG Fuel Issue on 14 & 16 Oct 21,resolved on 18 oct21 | [9 empty] | 404-10-625051-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Sangam vihar | Mr. Praveen Kumar Aggerwal S/O Sh. Mahesh Chand Aggerwal, House Number H-16/319,Khasra Numer - 1517,H-Block,Gali number -16,Sangam Vihar,Post Office - Sangam Vihar, Police Station - Sangam Vihar,New Delhi-110062 | 20289 | 20289 | 20289 | 20289 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9935 | New | Sharing | RTT | 12 | 7 | 0/150/280 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.5026 | 77.2523 | SR-DL000169 | 2021-07-18 | 2021-07-26 | 2021-08-03 | 111-2850-25772522 | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-10-06 |  |  | 2021-09-28 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-08 | 2021-10-08 |  |  |  | 2021-08-03 | ST202108406439 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037558/2021 | 2021-10-09 | 2021-10-11 | DL/01/5370/4209/0031/03/01/10204/NS/11102021 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-19 | 2021-10-11 | 2021-10-19 | 2021-10-11 | 2021-11-11 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4997 | [5 empty] | 2021-09-27 | 2021-10-06 | Pole mount required at Farend,Issue closed on 6th Oct 21 | [9 empty] | 404-10-620289-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q2 | Shiv Vihar, Kanjhawala Road, Karala | Mr. Ishan Vashisht S/O Sh. Satish Chandra Vashisht and Mr. Hunny Mathur S/O Sh. Ramesh Kumar Mathur, Plot number - D-2, Infrot front of House number - D-1, Khasra number - 86-87/8 & 13, Shiv Vihar Kanjhawala Road, Post office - Kanjhawala , Police Station - Kanjhawala, New Delhi-110081 | 21804 | 21804 | 21804 | 21804 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6642 | New | Sharing | RTT | 30 | 0 | 340/130/200 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.732 | 77.0285 | T21DL02835 | 2021-09-06 | 2021-09-13 | 2021-09-16 | 111-2873-24770279 | 2021-09-28 | 2021-09-29 |  |  |  |  | 2021-09-28 | 2021-09-30 | 2021-10-03 | 2021-10-04 | 2021-10-04 | 2021-10-06 |  |  |  | 2021-09-20 | ST202109525418 | S20210030004 |  |  | 2021-09-25 | P/FVC/DEL/1042075/2021 | 2021-10-06 | 2021-10-07 | DL/01/5126/0164/0031/03/01/10198/NS/07102021 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-10-19 | 2021-10-07 | 2021-10-19 | 2021-10-07 | 2021-11-11 | 2021-11-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 585 | [7 empty] | 40 Mtr Full Axs Armoured Optical Cable between RRUS / AIR with Full Axs connector and MU,Partially Installed_BBU Short(Roxtec Work parallel with ATC Team) | [9 empty] | 404-10-621804-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q2 | Mahipalpur Village(Relocation of 29) | Ms. Tarawati W/O Sh. Ram Kishan,House Number-669,Khata Khatauni Number - 119 Min,Village Mahipalpur,Bhaiya Chowk Desu Wali Gali Block-A,Near ICICI ATM,Police Station - Vasant Kunj North,Post Office - Mahipalpur,New Delhi-110037 | 21899 | 21899 | 21899 | 21899 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3030174 | Relocation | New_Built | RTT | 6 | 20.8 | 40/150/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5474 | 77.1289 | R/NN-628138 | 2021-08-28 | 2021-09-10 | 2021-09-16 | 111-2854-73771284 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-13 |  |  | 2021-09-23 | 2021-10-14 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-19 |  |  |  | 2021-09-20 | ST202109525420 | S20210030004 |  |  | 2021-09-25 | P/FVC/DEL/1042074/2021 | 2021-10-19 | 2021-10-20 | DL/01/5177/6403/0031/03/01/10231/NS/20102021 | 2021-10-20 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1413 | [5 empty] | 2021-09-29 | 2021-10-13 | Survey Rejected; Blockage at 40 degree and GSM movement issue at 270 degree,Issue closed on 4 Oct 21,Media Issue as on 09 Oct 21,Media Issue resolved on 11 oct 21,Issue resolved on 13 Oct 21,Main Unit Transfer Pending at WH End,TTB Running on Parent Site(71039) | [9 empty] | 404-10-621899-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 TD RRU 4412 , L_2100 RRU 12B1 Available on Parenet Site
Del | FY21_22 | Q2 | Pocket I, Nirvana Country, Gurgaon | Mr. Madan Singh,Khewat No. 65//63, Handbast No. 90, Village Adampur,Police Station - Huda Colony Sec 46 ,Post Office - Sec 49,Tehsil Wazirabad, District Gurgaon,Haryana-122018 | 21797 | 21797 | 21797 | 21797 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1371757 | New | Sharing | RTP | 6 | 17 | 0/80/220 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4195 | 77.0576 | R/RES-504983 | 2021-08-18 | 2021-08-20 | 2021-08-23 | 11106-2841-94770576 | 2021-09-27 | 2021-09-27 |  |  |  |  | 2021-09-28 | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-01 |  |  |  | 2021-08-31 | ST202108499257 | S20210028828 |  |  | 2021-09-17 | P/FVC/DEL/1039772/2021 | 2021-10-07 | 2021-10-08 | DL/05/5177/5241/0031/03/01/10200/NS/08102021 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-18 | 2021-10-08 | 2021-10-19 | 2021-10-08 | 2021-10-23 | 2021-10-25 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 971 | [7 empty] | HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 Sep 21,Installed_Link Done BBU Short,Installed_Link Done BBU Short(17216485)_Delivered on 7th Oct 21 | [9 empty] | 404-10-621797-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Mohan Cooperative Industrial Area(Relocation of 7186) | Government Land,South Delhi Municipal Corporation(SDMC),MBTS Location,In Front of House Number - 775,Near of Mohan Cooperative Industrial Area,Pocket A, Sarita Vihar,Police Station - Sarita Vihar,Post Office - Sarita Vihar,New Delhi-110044 | 20435 | 20435 | 20435 | 20435 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3060624 | Relocation | New_Built | GBM | 30 | 0 | 110/180/330 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5334 | 77.2866 | R/NN-633075 | 2021-08-03 | 2021-08-06 | 2021-08-23 | 111-2853-33772866 | 2021-10-27 | 2021-10-28 |  |  |  |  | 2021-10-26 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 |  |  |  | 2021-04-27 | ST202104194583 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028808/2021 | 2021-11-02 | 2021-11-03 | DL/01/5177/6416/0031/03/01/10269/NS/03112021 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-08 | 2021-11-03 | 2021-11-08 | 2021-11-03 | 2021-11-08 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 70 | [5 empty] | 2021-11-01 | 2021-11-02 | Survey rejected; 168M lat-long deviation found,Site Re released on 27.10.21,Installed SACFA Pending as on 1.11.21,issue resolved on 02.11.21 | [9 empty] | 404-10-620435-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY21_22 | Q2 | Village-Gaunchhi,Ballabgarh, Faridabad | Mr. Naresh Chandila, S/o Mr Lilu,House Number - 663,Khewat Number 1609/1468, Khatoni Number 2734, Musktil Number 75, Killa Number 16/1, Village - Gaunchhi,Post Office- Gaunchhi,Police station - Sanjay Colony,Tehsil- Ballabhgarh,Distict- Faridabad, Haryana 121004 | 21884 | 21884 | 21884 | 21884 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032271 | New | New_Built | RTT | 30 | 0 | 130/220/310 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.3406 | 77.282 | R/NN-628345 | 2021-09-03 | 2021-09-10 | 2021-09-16 | 11106-2834-07772820 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-07 |  |  | 2021-09-23 | 2021-10-07 | 2021-10-10 | 2021-10-11 | 2021-10-11 | 2021-10-13 |  |  |  | 2021-09-21 | ST202109526840 | S20210030073 |  |  | 2021-09-27 | P/FVC/DEL/1042147/2021 | 2021-10-13 | 2021-10-14 | DL/04/5177/0777/0031/03/01/10216/NS/14102021 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 130 | [5 empty] | 2021-09-29 | 2021-10-13 | Revise TND req. or 15Ghz 0.6 Mw req.,Partially Installed_Link Pending Media Issue,Issue resolved on 13 Oct 21 | [9 empty] | 404-10-621884-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Barwala | Mr. Sachin S/O Sh. Raj Pal, House Number - 138, Near Chaupal, & Punjab National Bank, Barwala, Police Station - Shahbad Dairy, Post Office - Barwala, Delhi-110039, | 21175 | 21175 | 21175 | 21175 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3060626 | New | New_Built | RTT | 9 | 10 | 50/180/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7615 | 77.0614 | R/NN-633337 | 2021-06-30 | 2021-07-05 | 2021-07-14 | 111-2876-16770620 | 2021-09-27 | 2021-09-28 | 2021-09-28 | 2021-10-22 |  |  | 2021-09-25 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-25 | 2021-10-26 |  |  |  | 2021-07-19 | ST202107388718 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036210/2021 | 2021-10-27 | 2021-10-28 | DL/01/5177/6414/0031/03/01/10262/NS/28102021 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4548 | [5 empty] | 2021-09-28 | 2021-10-27 | Survey rejected; 77M lat-long deviation found,Issue resloved on 22.10.21,Installed SACFA Pending as on 26.10.21Issue closed on 27.10.21 | [9 empty] | 404-10-621175-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q1 | Charms castle project, Raj Nagar Extension | Mr.Tarun Bhalla(Estate Manager),Charms Castle Project,Tower-D,Behind Of Quantum Residency,Plot No.1056,Raj Nagar Extention,Police Station Sihani Chungi ,Post Office Raj Nagar Extension,Ghaziabad,Uttar Pradesh-201003 | 13216 | 13216 | 13216 | 13216 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3008966 | New | New_Built | RTP | 7 | 70 | 0(at 6mtr)/180/280 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7004 | 77.4243 | R/NN-626306 | 2021-07-26 | 2021-07-30 | 2021-07-30 | 11109-2870-04774242 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-07 |  |  | 2021-09-23 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-14 |  |  |  | 2021-08-03 | ST202108406433 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037561/2021 | 2021-10-18 | 2021-10-19 | DL/04/5177/0779/0031/03/01/10230/NS/19102021 | 2021-10-19 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4087 | [5 empty] | 2021-09-29 | 2021-10-16 | Pole Mount req at Farend,Approval req. for dispatch Dual Pol. Mw Antenna,Revise TND req. or 15Ghz 0.6 Mw req.,Mount required as on 9th Oct 21,Mount Issue resolved on 12 Oct 21,Installed_Link Done Power Issue/Module req as on 14 Oct 21,Power Issue resolved on 16 Oct 21 & BBU Faulty,High RSSI in TDD,High RSSI in TDD,TDD RRU Down on 19 sep 21,issue resolved on 21.10.21 | [9 empty] | 404-10-613216-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Hyundai Motors | Plot No-C-11,Sector 29, Gurugram, Haryana 122022 | 27743 | 27743 | 27743 | 27743 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | SIS | HRHM452021 | New | New_Built | IBS | 0 | 20 | IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4696 | 77.0613 | NA | 2021-09-12 | 2021-09-17 | 2021-09-21 | 11106-2846-95770612 | 2021-09-28 | 2021-09-29 |  |  |  |  | 2021-09-29 | 2021-09-29 | 2021-10-03 | 2021-10-04 | 2021-10-04 | 2021-10-06 | [10 empty] | 2021-10-09 |  |  | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-11-11 | 2021-10-11 | 2021-11-30 | 2021-10-11 | 2021-10-16 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4627 | [5 empty] | 2021-10-05 | 2021-10-09 | Partially Installed_BBU Short,Partially Installed Link Done_BBU Short(17216492) as on 5 Oct 21,Media Issue resolved on 9th Oct 21 | [9 empty] | 404-10-627743-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q2 | Village Baraula(Relocation of 7794) | Rajwanti W/o Ramkesh Choudhary,H.No. B1 Khasra No. 225/1214 ,Hanumam Vihar ,Vill Baroula , Sec 49 , Noida, 201304 | 21675 | 21675 | 21675 | 21675 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001972 | New | New_Built | RTT | 12 | 16.5 | 0/210/310 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5589 | 77.3794 | R/NN-625344 | 2021-07-05 | 2021-07-14 | 2021-07-15 | 11109-2855-89773793 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-10-06 |  |  | 2021-09-20 | 2021-10-09 | 2021-10-11 | 2021-10-12 | 2021-10-12 | 2021-10-13 |  |  |  | 2021-04-08 | ST202104132854 | S20210006373 |  |  | 2021-06-08 | P/FVC/DEL/1028035/2021 | 2021-10-13 | 2021-10-14 | DL/03/5177/0911/0031/03/01/10217/NS/14102021 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11151 | [5 empty] | 2021-09-30 | 2021-10-13 | Survey Done_CAM Planned and Consumable Material requested,Survey Done_CAM Planned and Consumable Material requested(1025033) & Delivered on 6th Oct 21,Partially Installed_Link Done Media Issue,Issue resolved on 13 Oct 21 | [9 empty] | 404-10-621675-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219B0A ,FD RRU 2219B3, TD RRU 4412 Available on Parent site New L-2100 RRU 2219 to be send
Del | FY20_21 | Q2 | Sector-39 FBD(Relocation of 17135) | Mr. Ompal S/O Babu Ram,House Number .2/2,Near bharat petrol pump,Police Station Suraj Kund,Post office Suraj Kund,Tehsil badkal,Faridabad Haryana-121009 | 17270 | 17270 | 17270 | 17270 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3008969 | New | New_Built | GBM | 30 | 0 | 10/170/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4834 | 77.2904 | R/NN-626307 | 2021-07-25 | 2021-07-28 | 2021-07-29 | 11106-2848-33772904 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-13 |  |  | 2021-09-25 | 2021-10-16 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-21 |  |  |  | 2021-07-19 | ST202107388724 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036222/2021 | 2021-10-22 | 2021-10-23 | DL/02/5177/5042/0031/03/01/10247/NS/23102021 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5352 | [5 empty] | 2021-10-01 | 2021-10-22 | Nearend Survey Done_Parent Site Access Issue,Issue closed on 13 Oct 21,HOLD DUE TO 10 port Vertical beam antenna not in stock,Partial Installed_MW pending & Media Issue as on 20 oct 21,Issue resolved on 22.10.21 | [9 empty] | 404-10-617270-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4412
Del | FY20_21 | Q2 | Greater Noida(Relocation of 5618) | Plot Number H 163,SKG Food Industries,Site V,Near By PAP Automotive Industry,Village Kasna,Police Station - Kasna,Post Office - Kasna,Greater Noida,Uttar Pradesh-201310 | 21242 | 21242 | 21242 | 21242 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1987983 | New | New_Built | GBM | 30 | 0 | 50/180/290 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4309 | 77.5465 | R/NN-568967 | 2021-03-23 | 2021-08-15 | 2021-09-05 | 111-2843-09775465 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-10-13 |  |  | 2021-09-25 | 2021-10-13 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 |  |  |  | 2021-09-20 | ST202109525417 | S20210030004 |  |  | 2021-09-25 | P/FVC/DEL/1042076/2021 | 2021-10-22 | 2021-10-23 | DL/03/5177/0914/0031/03/01/10249/NS/23102021 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16931 | [5 empty] | 2021-09-30 | 2021-10-22 | Survey Done_CAM Planned and 3 Pole Mount required,Issue closed on 13 oct 21,Installed_Media Issue,Issue resolved on 22.10.21 | [9 empty] | 404-10-621242-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,TD RRU 4412 Available on Parenet Site, new RRU 2279 to be send in FD+TD
Del | FY20_21 | Q2 | Tihar Jail | Government Land, MBTS Location,Near Jail Number-6,7,8 &9 In Parking,Tihar Jail New Delhi,Police Station - Hari Nagar, post office - Janakpuri C4,New Delhi - 110058 | 21987 | 21987 | 21987 | 21987 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3030845 | EXISTING | Sharing | Cow | 30 | 0 | 50/210/320 | Sharing |  |  | YES | >18HRS | NO | 28.6153 | 77.1044 | R/RES-505678 | 2021-09-10 | 2021-09-13 | 2021-09-21 | 111-2861-52771043 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | 2021-09-26 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-08 |  |  |  | 2021-09-21 | ST202109526836 | S20210030073 |  |  | 2021-09-27 | P/FVC/DEL/1042144/2021 | 2021-10-09 | 2021-10-11 | DL/01/5177/6387/0031/03/01/10205/NS/11102021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9664 | [5 empty] | 2021-10-01 | 2021-10-09 | Survey done; Request hold due to GSM height confirmation awaited from planning,HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock,Partially Installed_Far-end Material Delivered at other INDUS site after discussion with ashwani k as on 7 Oct 21,Installed_Media Issue 08 Oct 21,Media Issue resolved on 9th Oct 21,TDD RRU Faulty,TDD RRU disable(70763) | [9 empty] | 404-10-621987-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Tihar Jail | Government Land,MBTS Location,Near Tree Number-2208 & Near Street Light Number-17 & Near Jail Number-4,Tihar Jail ,Police Station - Hari Nagar,Post office - Janakpuri C4, New Delhi - 110058 | 21988 | 21988 | 21988 | 21988 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3030850 | EXISTING | Sharing | Cow | 30 | 0 | 60/170/320 | SHARING |  | COW_SITE | YES | >18HRS | NO | 28.6166 | 77.099 | R/RES-505679 | 2021-09-10 | 2021-09-13 | 2021-09-21 | 111-2861-66770990 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-02 |  |  | 2021-09-26 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-20 |  |  |  | 2021-09-21 | ST202109526837 | S20210030073 |  |  | 2021-09-27 | P/FVC/DEL/1042146/2021 | 2021-10-20 | 2021-10-21 | DL/01/5177/6408/0031/03/01/10240/NS/21102021 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9664 | [5 empty] | 2021-10-01 | 2021-10-14 | Survey done; Request hold due to GSM height confirmation awaited from planning,HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock,Partially Installed_Far-end Material Delivered at other INDUS site after discussion with ashwani k as on 07 Oct 21,Installed_Media Issue 08 Oct 21,Media Issue resolved on 9th Oct 21,Installed_Media Issue as on 09 Oct 21,Issue resolved on 14 Oct 21 and 2G RRU Faulty as on 14 Oct 21,Partially Installed_2G RRU Faulty(70919_Delivered on 19.10.21),Service degraded alarm | [9 empty] | 404-10-621988-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Emaar Imperial Garden | Tower-8 Emaar Imperial Garden,Village Kherki Majra,Sector-102,Police Station - Sector - 9A,post office - Basai Gurugram Haryana 122006 | 21782 | 21782 | 21782 | 21782 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1373165 | EXISTING | Sharing | RTP | 6 | 52 | 130/210/310 | Sharing |  |  | YES | >18HRS | NO | 28.4805 | 76.9691 | R/RES-504974 | 2021-08-18 | 2021-08-20 | 2021-09-24 | 11106-2848-05769691 | 2021-09-30 | 2021-10-01 |  |  |  |  | 2021-10-02 | 2021-10-04 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-07 |  |  |  | 2021-09-18 | ST202109523542 | S20210029898 |  |  | 2021-09-25 | P/FVC/DEL/1042081/2021 | 2021-10-11 | 2021-10-12 | DL/05/5177/5159/0031/03/01/10207/NS/12102021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-17 | 2021-10-12 | 2021-10-17 | 2021-10-12 | 2021-10-17 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 13835 | [5 empty] | 2021-10-09 | 2021-10-11 | HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock,Installed_Link Pending(Farend Work Stopped by Operation),Issue resolved on 8 Oct 21,Installed_Media Issue as on 09 Oct 21,Issue closed on 11 oct 21 | [9 empty] | 404-10-621782-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | TULIP Violet, sector 69 | Government Land,Green Belt,GBM Location,Sec 69,Near Tulip Builders,Police Station - Badshahpur,Post Office - Badshahpur,Gurgaon,Haryana-122101 | 21795 | 21795 | 21795 | 21795 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1349275 | EXISTING | Sharing | GBM | 30 | 0 | 30/270/330 | SHARING |  | SHARING | YES | >18HRS | NO | 28.39 | 77.0313 | R/RES-504975 | 2021-08-18 | 2021-08-20 | 2021-09-24 | 11106-2839-00770313 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-07 |  |  | 2021-09-30 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-11 |  |  |  | 2021-08-31 | ST202108499256 | S20210028828 |  |  | 2021-09-17 | P/FVC/DEL/1039777/2021 | 2021-10-12 | 2021-10-13 | DL/05/5177/5141/0031/03/01/10210/NS/13102021 | 2021-10-13 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4265 | [5 empty] | 2021-10-01 | 2021-10-23 | Revise TND req. or 15Ghz 0.6 Mw req.,Partial Installed/Link Pending-RET not delivered as on 09th Oct 21,Installed_Link Done & Media LAN Cable theft 2 nos,SGW Issue resolved on 23rd Oct 21 | [9 empty] | 404-10-621795-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Emrald Plaza Sec 65 | Emerald Plaza,Sec 65,Nera by Golf Course Extension Rd,Police Station - Badshapur ,Post Office - Samaspur,Gurgaon,Haryana-122102. | 21798 | 21798 | 21798 | 21798 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1373168 | EXISTING | Sharing | RTP | 6 | 35 | 80/200/270 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4057 | 77.0682 | R/RES-504984 | 2021-08-18 | 2021-08-20 | 2021-09-24 | 11106-2840-56770681 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-12 |  |  | 2021-09-20 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-16 | 2021-10-17 |  |  |  | 2021-09-18 | ST202109523541 | S20210029898 |  |  | 2021-09-25 | P/FVC/DEL/1042080/2021 | 2021-10-20 | 2021-10-20 | DL/05/5177/5195/0031/03/01/10234/NS/20102021 | 2021-10-20 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-27 | 2021-10-22 | 2021-10-27 | 2021-10-22 | 2021-10-27 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 25305 | [5 empty] | 2021-10-01 | 2021-10-19 | Pole mount required at Farend,Alternate far-end req./Mail shared by shashank to Birender,New TND received on 11 Oct 21,Farend Survey WIP(Access Issue on 12th Oct 21),Installed_Media Issue as on 17 Oct 21,Issue closed on 19.10.21 | [9 empty] | 404-10-621798-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Shahpur Bamheta | Mr.Satti Choudhary S/o Mr.Siddi Singh,Plot Number 1 & 2,Khasra Number 1230,Shahpur Bamheta,Opposite K.L Steels Ltd,G.T Road,Lal Kua,Police Station - Kavi Nagar,Post Office - Chipyana Buzurg,Ghaziabad,Uttar Pradesh-201009 | 21894 | 21894 | 21894 | 21894 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032757 | New | New_Built | RTP | 6 | 15.4 | 90/210/330 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6328 | 77.4665 | R/NN-628388 | 2021-09-03 | 2021-09-13 | 2021-09-21 | 11109-2863-27774664 | 2021-09-30 | 2021-10-01 |  |  |  |  | 2021-10-02 | 2021-10-04 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-08 |  |  |  | 2021-09-23 | ST202109528793 | S20210030186 |  |  | 2021-09-27 | P/FVC/DEL/1042234/2021 | 2021-11-11 | 2021-11-12 | DL/04/5177/0782/0031/03/01/10271/NS/12112021 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-15 | 2021-11-12 | 2021-11-18 | 2021-11-12 | 2021-11-22 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1762 | [5 empty] | 2021-10-07 | 2021-11-10 | HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock,Partial Installed-Mains not connected/2 RRU short as on 7th Oct 21,Installed_Link Done Media Issue,BBU Faulty,Mains Power Issue,Media Issue resolved on 9th Oct 21,Installed_Link Done,BBU Faulty(1025098),Mains Power Issue closed on Wednesday,Issue closed on 10.11.21 | [9 empty] | 404-10-621894-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Gaur Siddhartam | Mr.KK Gupta,Gaur Siddhartham Apartment,Plot Number - BS08,Tower-B,Near Flat No.3211,Police Station - Siddharth Vihar,Post Office - Pratap Vihar Sec 11,Siddharth Vihar,Ghaziabad,Uttar Pradesh-201009 | 21791 | 21791 | 21791 | 21791 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 21791 | New | New_Built | RTT | 6 | 105 | 330/70/130/260 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6548 | 77.4046 | 21791 | 2021-08-10 | 2021-08-30 | 2021-09-02 | 11109-2865-48774046 | 2021-10-04 | 2021-10-05 | 2021-10-05 | 2021-10-20 |  |  | 2021-09-24 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-22 | 2021-10-23 |  |  |  | 2021-09-02 | ST202109505870 | S20210029004 |  |  | 2021-09-19 | P/FVC/DEL/1040618/2021 | 2021-10-24 | 2021-10-25 | DL/04/0031/0269/0031/03/01/10258/NS/25102021 | 2021-10-25 | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-15 | 2021-11-01 |  | 2021-11-01 | 2021-11-06 |  |  |  |  | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Site Dismantled | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 781 | [5 empty] | 2021-10-05 | 2021-10-23 | Shivam will revert for Far-end Mount requirement_781,Issue closed on 20 Oct 21,Installed_Farend Material Req/MCB req. as on 23rd Oct 21,Cable burnt on 25th oct 21 |  | 2021-11-02 |  | Power Issue due to GDA Sealed | [5 empty] | 404-10-621791-51 |  |  |  |  | Site Dismantled | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | AMRIT VIHAR | Mr. Jai Deep Tyagi S/O Raj Kumar Tyagi,House Number -66,Khasra number - 40/8,Inderprasth Colony,Gali number - 05,Block -B,Amrit Vihar,Post Office - Swaroop Nagar,Police Station - Swaroop Nagar,Delhi - 110084 | 20420 | 20420 | 20420 | 20420 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-5202 | New | Sharing | RTT | 12 | 7 | 50/180/300 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.7632 | 77.177 | SR-DL000139 | 2021-07-18 | 2021-07-30 | 2021-08-16 | 111-2876-31771770 | 2021-10-04 | 2021-10-05 | 2021-10-05 | 2021-10-06 |  |  | 2021-10-05 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-10 |  |  |  | 2021-08-04 | ST202108408418 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037393/2021 | 2021-10-11 | 2021-10-12 | DL/01/5370/2633/0031/03/01/10209/NS/12102021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-10-19 | 2021-10-12 | 2021-11-11 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4505 | [5 empty] | 2021-10-05 | 2021-10-06 | Pole mount required at Farend,Issue closed on 6th Oct 21 | [9 empty] | 404-10-620420-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | RANI KHERA | Mr Naresh Kumar S/O Sh. Chandan Singh,Plot Number.-8,Khasra Number-49/45,Near House Number -7,(Kartar Bhavan),Village Rani Khera,Post Office - Rani Khera,Police Station - Khanjawala,New Delhi - 110081 | 19766 | 19766 | 19766 | 19766 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3769 | New | Sharing | RTT | 15 | 7 | 320/90/220 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.7049 | 77.0263 | SR-DL000052 | 2021-01-12 | 2021-06-14 | 2021-07-29 | 111-2870-46770262 | 2021-10-04 | 2021-10-05 | 2021-10-05 | 2021-11-16 |  |  | 2021-09-29 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-11-18 |  |  |  | 2021-07-29 | ST202107401846 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037082/2021 | 2021-11-23 | 2021-11-24 | DL/01/5370/3671/0031/03/01/10293/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-12-04 | 2021-11-24 | 2021-11-29 | 2021-11-24 | 2021-12-11 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Non INDUS |  | M1 | 23427 | [5 empty] | 2021-10-05 | 2021-11-20 | Material return on 7th Oct 21,Issue closed on 14 oct 21,Material return due to Owner Issue_18.10.21,Issue closed on 16.11.21,Installed_Mains not connected & Farend Water loggin as on 18.11.21,Issue closed on 20.11.21 | [9 empty] | 404-10-619766-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Malibu Town | Chanchal Gautam,House No. GS-176(Near-House No.GS-178),Green Street,Malibu Town,Sector-47,Gurugram,Haryana-122018 | 23128 | 23128 | 23128 | 23128 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II_23128_DEL | New | New_Built | RTP | 4 | 18.3 | 40/200/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4253 | 77.0529 | 23128 | 2021-05-13 | 2021-06-02 | 2021-06-13 | 11106-2842-53770528 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-11-10 |  |  | 2021-10-22 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-12 | 2021-11-25 |  |  |  | 2021-06-16 | ST202106346569 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034052/2021 | 2021-11-25 | 2021-11-26 | DL/05/0031/0586/0031/03/01/10302/NS/26112021 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-12-06 | 2021-11-26 | 2021-12-05 | 2021-11-26 | 2021-12-04 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 17229 | [5 empty] | 2021-10-25 | 2021-11-23 | Material return on 25.10.21 due to Access Issue,Issue closed on 10.11.21,Partial installed-Infra and power wip/Signage board MW mount req. as on 13.11.21,Access Issue as on 15.11.21_Plan on 19.11.21,Issue closed on 23.11.21 | [9 empty] | 404-10-623128-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRU2219B0A RRU 4418 Available on Parenet Site, new 2279 RRU to be Send on site for FD+L_2100
Del | FY20_21 | Q2 | Interocean Shipping India Pvt Ltd. | A-17, Mohan Cooperative Near Sarita Vihar Metro Station Delhi | 27675 | 27675 | 27675 | 27675 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27675_DEL | New | New_Built | IBS | 0 | 10 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5306 | 77.2871 | 27675 | 2021-01-04 | 2021-01-28 | 2021-01-28 | 111-2853-05772871 | 2021-10-20 | 2021-10-21 | 2021-10-21 | 2021-10-22 |  |  | 2021-10-20 | 2021-10-22 | 2021-10-24 | 2021-10-25 | 2021-10-25 | 2022-01-04 | [10 empty] | 2022-01-04 |  |  | 2022-01-04 | 2022-01-05 | 2022-01-05 | 2022-01-06 | 2022-01-05 | 2022-01-07 | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-01-10 | 2022-01-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5318 | [5 empty] | 2021-10-21 | 2022-01-03 | BTS location changed, Combining to be change,Issue closed on 22.10.21,BB delivered Infra issue & MS Pad req as on 25.20.21,Battery bank not Installed_MS Pad req-Mains Issue & Farend antenna req Issue closed on 23.11.21,DAS Pending Sites(Access Issue as discussed with Kushabh) as on 26.11.21,Partial Installed-DAS pending(Ground,1,2 floors-1st ok/Sunday access /Link Done-Ping ok as on 21.12.21,Issue closed on 03.01.22 | [9 empty] | 404-10-627675-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q2 | Jugde's Enclave | Mr. Ashok Kumar Yadav S/o Mr.Veer Pal Singh,Khasra Number.563M/564M,Mohiuddinpur ,Village Kanawani,Oppsite Jasmine Safron High Bird Oxrich Avenue,Ghaziabad,Police Station Vijay Nagar,Post Office Shipra Suncity,Uttar Pradesh,201014 | 17538 | 17538 | 17538 | 17538 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | NIBAR CREATIONS | NI_17538_DEL | New | New_Built | GBM | 30 | 0 | 0/230/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.642 | 77.3857 | 17538 | 2021-05-15 | 2021-07-20 | 2021-07-27 | 11109.2864.19773856.CWIP-CL | 2021-10-04 | 2021-10-05 | 2021-10-05 | 2021-10-07 |  |  | 2021-10-05 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-09 | 2021-10-11 |  |  |  | 2021-07-29 | ST202107401837 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037087/2021 | 2021-10-16 | 2021-10-18 | DL/04/9035/0005/0031/03/01/10222/NS/18102021 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-25 | 2021-10-18 | 2021-10-25 | 2021-10-18 | 2021-11-10 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1443 | [5 empty] | 2021-10-05 | 2021-10-11 | Revise TND req. or 15Ghz 0.6 Mw req.,Police Issue_BB Not delivered_Pole Issue, Earthing pending,RET not delivered as on 09th Oct 21,issue closed on 11 oct21,Installed_HW Faulty(1025145)_HW Delivered on 15.10.21 | [9 empty] | 404-10-617538-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Sanskriti Apartment | Mr. Samarbir S/o- Shankar,Khevat Number - 223/222,Khatoni number - 272,Khasra number - 86 1/2,Village- Mewla Maharajpur,Police Station - Suraj Kund,Post Office - NHPC,Tehsil- Badkal,NHPC Colony,Near Sector 46, Faridabad, Haryana 121010 | 20481 | 20481 | 20481 | 20481 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/FRD/AT/8734 | New | New_Built | GBM | 30 | 0 | 60/130/210 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.4397 | 77.2955 | T21DL00422 | 2021-02-25 | 2021-08-14 | 2021-08-16 | 11106-2843-97772955 | 2021-10-04 | 2021-10-05 | 2021-10-05 | 2021-10-13 |  |  | 2021-09-30 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-16 | 2021-10-17 |  |  |  | 2021-08-17 | ST202108430890 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038097/2021 | 2021-10-17 | 2021-10-18 | DL/02/5126/0202/0031/03/01/10223/NS/18102021 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-23 | 2021-10-18 | 2021-10-23 | 2021-10-18 | 2021-10-23 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5041 | [5 empty] | 2021-10-05 | 2021-10-13 | Survey Rejected; Mains or DG supply not available,Issue closed on 13 Oct 21 | [9 empty] | 404-10-620481-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | shri ram institute(Relocation of 27214) | Government Land,Green Belt,GBM Location,Near Electric pole Number - 418-2/2 to SL418-2/3,And Near Shri ram Institute for Industrial Research Gate No. 1,shri ram Marg,Kamla Nehru Ridge, Civil Lines,Post Office - Malka Ganj,Police Station Mauris Nagar,Delhi, 110007 | 27747 | 27747 | 27747 | 27747 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL46 | New | New_Built | GBM | 30 | 0 | 350/90/210/280 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6804 | 77.2124 | 27747 | 2021-09-21 | 2021-09-24 | 2021-09-24 | 111-2868-04772123 | 2021-10-07 | 2021-10-08 | 2021-10-08 | 2021-10-11 |  |  | 2021-10-05 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-13 | 2021-10-16 |  |  |  | 2021-09-29 | ST202109540883 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042804/2021 | 2021-10-21 | 2021-10-22 | DL/01/0031/2922/0031/03/01/10241/NS/22102021 | 2021-10-22 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 513 | [5 empty] | 2021-10-08 | 2021-10-16 | Infra request Pending till 11 Oct 21,Infra Issue/Towe upper portion bend - Media Issue,Power Issue resolved on 16 Oct 21 & BBU Faulty,Installed_BBU Faulty(70947)_Delivered on 20.10.21,Parent Site having TDD 5 Sector, L2100 HW Fault | [9 empty] | 404-10-627747-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q2 | Express Park View 1 | Mr. Harish(Manejar),Plot Number.10A-10B,Towr Number. D,Express Park View -1,Taj Express Highway, Chi V,Post Office - Kasna,Police Station - Knowledge Park,Greater Noida,Uttar Pradesh 201310 | 25513 | 25513 | 25513 | 25513 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PO_25513_Del | New | New_Built | RTP | 6 | 55 | 0/180/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4327 | 77.5053 | 25513 | 2021-05-13 | 2021-08-02 | 2021-08-04 | 11109-2843-27775053 | 2021-10-07 | 2021-10-08 |  |  |  |  | 2021-10-09 | 2021-10-09 | 2021-10-11 | 2021-10-12 | 2021-10-12 | 2021-10-13 |  |  |  | 2021-08-06 | ST202108410692 | S20210014363 |  |  | 2021-08-12 | P/FVC/DEL/1037547/2021 | 2021-10-17 | 2021-10-18 | DL/03/0031/0344/0031/03/01/10224/NS/18102021 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-23 | 2021-10-18 | 2021-10-23 | 2021-10-18 | 2021-10-23 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5499 | [5 empty] | 2021-10-13 | 2021-10-16 | Installed_Link Pending & LOS Issue/Signage board req.,Installed_2G Media Issue as on 14 oct 21,Issue resolved on 16 Oct 21 | [9 empty] | 404-10-625513-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Near Jail - 1,2 & 3 | Government Land,Inside Jail Number 2,In Front of Jail Factory,Tihar Prison,Police Station - Janakpuri,Post Office - Nangal Raya, New Delhi-110058 | 21989 | 21989 | 21989 | 21989 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3030857 | New | New_Built | COW | 30 | 0 | 30/130/230 | COW |  | COW_SITE | YES | >18HRS | NO | 28.6179 | 77.1007 | R/RES-505680 | 2021-09-10 | 2021-09-13 | 2021-09-24 | 111-2861-79771007 | 2021-10-07 | 2021-10-08 |  |  |  |  | 2021-10-05 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-11 | 2021-10-13 |  |  |  | 2021-09-27 | ST202109535773 | S20210030452 |  |  | 2021-09-30 | P/FVC/DEL/1042629/2021 | 2021-10-13 | 2021-10-20 | DL/01/5177/6397/0031/03/01/10235/NS/20102021 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-23 | 2021-10-20 | 2021-10-23 | 2021-10-20 | 2021-10-25 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 638 | [5 empty] | 2021-10-14 | 2021-10-20 | Access Issue on 14th Oct 21,Pass received on 20 oct 21 | [9 empty] | 404-10-621989-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Prem Nagar, Najafgarh | Plot No. 113/1, Khasra No. 158, Village Roshanpura, Prem Nagar, G Block, Najafgarh, New Delhi-110043 | 21000 | 21000 | 21000 | 21000 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1389142 | New | New_Built | RTT | 12 | 10 | 40/180/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6002 | 76.9792 | R/NN-465852 | 2020-08-27 | 2020-10-26 | 2020-11-09 | 111-2860-02769792 | 2021-10-07 | 2021-10-08 | 2021-10-08 | 2021-10-14 |  |  | 2021-09-27 | 2021-10-14 | 2021-10-17 | 2021-10-18 | 2021-10-18 | 2021-10-23 |  |  |  | 2020-11-27 | ST202011158384 | S20200008804 |  |  | 2020-12-16 | P/FVC/DEL/1012734/2020 | 2021-10-24 | 2021-10-25 | DL/01/5177/6413/0031/03/01/10255/NS/25102021 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 30 | [5 empty] | 2021-10-08 | 2021-10-22 | Farend Owner Issue_5051,New TND received on 11 Oct 21,Shivam will revert for Far-end Mount requirement_30,Issue closed on 14 oct 21,Owner Issue_Mains Issue/Installation Hold as on 19.10.21,Issue closed on 22.10.21 | [9 empty] | 404-10-621000-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Khyala | Government Land ,Horticulture Department, South Delhi Municipal Corporation ( Park ),MBTS Location ,Infront of 830 Bus Stand,and Near House Number B-567, DDA Colony , Khyala, Post Office - Khyala ,Police Station - Khyala,New Delhi - 110018 | 21876 | 21876 | 21876 | 21876 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1374730 | New | New_Built | COW | 30 | 0 | 0/120/240 | COW |  | COW_SITE | YES | >18HRS | NO | 28.652 | 77.096 | R/RES-506008 | 2021-02-25 | 2021-08-14 | 2021-08-16 | 111-2865-20770960 | 2021-10-07 | 2021-10-08 |  |  |  |  | 2021-10-03 | 2021-10-09 | 2021-10-11 | 2021-10-12 | 2021-10-12 | 2021-10-13 |  |  |  | 2021-09-09 | ST202109513793 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040656/2021 | 2021-10-13 | 2021-10-14 | DL/01/5177/6350/0031/03/01/10214/NS/14102021 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-10-14 | 2021-10-19 | 2021-11-20 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4000 | [17 empty] | 404-10-621876-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | ANSALS AVANTIKA, CHIRANJIV VIHAR | GOVERNMENT BUILDING - CAMPUS EDUCATIONAL DEVELOPMENT SOCIETY, D-BLOCK, CHIRANJEEV VIHAR,ANSAL AVANTIKA,POLICE STATION - SHASTRI NAGAR,POST OFFICE - CHIRANJEEVI VIHAR,Ghaziabad, UTTAR PRADESH-201002 | 21356 | 21356 | 21356 | 21356 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GZBD-ENB-4126 | New | New_Built | RTT | 9 | 14 | 30/180/290 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6687 | 77.4778 | SR-DL000156 | 2021-07-18 | 2021-07-26 | 2021-08-05 | 11109-2866-86774778 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-13 | 2021-10-13 | 2021-10-15 | 2021-10-16 | 2021-10-16 | 2021-10-17 |  |  |  | 2021-08-04 | ST202108408415 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037388/2021 | 2021-10-17 | 2021-10-18 | DL/04/5370/3917/0031/03/01/10227/NS/18102021 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-23 | 2021-10-18 | 2021-10-23 | 2021-10-18 | 2021-10-23 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 619 | [17 empty] | 404-10-621356-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Sec 52,Gurgaon(Relocation of 15452) | Plot Number- 597,Sec-52,Police Station - Sector 46,Post Office - Wazirabad,Gurgaon Haryana 122413 | 20522 | 20522 | 20522 | 20522 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GRGN-ENB-4034 | New | New_Built | RTT | 12 | 10.5 | 0/90/200 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4317 | 77.0746 | SR-DL000081 | 2021-01-12 | 2021-07-23 | 2021-08-13 | 11106-2843-16770746 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-11 | 2021-10-13 | 2021-10-17 | 2021-10-18 | 2021-10-18 | 2021-10-20 |  |  |  | 2021-08-04 | ST202108408416 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037389/2021 | 2021-10-20 | 2021-10-21 | DL/05/5370/0253/0031/03/01/10237/NS/21102021 | 2021-10-21 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-30 | 2021-10-23 | 2021-10-30 | 2021-10-23 | 2021-10-30 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 718 | [7 empty] | MO WIP_10 Port Antenna Not in Stock,L2100 RRU Faulty(17315359_21.10.21) | [9 empty] | 404-10-620522-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 14B3 TD RRU 4412 , L_2100 RRU 12B1 Available on Parenet Site
Del | FY20_21 | Q2 | Kirti Nagar | Mr. Karamveer,Property Number. 329,Chara Mandi,Zakhira,Kirti Nagar,Police Station - Inderlok,Post Office - Zakhira, Delhi - 110015 | 19952 | 19952 | 19952 | 19952 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-5739 | New | New_Built | RTT | 12 | 11 | 0/90/180 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.667 | 77.1656 | SR-DL000146 | 2021-07-18 | 2021-08-11 | 2021-08-26 | 111-2866-69771655 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-13 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-16 |  |  |  | 2021-08-28 | ST202108496360 | S20210028670 |  |  | 2021-09-08 | P/FVC/DEL/1039404/2021 | 2021-10-16 | 2021-10-18 | DL/01/5370/2359/0031/03/01/10226/NS/18102021 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-10-25 | 2021-10-18 | 2021-10-25 | 2021-10-18 | 2021-11-10 | 2021-11-20 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 917 | [17 empty] | 404-10-619952-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Bawana JJ colony | Rahisha W/O Babu Khan, House No-923,Near Madina Masjid,Bawana JJ Colony, Delhi-110039 | 21147 | 21147 | 21147 | 21147 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FI_21147_DEL | New | New_Built | RTP | 9 | 12 | 90/230/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.8075 | 77.0545 | 21147 | 2021-05-21 | 2021-06-02 | 2021-06-14 | 111-2880-75770544 | 2021-10-11 | 2021-10-12 | 2021-10-12 | 2021-11-09 |  |  | 2021-10-09 | 2021-11-10 | 2021-11-10 | 2021-11-13 | 2021-11-13 | 2021-11-16 |  |  |  | 2021-06-18 | ST202106351943 | S20210011840 |  |  | 2021-07-11 | P/FVC/DEL/1034184/2021 | 2021-11-16 | 2021-11-17 | DL/01/5417/0005/0031/03/01/10277/NS/17112021 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-20 | 2021-11-17 | 2021-11-24 | 2021-11-17 | 2021-11-25 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19467 | [5 empty] | 2021-10-14 | 2021-11-16 | Material return due to Public Issue_14.10.21,Issue Closed on 09.11.21,Installed-BB installation pending/farend MW pole req as on 15.11.21,Issue closed on 16.11.21 | [9 empty] | 404-10-621147-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Golf Link, Sec. 23. | Mr. Harvinder Kumar S/O Chhatrasal Sehrawat, Khata Khatoni Number - 64/60,Khasra Number.24/1,Pochanpur Extension,Near Church,Police Station - Sector 23 Dwarka,Post Office - Sector 23 Dwarka, Delhi-110043 | 19603 | 19603 | 19603 | 19603 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-172 | New | New_Built | RTP | 6 | 19 | 60/180/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.563 | 77.0431 | 19603 | 2020-12-11 | 2021-10-05 | 2021-10-05 | 111-2856-29770430 | 2021-10-11 | 2021-10-12 | 2021-10-12 | 2021-10-22 |  |  | 2021-10-06 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-25 | 2021-10-27 |  |  |  | 2021-10-08 | ST202110554403 | S20210031332 |  |  | 2021-10-22 | P/FVC/DEL/1043938/2021 | 2021-10-27 | 2021-10-28 | DL/01/0031/2938/0031/03/01/10263/NS/28102021 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-10-28 | 2021-11-02 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4496 | [5 empty] | 2021-10-12 | 2021-10-27 | Survey Rejected; 104M lat-long deviation found,Issue resloved on 22.10.21,Partial Installed_BB delivered Infra Issue as on 25.10.21,Issue closed on 27.10.21 | [9 empty] | 404-10-619603-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | G-Block Pratap Vihar(Relocation of 7760) | Mr.Pritesh Kumar , Property No. F-8/5 & 8/6,Pratap Vihar,Sector-2,Ghaziabad,Uttar Peradesh-201009 | 21695 | 21695 | 21695 | 21695 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1953788 | New | New_Built | RTP | 9 | 15 | 30/150/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6543 | 77.4117 | R/NN-618359 | 2021-04-23 | 2021-06-03 | 2021-07-15 | 11109-2865-43774116 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-10 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-16 |  |  |  | 2021-07-19 | ST202107388710 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036226/2021 | 2021-10-16 | 2021-10-18 | DL/04/5177/0778/0031/03/01/10225/NS/18102021 | 2021-10-18 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 291 | [7 empty] | L2100 RRU Faulty_1025202 (Delivery Plan_20.10.21)_Delivered on 20.10.21,TTB Running on Parent Site(1025230)_L2100 RRU Delivered on 21.10.21 | [9 empty] | 404-10-621695-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,FD RRU 2219 B3 ,L_2100 RRU 12B1,TD RRU 4418 Available On parent Site
Del | FY20_21 | Q2 | Ashok Vihar Phase III(Relocation of 14473) | Mr Dinesh Katariya S/O Sh. Devraj Katariya,Khewat/Khata/Khasra No. 7231/2597,House Number - 01,Hall Colony,Gali number -B-6, Block - C,Ashok vihar phase - 3,Post office - Railway Road,Police Station - Sector 5 Gurgaon,Tehsil and District Gurgaon - 122017, | 21137 | 21137 | 21137 | 21137 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1853836 | New | New_Built | RTT | 15 | 8 | 0/180/290 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4926 | 77.0264 | R/NN-569121 | 2021-03-25 | 2021-07-21 | 2021-07-27 | 11106-2849-25770263 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-12 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-14 |  |  |  | 2021-08-19 | ST202108483951 | S20210028161 |  |  | 2021-09-27 | P/FVC/DEL/1042104/2021 | 2021-10-21 | 2021-10-22 | DL/05/5177/5300/0031/03/01/10245/NS/22102021 | 2021-10-22 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10964 | [5 empty] | 2021-10-14 | 2021-10-21 | Installed_Short Jumper Delivered,HW Delivered on 15.10.21,Installed_2G Media Issue,Issue closed on 19.10.21,Installed_SGW Issue as on 20 Oct 21,Issue closed on 21.10.21,TTB Running on Parent Site_SCFT Done | [9 empty] | 404-10-621137-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRUS 2219 B0A,FD RRU RRUS 2219 B3, L_2100 RRU RRUS12 B1, TD RRU 4412
Del | FY20_21 | Q2 | Adani Oyster Grande | Mr.Sagnik Datta,Khasra Number - 45//17,Tower-A,Adani Oyster Grande,Sector-102,Village Kherki Majra Dhankot,Dwarka Expressway,Police Station - Sector 102,Post Ofice - Sector 102,Tehsil - Kadipur,Gurgaon Haryana 122006 | 21895 | 21895 | 21895 | 21895 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1380324 | New | New_Built | RTP | 6 | 71 | 50/140/280 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4814 | 76.9734 | R/RES-506010 | 2021-09-22 | 2021-09-23 | 2021-09-27 | 11106-2848-14769734 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-10 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-16 |  |  |  | 2021-09-16 | ST202109522329 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041986/2021 | 2021-10-16 | 2021-10-19 | DL/05/5177/5158/0031/03/01/10228/NS/19102021 | 2021-10-19 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-11-14 | 2021-10-22 | 2021-11-18 | 2021-10-22 | 2021-10-27 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 18685 | [5 empty] | 2021-10-14 | 2021-10-18 | Partially Installed_Power Issue/Module Req,Integarted on Power Issue as on 16 Oct 21,Power Issue resolved on 18 oct 21,Media Issue resolved on 22.10.21 | [9 empty] | 404-10-621895-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q2 | Sector 17A, Greater Noida | Plot No-4,Near - Villa Number 1 to 18,Country Club,Supertech,Sector-17A,Police Station - Greater Noida,Post Office - Gurjinder Vihar,Greater Noida,Uttar Pradesh-203201 | 21875 | 21875 | 21875 | 21875 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1370924 | New | New_Built | RTP | 6 | 19 | 30/120/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.3708 | 77.5486 | R/RES-506011 | 2021-09-22 | 2021-09-23 | 2021-09-27 | 11109-2837-08775486 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-13 | 2021-10-12 | 2021-10-14 | 2021-10-15 | 2021-10-15 | 2021-10-16 |  |  |  | 2021-09-16 | ST202109522331 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041987/2021 | 2021-11-25 | 2021-11-25 | DL/03/5177/0812/0031/03/01/10298/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-09 | 2021-11-25 | 2021-12-05 | 2021-11-25 | 2021-12-02 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9513 | [5 empty] | 2021-10-16 | 2021-11-25 | Installed_Link Inst WIP-Height deviation 3rd sec,Issue closed on 25.11.21 | [9 empty] | 404-10-621875-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Krishna Nagar Faridabad | Mr. Rahul Chandila S/O Bhagat Chandila,Plot Number.826,Krishna Nagar, Sector-20B,Post Office - Sec 12 Faridabad,Police Station - Bata Chock,New Industrial Town,Faridabad,Haryana 121001 | 17391 | 17391 | 17391 | 17391 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1883970 | New | New_Built | GBM | 30 | 0 | 40/200/290 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.3858 | 77.3094 | R/NN-569809 | 2021-04-02 | 2021-07-21 | 2021-07-26 | 11106-2838-57773094 | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-10 | 2021-10-12 | 2021-10-15 | 2021-10-16 | 2021-10-16 | 2021-10-17 |  |  |  | 2021-07-29 | ST202107401817 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037073/2021 | 2021-10-18 | 2021-10-19 | DL/02/5177/5041/0031/03/01/10229/NS/19102021 | 2021-10-19 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-30 | 2021-10-23 | 2021-10-30 | 2021-10-23 | 2021-11-11 | 2021-11-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 889 | [7 empty] | VSWR Issue in L900(Antenna Port Faulty_17301081)_Delivered on 22.10.21 | [9 empty] | 404-10-617391-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | EMCD_77_Jhilmil Colony Shahdara (Relocation of 576 | Mrs. Vandana Khaneja W/O Gulshan,Shop Number. 17, Krishna Market, Jhilmil Colony, Shahdara, Police Station - Vivek Vihar, Post Office - Jhilmil,Delhi-110095 | 20907 | 20907 | 20907 | 20907 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3034878 | New | New_Built | RTP | 9 | 13 | 0/120/250 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6691 | 77.3068 | R/NN-628387 | 2021-09-03 | 2021-09-10 | 2021-09-16 | 111.2866.91773067.CWIP-CL | 2021-10-11 | 2021-10-12 |  |  |  |  | 2021-10-13 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-16 |  |  |  | 2021-09-21 | ST202109526838 | S20210030073 |  |  | 2021-09-27 | P/FVC/DEL/1042145/2021 | 2021-10-17 | 2021-10-18 | DL/01/5177/6399/0031/03/01/10221/NS/18102021 | 2021-10-18 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 104 | [7 empty] | MIMO Running on Parent Site(MIMO Delivered & Integrated on 21.10.21),Alarm on FDD 1st Sec VSWR(71108) | [9 empty] | 404-10-620907-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 14B3 TD RRU 4412 , L_2100 RRU 12B1 Available on Parenet Site
Del | FY20_21 | Q2 | Hari Nagar(Relocation of 703) | Satinder Kaur w/o Late Pritpal Singh,R/o M-1,Hari Nagar,Near Mother Diary,New Delhi-64 | 21238 | 21238 | 21238 | 21238 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | RLDLWDL0044 | New | New_Built | RTT | 12 | 12 | 20/220/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6238 | 77.1168 | 21238 | 2020-10-29 | 2021-04-20 | 2021-08-23 | 111-2862-38771167 | 2021-10-12 | 2021-10-13 |  |  |  |  | 2021-09-15 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-15 | 2021-10-16 |  |  |  | 2021-04-22 | ST202104166422 | S20210007457 |  |  | 2021-07-22 | P/FVC/DEL/1036059/2021 | 2021-10-17 | 2021-10-17 | DL/01/5113/0034/0031/03/01/10220/NS/17102021 | 2021-10-17 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-10-23 | 2021-10-28 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 884 | [7 empty] | MIMO Running on Parent Site(MIMO Delivered & Integrated on 21.10.21) | [9 empty] | 404-10-621238-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 RRU 4412 Available on Parenet Site, new 2279 RRU to be Send on site for FD+L_2100
Del | FY20_21 | Q2 | Rajat Vihar, Khoda Colony(relocation of 11464) | RC-97, Nehru Garden, Near Rajat Vihar, Khoda Colony Noida U.P-201301 | 20920 | 20920 | 20920 | 20920 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/NO/AT/3515 | New | New_Built | RTT | 15 | 13 | 350/150/250 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6102 | 77.3474 | T21DL02604 | 2020-07-24 | 2021-09-09 | 2021-09-16 | 11109-2861-02773473 | 2021-10-12 | 2021-10-13 | 2021-10-13 | 2021-10-14 |  |  | 2021-09-28 | 2021-10-14 | 2021-10-17 | 2021-10-18 | 2021-10-18 | 2021-10-20 |  |  |  | 2020-08-30 | ST202008056317 | S20200003704 |  |  | 2020-09-03 | P/FVC/DEL/1005038/2020 | 2021-10-20 | 2021-10-21 | DL/03/5126/0350/0031/03/01/10236/NS/21102021 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2021-11-11 | 2021-11-13 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4171 | [5 empty] | 2021-10-13 | 2021-10-14 | Pole required at Farend_SP awaited,Issue closed on 14 oct 21,Partially Installed_BBU Short(1025201)_Delivered on 20.10.21 | [9 empty] | 404-10-620920-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 RRU 4412 Available on Parenet Site, new 2279 RRU to be Send on site for FD+L_2100
Del | FY20_21 | Q2 | NAND NAGRI, SHAHDRA | Mr. Nate Ram S/O Sundari Prasad,House Number-A-1/230,Block A,Nand Nagri,Nand Nagri Police Station,Nand Nagri Post office,Shahdara, Delhi-110093 | 20247 | 20247 | 20247 | 20247 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPL026 | New | New_Built | RTP | 9 | 13 | 10/70/210 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6961 | 77.3068 | 20247 | 2021-06-10 | 2021-06-30 | 2021-07-07 | 111-2869-60773068 | 2021-10-12 | 2021-10-13 |  |  |  |  | 2021-10-13 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-15 | 2021-10-17 |  |  |  | 2021-07-09 | ST202107379590 | S20210012929 |  |  | 2021-07-16 | P/FVC/DEL/1035536/2021 | 2021-10-19 | 2021-10-20 | DL/01/5414/0001/0031/03/01/10232/NS/20102021 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-25 | 2021-10-20 | 2021-10-25 | 2021-10-20 | 2021-10-25 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 13111 | [5 empty] | 2021-10-16 | 2021-10-19 | Partial Installed-Power close/Canopy base issue,Issue closed on 17 Oct 21,Installed_Media Issue as on 17 Oct 21,Installed_Media Issue(Water Logging Issue at 13111) issue closed on 19.10.21 | [9 empty] | 404-10-620247-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Mukherjee Park | Hno. A-55, Khayala Road, Vishnu Garden, New Delhi 110018 | 18200 | 18200 | 18200 | 18200 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1364589 | New | New_Built | RTM | 12 | 10 | 10/120/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6486 | 77.1031 | R/NN-626315 | 2019-06-03 | 2019-06-17 | 2019-06-26 | 111-MDEL-1933741 | 2021-10-12 | 2021-10-13 | 2021-10-13 | 2021-10-16 |  |  | 2021-10-14 | 2021-10-16 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-11-24 |  |  |  | 2019-07-01 | 2019998099 | 2019998099 |  |  | 2019-07-19 | P/FVC/DEL/5722714/2019 | 2021-12-04 | 2021-12-06 | DL/01/5177/6455/0031/345/04/08647/NS/06122021 | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-09 | 2021-12-06 | 2021-12-10 | 2021-12-06 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1205 | [5 empty] | 2021-10-13 | 2021-12-03 | MO Punching required on Saturday and Delivery on Monday_18.10.21,Public Issue_Indus Canopy req_Plan on 22 Oct 21,Issue closed on 18.11.21,Public issue-Indus canopy Installed-Mains not connected/Farend material shifting pending as on 18.11.21,Issue closed on 20.11.21,Public Issue_Work Stopped as on 20.11.21,Issue closed on 03.12.21,Installed Fiber Down as on 03.12.21 | [9 empty] | 404-10-618200-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Mukundpur | Mr.Vinod Kumar,Khasra Number- 399,Village Sadullabad,Ved Vihar Extension,Pargana Loni,Police Station - Vijay Vihar,Post Office - Loni,Tehsil and District-Ghaziabad,Uttar Pradesh-201102 | 21224 | 21224 | 21224 | 21224 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1478339 | New | New_Built | GBM | 30 | 0 | 120/230/300 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.7359 | 77.2665 | R/NN-519686 | 2020-10-29 | 2021-08-12 | 2021-09-13 | 11109-2873-58772664 | 2021-10-12 | 2021-10-13 |  |  |  |  | 2021-09-13 | 2021-10-13 | 2021-10-17 | 2021-10-18 | 2021-10-18 | 2021-10-19 |  |  |  | 2021-09-09 | ST202109513822 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040668/2021 | 2021-10-19 | 2021-10-20 | DL/04/5177/0781/0031/03/01/10233/NS/20102021 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-30 | 2021-10-20 | 2021-10-30 | 2021-10-20 | 2021-11-10 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 694 | [5 empty] | 2021-10-18 | 2021-10-19 | Partially Installed_Infra Issue closed on 19.10.21 | [9 empty] | 404-10-621224-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | DLF Ankur Vihar Loni Ghaziabad(Relocation of 4190 | Mr. Subhas ji,Plot Number - S-8,Near House Number - S-9,DLF Ankur Vihar,Post Office - Loni,Police Station - DLF Ankur Vihar,Ghaziabad-201102 | 22002 | 22002 | 22002 | 22002 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3012979 | New | New_Built | RTP | 9 | 13 | 10/150/260 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7382 | 77.264 | R/RES-506014 | 2021-09-22 | 2021-09-23 | 2021-09-27 | 11109-2873-81772640 | 2021-10-12 | 2021-10-13 |  |  |  |  | 2021-10-13 | 2021-10-13 | 2021-10-17 | 2021-10-18 | 2021-10-18 | 2021-10-21 |  |  |  | 2021-09-24 | ST202109531877 | S20210030334 |  |  | 2021-09-28 | P/FVC/DEL/1042298/2021 | 2021-10-21 | 2021-10-22 | DL/04/5177/0773/0031/03/01/10242/NS/22102021 | 2021-10-22 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-30 | 2021-10-24 | 2021-10-30 | 2021-10-24 | 2021-11-11 | 2021-11-13 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1705 | [7 empty] | Partial Installed_Link Done-1 BBU Short,Partial Installed_Link Done-1 BBU Short(1025213_Delivery Plan)_BBU Delivered on 21.10.21,MIMO Running on Parent Site(1025248) as on 23rd Oct 21 | [9 empty] | 404-10-622002-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 RRU 4412 Available on Parenet Site, new 2279 RRU to be Send on site for FD+L_2100
Del | FY20_21 | Q2 | Dariyaganj(Relocation of 18) | Amit Chandra,Plot Number. 4574/15, Padam Chand Marg,Darya Ganj, Police Station - Daryaganj, Post Office - Ajmeri Gate,Delhi-110002 | 21898 | 21898 | 21898 | 21898 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1373224 | New | New_Built | RTT | 15 | 10 | 40/130/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6488 | 77.2427 | R/RES-506009 | 2021-09-22 | 2021-09-23 | 2021-09-27 | 111-2864-88772426 | 2021-10-14 | 2021-10-14 |  |  |  |  | 2021-10-11 | 2021-10-14 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 |  |  |  | 2021-09-16 | ST202109522330 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041988/2021 | 2021-10-22 | 2021-10-23 | DL/01/5177/6096/0031/03/01/10246/NS/23102021 | 2021-10-23 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10576 | [5 empty] | 2021-10-20 | 2021-10-22 | Installed LOS Issue_BBU Short(70981) & Cabinet faulty,_BBU Delivered on 21.10.21(71038),Installed_Link Done & Media Issue_Cabinet faulty(71038) as on 21.10.21,Issue resolved on 22.10.21,Provisioning Issue discussed with Shashank/Amit as on 23rd Oct 21 | [9 empty] | 404-10-621898-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412
Del | FY20_21 | Q2 | Rajpark Sultanpuri | Mr. Tilak Raj S/O Sh. Kalam Singh,Plot Number. A-220,Khasra number - 582,And Near Infront of Electric Pole number - 518-8/3/12/2/3,Village Sultanpur Majra,Block - A,Colony Known as Raj Park,Post Office - Sultanpuri,Police Station - Sultanpuri,Delhi - 110086 | 20521 | 20521 | 20521 | 20521 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-9460 | New | New_Built | RTT | 12 | 13 | 300/90/210 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6889 | 77.0735 | SR-DL000077 | 2021-01-12 | 2021-07-22 | 2021-08-16 | 111-2868-89770735 | 2021-10-14 | 2021-10-14 |  |  |  |  | 2021-10-14 | 2021-10-16 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 |  |  |  | 2021-08-04 | ST202108408417 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037391/2021 | 2021-10-23 | 2021-10-24 | DL/01/5370/5074/0031/03/01/10251/NS/24102021 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-30 | 2021-10-24 | 2021-10-30 | 2021-10-24 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1154 | [5 empty] | 2021-10-21 | 2021-10-22 | Partially Installed_Neighbour Issue,Issue resolved on 22.10.21,Installed_RRU Fautly TDD 2nd | [9 empty] | 404-10-620521-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Padam nagar, Faridabaad | Mr. Surender Kumar Jha S/O Ram Jha,Khasra Number. 35/2,Indra Complex Colony, Sector 87,Post Office - Sec 88,Police Station - Kheri Pul,Neharpar Faridabad,Haryana 121002 | 22048 | 22048 | 22048 | 22048 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-FDBD-ENB-3895 | New | New_Built | RTT | 9 | 10 | 0/120/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4168 | 77.3372 | SR-DL000144 | 2021-06-30 | 2021-07-30 | 2021-09-07 | 11106-2841-67773371 | 2021-10-14 | 2021-10-14 |  |  |  |  | 2021-10-14 | 2021-10-16 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 |  |  |  | 2021-08-04 | ST202108408427 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037386/2021 | 2021-10-24 | 2021-10-25 | DL/02/5370/3148/0031/03/01/10256/NS/25102021 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-10-25 | 2021-10-30 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15178 | [5 empty] | 2021-10-19 | 2021-10-20 | Mains Not Connected as on 19.10.21,Issue closed on 20.10.21,Installed_RSL Issue-Farend changed req as on 22nd Oct 21 | [9 empty] | 404-10-622048-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | NANDA BLOCK MAHAVEER ENCLAVE | Mr. Mithilesh,House Number. RZ-U-12, Nanda Block,Mahaveer Enclave, Police Station - Sector 1 Dwarka ,Post Office - Mahaveer Enclave, New Delhi-110059 | 19263 | 19263 | 19263 | 19263 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/SH/2081 | New | New_Built | RTT | 15 | 10 | 70/180/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6014 | 77.0728 | T21DL02733 | 2021-08-27 | 2021-10-05 | 2021-10-05 | 111-2860-14770727 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-21 |  |  | 2021-10-19 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-25 | 2021-10-26 |  |  |  | 2021-01-19 | ST202101017283 | S20210001143 |  |  | 2021-02-25 | P/FVC/DEL/1017926/2021 | 2021-10-26 | 2021-10-27 | DL/01/5126/1549/0031/03/01/10260/NS/27102021 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-11-15 | 2021-10-27 | 2021-11-19 | 2021-10-27 | 2021-11-01 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 145 | [5 empty] | 2021-10-19 | 2021-10-25 | Survey Rejected; Height deviation issue,Issue closed on 21.10.21,Partial Installed_Farend Access issue as on 25.10.21 | [9 empty] | 404-10-619263-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | CB 4,Supertech Capetown | Manish Plot Number. GH-01,Supertech Capetown,Crown Tower CB-4,Sector-74 ,Noida,Police Station - Sorkha,Post Office - Barola,Uttar Pradesh-201306 | 25198 | 25198 | 25198 | 25198 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Fine bunch | FI_25198_DEL | New | New_Built | RTP | 6 | 76 | 180/240/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5761 | 77.3922 | 25198 | 2021-02-21 | 2021-08-02 | 2021-08-03 | 11106.2836.97770779.CWIP-CL | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-28 |  |  | 2021-10-19 | 2021-10-29 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-02 |  |  |  | 2021-08-04 | ST202108408362 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037399/2021 | 2021-11-02 | 2021-11-03 | DL/03/0005/0026/0031/03/01/10268/NS/03112021 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-15 | 2021-11-03 | 2021-11-19 | 2021-11-03 | 2021-11-08 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5339 | [5 empty] | 2021-10-19 | 2021-10-28 | Survey Rejected; Mains cable not available, Cable tray not installed, PARSWA PAD required & Pole mount to be shift as per Building authority,Issue closed on 28.10.21 | [9 empty] | 404-10-625198-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Village Bajghera | Mr. Tejender Kaushik S/O Sh. Shree Bhagwan House Number - 68A,Khewat Number - 301//272,Khatouni Number - 306, Khasra Number - 19//24/2,Handbast Number - 61,Village Bajghera,Police Station- Bajghera Post Office- Palam Vihar,Gurugram Haryana 122017 | 21892 | 21892 | 21892 | 21892 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032305 | New | New_Built | RTT | 12 | 10 | 330/150/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5319 | 77.0224 | R/NN-628357 | 2021-09-03 | 2021-09-10 | 2021-09-16 | 11106-2853-19770223 | 2021-10-18 | 2021-10-19 |  |  |  |  | 2021-10-19 | 2021-10-19 | 2021-10-21 | 2021-10-22 | 2021-10-22 | 2021-10-23 |  |  |  | 2021-09-20 | ST202109525421 | S20210030004 |  |  | 2021-09-25 | P/FVC/DEL/1042078/2021 | 2021-10-23 | 2021-10-24 | DL/05/5177/5302/0031/03/01/10253/NS/24102021 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-11-11 | 2021-10-24 | 2021-11-24 | 2021-10-24 | 2021-10-29 | 2021-12-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4468 | [17 empty] | 404-10-621892-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRUS 02 B0 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Krishna Kunj | Ms. Rita Devi W/O Sh. Pappu Sharma,House Number-1248,Krishna Kunj,Gali Number-10,Naya Gaon,Police Station - Bhondsi,Post Office - Naya Gaon Gurugram Haryana 122102 | 21887 | 21887 | 21887 | 21887 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032295 | New | New_Built | RTT | 12 | 8.5 | 10/130/210 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.3697 | 77.0778 | R/NN-628354 | 2021-09-03 | 2021-09-13 | 2021-09-17 | 11106.2836.97770778.CWIP-CL | 2021-10-18 | 2021-10-19 |  |  |  |  | 2021-10-19 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-21 | 2021-10-22 |  |  |  | 2021-09-23 | ST202109528792 | S20210030186 |  |  | 2021-09-27 | P/FVC/DEL/1042233/2021 | 2021-10-23 | 2021-10-24 | DL/05/5177/5301/0031/03/01/10250/NS/24102021 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-10-24 | 2021-10-29 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11100 | [17 empty] | 404-10-621887-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRUS 02 B0 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Bhilangana Hydro Power Ltd | B-37 3rd Floor Sector 1 Noida | 27695 | 27695 | 27695 | 27695 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27695_DEL | New | New_Built | IBS | 0 | 19 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.591 | 77.312 | 27695 | 2021-04-15 | 2021-10-17 | 2021-10-17 | 11109-2859-10773119 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-21 |  |  | 2021-10-20 | 2021-10-22 | 2021-10-22 | 2021-10-23 | 2021-10-23 | 2021-11-01 | [10 empty] | 2021-11-01 |  |  | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-13 | 2021-11-02 | 2021-11-07 | 2021-11-02 | 2021-11-07 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5192 | [5 empty] | 2021-10-19 | 2021-10-21 | BTS location changed from Basement to Rooftop 160M; New planning and combining required,Permission Issue_1200 mtr cabling DAS | [9 empty] | 404-10-627695-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q2 | Paytm | B-26 Phase II Noida 201301 | 27737 | 27737 | 27737 | 27737 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27737 | New | New_Built | IBS | 0 | 10 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5362 | 77.4124 | 27737 | 2021-09-09 | 2021-10-17 | 2021-10-17 | 11109-2853-62774124 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 |  |  | 2021-09-23 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-22 | 2021-10-26 | [10 empty] | 2021-10-26 |  |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-11-12 | 2021-10-27 | 2021-11-29 | 2021-10-27 | 2021-11-01 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4925 | [5 empty] | 2021-10-19 | 2021-10-20 | Survey Rejected; Mains supply not availble, PARSWA PAD required,Issue closed on 20 Oct 21,Partial Installed-Cable tray req 2mtr/1000 mtr cabling DAS as on 22.10.21,Partial Installed_1000 mtr cabling DAS | [9 empty] | 404-10-627737-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q2 | AKUMS DRUGS & PHARMACEUTICAL LIMITED | C-131 ph-1 Mangolpuri Indutrial area Delhi -110087 | 27738 | 27738 | 27738 | 27738 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27738 | New | New_Built | IBS | 0 | 13 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6876 | 77.095 | 27738 | 2021-09-20 | 2021-10-17 | 2021-10-17 | 111.2868.76770949.CWIP-CL | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 |  |  | 2021-10-14 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-22 | 2021-10-26 | [10 empty] | 2021-10-26 |  |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-11-01 | 2021-10-27 | 2021-11-01 | 2021-10-27 | 2021-11-01 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1156 | [5 empty] | 2021-10-19 | 2021-10-20 | Survey Rejected; Mains supply not availble, PARSWA PAD required & Climbing ladder required,Issue closed on 20 Oct 21,Partial Installed_1000 mtr cabling DAS(MW Pwr connectr used) | [9 empty] | 404-10-627738-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q2 | Site 4, Sahibabad, Ghaziabad | Mr.Balvinder Singh S/o Mukhtyar Singh ,Plot No. 12/73,Site IV,Sahibabad,Police Station Surya Nagar,Post Office Chander Nagar,Ghaziabad ,Uttar Pradesh,201010 | 19666 | 19666 | 19666 | 19666 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | 19666 | New | New_Built | RTM | 12 | 14 | 0/120/240 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6608 | 77.3316 | 19666 | 2021-07-12 | 2021-07-21 | 2021-07-26 | 11109-2866-04773315 | 2021-10-18 | 2021-10-19 |  |  |  |  | 2021-10-19 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-21 | 2021-10-23 |  |  |  | 2021-07-26 | ST202107397093 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036560/2021 | 2021-10-25 | 2021-10-27 | DL/04/0031/0270/0031/03/01/10259/NS/27102021 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-11-01 | 2021-10-27 | 2021-11-01 | 2021-10-27 | 2021-11-01 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10689 | [5 empty] | 2021-10-23 | 2021-10-25 | Installed/Farend changed-MW pending/Access Issue Sunday | [9 empty] | 404-10-619666-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Vasant Vihar(Relocation of 7155) | GOVERNMENT LAND-GBM LOCATION-SDMC PARK,NEAR HOUSE NO. D-2A/8, VASANT VIHAR POLICE STATION-VASANT VIHAR,POST OFFICE-VASANT VIHAR | 23657 | 23657 | 23657 | 23657 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3051305 | New | New_Built | GBM | 30 | 0 | 60/120/190 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5661 | 77.1546 | R/NN-632118 | 2021-09-28 | 2021-10-05 | 2021-10-11 | 111-2856-71771557 | 2021-10-18 | 2021-10-19 |  |  |  |  | 2021-10-17 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-21 | 2021-10-22 |  |  |  | 2021-09-09 | ST202109513788 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040659/2021 | 2021-10-23 | 2021-10-24 | DL/01/5177/6411/0031/03/01/10252/NS/24102021 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-24 | 2021-10-30 | 2021-10-24 | 2021-10-30 | 2021-10-24 | 2021-11-10 | 2021-11-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 257 | [5 empty] | 2021-10-21 | 2021-10-22 | Partially Installed_Pole Issue(GSM & RRU),Issue closed on 22.10.21 | [9 empty] | 404-10-623657-51 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
Del | FY20_21 | Q2 | Radico Khaitan Limited | Plot number J1/B1 Mohan corporative industrial area Mathura road | 27726 | 27726 | 27726 | 27726 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27726_DEL | New | New_Built | IBS | 0 | 10 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5137 | 77.2976 | 27726 | 2021-10-05 | 2021-10-05 | 2021-10-11 | 111-2851-29772967 | 2021-10-20 | 2021-10-21 |  |  |  |  | 2021-10-19 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-23 | 2021-10-25 | [10 empty] | 2021-10-25 |  |  | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-11-13 | 2021-10-26 | 2021-10-31 | 2021-10-26 | 2021-10-31 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5355 | [5 empty] | 2021-10-23 | 2021-10-25 | Partial Installed_650 mtr cabling DAS_MS PAD and cable tray req Issue closed on 25.10.21 | [9 empty] | 404-10-62726-51 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q3 | NIT Faridabad | Mrs. Vidha Sharma W/O Mr. Om Prakash Sharma,House number - D-11,Nehru Ground,New Industrial Town,Faridabad,Post Office - B.K Chowk Faridabad,Police Station - B.K Chowk Faridabad, Faridabad Haryana 121001 | 21803 | 21803 | 21803 | 21803 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6165 | New | New_Built | RTP | 6 | 14 | 50/150/320 | ATC_LITE_POLE_SITE |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.3889 | 77.3046 | T21DL02831 | 2021-09-06 | 2021-09-24 | 2021-09-29 | 11106-2838-89773046 | 2021-10-22 | 2021-10-22 |  |  |  |  | 2021-10-22 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-28 | 2021-10-29 |  |  |  | 2021-09-29 | ST202109538513 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042830/2021 | 2021-10-29 | 2021-10-30 | DL/02/5126/0027/0031/03/01/10265/NS/30102021 | 2021-10-30 | 2021-10-30 | 2021-10-30 | 2021-10-30 | 2021-10-30 | 2021-11-04 | 2021-10-30 | 2021-11-04 | 2021-10-30 | 2021-11-04 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1725 | [17 empty] | 404-10-621803-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Village-Kamaruddin Nagar(Relocation of 14346) | Mr. Satish Kumar S/O Sh. Daya Kishan,House number - 57 & 57-A,Old number - 58,Khasra number - 13/24, & 23/2,Adhyapak Nagar,K-Block, Nagloi,Post Office - Nagloi,Police Station - Nagloi,New Delhi - 110041 | 21737 | 21737 | 21737 | 21737 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9789 | Relocation | Sharing | RTT | 15 | 7 | 0/120/220 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6707 | 77.0585 | SR-DL000149 | 2021-07-12 | 2021-08-11 | 2021-09-07 | 111-2867-06770585 | 2021-10-27 | 2021-10-28 |  |  |  |  | 2021-10-23 | 2021-10-29 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 |  |  |  | 2021-08-28 | ST202108496358 | S20210028670 |  |  | 2021-09-08 | P/FVC/DEL/1039409/2021 | 2021-11-01 | 2021-11-02 | DL/01/5370/4310/0031/03/01/10266/NS/02112021 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-14 | 2021-11-02 | 2021-11-18 | 2021-11-02 | 2021-11-07 | 2021-11-27 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1272 | [17 empty] | 404-10-621737-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU RRU2219B0A RRU 4418 Available on Parenet Site, new 2279 RRU to be Send on site for FD+L_2100
Del | FY20_21 | Q3 | Floridaa Appartment, sec 82, Faridabad | Mr. Rajkumar S/O Mahender,Handbast No. 115, Village Bhatola, Badoli (116), Baroli, Sector 82,Post Office - Sector 82,Police Station,Tehsil and District Faridabad-121004 | 21733 | 21733 | 21733 | 21733 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3042643 | New | New_Built | GBM | 30 | 0 | 0/80/280 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.3933 | 77.3527 | R/NN-629777 | 2021-09-21 | 2021-09-23 | 2021-09-28 | 11106-2839-33773526 | 2021-10-27 | 2021-10-28 | 2021-10-28 | 2021-11-10 |  |  | 2021-10-22 | 2021-11-12 | 2021-11-14 | 2021-11-15 | 2021-11-15 | 2021-11-16 |  |  |  | 2021-10-04 | ST202110547601 | S20210030891 |  |  | 2021-10-08 | P/FVC/DEL/1043087/2021 | 2021-11-20 | 2021-11-21 | DL/02/5177/5049/0031/03/01/10284/NS/21112021 | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2021-11-29 | 2021-11-22 | 2021-11-24 | 2021-11-22 | 2021-12-02 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15195 | [5 empty] | 2021-10-28 | 2021-11-20 | MW Mount req at Farend,Issue closed on 10.11.21,Installed_LOS Issue-On DG not started_Media Issue as on 16.11.21,Farend shifting pending/farend changed/Nearend installed-ON DG/Media Issue as on 17.11.21,Issue closed on 20.11.21 | [9 empty] | 404-10-621733-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Kasa Isles | Ashwani S/O Lt. Ram Pyare,Property No-30,Garhi Mendu,Bhajanpura, Delhi 110093 | 21590 | 21590 | 21590 | 21590 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPL023 | New | New_Built | RTP | 6 | 16 | 10/110/210 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7006 | 77.258 | 21590 | 2021-05-15 | 2021-06-02 | 2021-06-14 | 111-2870-06772579 | 2021-11-13 | 2021-11-13 |  |  |  |  | 2021-11-10 | 2021-11-13 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  |  | 2021-06-16 | ST202106346573 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034041/2021 | 2021-11-25 | 2021-11-25 | DL/01/5414/0002/0031/03/01/10300/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-10 | 2021-11-25 | 2021-11-29 | 2021-11-25 | 2021-12-04 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8183 | [5 empty] | 2021-11-16 | 2021-11-25 | Partial Installed_Power Issue- Infra team req for BB(mains close by 20),Issue closed on 25.11.21 | [9 empty] | 404-10-621590-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Sector-55,Faridabad | Faridabad Authority,MBTS Location,In Front of Hno.398/55, Sector 55,P.S. Sector 55,P.O. Sector 55, Faridabad, Haryana 121004 | 19724 | 19724 | 19724 | 19724 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | NIBAR CREATIONS | NI_19724_DEL | New | New_Built | RTT | 12 | 10 | 0/50/290 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3415 | 77.2942 | 19724 | 2021-05-18 | 2021-06-17 | 2021-06-21 | 11106-2834-15772942 | 2021-10-31 | 2021-11-01 | 2021-11-01 | 2021-11-17 |  |  | 2021-10-26 | 2021-11-19 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-24 |  |  |  | 2021-06-26 | ST202106362828 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034602/2021 | 2021-11-24 | 2021-11-25 | DL/02/9035/0004/0031/03/01/10296/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-12 | 2021-11-25 | 2021-12-03 | 2021-11-25 | 2021-12-04 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5548 | [5 empty] | 2021-11-01 | 2021-11-22 | Survey rejected; Pole mounts, Mains supply & Fall arrester not available, Monkey Issue,Infra pending-Tower tilted,GSM and MW pole mount req-,OD pad/Power issue-BB delivered, Signage board , tower not earth as on 22.11.21,Partial Installed_Link Done & Power Issue-ON DG down/tower not earth signage board req. as on 23.11.21 | [9 empty] | 404-10-619724-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Mauja Unchagaon Arya Nagar, Faridabad | Mr.Sunder S/O Mr.Leelu,House Number - 311,Killa Number - 5/1, 5/2,Village Unchagaon Arya Nagar,Police Station - Adarsh Nagar,Post Office - Arya Nagar,Ballabhgarh, District Faridabad-121004 | 21889 | 21889 | 21889 | 21889 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032263 | New | New_Built | RTP | 9 | 14 | 40/130/230 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.3306 | 77.3387 | R/NN-628344 | 2021-09-03 | 2021-09-13 | 2021-09-17 | 11106-2833-06773386 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-08 |  |  | 2021-10-28 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-10 | 2021-11-11 |  |  |  | 2021-09-23 | ST202109528784 | S20210030186 |  |  | 2021-09-27 | P/FVC/DEL/1042236/2021 | 2021-11-16 | 2021-11-17 | DL/02/5177/5045/0031/03/01/10275/NS/17112021 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-19 | 2021-11-17 | 2021-11-23 | 2021-11-17 | 2021-11-30 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4101 | [5 empty] | 2021-11-02 | 2021-11-15 | Pole Mount required at Farend,Issue closed on 8.11.21,Installed_Link Done-Media not provisioned,Issue closed on 15.11.21 | [9 empty] | 404-10-621889-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Omaxe World Street | Mr. Vipin Bisht (Manager).(Tea Bar) Shop Number - SCO 22, Terice,Omaxe World Street Sec -79,Police Station - BPTP Faridabad,Post Office - Sector 15,Faridabad,Haryana-121004 | 21704 | 21704 | 21704 | 21704 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/FRD/AT/8902 | New | New_Built | RTP | 9 | 14 | 60/130/300 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.3871 | 77.3547 | T21DL02684 | 2021-09-06 | 2021-09-24 | 2021-10-03 | 11106-2838-68773525 | 2021-11-08 | 2021-11-09 |  |  |  |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 2021-11-11 | 2021-11-11 | 2021-11-13 |  |  |  | 2021-10-06 | ST202110551396 | S20210031109 |  |  | 2021-10-22 | P/FVC/DEL/1043891/2021 | 2021-11-16 | 2021-11-17 | DL/02/5126/0204/0031/03/01/10276/NS/17112021 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-19 | 2021-11-18 | 2021-11-23 | 2021-11-18 | 2021-11-23 | 2021-11-27 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4527 | [5 empty] | 2021-11-13 | 2021-11-15 | Installed_Link Done-Media not provisioned,Issue closed on 15.11.21 | [9 empty] | 404-10-621704-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | DLF Phase 4,Gurgaon(Relocation of 23313) | Mrs. Jyoti ,House number - B-63, Phase - 1, Sushant Lok,Post Office - Sushant Lok,Police Station - Sushant Lok,Gurugram Haryana - 122009 | 21751 | 21751 | 21751 | 21751 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21751_DEL | Relocation | New_Built | GBM | 30 | 0 | 50/150270 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4655 | 77.0799 | 21751 | 2021-06-29 | 2021-07-21 | 2021-07-26 | 11106-2846-51770799 | 2021-11-08 | 2021-11-09 |  |  |  |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 2021-11-11 | 2021-11-11 | 2021-11-12 |  |  |  | 2021-08-03 | ST202108406432 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037556/2021 | 2021-11-23 | 2021-11-24 | DL/05/0031/0584/0031/03/01/10292/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-12-12 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-12-04 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4744 | [5 empty] | 2021-11-12 | 2021-11-23 | Installed/LOS Issue/Farend to be change-Mains issue,Installed_Power Issue_Plan after Vijay Confirmation as on 15.11.21,Issue closed on 23.11.21 | [9 empty] | 404-10-621751-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | indra enclave govindpuram GZB | Mrs. Prabha chauhan W/O Mr. Rajbeer Chauhan, Plot No. 33-34, Khasra no. 1359/1, Neelmani colony, Arthala, Mohan nagar post office, Mohan nagar police station, Ghaziabad, Uttar Pradesh-201007 | 21123 | 21123 | 21123 | 21123 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3008986 | New | New_Built | RTP | 12 | 12 | 60/120/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6802 | 77.397 | R/NN-626309 | 2021-07-25 | 2021-07-30 | 2021-07-30 | 11109-2868-02773970 | 2021-11-08 | 2021-11-09 | 2021-11-09 | 2021-11-11 |  |  | 2021-11-08 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-13 | 2021-11-15 |  |  |  | 2021-07-26 | ST202107397129 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036566/2021 | 2021-11-26 | 2021-11-26 | DL/04/5177/0787/0031/03/01/10301/NS/26112021 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-12-11 | 2021-11-26 | 2021-12-03 | 2021-11-26 | 2021-12-02 | 2021-12-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9722 | [5 empty] | 2021-11-09 | 2021-11-25 | MW Pole Req at Farend,Installed_Power Issue_2G Media Issue as on 15.11.21,Issue closed on 25.11.21 | [9 empty] | 404-10-621123-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Baljeet Nagar | T-1179,Gali No. 21B, Baljeet Nagar, New Delhi-110008 | 27128 | 27128 | 27128 | 27128 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-167 | New | New_Built | RTP | 9 | 16 | 40/120/220 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6579 | 77.1587 | 27128 | 2020-12-04 | 2021-02-26 | 2021-03-08 | 111-2865-78771587 | 2021-11-13 | 2021-11-13 | 2021-11-13 |  |  |  | 2021-11-15 | [8 empty] | 2021-03-13 | ST202103089552 | S20210004658 |  |  | 2021-07-08 | P/FVC/DEL/1033711/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Survey hold due to Public Issue | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 4713 | [5 empty] | 2021-11-13 |  | Survey hold due to Public Issue | [14 empty] | Survey hold due to Public Issue | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | IGL Pump | Delhi Development Authority , ( DDA) Park, infront of House Number = DB-6A, Kanhaiya Ji Marg, Block DB, Maya Enclave, Hari Nagar, Post Office - Hari Nagar,Police Station - Hari Nagar,New Delhi-110027 | 19753 | 19753 | 19753 | 19753 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1973501 | New | New_Built | GBM | 30 | 0 | 20/120/180 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6212 | 77.1072 | R/NN-618671 | 2021-04-29 | 2021-07-02 | 2021-07-19 | 111-2862-12771072 | 2021-10-27 | 2021-10-28 |  |  |  |  | 2021-10-26 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 |  |  |  | 2021-07-27 | ST202107398493 | S20210013822 |  |  | 2021-08-04 | P/FVC/DEL/1036781/2021 | 2021-11-01 | 2021-11-02 | DL/01/5177/6415/0031/03/01/10267/NS/02112021 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-13 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2022-01-17 | 2022-01-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 884 | [5 empty] | 2021-11-01 | 2021-11-02 | Power Issue |  | 2021-11-03 | 2021-12-29 | Power Issue | [5 empty] | 404-10-619753-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Maruti Kunj | Ram Bhateri 26/22, Khatauni no. 28 is situated at Village-Bhondsi, Tehsil-Sohna and District-Gurugram-122102 | 21142 | 21142 | 21142 | 21142 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/AT/8660 | New | New_Built | GBM | 30 | 0 | 60/200/310 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.3657 | 77.0677 | T20DL05068 | 2020-10-15 | 2020-11-19 | 2021-03-31 | 11106-2836-57770676 | 2021-10-27 | 2021-10-28 |  |  |  |  | 2021-10-25 | 2021-10-29 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-02 |  |  |  | 2021-03-26 | ST202103107520 | S20210005562 |  |  | 2021-06-14 | P/FBC/DEL/1031311/2021 | 2021-11-13 | 2021-11-13 | DL/05/5126/0289/0031/03/01/10272/NS/13112021 | 2021-11-13 | 2021-11-13 | 2021-11-13 | 2021-11-13 | 2021-11-13 | 2021-11-14 | 2021-11-13 | 2021-11-24 | 2021-11-13 | 2021-11-23 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11100 | [5 empty] | 2021-11-02 | 2021-11-12 | Installed_Media Issue as on 2.11.21,Issue resolved on 12.11.21 | [9 empty] | 404-10-621142-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | EMCD_4_DDA PARK MAYURVIHAR-1N DELHI | Government Land,EDMC Park,GBM Location,Near House Number- 96-B ,Opposite Electric Pole Number 408,And Near Sadbhawna Apartment Paket-4,Mayur Vihar, Phase-I, Police Station - Himmatpuri,Post Office - Mayur Vihar Phase- 1,New Delhi - 110093 | 13082 | 13082 | 13082 | 13082 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVI | VIDLMAY0800 | New | Sharing | GBM | 30 | 0 | 50/150/260 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.6023 | 77.2918 | 13082 | 2021-08-27 | 2021-09-27 | 2021-10-14 | 111-2860-22772917 | 2021-11-13 | 2021-11-13 |  |  |  |  | 2021-11-10 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-15 | 2021-11-16 |  |  |  | 2020-09-23 | ST202009086441 | S20200004981 |  |  | 2020-10-01 | P/FVC/DEL/1007197/2020 | 2021-11-19 | 2021-11-20 | DL/01/5113/0224/0031/03/01/10281/NS/20112021 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-12-10 | 2021-11-20 | 2021-11-23 | 2021-11-20 | 2021-11-23 | 2021-12-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 645 | [7 empty] | Installed_Freq | [9 empty] | 404-10-613082-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | VILL KULESRA | Mrs.Sumitra Upadhya W/o Mr.Ajay Kumar Upadhya,(Saraswati Public School)H.No 5,Gali No. 1,Near M.S Public School,F Block,Sanjay Vihar,Kuleshra,Greater Noida,Uttar Pradesh,201306 | 21418 | 21418 | 21418 | 21418 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPL031 | New | New_Built | RTP | 6 | 16 | 0/120/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5223 | 77.443 | 21418 | 2021-05-13 | 2021-06-02 | 2021-06-14 | 11109-2852-23774429 | 2021-11-13 | 2021-11-13 |  |  |  |  | 2021-11-10 | 2021-11-13 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-18 |  |  |  | 2021-06-16 | ST202106346575 | S20210011619 |  |  | 2021-07-10 | P/FVC/DEL/1034036/2021 | 2021-11-25 | 2021-11-25 | DL/03/5414/0004/0031/03/01/10299/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-10 | 2021-11-25 | 2021-11-29 | 2021-11-25 | 2021-12-02 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19970 | [5 empty] | 2021-11-16 | 2021-11-25 | Partial Installed_Power Issue- Infra team req for BB(mains close by 17),Installed_2G Media Issue & Mains not available as on 18.11.21,Issue closed on 25.11.21 | [9 empty] | 404-10-621418-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Vill-Dhankot , gurgaon | Mr. Raj Singh S/O Sh. Kohar Singh,Khewat number - 450/397,Village Dhankot,Near Basai Rail Overbridge,Sector 88 Gurgaon,Post Office - Basai Road Near Pataudi Road,Police Station - Scetor 9 Gurgaon,Haryana 122505 | 21873 | 21873 | 21873 | 21873 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVI | RJHAZGN0439 | New | Sharing | GBT | 30 | 0 | 40/180/310 | SHARING |  | SHARING | YES | >18HRS | NO | 28.4548 | 76.9625 | 21873 | 2021-09-06 | 2021-10-07 | 2021-10-11 | 11106-2845-47769625 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-17 |  |  | 2021-10-28 | 2021-11-19 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  |  | 2021-10-14 | ST202110559960 | S20210031636 |  |  | 2021-10-28 | P/FVC/DEL/1044057/2021 | 2021-12-18 | 2021-12-19 | DL/05/5113/0078/0031/03/01/10333/NS/19122021 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-24 | 2021-12-19 | 2021-12-22 | 2021-12-19 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4545 | [5 empty] | 2021-11-02 | 2021-12-18 | TND awaited,Issue Closed on 17.11.21,Installed_Farend Access issue(4545) as on 23.11.21,Issue closed on 17.12.21 and Media Issue reported on 17.12.21,Installed_Link Done & 2G Media Issue,Issue closed on 18.12.21 | [9 empty] | 404-10-621873-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | OFFICER CITY, P-Block | Mr. Puneet Tyagi(Director),Shivika Estates Pvt Ltd,Tower No. P,Officer City-1, City, Raj Nagar Extension, Ghaziabad, Uttar Pradesh 201003 | 21477 | 21477 | 21477 | 21477 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL-DEL-814 | New | New_Built | RTP | 6 | 43 | 30/150/210 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.702 | 77.4243 | 21477 | 2021-05-20 | 2021-05-21 | 2021-05-26 | 11109-2870-19774243 | 2021-11-13 | 2021-11-13 | 2022-03-03 |  |  |  | 2021-11-15 | 2022-03-03 | 2022-03-06 | [6 empty] | 2021-03-24 | ST202103102277 | S20210005329 |  |  | 2021-04-10 | P/FVC/DEL/1021522/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 07.03.22 | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 8010 | [5 empty] | 2021-11-17 |  | Farend Locator Inactive,Installation Plan(Revise TND required from 8010,23409 Access Not avl),SRN Done on 20.01.22,Installed_MW Pending(Revise TND required from 8010,23409 Farend access Not avl)_SRN Done on 20.01.22,Issue closed on 03.03.22,Material return on 07.03.22 | [14 empty] | Material return on 07.03.22 | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Wazidpur(Relocation of 7940) | Mr. Ankur Yadav S/o Mr. Balesh Yadav,House Number - 74,Near By Pradhan market,Village Hazratpur,Wajidpur,Police Station - Phase 3,Post Office - Chajjarsi ,Noida,Uttar Pradesh-201301 | 21854 | 21854 | 21854 | 21854 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032786 | Relocation | New_Built | RTP | 9 | 16.5 | 0/130/270 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6223 | 77.3766 | R/NN-628395 | 2021-09-03 | 2021-09-30 | 2021-10-16 | 11109-2862-22773766 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-03 |  |  | 2021-10-28 | 2021-11-07 | 2021-11-07 | 2021-11-08 | 2021-11-08 | 2021-11-09 |  |  |  | 2021-10-16 | ST202110561377 | S20210031698 |  |  | 2021-10-28 | P/FVC/DEL/1044031/2021 | 2021-11-17 | 2021-11-18 | DL/03/5177/0915/0031/03/01/10278/NS/18112021 | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-24 | 2021-11-18 | 2021-11-22 | 2021-11-18 | 2021-11-24 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1310 | [5 empty] | 2021-11-02 | 2021-11-15 | Technology deviation found b/w New and Parent site (TDD_TB),Issue closed on 3.11.21,Partial Installed_GSM mount lose,Power Issue & 3 MCB req,Partial Installed_Farend loggin Issue as on 08.11.21,Installed_2G Media Issue,Issue closed on 15.11.21 | [9 empty] | 404-10-621854-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q3 | Sadarpur, Ghaziabad | Mr. Styaveer Singh & Mr. Mangal Singh S/o Mr. Ajit Singh, Khasra Number 691, Village Sadarpur, Backside Of IGL Pump, Police Station Madhuban Bapudham, Post Office Sadarpur, Bapudham, Ghaziabad,Uttar Pradesh - 201001. | 19784 | 19784 | 19784 | 19784 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/8937 | New | New_Built | GBM | 30 | 0 | 340/120/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7051 | 77.4911 | T21DL02843 | 2021-09-06 | 2021-09-24 | 2021-10-03 | 11109-2870-51774910 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-19 |  |  | 2021-10-28 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  |  | 2021-10-04 | ST202110547602 | S20210030891 |  |  | 2021-10-08 | P/FVC/DEL/1043090/2021 | 2021-11-24 | 2021-11-25 | DL/04/5126/0259/0031/03/01/10295/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-10 | 2021-11-25 | 2021-12-03 | 2021-11-25 | 2021-12-04 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4087 | [5 empty] | 2021-11-02 | 2021-11-23 | Access available after Diwali; Owner not avl at home,Nearend Closed on 10.11.21,Material return due to Public Issue_13.11.21,Issue closed on 19.11.21,assembled/Infra issue-tower strengthening req as on 23.11.21,Installated/MW power cable short/Farend Installed-MDU Required | [9 empty] | 404-10-619784-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Maruti suzuki | Mr. Ankush,Plot Number- 7, Blackberry Sector-8,Police Station - Sector 8,Post Office - Bhangrola,IMT Manesar, Gurgaon,Haryana 122051 | 21698 | 21698 | 21698 | 21698 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-GRGN-192 | New | New_Built | RTP | 6 | 20 | 0/90/200/270 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.3699 | 76.8958 | 21698 | 2021-02-25 | 2021-09-06 | 2021-09-06 | 11106-2836-98768958 | 2021-11-02 | 2021-11-02 |  |  |  |  | 2021-10-29 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-08 | 2021-11-09 |  |  |  | 2021-09-09 | ST202109513821 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040670/2021 | 2021-11-13 | 2021-11-15 | DL/05/0031/0578/0031/03/01/10274/NS/15112021 | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2021-11-17 | 2021-11-15 | 2021-11-24 | 2021-11-15 | 2021-11-23 | 2021-12-04 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 16205 | [5 empty] | 2021-11-09 | 2021-11-13 | Installed_2G Media Issue,Issue resolved on 13.11.21 | [9 empty] | 404-10-621698-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Sec 70,Gurgaon(Relocation of 10844) | Mr.Monu Yadav S/O Mr.Bodan Ram, House Number - 172,Near Gaon Wala Kuan,Village Palra,Badshahpur,Police Station - Badshahpur,Post Office - Palra,Gurgaon,Haryana-122101 | 19264 | 19264 | 19264 | 19264 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19264_DEL | Relocation | New_Built | RTP | 9 | 13 | 330/120/240 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.3783 | 77.0221 | 19264 | 2019-02-06 | 2021-09-17 | 2021-09-24 | 11106-2837-82770220 | 2021-11-02 | 2021-11-03 |  |  |  |  | 2021-11-03 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 |  |  |  | 2021-09-24 | ST202109531879 | S20210030334 |  |  | 2021-09-28 | P/FVC/DEL/1042299/2021 | 2021-11-19 | 2021-11-20 | DL/05/0031/0581/0031/03/01/10280/NS/20112021 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-29 | 2021-11-20 | 2021-11-23 | 2021-11-20 | 2021-12-03 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1962 | [5 empty] | 2021-11-08 | 2021-11-18 | Partial Installed_Cable tray req & mains not connected as on 08.11.21,Installed_Link fine tune Pending/Stop by nagar nigam & Power issue as on 10.11.21,Clearance received on 18.11.21,Installed_BBU Faulty as on 18.11.21 | [9 empty] | 404-10-619264-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q3 | DDA ,SHANTINIKETAN | South Delhi Municipal Corporation(SDMC),MBTS Location In Front of H no.33/11,Rd Number 3, Sector 2, Shanti Niketan, New Delhi, Delhi 110021 | 13057 | 13057 | 13057 | 13057 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1901036 | New | New_Built | Cow | 30 | 0 | 0/70/180 | COW |  | SHARING | YES | >18HRS | NO | 28.5774 | 77.1701 | R/NN-570029 | 2021-04-07 | 2021-04-16 | 2021-04-26 | 111-2857-74771701 | 2021-10-27 | 2021-10-28 | 2021-10-28 | 2021-11-08 |  |  | 2021-10-17 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-10 | 2021-11-12 |  |  |  | 2021-04-27 | ST202104194584 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028815/2021 | 2021-11-17 | 2021-11-18 | DL/01/5177/6430/0031/03/01/10279/NS/18112021 | 2021-11-18 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2021-12-25 | 2021-12-17 | 2021-12-23 | 2021-12-17 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 962 | [5 empty] | 2021-10-28 | 2021-12-16 | Survey done; Material required after 06th-Nov-21 due to public issue at site,Issue closed on 8.11.21,Partial Installed_Cable tray,Mains Issue,signage board, dg not available as on 11.10.21,Integration WIP_Temp Power as on 13.11.21,Power Issue closed on 16.11.21,Lat Long drift_57 Mtr as on 18.11.21,Lat Long drift_57 Mtr(SACFA Need to reapply),Approval received on 16.12.21(2G+FD+TD & L2100 Pending) | [9 empty] | 404-10-613057-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Village Maycha Tehsil Dadri | Mr. Harsh Bhati S/O Kiranpal,House Number - 101,Gram Panchayat,Village Maycha,Greater Noida,Post Office - Dadri,Police Station - Dadri,Uttar Pradesh 203202 | 21918 | 21918 | 21918 | 21918 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3030256 | New | New_Built | GBM | 30 | 0 | 0/60/180 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4456 | 77.6023 | R/NN-628167 | 2021-08-31 | 2021-09-14 | 2021-10-01 | 11109-2844-56776022 | 2021-11-08 | 2021-11-09 | 2021-11-09 | 2021-11-11 |  |  | 2021-11-08 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-13 | 2021-11-23 |  |  |  | 2021-10-04 | ST202110547616 | S20210030891 |  |  | 2021-10-08 | P/FVC/DEL/1043088/2021 | 2021-11-23 | 2021-11-24 | DL/03/5177/0916/0031/03/01/10285/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-12-01 | 2021-11-24 | 2021-12-02 | 2021-11-24 | 2021-11-30 | 2021-12-02 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4474 | [5 empty] | 2021-11-09 | 2021-11-23 | Partial Installed_Public issue/MW pending-DG faulty & Farend Owner Issue as on 15.11.21,Issue closed on 23.11.21 | [9 empty] | 404-10-621918-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | Sec-117 Noida | Mr. Prakash Yadav S/o Richpal,Plot no. 5 Vill-Sorkha, Backside of Sri Ram Apartment,Police Station - Sector 49 Noida, Post Office - Sector 122 Noida ,Noida, Uttar Pradesh-201304. | 21937 | 21937 | 21937 | 21937 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVI | RJUPZNO0755 | New | Sharing | GBT | 40 | 0 | 40/150/310 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.5778 | 77.4012 | 21937 | 2021-09-22 | 2021-09-22 | 2021-10-15 | 11109-2857-78774012 | 2021-11-13 | 2021-11-13 |  |  |  |  | 2021-11-10 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-15 | 2021-11-17 |  |  |  | 2021-10-16 | ST202110561371 | S20210031698 |  |  | 2021-10-28 | P/FVC/DEL/1044030/2021 | 2021-11-26 | 2021-11-26 | DL/03/5113/0123/0031/03/01/10303/NS/26112021 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-11-26 | 2021-12-11 | 2021-11-26 | 2021-12-05 | 2021-11-26 | 2021-12-02 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10824 | [5 empty] | 2021-11-16 | 2021-11-25 | Partial installed_Farend Changed_New IP Plan Required,Installed_MW LOS Issue Not clear & Media Issue as on 18.11.21,Installed_Link Fine tune pending & Media Issue as on 20.11.21 | [9 empty] | 404-10-621937-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418
Del | FY20_21 | Q3 | IREO Commercial | IREO Commercial,Near Grand Hyatt,Alahwas,Sec 58, Gurugram,Haryana 122005 | 27759 | 27759 | 27759 | 27759 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | 27759 | New | New_Built | IBS | 0 | 17 | IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4167 | 77.1022 | 27759 | 2021-10-22 | 2021-10-25 | 2021-10-28 | 11106.2841.67771022.CWIP-CL | 2021-10-28 | 2021-10-29 |  |  |  |  | 2021-10-28 | 2021-10-30 | 2021-11-01 | 2021-11-02 | 2021-11-02 | 2021-11-07 | [10 empty] | 2021-11-13 |  |  | 2021-11-13 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-12-05 | 2021-11-24 | 2021-11-30 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15499 | [5 empty] | 2021-11-02 | 2021-11-12 | Partial Installed_Cable routing-Media Not Provisioned & Farend access issue 2.11.21,Media Issue closed on 7th Nov 21,Installed Farend Radio Faulty as on 07.11.21,Delivered on 10.11.21,Installed_Link Done-Media not provisioned,Issue resolved on 12.11.21,Coverage Issue_DAS Issue | [9 empty] | 404-10-627759-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q3 | House of diagnostics LLP | House Of Diagnostics, Plot Number - A-1/4, Prashant Vihar, Near Rohini Court, Delhi - 110085 | 27752 | 27752 | 27752 | 27752 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27752 | New | New_Built | IBS | 0 | 20 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.7108 | 77.1364 | 27752 | 2021-10-25 | 2021-10-28 | 2021-10-31 | 111-2871-07771364 | 2021-10-31 | 2021-11-01 |  |  |  |  | 2021-10-22 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-03 | 2021-11-10 | [10 empty] | 2021-11-11 |  |  | 2021-11-11 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-14 | 2021-11-12 | 2021-11-18 | 2021-11-12 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 555 | [5 empty] | 2021-11-03 | 2021-11-09 | Infra Pending -Power Issue,Cable tray, railing, ladder,Infra Issue closed on 09.11.21 | [9 empty] | 404-10-627752-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q3 | Kamalpur(Relocation of 11659) | Mr. Vikas Chaudhary S/O Sh. Ilam Singh,House Number - B-1384,Khasra Number - 94/23,Gali number - 6,Block - B, Baba Colony,Village Burari,Post Office - Burari,Police Station - Burari, Delhi-110084 | 22045 | 22045 | 22045 | 22045 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1484420 | New | New_Built | RTP | 9 | 16 | 0/120/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7502 | 77.2007 | R/RES-506786 | 2021-10-12 | 2021-10-13 | 2021-10-22 | 111-2875-01772006 | 2021-11-02 | 2021-11-02 | 2021-11-02 |  |  |  | 2021-11-04 | [8 empty] | 2021-10-16 | ST202110561376 | S20210031698 |  |  | 2021-10-28 | P/FVC/DEL/1044036/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; PARSWA Base damaged by Public Issue | Indus | PRI_Without Material |  |  | Indus |  | M1 | 1601 | [5 empty] | 2021-11-02 |  | Survey Rejected; PARSWA Base required | [14 empty] | Survey Rejected; PARSWA Base damaged by Public Issue | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q3 | Koat Goan | Mr.Gajender Choudhary S/o Late Hansraj Singh.House Numner - 72,Koatgaon,Near Koatgaon Phatak,Police Station - Kotwali Ghantaghar,Post Office - Bazaria,Ghazaibad,Uttar Pradesh-201001 | 22025 | 22025 | 22025 | 22025 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3052214 | New | New_Built | RTP | 9 | 11.8 | 40/120/300 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.646 | 77.4386 | R/NN-632754 | 2021-10-01 | 2021-10-14 | 2021-10-20 | 11109-2864-60774386 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-08 |  |  | 2021-11-04 | 2022-02-21 | 2022-02-21 | 2022-02-22 | 2022-02-22 | 2022-02-23 |  |  |  | 2021-10-23 | ST202110568682 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044619/2021 | 2022-03-05 | 2022-03-06 | DL/04/5177/00809/0031/03/01/10419/NS/06032022 | 2022-03-07 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-13 | 2022-03-10 | 2022-03-13 | 2022-03-10 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 25141 | [5 empty] | 2021-11-02 | 2022-03-04 | Farend MW Mount required/SR Required,Issue closed on 8.11.21,Material return due to Public Issue_10.11.21,Night Delivery and Installation required, Request Hold,Issue closed on 21.02.22,Installed_MW LOS Issue/Farend Access Issue_25141 as on 24.02.22,Installed_MW Pole Mount required_25141 as on 03.03.22 | [9 empty] | 404-10-622025-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q3 | HCL | hcl technology a 9 sector 3 Noida | 27758 | 27758 | 27758 | 27758 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27758 | New | New_Built | IBS | 0 | 10 | IBS/IBS/IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5793 | 77.3177 | 27758 | 2021-09-24 | 2021-10-24 | 2021-10-26 | 11109-2857-93773176 | 2021-11-08 | 2021-11-09 | 2021-11-09 | 2021-12-27 |  |  | 2021-11-10 | 2022-01-03 | 2022-01-03 | 2022-01-04 | 2022-01-04 | 2022-01-21 | [10 empty] | 2022-01-21 |  |  | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-25 | 2022-01-22 | 2022-01-25 | 2022-01-22 | 2022-02-04 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9139 | [5 empty] | 2021-11-09 | 2022-01-15 | Survey Rejected; Infra not ready (Only DAS material requested),Issue closed on 27.12.21,Hold due to TDD RRU & 1/2"Feeder,Partial Installed_Infra Issue_BB & smps pending,Mains req,Ladder req mummty to bts ,Base not grouted ,earthing strip not available (Only Material delivery Plan) & Farend M/W Installed as on 04.01.22,Partial Install/ Infra Pending- suddle Pending ,Cable tray req 6 mtr /Farend M/w installed/Das wip as on 06.01.22,Partial Installed_ Infra issue & Material damage approval Pending as on 09.01.22,Partial Installed_Material damage approval received on 10.01.22(IBS/Jumper N(M) to N(M))_MO Punched on 15.01.22(1026099) | [9 empty] | 404-10-627758-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q3 | IIFT MBTS | MBTS near outdoor hanger near food court,BACKSIDE OF HALL NO-7,Pragati Maidan, New Delhi, Delhi 110001 | 27767 | 27767 | 27767 | 27767 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27767 | New | New_Built | Cow | 30 | 0 | 0/70/160/250 | COW |  | COW_SITE | YES | >18HRS | NO | 28.6162 | 77.2448 | 27767 | 2021-11-01 | 2021-11-11 | 2021-11-11 | 111-2861-62772448 | 2021-11-11 | 2021-11-11 |  |  |  |  | 2021-11-09 | 2021-11-12 | 2021-11-12 | 2021-11-13 | 2021-11-13 | 2021-11-13 |  |  |  | 2021-11-12 | ST202111588790 | S20210033218 |  | 2021-11-14 | 2021-12-08 | P/FVC/DEL/1045886/2021 | 2021-11-14 | 2021-11-14 | DL/01/0031/2958/0031/03/01/10273/NS/13112021 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-11-14 | 2021-12-04 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [18 empty] | 404-10-627767-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Mangolpuri X Block | Mr.Lakhi Chand Aggarwal S/O Mr.Onkar Mal Aggarwal,Plot No. J-2/20,Block-J,JJ Colony,Police Station - Mangolpuri,Post Office - Mangolpuri, Mangolpuri, Delhi-110083 | 21823 | 21823 | 21823 | 21823 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016731 | New | New_Built | RTT | 12 | 10 | 0/120/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6974 | 77.085 | R/NN-627086 | 2021-08-09 | 2021-08-29 | 2021-09-05 | 111-2869-73770849 | 2021-11-15 | 2021-11-16 |  |  |  |  | 2021-11-14 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-11-19 |  |  |  | 2021-09-09 | ST202109513805 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040658/2021 | 2021-11-19 | 2021-11-20 | DL/01/5177/6434/0031/03/01/10282/NS/20112021 | 2021-11-20 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-11-24 | 2021-11-21 | 2021-11-24 | 2021-11-21 | 2021-12-04 | 2021-12-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4936 | [17 empty] | 404-10-621823-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SECTOR 39 GURGAON | Mr Rajender,Royal Residency,Plot Number 5,Imperial Court,Opposite Medanat Entry Gate,Sec 39,Police Station - Sector 46,Post Office - South City 1,Gurgaon Haryana-122001 | 21807 | 21807 | 21807 | 21807 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | VELDEL2364354 | New | Sharing | RTP | 6 | 50 | 0/90/270 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4404 | 77.0424 | 13748246 | 2021-09-06 | 2021-09-27 | 2021-10-18 | 11106-2844-04770423 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2022-02-19 |  |  | 2021-11-16 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-02-25 |  |  |  | 2021-10-23 | ST202110568677 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044616/2021 | 2022-02-25 | 2022-02-26 | DL/05/5126/00294/0031/03/01/10411/NS/26022022 | 2022-02-26 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-04 | 2022-02-28 | 2022-03-12 | 2022-03-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 784 | [5 empty] | 2021-11-19 | 2022-02-24 | Site not ready; Survey planned for 20 & 21 Nov-21,Material return on 23.11.21,Material return due to Access Issue_23.11.21_Site Cleared on 15.12.21 MO Punched and again Hold by Sandeep On 15.12.21,Locator Inactive as on 21.02.22,Locator issue resolved on 22.02.22,Partial installed /Farend public issue as on 24.02.22 | [9 empty] | 404-10-621807-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Gagan Vihar Brahampur | Mr.Neeraj Sharma S/O Mr.Vidya Ram Sharma,Plot Number. 85,Khasra Number. 314,House Number. A-442,Gali No. 14,Gagan Vihar,Bhopura,Police Station - Tulasi Niketan,Post Office - Bhopura,Ghaziabad,Uttar Pradesh-201005 | 21313 | 21313 | 21313 | 21313 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-BJUR-ENB-3227 | New | Sharing | RTT | 9 | 16 | 0/120/230 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.703 | 77.3277 | SR-DL000136 | 2021-07-18 | 2021-07-26 | 2021-08-05 | 11109-2870-30773277 | 2021-11-16 | 2021-11-17 | 2021-11-17 | 2021-11-20 |  |  | 2021-11-11 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  |  | 2021-08-03 | ST202108406437 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037560/2021 | 2021-11-23 | 2021-11-24 | DL/04/5370/3773/0031/03/01/10289/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-11-30 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1977 | [5 empty] | 2021-11-17 | 2021-11-20 | Pole Required at Farend/SR Required | [9 empty] | 404-10-621313-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Nai Basti Main Road, Devli, sangam vihar | Khasra No. 409, Khata and Khatauni No. 604, Village Devli,Nai Basti Main Road, Devli, sangam vihar Tehsil Mehrauli, New Delhi-110062 | 21133 | 21133 | 21133 | 21133 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1540966 | New | New_Built | RTP | 9 | 9.5 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5051 | 77.233 | R/NN-559727 | 2020-11-23 | 2020-12-02 | 2020-12-09 | 111-2850-51772330 | 2021-12-07 | 2021-12-07 |  |  |  |  | 2021-12-08 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2021-12-11 |  |  |  | 2020-12-12 | ST202012172412 | S20200009536 |  |  | 2020-12-28 | P/FVC/DEL/1014708/2020 | 2021-12-21 | 2021-12-22 | DL/01/5177/06472/0031/06/05/12842/NS/22122021 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-27 | 2021-12-22 | 2021-12-25 | 2021-12-22 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 712 | [5 empty] | 2021-12-11 | 2021-12-21 | Installed_Farend MW mount req,Issue closed on 13.12.21,Installed/Farend-4578-MW mount issue late close on 14.12.21,Installed_LOS Issue as on 15.12.21,Installed_Farend Access Issue 712 as on 19.12.21,Issue closed on 20.12.21,Installed_Link Done & Media Provioning issue closed on 21.12.21 | [9 empty] | 404-10-621133-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on Parent site
Del | FY20_21 | Q4 | Bahlolpur(Relocation of 20063) | Government Land,Noida Authority,GBM Location,In Front of Pole Number-102,Main, Pusta Rd, Chotpur Colony,Thana Phase 3rd Gautam Budh Colony, Sector 63 A, Noida, Uttar Pradesh 201301 | 21732 | 21732 | 21732 | 21732 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | VIUPZNO0818 | Relocation | Sharing | GBM | 30 | 0 | 10/80/190 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.6271 | 77.3944 | 21732 | 2021-08-27 | 2021-09-27 | 2021-10-16 | 11109-2862-70773943 | 2021-11-16 | 2021-11-17 | 2021-11-17 | 2021-11-20 |  |  | 2021-11-17 | 2021-11-20 | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2021-11-24 |  |  |  | 2021-10-16 | ST202110561372 | S20210031698 |  |  | 2021-10-28 | P/FVC/DEL/1044035/2021 | 2021-11-24 | 2021-11-25 | DL/03/5113/0135/0031/03/01/10297/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-10 | 2021-11-25 | 2021-12-02 | 2021-11-25 | 2021-12-11 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1727 | [5 empty] | 2021-11-17 | 2021-11-24 | Pole Required at Farend/SR Required,Technology deviation found (TTD_TB),Issue closed on 20.11.21,Partial Installed_Media issue as on 23.11.21,Issue closed on 24.11.21 | [9 empty] | 404-10-621732-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | Khayala,Narsing Garden(Relocation of 11441) | Mr. Rishi Nagar S/O Late Sh. Jagdish Nagar,House Number - RZ-97,Khasra Number - 16/22,Village Khyala,Narsingh Garden,Post Office - Village Khyala,Police Station - Village Khyala,New Delhi-110018 | 21851 | 21851 | 21851 | 21851 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3054114 | Relocation | New_Built | RTT | 12 | 11.5 | 0/110/240 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6603 | 77.1019 | R/NN-632972 | 2021-10-09 | 2021-10-14 | 2021-10-26 | 111-2866-02771019 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-20 |  |  | 2021-11-18 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  |  | 2021-09-23 | ST202109528781 | S20210030186 |  |  | 2021-09-27 | P/FVC/DEL/1042235/2021 | 2021-11-23 | 2021-11-24 | DL/01/5177/6439/0031/03/01/10290/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-12-12 | 2021-11-24 | 2021-12-03 | 2021-11-24 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 923 | [5 empty] | 2021-11-19 | 2021-11-20 | Survey Rejected; 03 Pole mounts required | [9 empty] | 404-10-621851-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Adarsh Nagar, Uncha gaon, Ballabhgarh, Faridabad | Mr. Anurag Nagar,Plot number 199,Khasra number 55/2,Rakba 209 Varg Gaj,Adarsh Nagar, Uncha gaon,Tehsil Ballabhgarh,Police Station Adarsh Nagar,Post Office,Ballabgarh Faridabad - 121004 | 20708 | 20708 | 20708 | 20708 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nettel | NE_20708_DEL | New | New_Built | RTP | 9 | 14 | 40/150/240 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3235 | 77.3198 | 20708 | 2021-05-15 | 2021-06-02 | 2021-07-08 | 11106-2832-35773197 | 2021-11-18 | 2021-11-19 | 2022-01-15 | 2022-01-17 |  |  | 2021-11-16 | 2022-01-17 | 2022-01-17 | 2022-01-18 | 2022-01-18 | 2022-03-12 |  |  |  | 2021-07-13 | ST202107382773 | S20210013039 |  |  | 2021-07-17 | P/FVC/DEL/1035697/2021 | 2022-03-13 | 2022-03-14 | DL/02/0031/00272/0031/03/01/10442/NS/14032022 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-04-17 | 2022-03-14 | 2022-03-15 | 2022-03-14 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 5679 | [5 empty] | 2021-11-19 | 2022-03-13 | Hold due to MINI-LINK 6363 23/02L stuck in reserved IUT,Public Issue as On 24.11.21,Issue closed on 15.01.22,Public issue_Material delivered on Ground Floor as on 18.01.22,Installed_RET faulty as on 12.03.22,Power Cut on 13.03.22 | [9 empty] | 404-10-620708-11 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SECTOR 14 GURGAON | Mr. Mahavir Singh S/o Sh. Shish Ram House Number-425/14 Sector-14 Police Station-Sector-14 Post Office-Sector-14 Gurugram-122001 | 21881 | 21881 | 21881 | 21881 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | VELDEL2372361 | New | Sharing | RTP | 6 | 15 | 40/140/250 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4761 | 77.0479 | 13748247 | 2021-09-06 | 2021-10-20 | 2021-10-28 | 11106.2847.61770478.CWIP-CL | 2021-11-22 | 2021-11-23 |  |  |  |  | 2021-11-09 | 2021-11-23 | 2021-11-23 | 2021-11-24 | 2021-11-24 | 2021-11-25 |  |  |  | 2021-11-03 | ST202111581274 | S20210032784 |  |  | 2021-11-19 | P/FVC/DEL/1044823/2021 | 2021-11-26 | 2021-11-27 | DL/05/5126/0291/0031/03/01/10304/NS/27112021 | 2021-11-27 | 2021-11-27 | 2021-11-27 | 2021-11-27 | 2021-11-27 | 2021-12-12 | 2021-11-27 | 2021-12-08 | 2021-11-27 | 2021-12-03 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5559 | [5 empty] | 2021-11-24 | 2021-11-25 | Owner Issue | [9 empty] | 404-10-621881-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Shaheen Bagh(Relocation of 5130) | Mr. Nitin S/O Late.Surajpal, House Number - G-56,Block G,Post Office - Sarita Vihar,Police Station - Sarita Vihar ,Shaheen Bagh, Jasola,New Delhi, Delhi 110025 | 19869 | 19869 | 19869 | 19869 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | AM_19869_Del | Relocation | New_Built | RTP | 6 | 18 | 350/60/270 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.5434 | 77.3031 | T21DL02725 | 2021-08-18 | 2021-10-20 | 2021-10-28 | 111-2854-33773031 | 2021-11-27 | 2021-11-28 | 2021-11-28 | 2021-11-30 |  |  | 2021-11-23 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-06 |  |  |  | 2019-12-06 | 2019422143 | 2019422143 |  |  | 2020-03-09 | P/FVC/DEL/5987252/2020 | 2021-12-06 | 2021-12-07 | DL/01/5126/1556/0031/345/04/08648/NS/07122021 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-12 | 2021-12-07 | 2021-12-10 | 2021-12-07 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5875 | [5 empty] | 2021-11-28 | 2021-11-30 | Owner Not avl,Access avl on 30.11.21,Partial Installed-BBU Faulty 5216(SRN kitty)/Farend RFAI not clear-canopy power cable short as on 02.12.21,Installed_BBU Faulty(BBU In Transit_Delivered on 06.12.21) | [9 empty] | 404-10-619869-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | MCF,BASE TENNIS ACADEMY PARK | Government Land,Municipal Corporation of Faridabad(MCF),Sports Complex NIT 3,Near By House No. 3C/255,Opposite ESIC Hospital, Block -C, NIT 3,Police Station - NIT 3,Post office - New Industrial TWP 1,Faridabad, Haryana 121001 | 20311 | 20311 | 20311 | 20311 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032251 | New | New_Built | GBM | 30 | 0 | 80/200/330 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.3956 | 77.2922 | R/NN-628341 | 2021-09-03 | 2021-09-10 | 2021-09-16 | 11106-2839-55772922 | 2021-11-25 | 2021-11-26 | 2021-11-26 | 2021-11-27 |  |  | 2021-11-20 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-03 |  |  |  | 2021-09-18 | ST202109523543 | S20210029898 |  |  | 2021-09-25 | P/FVC/DEL/1042083/2021 | 2021-12-03 | 2021-12-04 | DL/02/5177/5053/0031/03/01/10309/NS/04122021 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-10 | 2021-12-04 | 2021-12-10 | 2021-12-04 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 910 | [5 empty] | 2021-11-26 | 2021-11-27 | Installed_Suspected BBU Faulty | [9 empty] | 404-10-620311-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sec-122, C-Block, Noida | GBM Location Green Bailt Noida Authority,Sector 122 Noida,Front of Prateek laurel Tower No B Noida U.P-201304 | 21682 | 21682 | 21682 | 21682 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1776774 | New | New_Built | GBM | 30 | 0 | 120/180/340 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.5884 | 77.3959 | R/NN-566957 | 2021-02-24 | 2021-03-12 | 2021-03-18 | 11109-2858-84773959 | 2021-11-25 | 2021-11-26 | 2021-11-26 | 2021-11-27 |  |  | 2021-11-27 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-03 |  |  |  | 2021-03-18 | ST202103094624 | S20210004928 |  |  | 2021-08-04 | P/FVC/DEL/1036729/2021 | 2021-12-03 | 2021-12-04 | DL/03/5177/0920/0031/03/01/10311/NS/04122021 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-10 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11466 | [5 empty] | 2021-11-26 | 2021-12-03 | Partial Installed/MW installed-mains not available/ON DG not available,as on 02.12.21 | [9 empty] | 404-10-621682-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Nihal Vihar, Nangloi | Plot no. RZQ-32, khasra no. 34/12, Nihal Vihar, Nangloi, Delhi -110041 | 20006 | 20006 | 20006 | 20006 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20006_DEL | New | New_Built | RTP | 9 | 16 | 30/120/200/300 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6631 | 77.0645 | 20006 | 2019-10-05 | 2020-09-25 | 2020-10-01 | 111.MDEL.2004772 | 2021-11-15 | 2021-11-16 |  |  |  |  | 2021-11-14 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-11-19 |  |  |  | 2019-12-20 | 2019452681 | 2019452681 |  |  | 2020-01-14 | P/FVC/DEL/5944642/2020 | 2021-11-19 | 2021-11-20 | DL/01/0031/2967/0031/03/01/10283/NS/20112021 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-20 | 2021-11-23 | 2021-11-20 | 2021-11-22 | 2021-11-20 | 2021-11-25 | 2021-12-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1272 | [17 empty] | 404-10-620006-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Subhash Colony, Ballabhgarh. Faridabad | Dallu Ram S/o Rajesh Ram,House Number.624,Subhash Colony,Post Office.Ballabhgarh,Police Station.Bllabhgarh, Faridabad Haryana-121004 | 21880 | 21880 | 21880 | 21880 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | VELDEL091524 | New | Sharing | RTP | 9 | 10 | 350/70/200 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.3277 | 77.3148 | T20DL05265 | 2021-09-06 | 2021-10-20 | 2021-10-20 | 11106.2832.76773147.CWIP-CL | 2021-11-18 | 2021-11-19 |  |  |  |  | 2021-11-10 | 2021-11-23 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-27 |  |  |  | 2021-10-23 | ST202110568681 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044618/2021 | 2021-12-01 | 2021-12-02 | DL/02/5126/0124/0031/03/01/10308/NS/02122021 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-12 | 2021-12-02 | 2021-12-10 | 2021-12-02 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4116 | [5 empty] | 2021-11-19 | 2021-12-01 | Hold due to MINI-LINK 6363 23/02L stuck in reserved IUT,Cable tray required for One building to another building,Partial Installed-Link done BBU Faulty & Cable tray Installed_02:39 PM as on 26.11.21,Installed_2G Media Issue as on 29.11.21,Media Issue closed on 01.12.21 | [9 empty] | 404-10-621880-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418
Del | FY20_21 | Q4 | TPDDL(NDPL),Kirti Nagar | BUM – Kirti Nagar Zone-1301+1303, H-Block,Kirti Nagar,Moti Nagar,Delhi | 28582 | 28582 | 28582 | 28582 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_28582_DEL | New | New_Built | IBS | 0 | 11 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6152 | 77.1426 | 28582 | 2020-09-29 | 2020-10-09 | 2020-10-09 | 111-MDEL-1927676 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-09 |  |  | 2021-11-26 | 2021-12-10 | 2021-12-15 | 2021-12-16 | 2021-12-16 | 2021-12-17 | [10 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2021-12-24 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11290 | [5 empty] | 2021-12-02 | 2021-12-17 | LOS Blocked_907,Issue closed on 09.12.21,Locator Inactive resolved on 12.12.21,Partial Installed_Power Issue Infra Team req & Signage board & POP team req. as on 16.12.21 | [9 empty] | 404-10-628582-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Amarpali Zodiac 1(Relocation of 23640) | Mr. Ved Prakash,khasra no.44,Near by FNG expressway service road,Infront of Amrapali Zodiac, Village Sarfabad, Noida U.P.-201301 | 25048 | 25048 | 25048 | 25048 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL44 | Relocation | New_Built | GBM | 30 | 0 | 30/140/320 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5832 | 77.3967 | 25048 | 2021-01-11 | 2021-03-16 | 2021-03-19 | 11109-2858-31773966 | 2021-11-16 | 2021-11-17 | 2021-11-17 |  |  |  | 2021-11-18 | [8 empty] | 2021-03-18 | ST202103094626 | S20210004928 |  |  | 2021-08-04 | P/FVC/DEL/1036721/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Mains or DG supply not availble | 3rd Party PRI | PRI_Without Material |  |  | Indus |  | M1 | 25161 | [5 empty] | 2021-11-17 |  | Survey Rejected; Mains or DG supply not availble | [14 empty] | Survey Rejected; Mains or DG supply not availble | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | Vishnu Colony | Dharamvir S/O Murari Lal,Khasra Number - 668,Vishnu Colony,Post Office - Ballabhgarh,Police Station - Ballbhgarh,Faridabad, Haryana-121004 | 21809 | 21809 | 21809 | 21809 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | RJHAZBG0204 | New | Sharing | GBT | 30 | 0 | 140/210/300 | SHARING |  | 3RD_PARTY | YES | >18HRS | NO | 28.3291 | 77.32 | 21809 | 2021-08-09 | 2021-10-07 | 2021-10-11 | 11106-2832-90773199 | 2021-11-16 | 2021-11-17 |  |  |  |  | 2021-11-17 | 2021-11-17 | 2021-11-19 | 2021-11-20 | 2021-11-20 | 2021-11-23 |  |  |  | 2021-10-14 | ST202110559959 | S20210031636 |  |  | 2021-10-28 | P/FVC/DEL/1044056/2021 | 2021-11-23 | 2021-11-24 | DL/02/5113/0057/0031/03/01/10287/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-11-29 | 2021-11-24 | 2021-12-04 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4116 | [5 empty] | 2021-11-20 | 2021-11-23 | Partially Installed_Media Issue,Issue closed on 23.11.21 | [9 empty] | 404-10-621809-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | GURU HARKISHAN NAGAR | Plot no-35-B,khasra No-16/14,Matiala Ext,Uttam nagar,Guru harkishan Nagar,Delhi-110059 | 20013 | 20013 | 20013 | 20013 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20013_DEL | New | New_Built | RTP | 6 | 16 | 30/100/170 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6148 | 77.0445 | 20013 | 2019-10-05 | 2020-09-25 | 2020-10-01 | 111-MDEL-2004771 | 2021-11-17 | 2021-11-17 |  |  |  |  | 2021-11-14 | 2021-11-17 | 2021-11-19 | 2021-11-20 | 2021-11-20 | 2021-11-22 |  |  |  | 2019-11-21 | 2019694195 | 2019694195 |  |  | 2019-12-18 | P/FVC/DEL/5911019/2019 | 2021-11-23 | 2021-11-24 | DL/01/0031/2972/0031/03/01/10286/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-12-10 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-12-03 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 803 | [5 empty] | 2021-11-21 | 2021-11-22 | Partial Installed_Mains Not connected,Signage board req_Wrong Media Port Given 1/2/2,Issue closed on 22.11.21 | [9 empty] | 404-10-620013-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Mahagun My-woods 3 | Gaur City-2,Tower-K,11th Avenue,Greater Noida Extension-201009 | 17571 | 17571 | 17571 | 17571 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | VELDEL238347 | New | Sharing | RTP | 6 | 65 | 20/120/220/300 | SHARING |  | SHARING | YES | >18HRS | NO | 28.6189 | 77.4244 | 13737164 | 2021-08-27 | 2021-10-20 | 2021-10-20 | 11109.2861.88774244.CWIP-CL | 2021-11-22 | 2021-11-23 |  |  |  |  | 2021-11-18 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-05 |  |  |  | 2018-06-14 | 2018959362 | 2018959362 |  |  | 2018-07-11 | P/FVC/DEL/4949198/2018 | 2021-12-14 | 2021-12-16 | DL/03/5126/0328/0031/03/01/10330/NS/16122021 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-24 | 2021-12-16 | 2021-12-18 | 2021-12-16 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-11-24 | 2021-12-13 | Material return on 24.11.21,Partial Installed-cable tray req._Media issue as on 02.12.21,Partial installed_Infra Issue-8 mtr Ladder req- Mount to canopy & MEDIA - FTTH as on 03.12.21,Issue closed on 13.12.21 | [9 empty] | 404-10-617571-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector 41, Faridabad | Mr. Riyank(Managaer),NHPC Colony,Tower A8,On the Roof of Flat No. 801 to 804, Sector-41,Post Office - Surajkund,Police Station - Surajkund,Faridabad, Haryana 121010 | 21747 | 21747 | 21747 | 21747 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3047254 | New | New_Built | RTP | 6 | 28 | 80/210/310 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4702 | 77.2899 | R/NN-632116 | 2021-09-28 | 2021-10-23 | 2021-10-28 | 11106.2847.02772899.CWIP-CL | 2021-11-22 | 2021-11-23 |  |  |  |  | 2021-11-20 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-26 |  |  |  | 2021-11-03 | ST202111581276 | S20210032784 |  |  | 2021-11-19 | P/FVC/DEL/1044818/2021 | 2021-11-29 | 2021-11-30 | DL/02/5177/5052/0031/03/01/10306/NS/30112021 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2021-12-11 | 2021-11-30 | 2021-12-05 | 2021-11-30 | 2021-12-11 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4246 | [5 empty] | 2021-11-26 | 2021-11-29 | Partially Installed_12 Jumper Short & Eagle Issue at Farend_4246,Installed_2G Media Issue,Issue Closed on 29.11.21 | [9 empty] | 404-10-621747-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector-63 Noida(Relocation of 7534) | Mayur Dixit(Manager),Plot Number - H-161,Suite Number 4,BSI Building Park,Sector 63,Post Office - Sector 63,Police Station - Sec 62 Noida, Uttar Pradesh 201301 | 21902 | 21902 | 21902 | 21902 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3030185 | Relocation | New_Built | RTP | 9 | 16 | 0/130/220 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6253 | 77.3784 | R/NN-628144 | 2021-08-31 | 2021-09-16 | 2021-10-27 | 11109.2862.52773784.CWIP-CL | 2021-11-22 | 2021-11-23 |  |  |  |  | 2021-11-21 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-26 |  |  |  | 2021-11-10 | ST202111586348 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045111/2021 | 2021-12-09 | 2021-12-10 | DL/03/5177/0922/0031/345/04/08654/NS/10122021 | 2021-12-10 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-22 | 2021-12-15 | 2021-12-18 | 2021-12-15 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2021-11-26 | 2021-12-09 | 1025540(TPT Having Shortage Material),1GSM Faulty Delivered_Partially Installed Media Issue(FMS) as on 26.11.21,Issue closed on 09.12.21 | [9 empty] | 404-10-621902-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available On parent site
Del | FY20_21 | Q4 | DOMESTIC FLIGHT APRON AREA IGI DELHI(TERMINAL-2) | Airport Terminal 2,At Node D 41,Near Vistara Airlines,Police Station - Mahipalpur,Post Office - Krishna Nagar, New Delhi - 110051 | 20720 | 20720 | 20720 | 20720 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3014060 | New | New_Built | RTP | 6 | 7 |  | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5523 | 77.087 | R/NN-626792 | 2021-08-04 | 2021-08-12 | 2021-08-20 | 111-2855-22770870 | 2021-12-07 | 2021-12-08 | 2021-12-08 | 2022-04-08 |  |  | 2021-12-09 | 2022-04-08 | 2022-04-13 | 2022-04-15 | 2022-04-15 | 2022-04-17 |  |  |  | 2021-08-21 | ST202108486033 | S20210028308 |  |  | 2021-09-05 | P/FVC/DEL/1039102/2021 | [17 empty] | PRI_Closed | Integration_Pending | Installed/Link done/Tower earthing pending | Jitender | X | 2022-04-08 | PRI | Indus |  | M1 | 4164 | [5 empty] | 2021-12-08 | 2022-04-21 | Pass Required,Survey Rejected; Mains supply not availble, PARSWA RACK not installaed, SMPS/BB not installed, Earthing work not done yet,Material dispatch Plan on 15.12.21,Material return on 15.12.21,Issue closed on 14.02.22 again Hold by Indus on 15.02.22,Material Dispatch Plan on 13.04.22,Material Dispatch Hold by Indus 08 Apr 22 to 14 Apr 22 & Still Installation Pass & EB Awaited on Sites,Material Delivered with Indus Team on 15.04.22,Partial Installed/Tower earthing not available/Mains power not connected as on 19.04.22,Installed/Link done/Tower earthing pending as on 21.04.22 | [14 empty] | Material Delivered with Indus Team | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | EMCD_West Arjun Nagar | Mr. Satish Chand S/O Jaybhan,H No- 22-A, Old Anarkali, Krishna Nagar, Delhi-110051 | 17804 | 17804 | 17804 | 17804 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1956461 | New | New_Built | RTT | 12 | 13 |  | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6558 | 77.2883 | R/NN-618373 | 2021-04-23 | 2021-05-03 | 2021-05-04 | 111-2865-57772882 | 2021-12-08 | 2021-12-09 |  |  |  |  | 2021-12-10 | 2021-12-09 | 2021-12-10 | [6 empty] | 2021-04-21 | ST202104161245 | S20210007316 |  |  | 2021-07-22 | P/FVC/DEL/1036288/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Access Issue_SRN Done on 10.01.22 | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 667 | [5 empty] | 2021-12-11 |  | Assembled-Access on Monday - Limited access,Material Delivered on 11.12.21,Access Issue_SRN Done on 10.01.22 | [14 empty] | Access Issue_SRN Done on 10.01.22 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector 15,Faridabad(Relocation of 14172) | Municipal Corporation of Faridabad ,GBM Location,Green Belt,In front of Prerna Dham, Opp APJ School,Near Electric Pole No.L/110612060779/66ITIPRERN/DT5219,Sector-15, Faridabad,Haryana 121007 | 21717 | 21717 | 21717 | 21717 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Olympians | OL_21717_Del | Relocation | New_Built | GBM | 30 | 0 | 40/140/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3908 | 77.3219 | 21717 | 2021-03-31 | 2021-04-05 | 2021-04-13 | 11106-2839-08773219 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-20 |  |  | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  |  | 2021-04-08 | ST202104132855 | S20210006373 |  |  | 2021-06-08 | P/FVC/DEL/1028034/2021 | 2021-11-24 | 2021-11-25 | DL/02/0031/0241/0031/03/01/10294/NS/25112021 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-12-10 | 2021-11-25 | 2021-12-08 | 2021-11-25 | 2021-12-05 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4586 | [5 empty] | 2021-11-19 | 2021-11-25 | Mount req at Farend,Installed/Temporary power, Signage board req,/ Farend MW mount req. as on 22.11.21,Installed_Link done & Media Issue-Signage Board req. as on 23.11.21,2G Media closed on 25.11.21 | [9 empty] | 404-10-621717-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector-99 | Noida Green Belt in front of Tower T9, supreme tower, Sec 99 Noida ,Uttar Pradesh 201303 | 16279 | 16279 | 16279 | 16279 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVI | TV_16279_DEL | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5469 | 77.36 | 16279 | 2020-10-01 | 2021-01-12 | 2021-05-01 | 11109-2854-69773599 | 2021-12-08 | 2021-12-09 | 2021-12-09 | 2021-12-17 |  |  | 2021-12-03 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-20 | 2021-12-21 |  |  |  | 2021-04-21 | ST202104161249 | S20210007316 |  |  | 2021-07-22 | P/FVC/DEL/1036289/2021 | 2021-12-21 | 2021-12-22 | DL/03/5113/00136/0031/06/05/12837/NS/22122021 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-31 | 2021-12-22 | 2021-12-25 | 2021-12-22 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1437 | [5 empty] | 2021-12-09 | 2021-12-21 | Survey Rejected; Mains supply not available,Issue Closed on 17.12.21,Partial Installed_Link Done/On DG - 2G Media Issue as on 20.12.21,Issue closed on 21.12.21 | [9 empty] | 404-10-616279-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Tilak Nagar | Government land,South Delhi Municipal Corporation (SDMC )Park,MBTS Location,Near Hosue Number 37,Double Story and Infront of E-Block,Tilak Apartments ,Tilak Nagar,Police Station - Tilak Vihar,Post Office -Tilak Nagar,New Delhi-110018 | 20682 | 20682 | 20682 | 20682 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001968 | New | New_Built | Cow | 30 | 0 | 110/210/310 | COW |  |  | YES | >18HRS | NO | 28.6422 | 77.0854 | R/NN-625341 | 2021-07-05 | 2021-07-13 | 2021-07-15 | 111-2864-21770853 | 2021-11-27 | 2021-11-29 |  |  |  |  | 2021-11-28 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-03 |  |  |  | 2021-07-26 | ST202107397090 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036568/2021 | 2021-12-03 | 2021-12-04 | DL/01/5177/6453/0031/03/01/10310/NS/04122021 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-04 | 2021-12-10 | 2021-12-04 | 2021-12-10 | 2021-12-04 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 908 | [5 empty] | 2021-12-02 | 2021-12-03 | Partial Installed/MW installed-mains not available/ON DG,as on 02.12.21 | [9 empty] | 404-10-620682-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | Navjeevan Vihar(Relocation of 11276) | SOUTH DELHI MUNICIPAL CORPORATION,NEAR H NO-86 & WATER TANK OPP-DHALAO,BEHIND NAVJEEVAN VIHAR MARKET, ADHCHINI VILLAGE South Delhi,Delhi-110017 | 21706 | 21706 | 21706 | 21706 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3009421 | Relocation | New_Built | GBM | 30 | 0 | 0/150/300 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5322 | 77.1998 | R/NN-626352 | 2021-07-27 | 2021-08-12 | 2021-08-18 | 111-2853-21771998 | 2021-11-15 | 2021-11-16 | 2021-11-18 | 2022-01-27 |  |  | 2021-11-17 | 2022-01-28 | 2022-01-30 | 2022-01-31 | 2022-01-31 | 2022-02-01 |  |  |  | 2021-05-10 | ST202105243479 | S20210009050 |  |  | 2021-07-08 | P/FVC/DEL/1033873/2021 | 2022-02-01 | 2022-02-02 | DL/01/5177/06525/0031/06/05/13114/NS/02022022 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-07 | 2022-02-02 | 2022-02-03 | 2022-02-02 | 2022-02-09 | 2022-02-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 919 | [5 empty] | 2021-11-18 | 2022-01-27 | Material return due to Access Issue_18.11.21,Issue closed on 27.01.22 | [9 empty] | 404-10-621706-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | Shahid Nagar 2(Relocation of 23889) | MR. Jamil,House Number - D-484, Block-D, Near Bengali Hotel, Shahid Nagar,Police Station - Shaheed Nagar,Post office - Pasonda,District - Ghaziabad,Uttar Pradesh 201205 | 21990 | 21990 | 21990 | 21990 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1008777 | Relocation | Sharing | RTT | 10 | 11 | 60/220/320 | SHARING |  | SHARING | YES | >18HRS | NO | 28.6823 | 77.3348 | R/RES-505839 | 2021-09-16 | 2021-10-04 | 2021-10-16 | 11109-2868-23773347 | 2021-12-08 | 2021-12-09 | 2021-12-09 | 2021-12-17 |  |  | 2021-12-03 | 2021-12-17 | 2021-12-19 | 2021-12-20 | 2021-12-20 | 2021-12-21 |  |  |  | 2021-10-08 | ST202110554406 | S20210031332 |  |  | 2021-10-22 | P/FVC/DEL/1043931/2021 | 2021-12-21 | 2021-12-22 | DL/04/5177/0703/0031/345/04/08679/NS/22122021 | 2021-12-22 | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-01-13 | 2022-01-12 | 2022-01-15 | 2022-01-12 | 2022-01-17 | 2022-01-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 625 | [5 empty] | 2021-12-09 | 2022-01-12 | Survey rejected; 03 Pole mounts required,Issue closed on 17.12.21,Partial installed_Farend Owner Issue(625) as on 20.12.21,Issue closed on 21.12.21,SGW Issue on 22.12.21,SGW Issue closed on 12.01.22 | [9 empty] | 404-10-621990-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sharadanand Park | Mr. Ashok Kumar S/h. Nem Singh,Plot number B-153, Khasra number - 16/16, Gali number - 8, Swaroop Nagar, Post Office -Swaroop Nagar, Police Station - Burari, Delhi-110042, | 21919 | 21919 | 21919 | 21919 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3043997 | New | New_Built | RTT | 12 | 12 | 0/120/250 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7495 | 77.1571 | R/NN-630151 | 2021-09-22 | 2021-10-11 | 2021-10-16 | 111-2874-95771570 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-20 |  |  | 2021-11-10 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  |  | 2021-10-20 | ST202110564525 | S20210031884 |  |  | 2021-11-13 | P/FVC/DEL/1044433/2021 | 2021-11-23 | 2021-11-24 | DL/01/5177/6440/0031/03/01/10288/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-11-29 | 2021-11-24 | 2021-11-30 | 2021-12-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5621 | [5 empty] | 2021-11-16 | 2021-11-20 | Pole Required at Farend/SR Required | [9 empty] | 404-10-621919-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sonia Vihar | Mrs. Sheela Devi W/O Dharamveer Singh, House Number- E 4/340, Sonia Vihar 4 1/2 Pusta, Police Station - Khajuri Khas, Post Office - Sonia Vihar 3 Pusta, New Delhi-110095 | 21931 | 21931 | 21931 | 21931 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | ID-1011126 | New | Sharing | RTP | 9 | 11.5 | 0/120/240 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.7322 | 77.2508 | 13750431 | 2021-09-22 | 2021-10-20 | 2021-10-20 | 111-2873-22772508 | 2021-11-16 | 2021-11-17 |  |  |  |  | 2021-11-17 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-23 |  |  |  | 2021-10-23 | ST202110568680 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044615/2021 | 2021-11-23 | 2021-11-24 | DL/01/5126/1553/0031/03/01/10291/NS/24112021 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-11-30 | 2021-11-24 | 2021-12-03 | 2021-12-20 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4190 | [7 empty] | Partial Installed_24 Nos Jumper short & Black pwr cable short,Partial Installed-3 nos Jumper damaged_MW pending | [9 empty] | 404-10-621931-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | ALI VIHAR | Mr. Hemraj S/O Mahipal,Plot Number A-692,Aali Vihar, Sarita Vihar, Post Office - Sarita Vihar,Police Station - Sarita Vihar,New Delhi, Delhi 110076 | 21942 | 21942 | 21942 | 21942 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-1729 | New | Sharing | RTT | 12 | 11 | 10/120/200 | SHARING |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.517 | 77.3056 | SR-DL000187 | 2021-10-18 | 2021-10-18 | 2021-10-21 | 111-2851-69773055 | 2021-12-01 | 2021-12-01 |  |  |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-04 | 2021-12-06 |  |  |  | 2021-10-23 | ST202110568683 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044620/2021 | 2021-12-09 | 2021-12-10 | DL/01/5370/2360/0031/345/04/08653/NS/10122021 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-18 | 2021-12-10 | 2021-12-15 | 2021-12-10 | 2021-12-18 | 2021-12-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 139 | [5 empty] | 2021-12-06 | 2021-12-09 | Installed_2G Media Issue,Issue closed on 09.12.21 | [9 empty] | 404-10-621942-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Hanuman Chowk, Qutub Vihar | Mr. Diwan Singh S/o Sh. Bishan Singh ,Khasara Number-23/22 ,PP Number-33 ,Qutub Vihar Phase-2 Block-B, Police Station-Chawla, Post Office-Chawla ,Najafgarh New Delhi-110043 | 21944 | 21944 | 21944 | 21944 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-2928 | New | Sharing | RTT | 15 | 6.8 | 20/80/150 | SHARING |  | SHARING | YES | >18HRS | NO | 28.5704 | 77.0151 | SR-DL000199 | 2021-09-22 | 2021-10-24 | 2021-10-27 | 11109.2865.14774055.CWIP-CL | 2021-12-07 | 2021-12-07 |  |  |  |  | 2021-12-06 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2021-12-11 |  |  |  | 2021-11-10 | ST202111586347 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045139/2021 | 2021-12-11 | 2021-12-13 | DL/01/5370/2573/0031/03/01/10324/NS/13122021 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-21 | 2021-12-13 | 2021-12-16 | 2021-12-13 | 2021-12-24 | 2021-12-24 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 966 | [17 empty] | 404-10-621944-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Jeevan Park | Mr Joginder Singh S/o Sh Narayan Singh, Plot Number - 26-C,Block C,Jivan Park,Uttam Nagar,Police Station - Uttam Nagar,Post Office - Uttam Nagar,New Delhi 110059 | 21946 | 21946 | 21946 | 21946 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-4106 | New | Sharing | RTT | 9 | 15 | 350/180/270 | SHARING |  | SHARING | YES | >18HRS | NO | 28.6192 | 77.0736 | SR-DL000189 | 2021-09-22 | 2021-10-22 | 2021-10-25 | 111-2861-91770735 | 2021-12-01 | 2021-12-01 |  |  |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-04 | 2021-12-06 |  |  |  | 2021-10-27 | ST202110572299 | S20210032268 |  |  | 2021-11-19 | P/FVC/DEL/1044874/2021 | 2021-12-11 | 2021-12-13 | DL/01/5370/3132/0031/06/05/12719/NS/13122021 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-15 | 2021-12-13 | 2021-12-22 | 2021-12-13 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 546 | [5 empty] | 2021-12-06 | 2021-12-11 | Installed_2G Media Issue closed on 11.12.21 | [9 empty] | 404-10-621946-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VILLAGE-ISSA PUR | Mr. Manish Kumar S/O Sh. Surender Singh, House Number-141 ,Chaudhary Mohalla Issapur ,Police Station-Jaffarpur, Post Office-Issapur New Delhi-110073 | 21971 | 21971 | 21971 | 21971 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9099 | New | Sharing | RTT | 12 | 7.7 | 90/190/290 | SHARING |  | SHARING | YES | >18HRS | NO | 28.5781 | 76.8646 | SR-DL000212 | 2021-09-22 | 2021-10-24 | 2021-10-27 | 111-2857-80768646 | 2021-12-07 | 2021-12-07 |  |  |  |  | 2021-12-06 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2021-12-11 |  |  |  | 2021-11-10 | ST202111586346 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045123/2021 | 2021-12-11 | 2021-12-13 | DL/01/5370/2950/0031/345/04/08657/NS/13122021 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-17 | 2021-12-13 | 2021-12-16 | 2021-12-13 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4486 | [5 empty] | 2021-12-10 | 2021-12-11 | Partially Installed_Media Issue as on 10.12.21,Issue closed on 11.12.21 | [9 empty] | 404-10-621971-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Khadda Colony(Relocation of 11705) | Mr. Mumtaj S/O Irshad,House Number - E-664,20 Futta Road,Near Umar Masjid,Jaithpur Extn. Part II,Post Office - Jaithpur,Police Station - Jaithpur,-110044 | 21983 | 21983 | 21983 | 21983 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1283742 | New | Sharing | RTP | 6 | 19 | 10/110/240 | SHARING |  | SHARING | YES | >18HRS | NO | 28.5134 | 77.335 | R/RES-506015 | 2021-09-22 | 2021-10-05 | 2021-10-27 | 111-2851-34773349 | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2021-12-04 |  |  | 2021-11-12 | 2021-12-04 | 2021-12-07 | 2021-12-08 | 2021-12-08 | 2021-12-16 |  |  |  | 2021-10-14 | ST202110559955 | S20210031636 |  |  | 2021-10-28 | P/FVC/DEL/1044050/2021 | 2021-12-16 | 2021-12-17 | DL/01/5177/3561/0031/345/04/08669/NS/17122021 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2021-12-25 | 2021-12-18 | 2021-12-18 | 2021-12-18 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4550 | [5 empty] | 2021-11-23 | 2021-12-13 | Technology deviation and 03 pole mounts required,Issue closed on 30.11.21,TDD_TB and M_MIMO also required at site and for that pole mount and MCB not available at site as on 30.11.21,As Per Indus Clear for Material dispatch on 04.12.21,Delivered/agreement access issue as on 08.12.21,Issue closed on 13.12.21,Limited Access Issue on 14.12.21 & 15.12.21 | [9 empty] | 404-10-621983-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | Fajalpur Gurgaon(Relocation of 5761) | Mr. Balbir Bedi,Khasara Number-11/7/1/1,Village Fazilpur,Police Station - Badshahpur,Post Office - Badshahpur, Jharsa , Gurugram-122018 | 21991 | 21991 | 21991 | 21991 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3043176 | New | New_Built | RTP | 9 | 16.6 | 150/220/340 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4138 | 77.025 | R/NN-629855 | 2021-09-22 | 2021-09-30 | 2021-10-27 | 11106.2841.37770250.CWIP-CL | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2022-01-20 |  |  | 2021-11-20 | 2022-01-20 | 2022-01-20 | 2022-01-21 | 2022-01-21 | 2022-01-22 |  |  |  | 2021-11-10 | ST202111586362 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045114/2021 | 2022-01-22 | 2022-01-23 | DL/05/5177/05316/0031/03/01/10377/NS/23012022 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-29 | 2022-01-23 | 2022-01-25 | 2022-01-23 | 2022-02-04 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4192 | [5 empty] | 2021-11-23 | 2022-01-20 | Pole Mount required at Farend,Work Stopped by Owner as on 26.11.21,SRN Done_19.12.21,Issue closed on 20.01.22 | [9 empty] | 404-10-621991-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available On parent site
Del | FY20_21 | Q4 | Sec 9 Faridabad(Relocation of 15319) | Government Land,Faridabad Authority,GBM Location,In Front of Tuwel Number - 103,Sector 9, Faridabad,Post Office - Sector 8,Police Station - Sector 8,Faridabad, Haryana 121007 | 27745 | 27745 | 27745 | 27745 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Olympians | G/17/F | Relocation | New_Built | GBM | 0 | 27 | 30/120/220/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3798 | 77.3372 | 27745 | 2021-09-21 | 2021-09-24 | 2021-09-24 | 11106-2837-97773371 | 2021-12-01 | 2021-12-02 |  |  |  |  | 2021-11-26 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-08 | 2021-12-11 |  |  |  | 2021-09-29 | ST202109538515 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042814/2021 | 2021-12-15 | 2021-12-16 | DL/02/0031/0244/0031/06/05/12749/NS/16122021 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-23 | 2021-12-16 | 2021-12-18 | 2021-12-16 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15195 | [5 empty] | 2021-12-02 | 2021-12-14 | Hold due to 40 Mtr OFC Not in Stock,Partial Installed_Mains not available/signage board req./tower not earth as on 08.12.21,Issue closed on 09.12.21,Installed_Media Issue as on 11.12.21,Issue closed on 14.12.21 | [9 empty] | 404-10-627745-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | ARTEMIS MEDICARE SERVICES PRIVATE LIMITED | New Building G1 , G2, G3 Artemis Hospital, Sector 51, Gurgaon | 27741 | 27741 | 27741 | 27741 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27741_DEL | New | New_Built | IBS | 0 | 0 | IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4311 | 77.0716 | 27741 | 2021-09-21 | 2021-11-11 | 2021-11-13 | 11106-2843-10770715 | 2021-11-15 | 2021-11-16 |  |  |  |  | 2021-11-14 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-12-13 | [10 empty] | 2021-12-13 |  |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-23 | 2021-12-14 | 2021-12-18 | 2021-12-14 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1689 | [5 empty] | 2021-11-22 | 2021-12-13 | Access after 29th Nov & Installed-BBU Used-Cable routing pending 3000 mtr DAS/Link done as on 22.11.21,Issue Closed on 29.11.21,Partially Installed-3rd Floor Permission Issue as on 09.12.21,approval received on 13.12.21 | [9 empty] | 404-10-627741-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | NEELKANTH DRUGS PVT. LTD. | plot no 153 154 Patparganj industrial area new Delhi 110092 | 27751 | 27751 | 27751 | 27751 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27751 | New | New_Built | IBS | 0 | 0 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.6411 | 77.3124 | 27751 | 2021-10-12 | 2021-11-11 | 2021-11-13 | 111-2864-11773123 | 2021-11-15 | 2021-11-16 |  |  |  |  | 2021-11-14 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-11-21 | [10 empty] | 2021-11-22 |  |  | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2021-11-25 | 2021-11-22 | 2021-11-25 | 2021-11-22 | 2021-11-30 | 2021-12-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1486 | [7 empty] | Installed_Ping ok,DAS WIP 500 mtr | [9 empty] | 404-10-627751-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | PHQ Near Sardar Patel Bhawan(Relocation of 17303) | Police Head Quarter (New Building),Jai Singh Marg, Hanuman Road Area, Connaught Place, New Delhi 110001 | 21070 | 21070 | 21070 | 21070 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | IBUS | UNL_DL_DEL_0011_ | New | New_Built | IBS | 0 | 0 | IBS/IBS/IBS/IBS | PURE_IBS |  | 3RD_PARTY | YES | >18HRS | NO | 28.625 | 77.2121 | 21070 | 2021-08-27 | 2021-10-20 | 2021-11-11 | 111-2862-49772120 | 2021-11-16 | 2021-11-16 |  |  |  |  | 2021-11-14 | 2021-11-17 | 2021-11-17 | 2021-11-18 | 2021-11-18 | 2021-11-21 |  |  |  | 2021-11-15 | ST202111589874 | S20210033274 |  |  | 2021-12-08 | P/FVC/DEL/1045893/2021 | 2021-11-22 |  |  | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-29 | 2021-11-23 | 2021-11-24 | 2021-11-23 | 2021-11-30 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10715 | [5 empty] | 2021-11-21 | 2021-11-22 | Partial installed-BBU Ping Ok/Combining material short-load,Jumper_2G Media Issue/IP Plan required,Issue closed on 22.11.21 | [9 empty] | 404-10-621070-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Orient Craft | Plot No 3, 5 ,Orient Craft , Sector 37,Gurgaon. | 27734 | 27734 | 27734 | 27734 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27734_DEL | New | New_Built | IBS | 0 | 0 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4361 | 77.0092 | 27734 | 2021-08-24 | 2021-11-13 | 2021-11-15 | 11106-2843-60770092 | 2021-11-16 | 2021-11-17 |  |  |  |  | 2021-11-15 | 2021-11-17 | 2021-11-23 | 2021-11-24 | 2021-11-24 | 2021-12-04 | [10 empty] | 2021-12-04 |  |  | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-13 | 2021-12-06 | 2021-12-12 | 2021-12-06 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8186 | [5 empty] | 2021-11-17 | 2021-12-03 | Delay due to CATS Issue,Partial Installed-Link done_Infra pending-Cable tray req with DAS 1000 mtr cable routing,Access avl Sat and Sunday as on 25.11.21,Issue Closed on 29.11.21,Link Done_DAS WIP & Farend Access Issue as on 30.11.21,Installed/Link done/Farend Access issue as on 02.12.21,Issue closed on 03.12.21 | [9 empty] | 404-10-627734-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q4 | Harsh Vihar | Mr. Anita w/o sunil kumar,Khasara No- 25/25,At - Budh Bazar Chowk,Village - Mandoli,Budh Vihar,Police Station - Mandoli, Post Office - Mandoli, Delhi-110093 | 21928 | 21928 | 21928 | 21928 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6121 | New | New_Built | GBM | 30 | 0 | 50/230/340 | STANDARD_PRODUCT |  | COW_SITE | YES | >18HRS | NO | 28.705 | 77.314 | T21DL03015 | 2021-09-22 | 2021-10-20 | 2021-11-11 | 111-2870-50773140 | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2021-11-29 |  |  | 2021-11-12 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-03 | 2021-12-04 |  |  |  | 2021-11-12 | ST202111588373 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045808/2021 | 2021-12-10 | 2021-12-10 | DL/01/5126/0070/0031/345/04/08646/NS/06122021 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-18 | 2021-12-10 | 2021-12-15 | 2021-12-10 | 2021-12-18 | 2021-12-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1647 | [5 empty] | 2021-11-23 | 2021-12-09 | 03 GSM pole mounts required,Issue Closed on 29.11.21,Installation WIP,Infra Team on the way 125 Amp MCB required as on 03.12.21,SACFA Pending as on 04.12.21,Issue closed on 09.12.21 | [9 empty] | 404-10-621928-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Block L, Govindpuram | (Dehradun Public School),Govindpuram,I Block,Near By Punjab National Bank,Police Station - Bapudham,Post Office - Govindpuram,Ghaziabad,Uttar Pradesh-201013. | 21927 | 21927 | 21927 | 21927 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1337102 | New | New_Built | RTP | 9 | 13 | 50/170/230 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6829 | 77.4828 | R/RES-506013 | 2021-09-22 | 2021-10-12 | 2021-11-12 | 11109.2868.29774828.CWIP-CL | 2021-11-22 | 2021-11-23 |  |  |  |  | 2021-11-18 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-25 | 2021-11-26 |  |  |  | 2021-11-10 | ST202111586364 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045120/2021 | 2021-12-07 | 2021-12-08 | DL/04/5177/0790/0031/06/05/12684/NS/08122021 | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2021-12-11 | 2021-12-08 | 2021-12-10 | 2021-12-08 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 599 | [5 empty] | 2021-11-26 | 2021-12-07 | Nearend & MW Installed_Media Issue(2G RRU Used) as on 26.11.21,Media Issue closed on 07.12.21 | [9 empty] | 404-10-621927-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Safe Express Gurgaon | Plot No. 27, Udyog Vihar -IV, Sector 18, GGN | 27756 | 27756 | 27756 | 27756 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FNL-IBS-008 | New | New_Built | IBS | 0 | 0 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4913 | 77.079 | NA | 2021-10-24 | 2021-11-13 | 2021-11-16 | 11106-2849-13770789 | 2021-11-27 | 2021-11-29 | 2021-11-29 | 2021-12-01 |  |  | 2021-11-22 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-04 | 2021-12-06 | [10 empty] | 2021-12-06 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-12 | 2021-12-07 | 2021-12-16 | 2021-12-07 | 2021-12-19 | 2021-12-20 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 138 | [5 empty] | 2021-11-29 | 2021-12-01 | SURVEY REJECT AND PARSWA BASE PAD REQUIRED,Issue Closed on 01.12.21 | [9 empty] | 404-10-627756-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+TD | 2G RRU 2219, TD RRU 4418
Del | FY20_21 | Q4 | Pratap Vihar (Relocation of 10057) | Mr.Harpreet Kaur,Apex Heights Private Limited,Plot Number- 4/BS-2/3,Siddharth Vihar Yogna,Police Station - Vijay Nagar,Post Office - Vijay Nagar,Ghaziabad,Uttar Pradesh-201009 | 21994 | 21994 | 21994 | 21994 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3045093 | New | New_Built | RTP | 6 | 99 | 40/180/290 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6514 | 77.4055 | R/RES-505839 | 2021-11-01 | 2021-11-17 | 2021-11-20 | 11109-2865-14774055 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-07 |  |  | 2021-12-01 | 2021-12-07 | 2021-12-10 | 2021-12-11 | 2021-12-11 | 2021-12-11 |  |  |  | 2021-10-20 | ST202110564522 | S20210031884 |  |  | 2021-11-13 | P/FVC/DEL/1044421/2021 | 2021-12-11 | 2021-12-13 | DL/04/5177/0793/0031/03/01/10325/NS/13122021 | 2021-12-13 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-21 | 2021-12-14 | 2021-12-16 | 2021-12-14 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9718 | [5 empty] | 2021-12-01 | 2021-12-07 | Pole Mount required at Farend_9718,Issue closed on 07.12.21 | [9 empty] | 404-10-621994-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | Prateek Grand City | Mr.Raj Shekher Sharma,Plot Number-4/BS-01&4/BS-05,Tower No. C-9, Prateek Grand City,Siddharth Vihar,Police Station - Vijay Nagar,Post Office - Vijay Nagar, NH-24,Ghaziabad,Uttar Pradesh-201009 | 21794 | 21794 | 21794 | 21794 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3017375 | New | New_Built | RTP | 4 | 91 | 0/70/280 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6472 | 77.405 | R/NN-630201 | 2021-11-01 | 2021-11-17 | 2021-11-20 | 11109-2864-71774050 | 2021-12-01 | 2021-12-01 |  |  |  |  | 2021-11-30 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-04 | 2021-12-06 |  |  |  | 2021-10-20 | ST202110564523 | S20210031884 |  |  | 2021-11-13 | P/FVC/DEL/1044444/2021 | 2021-12-14 | 2021-12-15 | DL/04/5177/0794/0031/03/01/10329/NS/15122021 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-21 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1443 | [5 empty] | 2021-12-06 | 2021-12-13 | Installed_RRU Faulty & Mains Not available,Issue closed on 13.12.21 | [9 empty] | 404-10-621794-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | PASONDA(Relocation of 20276) | Mr. Haji Iqbal S/o Mr. Nizamuddin,Khasra Number - 3720/3721(Star Parking),Pasonda,Near By Karan gate Police Chowki,Police Station - Tila Mod,Post Office - Pasonda,Ghaziabad,Uttar Pradesh- 201005 | 21687 | 21687 | 21687 | 21687 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3042685 | New | New_Built | GBM | 30 | 0 | 10/150/250 | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6897 | 77.3585 | R/NN-629801 | 2021-09-21 | 2021-09-30 | 2021-11-11 | 11109-2868-96773585 | 2021-12-04 | 2021-12-04 |  |  |  |  | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2021-12-07 | 2021-12-07 | 2021-12-09 |  |  |  | 2021-11-15 | ST202111589873 | S20210033274 |  |  | 2021-12-08 | P/FVC/DEL/1045892/2021 | 2021-12-14 | 2021-12-15 | DL/04/5177/0795/0031/03/01/10328/NS/15122021 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-23 | 2021-12-15 | 2021-12-23 | 2021-12-15 | 2021-12-24 | 2021-12-24 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4294 | [5 empty] | 2021-12-04 | 2021-12-14 | Hold due to 40 Mtr OFC Not in Stock,Partial Installed_Farend Radio Faulty-Mains not available/DG not available as on 07.12.21,Installed_Media Issue 09.12.21,Issue closed on 14.12.21 | [9 empty] | 404-10-621687-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on Parent site
Del | FY20_21 | Q4 | Rajiv Colony | Government Land,MCF,Green Belt,MBTS LocationNear-Plot Number-P 1599,Rajiv Colony, Sector 56A, Near RJIO Tower, Sec-56,Police Station-Sector 58,Post Office-Rajiv Colony, Faridabad,Haryana-121004 | 22014 | 22014 | 22014 | 22014 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1635617 | New | New_Built | Cow | 30 | 0 | 0/120/240 | COW |  |  | YES | >18HRS | NO | 28.3262 | 77.2896 | R/RES-507204 | 2021-10-29 | 2021-11-01 | 2021-11-20 | 11106-2832-62772895 | 2021-12-04 | 2021-12-04 |  |  |  |  | 2021-12-04 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-08 | 2021-12-09 |  |  |  | 2021-11-12 | ST202111588375 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045810/2021 | 2021-12-09 | 2021-12-10 | DL/02/5177/5033/0031/345/04/08655/NS/10122021 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-15 | 2021-12-10 | 2021-12-15 | 2021-12-10 | 2021-12-18 | 2021-12-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 130 | [5 empty] | 2021-12-04 | 2021-12-06 | Hold due to 40 Mtr OFC Not in Stock | [9 empty] | 404-10-622014-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on Parent site
Del | FY20_21 | Q4 | East Sagarpur(Relocation of 11325) | Mrs. Chameli Devi W/o Mr Bhup Singh Yadav, Plot Number - 23A, East Sagarpur, Nasirpur, Police Station - Sagarpur,Post Office - Sagarpur,New Delhi 110045 | 19498 | 19498 | 19498 | 19498 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-3593 | New | New_Built | RTT | 12 | 10 | 60/160/220 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6002 | 77.1033 | SR-DL000155 | 2020-07-13 | 2020-07-24 | 2021-11-11 | 111-2860-02771032 | 2021-12-04 | 2021-12-04 |  |  |  |  | 2021-12-04 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-08 | 2021-12-09 |  |  |  | 2021-11-12 | ST202111588368 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045803/2021 | 2021-12-09 | 2021-12-10 | DL/01/5370/0909/0031/06/05/12708/NS/10122021 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-17 | 2021-12-10 | 2021-12-15 | 2021-12-10 | 2021-12-18 | 2021-12-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 823 | [5 empty] | 2021-12-04 | 2021-12-06 | Hold due to 20 Mtr OFC Not in Stock,Partial Installed_MW installed-Farend Radio Faulty as on 08.12.21 | [9 empty] | 404-10-619498-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on Parent site
Del | FY20_21 | Q4 | Sec-17,Faridabad | Government Land,Municipal Corporation of Faridabad(MCF),Green Belt Area,GBM Location,Near MCF Tube well Number T6/14,Ward Number 32,Chaudhary Charan Singh Marg, Sector 14,Post Office - Sec 14 Faridabad,Police station - Sec 14 Faridabad, Faridabad, Haryana 121006 | 21361 | 21361 | 21361 | 21361 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1701151 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4026 | 77.3338 | R/NN-564608 | 2021-11-12 | 2021-11-21 | 2021-12-02 | 11106-2840-26773338 | 2021-12-07 | 2021-12-07 |  |  |  |  | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2021-12-11 |  |  |  | 2021-09-11 | ST202109516803 | S20210029559 |  |  | 2021-09-19 | P/FVC/DEL/1040872/2021 | 2021-12-11 | 2021-12-13 | DL/02/5177/5059/0031/03/01/10326/NS/13122021 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-21 | 2021-12-13 | 2021-12-17 | 2021-12-13 | 2021-12-24 | 2021-12-24 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19316 | [17 empty] | 404-10-621361-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | The Shopping Mall (DLF Shopping Center) | The Shopping Mall (DLF Shopping Center),Arjun Marg, Block E, DLF Phase-1, Sector 26A, Gurgaon, 122002 | 27768 | 27768 | 27768 | 27768 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL-DEL-622 | New | New_Built | IBS | 0 | 0 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.4661 | 77.0995 | NA | 2021-11-30 | 2021-11-30 | 2021-11-30 | 11106-2846-60770995 | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2022-01-13 |  |  | 2021-12-04 | 2022-01-13 | 2022-01-16 | 2022-01-17 | 2022-01-17 | 2022-01-17 | [10 empty] | 2022-01-17 |  |  | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-20 | 2022-01-18 | 2022-01-22 | 2022-01-18 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 940 | [5 empty] | 2021-12-10 | 2022-01-13 | Pole Mount req at Farend_940,SR received on 16.12.21,Infra Request Hold by Vijay,Issue closed on 13.01.22 | [9 empty] | 404-10-627768-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Fatehpur Chanderi | Mr. Kamal Kunj,House Number - 244/21-B,Sector - 21 B,Faridabad,Police Station - NIT Faridabad,Post Office - Sec 21,Faridabad Haryana 121001 | 11281 | 11281 | 11281 | 11281 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3064096 | New | New_Built | RTT | 12 | 9 | 150/240/340 | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4181 | 77.2992 | R/NN-634113 | 2021-10-29 | 2021-11-01 | 2021-11-11 | 11106-2841-80772991 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-17 |  |  | 2021-12-15 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-20 | 2021-12-21 |  |  |  | 2021-11-12 | ST202111588371 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045806/2021 | 2021-12-21 | 2021-12-22 | DL/02/5177/05066/0031/03/01/10340/NS/22122021 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-30 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 808 | [5 empty] | 2021-12-14 | 2021-12-21 | Survey rejected; 03 Pole mounts required and site is on Sub-Meter,Issue Closed on 17.12.21,Farend Pole Mount required_808 as on 20.12.21,Issue closed on 20.12.21,Partial Installed_Link Done - 2G Media Issue closed on 21.12.21 | [9 empty] | 404-10-611281-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Om Enclave, Faridabad | Smt Lata Kumari W/o Sh Rupesh Kumar, Khewat/Khata Number-1 min, Mu Number-28, Killa Number-15/1(5-3), 16(5-3), 24/2(6-7), Ismailpur,Post Office- Mithapur, Police Station-Mithapur, Faridabad, Haryana-121009 | 21950 | 21950 | 21950 | 21950 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-FDBD-ENB-3911 | New | New_Built | RTT | 9 | 10 | 120/260/330 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.49 | 77.3311 | SR-DL000188 | 2021-09-22 | 2021-10-24 | 2021-10-27 | 11106-2848-99773310 | 2021-12-14 | 2021-12-14 |  |  |  |  | 2021-12-12 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-17 | 2021-12-17 |  |  |  | 2021-11-10 | ST202111586344 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045136/2021 | 2021-12-18 | 2021-12-19 | DL/02/5370/3858/0031/06/05/12804/NS/19122021 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-25 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5477 | [5 empty] | 2021-12-17 | 2021-12-18 | Installed_Link Done & 2G Media Issue,Issue closed on 18.12.21 | [9 empty] | 404-10-621950-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VILLAGE-MANKROLA | Mr Satish Kumar S/o Sh Om Parkash,Village - Mankrola(42),Near Hoshiyar Singh's House,Police station - Sector - 9A,Post office - Mankrola,Gurgaon,Haryana -122505 | 21972 | 21972 | 21972 | 21972 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GRGN-ENB-9066 | New | New_Built | GBT | 25 | 0 | 30/130/210 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5038 | 76.9007 | SR-DL000216 | 2021-09-22 | 2021-10-18 | 2021-10-21 | 11106-2850-37769006 | 2021-12-14 | 2021-12-14 |  |  |  |  | 2021-12-12 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-17 | 2021-12-19 |  |  |  | 2021-11-19 | ST202111595371 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045401/2021 | 2021-12-19 | 2021-12-20 | DL/05/5370/2925/0031/06/05/12815/NS/20122021 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-25 | 2021-12-20 | 2021-12-23 | 2021-12-20 | 2022-01-24 | 2022-01-31 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9942 | [7 empty] | Installed_MW Pending-Power and LAN cable short | [9 empty] | 404-10-621972-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | MUNIPAL SINGH COLONY | Mr Brajesh S/o Late Sh Khemchand Plot Number-1, Part of Khasra Number-693 Min, H P Colony, Shahpur Bamheta, Near By Delhi Merrut Expressway,Kulesra,Police Station Kavi Nagar,Post Office Bamheta,Ghaziabad,Uttar Pradesh-201001. | 21952 | 21952 | 21952 | 21952 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GZBD-ENB-4121 | New | New_Built | RTT | 9 | 10 | 10/120/260 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6484 | 77.4697 | SR-DL000194 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-01 | 11109-2864-84774697 | 2021-12-14 | 2021-12-14 |  |  |  |  | 2021-12-12 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-17 | 2021-12-18 |  |  |  | 2021-11-12 | ST202111588370 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045805/2021 | 2021-12-18 | 2021-12-19 | DL/04/5370/5062/0031/06/05/12802/NS/19122021 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-27 | 2021-12-19 | 2021-12-22 | 2021-12-19 | 2022-01-03 | 2022-01-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5060 | [17 empty] | 404-10-621952-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Tigaon | Mr. Satvir Singh Adhana S/o Mr. Samat Singh,Plot Number- 644, VPO- Tigaon,Police Station- Tigaon,Post office- Tigaon,Ballabhgarh,District- Faridabad, Haryana 121101 | 21872 | 21872 | 21872 | 21872 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6855 | New | New_Built | GBM | 30 | 0 | 0/100/220 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.3472 | 77.397 | T21DL03110 | 2021-09-06 | 2021-10-20 | 2021-10-28 | 11106-2834-72773969 | 2021-12-14 | 2021-12-14 |  |  |  |  | 2021-12-12 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-17 | 2021-12-17 |  |  |  | 2021-11-03 | ST202111581273 | S20210032784 |  |  | 2021-11-19 | P/FVC/DEL/1044820/2021 | 2021-12-22 | 2021-12-23 | DL/02/5126/00208/0031/03/01/10346/NS/23122021 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2021-12-30 | 2021-12-23 | 2021-12-25 | 2021-12-23 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 149 | [5 empty] | 2021-12-17 | 2021-12-20 | Farend Owner Issue_149,Issue closed on 20.12.21 | [9 empty] | 404-10-621872-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Saurabh Vihar, Jaitpur, Badarpur(Relocation of 1635) | Mr. Chetan S/O Hera Lal,House Number N-534/20,N Block Amar Market, Saurabh vihar,Jaitpur, Post Office - Badarpur,Police Station - Badarpur, Badarpur, 110044 | 20722 | 20722 | 20722 | 20722 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/8910 | New | New_Built | RTP | 9 | 14 | 0/100/260 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.5088 | 77.3189 | T21DL02799 | 2021-09-06 | 2021-10-20 | 2021-11-16 | 111-2850-87773189 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-17 |  |  | 2021-12-16 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 |  |  |  | 2021-11-19 | ST202111595351 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045395/2021 | 2021-12-22 | 2021-12-23 | DL/01/5126/01559/0031/345/04/08685/NS/23122021 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2022-01-02 | 2021-12-23 | 2021-12-25 | 2021-12-23 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 842 | [5 empty] | 2021-12-14 | 2021-12-17 | MO Hold_Tech Deviation from Parent Site TB 2 Sector & L2100 1 Sector,Issue Closed on 17.12.21 | [9 empty] | 404-10-620722-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Parsvnath Green Ville | House Numbar.21,Dhani,Sector-48,Police Station Badshahpur,Post Office Badshahpur,Gurugram,Haryana-122001 | 15922 | 15922 | 15922 | 15922 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | AIPL | AIPLDLGM21S398 | New | New_Built | RTP | 9 | 12.5 | 340/120/230 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.409 | 77.0381 | 15922 | 2019-10-17 | 2021-08-14 | 2021-08-16 | 11106-2840-90770381 | 2021-12-15 | 2021-12-16 | 2021-12-16 | 2021-12-20 |  |  | 2021-12-13 | 2021-12-21 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2022-03-25 |  |  |  | 2021-08-17 | ST202108430893 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038094/2021 | 2022-03-25 | 2022-03-27 | DL/05/5404/00002/0031/03/01/10471/NS/27032022 | 2022-03-27 | 2022-03-27 | 2022-03-27 | 2022-03-27 | 2022-03-27 | 2022-03-30 | 2022-03-27 | 2022-03-31 | 2022-03-27 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-24 |  | Indus |  | M1 | 11145 | [5 empty] | 2021-12-16 | 2022-03-25 | Hold by Shashank_TND awaited,Issue closed on 20.12.21,Public Issue as on 22.12.21,Partially Installed_Link Done & GPS Down/Access Required at Nearend as on 23.03.22,TDD RRU Down,Access required as on 24.03.22,TDD RRU Down,Access required | [9 empty] | 404-10-615922-11 |  |  |  |  | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Punjabi Colony Narela | Mr. Manjeet Maan S/O Sh. Satish Maan,Flat Number- 4,Khasra Number - 511,Village Mamoorpur,Block - G,Punjabi Colony,Narela,Post Office - Narela,Police Station - Narela , Delhi - 110040 | 21945 | 21945 | 21945 | 21945 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-3972 | New | New_Built | RTT | 9 | 14 | 20/200/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.8445 | 77.0928 | SR-DL000202 | 2021-09-22 | 2021-10-31 | 2021-11-18 | 111-2884-45770928 | 2021-12-15 | 2021-12-16 |  |  |  |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-19 |  |  |  | 2021-11-19 | ST202111595349 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045393/2021 | 2021-12-19 | 2021-12-20 | DL/01/5370/****/0031/06/05/12812/NS/20122021 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-27 | 2021-12-20 | 2021-12-22 | 2021-12-20 | 2022-01-03 | 2022-01-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4115 | [7 empty] | Partial installed_MW pending | [9 empty] | 404-10-621945-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | New Gopal Nagar | Mr. Nishant S/o Sh. Birsen Yadav House Number- D-25,New Gopal Nagar,Police Station - Baba Haridas Nagar,Post Office - Najafgarh New delhi-110043 | 21968 | 21968 | 21968 | 21968 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-4360 | New | New_Built | RTP | 12 | 6.3 | 80/160/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6048 | 76.9613 | SR-DL000206 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-18 | 111-2860-47769612 | 2021-12-15 | 2021-12-15 |  |  |  |  | 2021-12-17 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-18 |  |  |  | 2021-11-19 | ST202111595370 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045400/2021 | 2021-12-18 | 2021-12-19 | DL/01/5370/****/0031/345/04/08671/NS/19122021 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-25 | 2021-12-19 | 2021-12-22 | 2021-12-19 | 2022-01-03 | 2022-01-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 660 | [17 empty] | 404-10-621968-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Jawahar Colony | Mr. Tarun Gupta S/o Mr Babu Lal,Khasra Number - 68/2,Stotre Number - 3896,Jawahar colony,Post Office - Sanjay Colony,Police Station - Saran,NIT Faridabad,Haryana 121005 | 23473 | 23473 | 23473 | 23473 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/FRD/AT/8949 | New | New_Built | RTP | 6 | 15 | 140/220/300 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.3625 | 77.2877 | T21DL03014 | 2021-08-27 | 2021-10-20 | 2021-11-11 | 11106-2836-25772876 | 2021-12-15 | 2021-12-16 |  |  |  |  | 2021-12-13 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-19 |  |  |  | 2021-11-12 | ST202111588361 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045797/2021 | 2022-01-05 | 2022-01-06 | DL/02/5126/00211/0031/06/05/12910/NS/06012022 | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-01-07 | 2022-01-06 | 2022-01-11 | 2022-01-07 | 2022-01-07 | 2022-01-07 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 800 | [5 empty] | 2021-12-18 | 2022-01-05 | Public/Infra/Media Issue,Installed_Media Issue resolved as Per shashank_20.12.21,Access avl on 27.12.21,Media Issue as on 27.12.21,Installed_Access Issue as on 29.12.21,Issue closed on 05.01.2022 |  | 2022-01-07 |  | Power Issue | [5 empty] | 404-10-623473-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Ce info System Pvt Ltd | Building No. 237 Okhla Industrial Estate Phase -3. Delhi 110020 | 27763 | 27763 | 27763 | 27763 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27763 | New | New_Built | IBS | 0 | 16 | IBS/IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.551 | 77.2689 |  | 2021-11-12 | 2021-11-27 | 2021-12-07 | 111-2855-10772688 | 2021-12-15 | 2021-12-16 |  |  |  |  | 2021-12-15 | 2021-12-17 | 2021-12-20 | 2021-12-21 | 2021-12-21 | 2021-12-23 | [10 empty] | 2021-12-23 |  |  | 2021-12-23 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-30 | 2021-12-24 | 2021-12-25 | 2021-12-24 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9123 | [5 empty] | 2021-12-21 | 2021-12-23 | DAS WIP & Access limited_Link done,issue closed on 23.12.21 | [9 empty] | 404-10-627763-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 12B3 , TD RRU 4418
Del | FY20_21 | Q4 | Music Broadcast Private Limited | 1st & 3rd Floor , Music Broadcast Limited, 203, Okhla Industrial Area, Phase- III, New Delhi – 110020 | 27736 | 27736 | 27736 | 27736 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27736 | New | New_Built | IBS | 0 | 13 | IBS | PURE_IBS |  |  | YES | >18HRS | NO | 28.5495 | 77.2728 |  | 2021-11-12 | 2021-11-27 | 2021-12-07 | 111-2854-94772728 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-16 |  |  | 2021-11-17 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-21 | [10 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-28 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 17410 | [5 empty] | 2021-12-15 | 2021-12-21 | TND received on 16.12.21,POP Team_Cable tray 20 mtr & Partial Installed_DAS-600 Mtr Cabling as on 18.12.21,Access Avl on 21.12.21,Issue closed on 21.12.21 | [9 empty] | 404-10-627736-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Sanjay Gandhi Memorial Nagar | Mr.Manas Ranjan Nanda- 9250350480,Plot Number 6, Khasra Number 131/3/3(4-9),Pocket A, Sanjay Gandhi Memorial Nagar, Sec 48, NIT Faridabad ,Near By Bhatia Hospital, Police Station - NIT 3,Post Office - NH 3(Yogdham Mandir),Faridabad,Haryana-121001. | 21882 | 21882 | 21882 | 21882 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | GTL | DEL/RTT/K/20475 | New | New_Built | RTT | 18 | 7.8 | 0/140/270 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3989 | 77.2886 | NA | 2021-09-06 | 2021-11-22 | 2021-11-22 | 11106-2839-88772885 | 2021-12-15 | 2021-12-16 |  |  |  |  | 2021-12-17 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-23 |  |  |  | 2021-12-07 | ST202112604788 | S20210034198 |  |  | 2021-12-16 | P/FVC/DEL/1046204/2021 | 2021-12-23 | 2021-12-24 | DL/02/5297/0069/0031/345/04/08690/NS/24122021 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-31 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 910 | [5 empty] | 2021-12-18 | 2021-12-23 | Partial Installed_Condute Pipe req both end for MW as on 18.12.21,Media Issue as on 18.12.21,Media Issue closed on 23.12.21 | [9 empty] | 404-10-621882-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Siraspur | Mr. Bijender Kumar,House Number - 104/2,Village Siraspur,Post Office - Samaypur,Police Station - Samaypur,New Delhi 110042 | 21970 | 21970 | 21970 | 21970 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-8961 | New | New_Built | RTP | 12 | 11 | 80/160/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7619 | 77.1272 | SR-DL000201 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-16 | 111-2876-19771272 | 2021-12-15 | 2021-12-16 | 2021-12-16 | 2021-12-16 |  |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-19 |  |  |  | 2021-11-19 | ST202111595350 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045394/2021 | 2021-12-19 | 2021-12-20 | DL/01/5370/****/0031/06/05/12810/NS/20122021 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-27 | 2021-12-20 | 2021-12-23 | 2021-12-20 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 177 | [5 empty] | 2021-12-16 | 2021-12-19 | Nearend Survey Done_MW Mount req at Farend_177 & SR Required or Farend,SR received on 16.12.21,Partial Installed_Farend Pole req as on 18.12.21,Issue closed on 19.12.21 | [9 empty] | 404-10-621970-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Ask Automotive | Mr. Arun,ASK Automotive Pvt. Ltd. Plot Number - 13, 14, Sector- 05, IMT Manesar, Police station -Sec 8 Manesar,Post office - Bhangrola, Gurgaon, Haryana 122052 | 27750 | 27750 | 27750 | 27750 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27750 | New | New_Built | RTP | 6 | 25 | 10/110/210 | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.3667 | 76.9223 | NA | 2021-10-23 | 2021-12-05 | 2021-12-05 | 11106-2836-66769221 | 2021-12-15 | 2021-12-16 | 2021-12-16 | 2021-12-27 |  |  | 2021-12-10 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-05 | 2022-01-22 |  |  |  | 2021-12-07 | ST202112604796 | S20210034198 |  |  | 2021-12-16 | P/FVC/DEL/1046207/2021 | 2022-01-22 | 2022-01-23 | DL/05/0031/00611/0031/03/01/10378/NS/23012022 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-31 | 2022-01-23 | 2022-01-27 | 2022-01-23 | 2022-02-04 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15112 | [5 empty] | 2021-12-16 | 2022-01-22 | Currently distance b/w BTS location to OD Tower is 90M while BTS to IBS location is 30M only, BTS and Infra location to shift near OD pole location as per Planning Mr. Trilok,2Qty 200M OFC for IBS location (2G-1800+ TDD),200M (100M*2qty) 2*6 Sqmm power cable for IBS location RRU,Issue closed on 27.12.21,Hold due to TDD RRU & 1/2"Feeder,Installation Plan_Gps Ldf cable short as on 05.01.22,Partial Installed /Infra issue -Pole mount req -3 nos (2.5 mtr ) & Nut bolt Issue -Gps Ldf cable short as on 06.01.22,Issue closed on 07.01.22,Partial Installed & Das WIP_2400 mtr as on 07.01.22,Partial Installed & Das WIP_2400 mtr,Access Avl on Saturday & Sunday as on 10.01.22,Issue closed on 22.01.22 | [9 empty] | 404-10-627750-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | NSG Camp,Manesar1 | GOVERNMENT LAND,MBTS LOCATION,BEHIND 13 SRG MOTOR TRANSPORT,NATIOANAL SECURITY GUARD(NSG) OFFICE,POST OFFICE - MANESAR,POLICE STATION - MANESAR GURGAON HARYANA-122051 | 16873 | 16873 | 16873 | 16873 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 16873 | New | New_Built | Cow | 30 | 0 | 0/120/240 | Cow |  |  | YES | >18HRS | NO | 28.3477 | 76.9589 | NA | 2021-11-12 | 2021-11-27 | 2021-12-07 | 11106-2834-76769588 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-16 |  |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2021-12-18 | 2021-12-18 | 2021-12-21 |  |  |  | 2021-12-15 | ST202112617423 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046889/2021 | 2021-12-28 | 2021-12-29 | DL/05/0031/00601/0031/345/04/08694/NS/29122021 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-01-04 | 2021-12-29 | 2021-12-31 | 2021-12-29 | 2022-01-10 | 2022-01-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 19170 | [5 empty] | 2021-12-15 | 2021-12-28 | Survey Rejected; 340M Lat-Long deviation found,Partial Installed-GSM movement Issue 2nd sector as on 18.12.21,Installed_GSM Required - 10 port (Planning Issue) as on 20.12.21,Issue closed on 21.12.21_SACFA Pending,Installed_Power Issue & TD SACFA_Pending as on 26.12.21,Issue closed on 28.12.21 | [9 empty] | 404-10-616873-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Madhu Vihar(Relocation of 2321) | Smt Trilochan Kaur W/o Late Sh Jaspal Singh,House Number - A-143,Block A,Near Asam Plywood,Madhu Vihar,Police Station - Mandawali,Post Office - Madhu vihar, Delhi-110092 | 20517 | 20517 | 20517 | 20517 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-9294 | New | New_Built | RTT | 9 | 11 | 100/180/240 | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6362 | 77.3055 | SR-DL000137 | 2021-07-18 | 2021-08-05 | 2021-10-07 | 111-2863-61773054 | 2021-12-16 | 2021-12-17 | 2021-12-17 |  |  |  | 2021-12-18 | [8 empty] | 2021-08-18 | ST202108483261 | S20210028126 |  |  | 2021-09-01 | P/FVC/DEL/1038761/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Blockage issue in all 3 sectors | 3rd Party PRI | PRI_Without Material |  |  | Indus |  | M1 | 317 | [5 empty] | 2021-12-17 |  | Survey Rejected; Blockage issue in all 3 sectors | [14 empty] | Survey Rejected; Blockage issue in all 3 sectors | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q4 | PARAMHANS VIHAR | Mr.Pawan Kumar S/O Mr.Roshan Lal,House Number- B 358,Paras hans vihar, Ghatori Khurd,Laxmi Garden, Police Station-Indrapuri, Post Office-Loni ,Ghaziabad, Uttar Pradesh-201102 | 21973 | 21973 | 21973 | 21973 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-LONI-ENB-1510 | New | New_Built | RTT | 12 | 7.3 | 90/160/320 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7323 | 77.2937 | SR-DL000211 | 2021-09-22 | 2021-10-24 | 2021-10-27 | 11109-2873-23772937 | 2021-12-16 | 2021-12-17 |  |  |  |  | 2021-12-16 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-20 | 2021-12-21 |  |  |  | 2021-11-03 | ST202111581277 | S20210032784 |  |  | 2021-11-19 | P/FVC/DEL/1044822/2021 | 2021-12-21 | 2021-12-22 | DL/04/5428/0185/0031/345/04/08678/NS/22122021 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-28 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4255 | [5 empty] | 2021-12-20 | 2021-12-20 | Farend Owner Issue_4255 as on 20.12.21,Issue closed on 20.12.21 | [9 empty] | 404-10-621973-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SAMAY PUR | Mr. Sharmila W/O Sh. Somesh Yadad,House number - 248,Khasra Number - 12/26,Railway Station Road,Near Gali number - 11,Samaypur,Post Office - Samaypur,Police Station - Samaypur,Delhi - 110042 | 21969 | 21969 | 21969 | 21969 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-8826 | New | New_Built | RTT | 9 | 14 | 40/130/310 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.7481 | 77.1422 | SR-DL000209 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-11 | 111-2874-81771422 | 2021-12-16 | 2021-12-17 | 2021-12-17 | 2021-12-20 |  |  | 2021-12-18 | 2021-12-21 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2021-11-12 | ST202111588365 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045801/2021 | 2021-12-23 | 2021-12-24 | DL/01/5428/2748/0031/06/05/12858/NS/24122021 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-29 | 2021-12-24 | 2021-12-25 | 2021-12-24 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 974 | [5 empty] | 2021-12-17 | 2021-12-23 | MW Mount & MCB required at Farend_974,Issue closed on 20.12.21,Installed_MW Pending & Media Issue as on 22.12.21,Media Issue closed on 23.12.21 | [9 empty] | 404-10-621969-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | DLF Phase-3 Gurgaon(Relocation of 10660) | Mr. Rakesh,House Number - U-52/9,Gali No. 52, U Block,DLF Phase-3, Sector 24,Post Office - Dlf Phase 2,Police Station - Dlf Phase 2,District- Gurgaon, Haryana 122002 | 22044 | 22044 | 22044 | 22044 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1301558 | Relocation | sharing | RTP | 6 | 21 | 40/110/220 | Indus_Lite+ | Indus_Lite+ | Sharing available | YES | >18HRS | NO | 28.4901 | 77.0948 | R/RES-506785 | 2021-10-12 | 2021-10-14 | 2021-10-16 | 11106-2849-01770948 | 2021-11-16 | 2021-11-17 | 2021-11-17 | 2022-03-14 |  |  | 2021-11-18 | 2022-03-15 | 2022-03-16 | [6 empty] | 2021-10-16 | ST202110561375 | S20210031698 |  |  | 2021-10-28 | P/FVC/DEL/1044032/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 17.03.22 | Indus | PRI_Without Material |  |  | Indus |  | M1 | 9025 | [5 empty] | 2021-11-17 |  | Technology deviation found (TTD_TB) & Blockage issue at 0 degree,Material return due to Owner Issue issue at 20.11.21,Issue closed on 12.12.21,Material return on 15.12.21,Material return on 17.03.22 | [14 empty] | Material return on 17.03.22 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412
Del | FY20_21 | Q4 | SHAKTI VIHAR | Mr.Vijay Sharma S/o Mr.Ravinder Sharma,House Number 26A ,Gali No 7/7, Shakti Vihar,Near By Gurudwara, Police Station - Jaitpur, Post Office - Meethapur,Meethapur, Delhi - 110044. | 25555 | 25555 | 25555 | 25555 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-195 | New | New_Built | RTP | 6 | 13.9 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4978 | 77.3225 | 25555 | 2021-08-27 | 2021-09-06 | 2021-10-11 | 111-MDEL-2076122 | 2022-01-08 | 2022-01-08 |  |  |  |  | 2022-01-07 | 2022-01-09 | 2022-01-09 | 2022-01-10 | 2022-01-10 | 2022-01-11 |  |  |  | 2021-10-14 | ST202110559962 | S20210031636 |  |  | 2021-10-28 | P/FVC/DEL/1044054/2021 | 2022-01-13 | 2022-01-14 | DL/01/0031/03054/0031/03/01/10367/NS/14012022 | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-01-18 | 2022-01-14 | 2022-02-07 | 2022-01-14 | 2022-02-15 | 2022-02-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 842 | [5 empty] | 2022-01-10 | 2022-01-11 | Partial installed_M/w Pending ,Farend Installed /Media Provision issue as o 10.01.22,Issue closed on 11.01.22 |  | 2022-01-14 | 2022-02-06 | Power Issue | [5 empty] | 404-10-625555-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Rps Savana City, Sector 88, Faridabad | Mr. Sunil M/O Saroj,Khewat Number - 199,Khatuni Number - 257,and258,Mustakil No - 16/17,RPS City,Sector 88,Post Office - Sector88,Police Station - Sector 88,Faridabad, Haryana 121002 | 21846 | 21846 | 21846 | 21846 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3054109 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4207 | 77.3532 | R/NN-632971 | 2021-10-09 | 2021-10-14 | 2021-10-22 | 11106-2842-07773532 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-27 |  |  | 2021-12-20 | 2021-12-28 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-30 |  |  |  | 2021-10-27 | ST202110572263 | S20210032268 |  |  | 2021-11-19 | P/FVC/DEL/1044880/2021 | 2022-01-03 | 2022-01-04 | DL/02/5177/05070/0031/345/04/08701/NS/04012022 | 2022-01-04 | 2022-01-04 | 2022-01-04 | 2022-01-05 | 2022-01-04 | 2022-01-07 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-10 | 2022-01-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4851 | [5 empty] | 2021-12-24 | 2022-01-03 | Survey Rejected; Mains Supply not available,Issue closed on 27.12.21,Installed_2G Freq Req LOS Issue as on 30.12.21,Issue closed 0n 03.01.22 | [9 empty] | 404-10-621846-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Ambedkar Basti, Maujpur, Shahdara | Mr. Lalit S/O Chaudhary Ajit Singh,K-199,Ambedkar Basti, Maujpur, Shahdara, Police Station - Jafrabad, Post Office - Maujpur, New Delhi-110053 | 21270 | 21270 | 21270 | 21270 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | NA | New | New_Built | RTP | 9 | 13.5 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6902 | 77.2722 | NA | 2021-10-14 | 2021-10-20 | 2021-11-11 | 111-2869-01772721 | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2022-01-14 |  |  | 2021-12-27 | 2022-01-15 | 2022-01-15 | 2022-01-16 | 2022-01-16 | 2022-01-17 |  |  |  | 2021-11-12 | ST202111588363 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045799/2021 | 2022-01-17 | 2022-01-18 | DL/01/5433/00001/0031/06/05/13002/NS/18012022 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | 2022-01-18 | 2022-01-20 | 2022-01-18 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 281 | [5 empty] | 2021-12-31 | 2022-01-14 | Survey Rejected; Climbing ladder and safety railing required at Mumty, GSM pole mounts movement required for required degree,Issue closed on 14.01.2022,6 Port Antenna Not in Stock,3MTR KINIA TO DIN jumper not in stock as on 15th Jan 22 | [9 empty] | 404-10-621270-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sangam Vihar colony, Khora | Mr. Mohd Ismaeel, House number - 27, Rajiv Nagar, Khora Colony Makanpur, Post Office - Khora Colony , Police Station - Khora, Noida Uttar Pradesh - 201012 | 21739 | 21739 | 21739 | 21739 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | NA | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.6308 | 77.3373 | 51639 | 2021-06-01 | 2021-10-20 | 2021-11-12 | 11109-2863-07773372 | 2022-01-08 | 2022-01-08 |  |  |  |  | 2022-01-10 | 2022-01-12 | 2022-01-14 | 2022-01-15 | 2022-01-15 | 2022-02-23 |  |  |  | 2021-11-15 | ST202111589875 | S20210033274 |  |  | 2021-12-08 | P/FVC/DEL/1045894/2021 | 2022-02-24 | 2022-02-25 | DL/03/5414/00005/0031/06/05/13307/NS/25022022 | 2022-02-26 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 |  | 2022-02-28 | 2022-03-04 | 2022-02-28 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 1312 | [5 empty] | 2022-01-08 | 2022-02-23 | 6 Port MultiBand Antenna not in Stock,Issue closed on 12.01.22,Public Issue as on 17.01.22,Public Issue & Farend commissioned Pole blockage issue as on 14.02.22,Nearend Access Permission Issue/Farend MW - MCB req as on 17.02.22,Issue closed on 23.02.22 | [9 empty] | 404-10-621739-11 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | B-1 Block, Ashok Vihar(Relocation of 244) | Hno. B-1/155, 02nd & 03rd Floor, Ashok Vihar-2,Delhi-110052 | 20798 | 20798 | 20798 | 20798 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-155 | Relocation | New_Built | RTP | 9 | 13 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.695 | 77.1762 | 20798 | 2020-10-21 | 2020-10-31 | 2020-11-03 | 111-2869-50771761 | 2022-01-15 | 2022-01-15 |  |  |  |  | 2022-01-11 | 2022-01-17 | 2022-01-17 | 2022-01-18 | 2022-01-18 | 2022-01-19 |  |  |  | 2020-11-06 | ST202011138246 | S20200007745 |  |  | 2020-12-22 | P/FVC/DEL/1012887/2020 | 2022-01-20 | 2022-01-21 | DL/01/0031/03075/0031/345/04/08718/NS/21012022 | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-01-27 | 2022-01-21 | 2022-01-23 | 2022-01-21 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 209 | [5 empty] | 2022-01-18 | 2022-01-20 | Material Receive Only -Public issue -security required as on 18.01.22,Installed_Public/2G Media Issue as on 19.01.22,Issue closed on 20.01.22 | [9 empty] | 404-10-620798-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available On parent site
Del | FY20_21 | Q4 | CARTERPURI | Mr. Vikram Singh S/O Sh. Mahender Singh,House Number - 133,Palam Vihar Extension,kartarpuri Police Station - Sector-22,Post Office - kartarpuri,Gurugram Haryana 122017 | 19699 | 19699 | 19699 | 19699 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | FCM_TOWER | NCR/36 | New | New_Built | RTP | 9 | 13.5 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4991 | 77.0409 | 19699 | 2020-10-01 | 2021-10-20 | 2021-11-13 | 11106-2849-90770409 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-22 |  |  | 2021-12-20 | 2021-12-22 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2022-01-08 |  |  |  | 2021-03-18 | ST202103095677 | S20210004955 |  |  | 2021-06-06 | P/FVC/DEL/1027945/2021 | 2022-01-08 | 2022-01-10 | DL/05/5410/00017/0031/345/04/08709/NS/10012022 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-11 | 2022-01-10 | 2022-01-11 | 2022-01-10 | 2022-01-17 | 2022-01-23 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8051 | [5 empty] | 2021-12-20 | 2022-01-08 | Hold due to locator & infra request pending & 6 port Antenna Not In Stock,Locator Issue resolved on 22.12.21,Installed_Farend MW Installed,cable tray Inst pending & mains not connected as on 23.12.21,Issue closed on 08.01.22 | [9 empty] | 404-10-619699-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | EMCD_60_Shahdara-1 | Mr. Indrajeet Singh S/o Lt. Sadur Singh Bindra,Bearing Property Number. 106/1-A, Khasra Number. 642, Village Chandrawali Alias, Teliwara, Shahdara,Police Station - Shahdara Post Office - Shahdara,Delhi-110032 | 18014 | 18014 | 18014 | 18014 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3021764 | New | New_Built | RTP | 6 | 16 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6722 | 77.29 | R/NN-627532 | 2021-08-17 | 2021-10-08 | 2021-10-16 | 111-2867-22772900 | 2021-12-20 | 2021-12-20 |  |  |  |  | 2021-12-19 | 2021-12-21 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2021-10-23 | ST202110568675 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044623/2021 | 2021-12-23 | 2021-12-24 | DL/01/5177/06475/0031/03/01/10349/NS/24122021 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-31 | 2021-12-24 | 2021-12-25 | 2021-12-24 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10217 | [5 empty] | 2021-12-22 | 2021-12-23 | Installed_MW Pending & Media Issue as on 22.12.21,Media Issue closed on 23.12.21 | [9 empty] | 404-10-618014-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Block G, Molar band Extension, Faridabad(Relocation of 27041) | Mr.Kulshaan Singh S/O Mr.Jitender Pal Singh,Plot Number - 19,Khasra No. 1631/2,Block-G,Molarband Extension,Badarpur,Police Station - Badarpur,Post Office - Badarpur,Faridabad,Haryana-121003 | 21773 | 21773 | 21773 | 21773 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016771 | Relocation | New_Built | RTT | 12 | 8 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.4881 | 77.3049 | R/NN-627102 | 2021-08-09 | 2021-10-05 | 2021-10-27 | 11106-2848-81773048 | 2021-12-28 | 2021-12-29 |  |  |  |  | 2021-12-30 | 2022-01-03 | 2022-01-03 | 2022-01-04 | 2022-01-04 | 2022-01-07 |  |  |  | 2021-11-10 | ST202111586349 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045113/2021 | 2022-01-07 | 2022-01-08 | DL/02/5177/05071/0031/06/05/12916/NS/08012022 | 2022-01-08 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-12 | 2022-01-10 | 2022-01-23 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 683 | [5 empty] | 2022-01-04 | 2022-01-10 | Hold due to TDD RRU & 1/2"Feeder,Partial Install_Infra issue (sub meter connection pending) & Farend Installed as on 04.01.22,Issue closed on 05.01.2022,Access Not avl on 08.01.22,Issue closed on 10.01.22 |  | 2022-01-11 | 2022-01-20 | Power Issue Closed on 20.01.22 | [5 empty] | 404-10-621773-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 available on Parent SIte
Del | FY20_21 | Q4 | Park View Residency | Mr. Amitabh singh,Khashra Number - 20/6,Tower-7 Park View Residency Sector-3,Village sarai allawardi,Police Station - palam Vihar Sec B,Post Office - Palam Vihar, Gurugram Haryana 122012 | 21858 | 21858 | 21858 | 21858 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032281 | New | New_Built | RTP | 6 | 50 |  | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4986 | 77.023 | R/NN-628350 | 2021-09-03 | 2021-09-29 | 2021-10-11 | 11106-2849-85770230 | 2021-12-31 | 2021-12-31 | 2021-12-31 |  |  |  | 2022-01-02 | [8 empty] | 2021-10-14 | ST202110559956 | S20210031636 |  |  | 2021-10-28 | P/FVC/DEL/1044058/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Blockage Issue | Bharti Planning | PRI_Without Material | 2022-03-24 |  | Indus |  | M1 | 8051 | [5 empty] | 2021-12-31 |  | Survey Rejected; Mains supply not available, Blockage issue at 10 and 280 degree,Maerial return due to Public Issue_21.02.22,Issue closed on 24.03.22,Survey done; Material request hold (CWIP Issue) | [14 empty] | Blockage Issue_Hold By Manoj | Bharti Planning | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Gokhle Market | GBM Location,North Delhi Municipal Corporation Park, Near Dhalao number - CLZ/78/D/16, Club road, Civil Lines, New Delhi-110054, | 17681 | 17681 | 17681 | 17681 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001971 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6695 | 77.2237 | R/NN-621208 | 2021-06-30 | 2021-07-12 | 2021-07-15 | 111-2866-94772236 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-27 |  |  | 2021-12-25 | 2021-12-28 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-30 |  |  |  | 2021-07-26 | ST202107397089 | S20210013730 |  |  | 2021-07-29 | P/FVC/DEL/1036559/2021 | 2022-01-03 | 2022-01-04 | DL/01/5177/06484/0031/345/04/08703/NS/04012022 | 2022-01-04 | 2022-01-04 | 2022-01-04 | 2022-01-05 | 2022-01-04 | 2022-01-09 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-02-02 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 208 | [5 empty] | 2021-12-24 | 2021-12-30 | Survey Rejected; Mains Supply not available,Issue closed on 27.12.21,Partial Installed_Nearend MW Mount req. as on 29.12.21,Issue closed as on 30.12.21 |  | 2022-01-05 | 2022-01-20 | Power Issue | [5 empty] | 404-10-617681-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | NEAR GOYAL HOSPITAL, SECTOR - 7 | Government Land,Municipal Corporation of Faridabad(MCF), Green Belt (Area),GBM Location,Near Nageshwari Hanuman Mandir,Opposite H No. 583-7B,Sector- 7/8 Dividing Road,Post Office - Sec 8,Police Station - Sec 8,District- Faridabad, Haryana 121006 | 21202 | 21202 | 21202 | 21202 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3052510 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.3637 | 77.3291 | R/NN-632692 | 2021-10-05 | 2021-10-09 | 2021-10-16 | 11106-2836-36773290 | 2022-01-12 | 2022-01-13 |  |  |  |  | 2022-01-11 | 2022-01-13 | 2022-01-15 | 2022-01-16 | 2022-01-16 | 2022-01-17 |  |  |  | 2021-09-18 | ST202109523544 | S20210029898 |  |  | 2021-09-25 | P/FVC/DEL/1042084/2021 | 2022-01-17 | 2022-01-18 | DL/02/5177/05073/0031/03/01/10371/NS/18012022 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | 2022-01-18 | 2022-01-19 | 2022-01-18 | 2022-01-24 | 2022-01-31 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 565 | [17 empty] | 404-10-621202-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Thakkar Bapa Nagar(Relocation of 1237) | Mr. Jagdish Puri,House Number- 16/21-E, Anandpuri,Tank Road, Karol Bagh,Police Station - Karol Bagh,Post Office - Karol Bagh,Delhi-110005 | 21770 | 21770 | 21770 | 21770 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | GTL | DEL/RTT/K/19884 | Relocation | Sharing | RTT | 9 | 11 |  | SHARING |  | SHARING | YES | >18HRS | NO | 28.6517 | 77.1788 | 21770 | 2021-08-05 | 2021-11-30 | 2021-12-01 | 111-2865-16771787 | 2021-12-27 | 2021-12-27 |  |  |  |  | 2021-12-25 | 2021-12-28 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2022-01-21 |  |  |  | 2021-12-13 | ST202112614875 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046023/2021 | 2022-01-21 | 2022-01-22 | DL/01/5297/0238/0031/03/01/10375/NS/22012022 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-29 | 2022-01-22 | 2022-01-28 | 2022-01-22 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 775 | [5 empty] | 2021-12-29 | 2022-01-20 | Consumable Delivered_Parent Site Not Dismantled as on 30.12.21_Plan on 03.01.22,Partial installed_Material short-GSM 3 nos req 4 port,GPS kit, TN 2P damage by Indus Team as on 03.01.22,Partial Install-Tower Strengthning Issue as on 05.01.2022,Partial Install / Tower overloaded Issue/2G Media Issue as on 06.01.22,Partial Install / Tower overloaded Issue,1/2", straight 7/16(m) -4.3.10 (m), 10m, Jumper cable NOT IN STOCK as on 15.01.22,Issue closed on 20.01.22 | [9 empty] | 404-10-621770-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | material to be cam from parent site
Del | FY20_21 | Q4 | SECTOR-3,VASUNDHARA(Relocation of 15868) | Mr.Neeraj Kumar S/O Mr.Jawahar Singh,House Number - 3/704,Sector-3,Vasundhara,Police Station - Vasundhara,Post Office - Vasundhara,Ghaziabad,Uttar Pradesh-201012 | 18366 | 18366 | 18366 | 18366 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3023440 | Relocation | New_Built | RTT | 9 | 12.5 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.663 | 77.3854 | R/NN-636279 | 2021-11-18 | 2021-11-23 | 2021-12-01 | 11109-2866-29773854 | 2021-12-20 | 2021-12-20 |  |  |  |  | 2021-12-19 | 2021-12-21 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2021-12-23 |  |  |  | 2021-12-15 | ST202112617453 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046939/2021 | 2021-12-26 | 2021-12-27 | DL/04/5177/00798/0031/03/01/10353/NS/27122021 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-04 | 2021-12-27 | 2022-01-04 | 2021-12-27 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 7370 | [5 empty] | 2021-12-22 | 2021-12-26 | Partial installed_Link Done-SACFA req as on 22.12.21,Installed_SACFA req as on 23.12.21,FD & TD SACFA_Pending as on 26.12.21 | [9 empty] | 404-10-618366-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q4 | South patelnagar(Relocation of 4346) | Mrs. Harpinder kaur, House Number - 2979/1,Ranjeet Nagar, Patel nagar south,Police Station - New Ranjeet Nagar,Post Office -Block 7 Ranjeet Nagar,Delhi-110008 | 21392 | 21392 | 21392 | 21392 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/8938 | Relocation | Sharing | RTP | 9 | 14 |  | SHARING |  | SHARING | YES | >18HRS | NO | 28.6452 | 77.1636 | T21DL02844 | 2021-09-06 | 2021-11-30 | 2021-11-30 | 111-2864-51771636 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2022-02-28 |  |  | 2021-12-26 | 2022-02-28 | 2022-03-01 | 2022-03-04 | 2022-03-04 | 2022-03-05 |  |  |  | 2021-12-15 | ST202112617439 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046931/2021 | 2022-03-05 | 2022-03-06 | DL/01/5126/01564/0031/03/01/10418/NS/06032022 | 2022-03-06 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-20 | 2022-03-11 | 2022-03-20 | 2022-03-11 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9658 | [5 empty] | 2021-12-29 | 2022-02-28 | Survey Rejected; Mains supply not availble and Blockage issue at 120 degree,Maerial return due to Public Issue_21.02.22,Issue closed on 28.02.22 | [9 empty] | 404-10-621392-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 available on Parent SIte
Del | FY20_21 | Q4 | M3M Marina Seirra | Mr. Rajesh Chahal (Estate Manager),EWS Tower M3M The Marina Sector-68 Gurugram,Post office - Badshahpur,Police Station - Badshapur,Haryana 122101 | 27705 | 27705 | 27705 | 27705 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS+Macro | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | SIS | HRMS582021 | New | New_Built | RTT | 6 | 48 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3769 | 77.0431 | 27705 | 2021-05-20 | 2021-07-13 | 2021-07-15 | 11106-2837-68770431 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2021-12-31 |  |  | 2021-12-17 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-05 | 2022-01-13 |  |  |  | 2021-12-15 | ST202112617446 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046933/2021 | 2022-01-13 | 2022-01-14 | DL/05/9006/00004/0031/03/01/10366/NS/14012022 | 2022-01-14 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-18 | 2022-01-15 | 2022-01-17 | 2022-01-15 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4265 | [5 empty] | 2021-12-23 | 2022-01-12 | Survey Rejected; GSM pole mounts required,Survey Rejected; Safety railing required at Mumty,Issue closed on 31.12.21,Hold due to TDD RRU & 1/2"Feeder,Partial Installed/Tower Pole Nut & Battery load Issue/2G media issue& short material. Re. --Gps Ldf cable short,TRIPLEXER-3 ,3 WAY SPILITER-1 ,2 WAY SPILITER-1,4 WAY SPILITER-1,DUMMY LOAD-3 .N- MALE1/2 JUMPER-4 NOS,DIN (N -MALE) TO N MALE -3 /Farend Link Done as on 06.01.22,Issue closed on 09.01.22,Partially Installed_FMS Issue(SIS) as on 10.01.22,Issue closed on 12.01.22 | [9 empty] | 404-10-627705-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | JALVAYU VIHAR | HUDA Play Ground,MBTS Location In front of H. No. - 491,Sector 31,Gurgaon Haryana 122003 | 25499 | 25499 | 25499 | 25499 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NBGC-25499 | New | New_Built | Cow | 30 |  |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4563 | 77.0514 | 25499 | 2021-04-23 | 2021-05-03 | 2021-05-26 | 11106-2845-62770513 | 2021-12-28 | 2021-12-29 | 2021-12-29 |  |  |  | 2021-12-30 | [8 empty] | 2021-05-28 | ST202105303946 | S20210010398 |  |  | 2021-07-22 | P/FVC/DEL/1036080/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Tower dismantled from planned location due to Public issue | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 5393 | [5 empty] | 2021-12-29 |  | Survey Rejected; Tower dismantled from planned location due to Public issue | [14 empty] | Survey Rejected; Tower dismantled from planned location due to Public issue | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Village-Mamapur | Mr.Pankaj S/O Mr.Deshraj,Khasra Number-48/1,Krishna Colony,Village-Mamurpur,Narela,Police Station-Narela,Post Office-Narela,Delhi-110040 | 21891 | 21891 | 21891 | 21891 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/9021 | New | New_Built | RTP | 9 | 16 |  | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.8572 | 77.1086 | T21DL03252 | 2021-11-01 | 2021-11-23 | 2021-11-24 | 111-2885-71771085 | 2021-12-23 | 2021-12-24 | 2021-12-24 | 2021-12-27 |  |  | 2021-12-18 | 2021-12-28 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 |  |  |  | 2021-12-15 | ST202112617433 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046928/2021 | 2022-01-03 | 2022-01-04 | DL/01/5126/01561/0031/03/01/10360/NS/04012022 | 2022-01-04 | 2022-01-04 | 2022-01-04 | 2022-01-05 | 2022-01-04 | 2022-01-11 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5425 | [5 empty] | 2021-12-24 | 2021-12-27 | Survey done; Material request hold due to CWIP,Issue closed on 27.12.21 | [9 empty] | 404-10-621891-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | GARI HARSHU | Ms. Kumari Gudiya W/O Sh. Neeraj Kumar Singh,Khata/Khewat No.411/425 Ta 429, M. No. 27 Kila No. 9(8-0), 2 (8-0), 1 (8-0), 10 (8-0) 12/1(2-15),House Number-4 ,Gali Number-4,Near Laxmi Narayan Mandir Garhi Harsaru,Police Station - Sector-10A,Post Office - Garhi Harsaru,Gurugram Haryana 122505 | 21383 | 21383 | 21383 | 21383 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVI | TV_21383_DEL | New | New_Built | RTP | 9 | 13 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.4486 | 76.9344 | 21383 | 2020-12-28 | 2021-09-09 | 2021-09-16 | 11106-2844-85769343 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-28 |  |  | 2021-12-26 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-03-10 |  |  |  | 2021-09-23 | ST202109528779 | S20210030186 |  |  | 2021-09-27 | P/FVC/DEL/1042245/2021 | 2022-03-23 | 2022-03-24 | DL/05/5113/00113/0031/03/01/10456/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 |  | 2022-03-24 | 2022-03-25 | 2022-03-24 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 5157 | [5 empty] | 2021-12-24 | 2022-03-23 | Survey Rejected; Climbing ladder required at Mumty closed on 27.12.21,Public Issue,Material Delivery Date req,Issue closed on 28.12.21,Public Issue at Nearend as on 02.01.22,MCD Issue_Material With Toco as on 02.02.22,Public issue_1829817 Shortage Material Delivery Plan on 06.03.22,Public Issue_MW Installed-Interference & LAN cable req as on 07.03.22,Installed by Toco_Link interference as on 10.03.22,Installed by Toco_HW Down,Access Issue till 16.03.22,Access awaited Team on Site as on 23.03.22 | [9 empty] | 404-10-621383-11 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | MAIN ROAD BURARI | Mr Joginder Bhardwaj S/o Sh Ram Prakash,Khasra number - 346, Main Road Burari, Lal Dora , Village Burari , Post Office - Burari , Police Station - Burari , Delhi - 110084 | 21947 | 21947 | 21947 | 21947 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9610 | New | Sharing | RTT | 12 | 12 |  | SHARING |  | SHARING | YES | >18HRS | NO | 28.7494 | 77.1983 | SR-DL000191 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-11 | 111-2874-93771982 | 2021-12-20 | 2021-12-20 |  |  |  |  | 2021-12-18 | 2021-12-21 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2021-11-12 | ST202111588364 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045800/2021 | 2021-12-22 | 2021-12-23 | DL/01/5428/1803/0031/03/01/10345/NS/23122021 | 2021-12-23 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-01 | 2021-12-27 | 2022-01-05 | 2021-12-27 | 2022-01-03 | 2022-01-09 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 933 | [7 empty] | Antenna Faulty on 23.12.21,Antenna Delivered on 25.12.21 | [9 empty] | 404-10-621947-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VILLAGE - NARAINA | Mr. Kaushal Kumar Nirmal S/O Sh. Gyan chand , House number - WZ-772, Naraina Village,South west Delhi, Naraina, Post Office - Naraina , Police Station - Naraina , New Delhi 110028 | 21960 | 21960 | 21960 | 21960 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3064 | New | Sharing | RTT | 9 | 13 |  | SHARING |  | SHARING | YES | >18HRS | NO | 28.62 | 77.1416 | SR-DL000198 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-01 | 111-2862-00771415 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2021-12-27 |  |  | 2021-12-15 | 2021-12-28 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-30 |  |  |  | 2021-11-12 | ST202111588360 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045796/2021 | 2021-12-30 | 2021-12-31 | DL/01/5428/2768/0031/345/04/08696/NS/31122021 | 2021-12-31 | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-01-05 | 2022-01-03 | 2022-01-09 | 2022-01-03 | 2022-01-10 | 2022-01-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4184 | [5 empty] | 2021-12-23 | 2021-12-30 | Survey done; Material request hold due to CWIP,Issue closed on 27.12.21,Partial Installed_2G Media Issue as on 29.12.21,Issue closed as on 30.12.21 | [9 empty] | 404-10-621960-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Block B, Nathu Pura, Burari | Mrs. Reeta Tripathi W/O Sh. Dheeraj Kumar,House number - B-253/A,Khasra Number - 19/3, Block - B,(Falls in Lal Dora),Village Nathupura, Post Office - Burari , Police Station - Burari, Delhi-110084 | 22023 | 22023 | 22023 | 22023 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3055810 | New | New_Built | RTT | 12 | 10 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.7715 | 77.1761 | R/NN-633123 | 2021-10-11 | 2021-10-23 | 2021-10-27 | 111-2877-14771760 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2022-01-06 |  |  | 2021-12-23 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-13 | 2022-01-14 |  |  |  | 2021-11-10 | ST202111586350 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045124/2021 | 2022-01-15 | 2022-01-17 | DL/01/5177/06506/0031/345/04/08714/NS/17012022 | 2022-01-17 | 2022-01-17 | 2022-01-17 | 2022-01-17 | 2022-01-17 | 2022-01-22 | 2022-01-17 | 2022-01-18 | 2022-01-17 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4505 | [5 empty] | 2021-12-29 | 2022-01-14 | Pole Mount required at Farend_4505,Issue closed on 06.01.22,6 Port MultiBand Antenna not in Stock,resolved on 10.01.22,Partial Installed-GSM Pole required -2 Nos/Power Issue as on 13.01.22,Issue closed as on 14.01.22 | [9 empty] | 404-10-622023-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | WEST AVENUE ROAD PUNJABI BAGH | Mr. Mandeep Kaur,Plot Number - 23,West Avanue Road,Punjabi Bagh,Post Office - Punjabi Bagh,Police Station - Punjabi Bagh, New Delhi - 110026 | 22078 | 22078 | 22078 | 22078 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3082625 | New | New_Built | RTP | 6 | 20 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6706 | 77.1312 | R/NN-636272 | 2021-11-22 | 2021-11-26 | 2021-11-30 | 111-2867-06771312 | 2021-12-19 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | 2021-12-17 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-22 | 2021-12-23 |  |  |  | 2021-12-20 | ST202112622972 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046897/2021 | 2022-01-04 | 2022-01-05 | DL/01/5177/06487/0031/03/01/10362/NS/05012022 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-06 | 2022-01-05 | 2022-01-09 | 2022-01-06 | 2022-01-09 | 2022-01-06 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1209 | [5 empty] | 2021-12-20 | 2022-01-04 | Farend SR Required,Delivered_SACFA Pending as on 22.12.21,Installed_SACFA req as on 23.12.21,Installed_Power Issue & TD SACFA_Pending as on 26.12.21,Issue closed on 04.01.22 | [9 empty] | 404-10-622078-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Max Healthcare Institute Ltd | A-364, Sector – 19, Noida | 27690 | 27690 | 27690 | 27690 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | IBS |  | 20 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.5742 | 77.3233 | NA | 2021-03-27 | 2021-09-08 | 2021-09-08 | 11109-2857-42773229 | 2022-01-12 | 2022-01-13 |  |  |  |  | 2022-01-11 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-15 | 2022-01-16 | [10 empty] | 2022-01-17 |  |  | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-25 | 2022-01-18 | 2022-01-20 | 2022-01-18 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8058 | [5 empty] | 2022-01-15 | 2022-01-17 | Partial Install/Combining Material short as o 15.01.22,Installed_Media Issue as on 17.01.22,Media Issue closed on 17.01.22 | [9 empty] | 404-10-621690-11 | [5 empty] | MAPA_&_On_Air_(MS2) | TD | TD RRU 4418
Del | FY20_21 | Q4 | POLYCAB INDIA LIMITED | PLOT NO B 9 SECTOR 3 1ST FLOOR NOIDA Gautam Buddha Nagar 201301 | 27764 | 27764 | 27764 | 27764 |  |  |  | G900_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | IBS |  | 13 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.5795 | 77.3204 | NA | 2021-11-12 | 2021-11-26 | 2021-11-26 | 11109-2857-94773204 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2022-01-04 |  |  | 2021-12-22 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-06 | 2022-01-08 | [10 empty] | 2022-01-08 |  |  | 2022-01-09 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-12 | 2022-01-10 | 2022-01-12 | 2022-01-10 | 2022-02-02 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5628 | [5 empty] | 2021-12-23 | 2022-01-07 | Survey Rejected; Climbing ladder requiredand Infra material shifting required at new location,Issue closed on 27.12.21,Pole Mount required at Farend_5628 as on 27.12.21,Material dispatch clearance received from Gaurav A on 04.01.22,Partial Install/Das Pending -POP Cutting Team req. /Infra issue -Boundry railing not installed/M/w Farend link Done as on 06.01.22-Issue closed on 07.01.22 | [9 empty] | 404-10-627764-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Haier Appliances | Mr.Arun (Manager).(Chinese Guest House )Plot Number H -06,Haier Appliances PVT LTD Integrated industrial township DMIC,Opposite Villag Raipur Banger,Police Station -Dadri,Post Office - Kasna,Greater Noida | 27760 | 27760 | 27760 | 27760 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | RTP | 9 | 15 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4636 | 77.5878 | NA | 2021-11-12 | 2021-11-26 | 2021-11-26 | 11109-2846-48775893 | 2021-12-20 | 2021-12-21 |  |  |  |  | 2021-12-19 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2021-12-24 |  |  |  | 2021-12-13 | ST202112614871 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046020/2021 | 2021-12-24 | 2021-12-27 | DL/03/0031/00368/0031/03/01/10355/NS/27122021 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-02 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8005 | [5 empty] | 2021-12-20 | 2021-12-24 | TND awaited,Partial Installed_Link Done as on 23.12.21,TDD SACFA received on 24.12.21 | [9 empty] | 404-10-627760-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | NSG Camp,Manesar | Government Land,MBTS location,Near Park No-20 And Near Quarter No-802 to 910,Natioanal Security Guard(NSG) Office,Post Office - Manesar,Police Station - Manesar,Manesar,Gurugram,Haryana-122051 | 19599 | 19599 | 19599 | 19599 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | Cow | 30 | 0 |  | Cow |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.345 | 76.9418 | NA | 2021-11-12 | 2021-11-26 | 2021-11-26 | 11106-2834-49769418 | 2021-12-20 | 2021-12-21 |  |  |  |  | 2021-12-17 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2021-12-28 |  |  |  | 2021-12-15 | ST202112617417 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046923/2021 | 2021-12-28 | 2021-12-29 | DL/05/0031/00602/0031/35/04/00026/NS/29122021 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-01-03 | 2021-12-29 | 2022-01-03 | 2021-12-29 | 2022-01-03 | 2022-01-09 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1720 | [5 empty] | 2021-12-23 | 2021-12-28 | Partial Installed_Mains Not avl,Partial Installed_Mains Not avl & SACFA_Pending as on 23.12.21,Partial Installed_Power Issue & FD SACFA_Pending as on 26.12.21,Issue closed on 28.12.21 | [9 empty] | 404-10-619599-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Inder Enclave PH 2(Relocation of 11300) | Mr. Rahul Yadav,House Number -D -299,Inder Enclave,Phase II, Mubarak Pur Road,Nangloi,Post Office - Aman Vihar Old,Police Station - Prem Vihar,Delhi - 110086 | 22057 | 22057 | 22057 | 22057 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | NA | New | New_Built | RTT | 15 | 9 | 0/90/190 | SHARING |  | SHARING | YES | >18HRS | NO | 28.7073 | 77.0447 | NA | 2021-11-12 | 2021-11-26 | 2021-11-26 | 111-2870-72770446 | 2021-12-23 | 2021-12-24 |  |  |  |  | 2021-12-22 | 2021-12-24 | 2021-12-25 | 2021-12-25 | 2021-12-26 | 2021-12-26 |  |  |  | 2021-12-13 | ST202112614874 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046022/2021 | 2021-12-27 | 2021-12-27 | DL/01/5126/01560/0031/03/01/10354/NS/27122021 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-03 | 2021-12-27 | 2022-01-05 | 2021-12-27 | 2022-01-10 | 2022-01-15 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [18 empty] | 404-10-622057-11 | [5 empty] | MAPA_&_On_Air_(MS2)
Del | FY20_21 | Q4 | Larsen & Toubro | Tower-A, Mathura Rd, Sector 27D, Faridabad | 27770 | 27770 | 27770 | 27770 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | IBS | 0 | 20 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.4763 | 77.3037 | NA | 2021-11-12 | 2021-11-26 | 2021-11-26 | 11106-2847-63773043 | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2021-12-28 |  |  | 2021-12-19 | 2021-12-28 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-30 | [10 empty] | 2022-01-02 |  |  | 2022-01-02 | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-01-06 | 2022-01-03 | 2022-01-09 | 2022-01-03 | 2022-01-10 | 2022-01-15 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11356 | [5 empty] | 2021-12-24 | 2021-12-30 | Survey Rejected; Cable tray required,Issue closed on 27.12.21,Pole required at Farend as discuused with Ashwani K,Issue closed on 28.12.21,Installed_Farend MW mount req & Media Issue as on 29.12.21,Issue closed on 30.12.21 | [9 empty] | 404-10-627770-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Badpura, Pargana and Tehsil Dadri | Mr. Balrajl S/o Mr. Gurga,Village Badhpura,Near By NTPC RO Plant,Dadri,Police Station - Dadri,Post Office - Dadri,Goutam Buddh Nagar,Uttar Pradesh- 203207. | 19762 | 19762 | 19762 | 19762 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3061266 | New | New_Built | RTT | 9 | 12.5 |  | INDUS_LITE+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5625 | 77.5499 | R/NN-633770 | 2021-10-18 | 2021-11-26 | 2021-12-18 | 11109-2856-25775499 | 2021-12-28 | 2021-12-29 |  |  |  |  | 2021-12-30 | 2022-01-03 | 2022-01-04 | [6 empty] | 2021-12-20 | ST202112622860 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046890/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material Delivered by Toco_SRN Done on 23.03.22 | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 5842 |  |  | 1042239/3317134 | 2022-03-23 |  | 2022-01-05 |  | Hold due to TDD RRU & 1/2"Feeder,Material at 1st Floor _Public Issue/hold till further confirmation as on 05.01.2022 | [14 empty] | Material Delivered by Toco_SRN Done on 23.03.22 | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Bhangel Begampur | Mr.Natthi Singh Nagar,Khasra Number - 120,Village - Bhangel Begampur,Police Station - Bhangel,Post Office - Sector-110 Noida,Gautam Buddha Nagar,Uttar Pradesh-201304 | 21874 | 21874 | 21874 | 21874 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3079316 | New | New_Built | RTP | 9 | 19 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.5407 | 77.3862 | R/NN-634773 | 2021-11-08 | 2021-11-26 | 2021-12-18 | 11109-2854-06773861 | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2022-01-11 |  |  | 2021-12-31 | 2022-01-12 | 2022-01-14 | 2022-01-15 | 2022-01-15 | 2022-01-20 |  |  |  | 2021-12-20 | ST202112622973 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046898/2021 | 2022-01-20 | 2022-01-21 | DL/03/5177/00925/0031/345/04/08719/NS/21012022 | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-01-25 | 2022-01-21 | 2022-01-23 | 2022-01-21 | 2022-02-02 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 621 | [5 empty] | 2021-12-31 | 2022-01-11 | Survey Rejected; Mains supply not available, GSM pole mount movement required to aceive 320 degree,Issue closed on 11.01.22,6 Port MultiBand Antenna not in Stock,Partial Install-Temp pwr/Infra issue Main req./Farend Installed as on 15.01.22,Installed_Temp Power/HW Faulty as on 17.01.22 | [9 empty] | 404-10-621874-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Kronos Solutions India Pvt Ltd | OKAYA CENTER,PLOT NO B-5,TOWER 3,4,SECTOR 62 NOIDA UP 201301 | 27271 | 27271 | 27271 | 27271 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27271_DEL | New | New_Built | IBS |  | 20 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.6236 | 77.3617 | 27271 | 2021-08-27 | 2021-12-27 | 2021-12-09 | 11109-2862-35773608 | 2021-12-31 | 2022-01-03 | 2022-01-03 | 2022-01-06 |  |  | 2022-01-02 | [32 empty] | PRI_Closed | MO_Pending | N MALE CONNECTOR 7/8 & N(M) TO N(F) JUMPER NOT IN STOCK,MW Mount req at Farend 1312 | Ericsson/SCM | X | MO_Pending |  | Indus |  | M1 | 1312 | [5 empty] | 2022-01-03 | 2022-01-06 | MW Mount req at Farend_1312,Issue closed on 06.01.22 | [14 empty] | N MALE CONNECTOR 7/8 & N(M) TO N(F) JUMPER NOT IN STOCK | Ericsson/SCM | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Sector 25 Faridabad | Mr. Chanderawato W/O Sukhram,Khasra Number - 104/12/2,Rajiv Colony,Sector 25, Faridabad,Post Office - Ballbahgarh,Police Station - Ballbahgarh,Faridabad Haryana 121004 | 17633 | 17633 | 17633 | 17633 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3078305 | New | New_Built | GBM | 30 | 0 |  | COW |  |  | YES | >18HRS | NO | 28.329 | 77.2953 | R/NN-635946 | 2021-11-17 | 2021-11-22 | 2021-12-15 | 11106-2832-90772953 | 2022-01-04 | 2022-01-05 | 2022-01-05 | 2022-01-09 |  |  | 2021-12-27 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-12 | 2022-01-14 |  |  |  | 2021-12-15 | ST202112617451 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046937/2021 | 2022-01-14 | 2022-01-15 | DL/02/5177/05072/0031/03/01/10368/NS/15012022 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-20 | 2022-01-15 | 2022-01-16 | 2022-01-15 | 2022-01-24 | 2022-01-31 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 130 | [5 empty] | 2022-01-05 |  | Survey Rejected; Mains supply not available and 03 pole mounts required,Issue closed on 09.01.22,Partial Install_Nearend MW Pole Mount Issue as on 12.01.22,Issue as on 13.01.22 | [9 empty] | 404-10-617633-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sec-8 Rohini | Mrs Nutan Gupta W/O Mr. Kishan Chand,House number - 150, Block - B , Pocket - 4,Sector-7, Post Office - Rohini Sector - 7,Police Station - Rohini Sector 7,Rohini, Delhi-110085 | 21859 | 21859 | 21859 | 21859 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032225 | New | New_Built | GBM | 12 | 14 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7042 | 77.1206 | R/NN-628332 | 2021-09-03 | 2021-09-24 | 2021-10-01 | 111-2870-41771206 | 2022-01-04 | 2022-01-05 | 2022-01-05 |  |  |  | 2022-01-06 | [8 empty] | 2021-10-04 | ST202110547618 | S20210030891 |  |  | 2021-10-08 | P/FVC/DEL/1043098/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Access(Public and Owner) Issue | Indus | PRI_Without Material |  | PRI | Indus |  | M1 | 549 | [5 empty] | 2022-01-05 |  | Survey Rejected; Access(Public and Owner) Issue | [14 empty] | Survey Rejected; Access(Public and Owner) Issue | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Wellnex Expert | 4-39, Natraj Rd, DLE Industrial Area, Kirti Nagar, New Delhi, Delhi 110015. | 27772 | 27772 | 27772 | 27772 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | IBS |  | 25 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.6556 | 77.1419 | NA | 2021-11-12 | 2021-11-26 | 2021-11-26 | 111-2865-56771418 | 2022-01-08 | 2022-01-08 | 2022-01-08 | 2022-01-09 |  |  | 2022-01-06 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-11 | 2022-01-12 | [10 empty] | 2022-01-12 |  |  | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-01-18 | 2022-01-13 | 2022-01-15 | 2022-01-13 | 2022-02-09 | 2022-02-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | [5 empty] | M1 | [6 empty] | 2022-01-08 | 2022-01-09 | Access Avl on 09.01.22_Material request without Media readiness,Partially Installed_DAS 300 Mtr as on 11.01.22 | [9 empty] | 404-10-627772-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Shiv Park Village Kakrola (Relocation of 15368) | Mr. Jai Prakash Gehlot, Plot Number - 120,Khasra Number - 27/9,Shiv Park,Old Palam Road,Post Office - Kakrola,Police Station - Dwarka,New Delhi 110078 | 21749 | 21749 | 21749 | 21749 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | RTT | New | New_Built | RTT | 18 | 7.3 |  | INDUS_LITE+ |  |  | YES | >18HRS | NO | 28.6096 | 77.0324 | R/NN-634771 | 2021-11-08 | 2021-11-23 | 2021-12-25 | 111-2860-95770323 | 2022-01-12 | 2022-01-13 |  |  |  |  | 2022-01-07 | 2022-01-15 | 2022-01-15 | 2022-01-16 | 2022-01-16 | 2022-01-17 |  |  |  | 2021-12-15 | ST202112617454 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046940/2021 | 2022-01-19 | 2022-01-20 | DL/01/5177/06512/0031/06/05/13030/NS/20012022 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-22 | 2022-01-20 | 2022-01-22 | 2022-01-20 | 2022-02-03 | 2022-02-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15872 | [5 empty] | 2022-01-13 | 2022-01-18 | 6 Port Antenna Not in Stock,3MTR KINIA TO DIN jumper not in stock as on 15th Jan 22,Installed_Power Issue as on 17.01.22,Installed_Power Issue Closed on 18.01.22 | [9 empty] | 404-10-621749-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | Village-Haldauni, Paragna, Dadari | Mr.Lekhraj Sharma S/o Mr.Late Layak Ram Sharma,Khata Khatoni Number - 00555,Khasra Number - 614,Village Haldauni,Near By Maa Chaumunda Mandir,Kulesra,Police Station - Ecotech 3,Post Office - Kulesra,Greater Noida,Uttar Pradesh-201306. | 21886 | 21886 | 21886 | 21886 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3065542 | New | New_Built | RTT | 9 | 14 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.5379 | 77.4447 | R/NN-634425 | 2021-10-29 | 2021-10-30 | 2021-11-23 | 11109-2853-78774447 | 2022-01-19 | 2022-01-19 |  |  |  |  | 2022-01-18 | 2022-01-20 | 2022-01-20 | 2022-01-21 | 2022-01-21 | 2022-01-22 |  |  |  | 2021-12-07 | ST202112604789 | S20210034198 |  |  | 2021-12-15 | P/FVC/DEL/1046205/2021 | 2022-01-22 | 2022-01-23 | DL/03/5177/00926/0031/03/01/10376/NS/23012022 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 2022-01-27 | 2022-01-23 | 2022-01-25 | 2022-01-23 | 2022-02-02 | 2022-02-05 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4112 | [17 empty] | 404-10-621886-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Chipiyana Buzurg, Ghaziabad | Mrs.Reena Tiwari W/o Mr. Shiv Bhan Tiwari ,Khasra Number 491, Panchlok Colony, Chipyana Bujurg, Police Station Bisrakh, Post Office Chipyana Bujurg , Gautam Buddh Nagar,Uttar Pradesh- 201009. | 19785 | 19785 | 19785 | 19785 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/9032 | New | New_Built | RTP | 6 | 13 |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.6317 | 77.4527 | T21DL03263 | 2021-11-01 | 2021-11-23 | 2021-11-23 | 11109-2863-17774527 | 2022-01-31 | 2022-02-01 | 2022-02-01 |  |  |  | 2022-02-02 | [8 empty] | 2021-12-15 | ST202112617424 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046926/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey rejected; ATC PARSWA Required and Public issue | ATC | PRI_Without Material | 2022-04-18 | PRI | Indus |  | M1 | 536 | [5 empty] | 2022-02-01 |  | Survey Rejected; Access on 03rd-Feb-22,Survey done; Building height not measured due to Public issue and PARSWA approval not received for dispatch,Survey rejected; ATC PARSWA Required and Public issue as on 19.04.22 | [14 empty] | Survey Rejected; Access on 03rd-Feb-22,Survey done; Building height not measured due to Public issue and PARSWA approval not received for dispatch | ATC | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Pushp Vihar | Sector 7, Pushp Vihar,Behind Of flat no.1103,opposite Model Park, New Delhi-110017 | 16748 | 16748 | 16748 | 16748 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1386876 | New | New_Built | Cow | 30 |  |  | COW |  |  | YES | >18HRS | NO | 28.53 | 77.2298 | R/NN-459563 | 2021-12-06 | 2021-12-17 | 2021-12-27 | 111-2852-99772298 | 2022-01-18 | 2022-01-18 |  |  |  |  | 2022-01-17 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-21 | 2022-01-23 |  |  |  | 2020-08-27 | ST202008053885 | S20200003565 |  |  | 2020-09-01 | P/FVC/DEL/1004908/2020 | 2022-01-23 | 2022-01-24 | DL/01/5177/06519/0031/03/01/10380/NS/24012022 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-31 | 2022-01-24 | 2022-01-27 | 2022-01-24 | 2022-02-03 | 2022-02-05 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4974 | [17 empty] | 404-10-616748-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SUPERTECH-2 | Manish Plot No.GH-01,Supertech Capetown North Eye,Tower ORB,Sector-74 ,Noida,Police Station - Sorkha,Post Office - Barola,Uttar Pradesh-201306 | 25200 | 25200 | 25200 | 25200 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Fine bunch | FB0025 | New | New_Built | RTP | 6 | 97 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.5748 | 77.3872 | 25200 | 2021-02-21 | 2021-08-02 | 2021-08-03 | 11109.MNOI.1602979.CWIP-CL | 2022-01-17 | 2022-01-18 | 2022-01-18 | 2022-01-21 |  |  | 2022-01-12 | 2022-01-21 | 2022-01-23 | 2022-01-24 | 2022-01-24 | 2022-01-25 |  |  |  | 2021-08-04 | ST202108408363 | S20210014226 |  |  | 2021-08-08 | P/FVC/DEL/1037387/2021 | 2022-01-25 | 2022-01-29 | DL/03/0031/00374/0031/03/01/10384/NS/29012022 | 2022-01-29 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 2022-01-31 | 2022-02-01 | 2022-01-31 | 2022-02-09 | 2022-02-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5339 | [5 empty] | 2022-01-18 | 2022-01-21 | Farend Owner Issue at 17295,Alternate farnd received on 21.01.22,100 Mtr OFC Faulty on 25.01.22 | [9 empty] | 404-10-625200-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Unitech Commercial Tower-2 | Unitech Commercial Tower-2, Sector-45, Arya Samaj road, Block B, Greenwood city, Gurgaon Haryana, 122003 | 27696 | 27696 | 27696 | 27696 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | IBUS | UNL_HR_GGN_0052 | New | New_Built | IBS |  | 15 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.444 | 77.06 | 27696 | 2021-08-27 | 2021-09-24 | 2021-09-27 | 11106-2844-39770599 | 2022-01-31 | 2022-02-01 | 2022-02-01 | 2022-02-03 |  |  | 2022-01-29 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-05 | 2022-02-05 | [10 empty] | 2022-02-08 |  |  | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-14 | 2022-02-09 | 2022-02-10 | 2022-02-09 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5919 | [5 empty] | 2022-02-01 | 2022-02-08 | Pole required at Farend_397,Issue will closed parallel_Installed_Media Provisioning Issue(Farend change) as on 05.02.22,Installed_Link done-Media issue,Issue closed on 08.02.22,Installed_Link done as on 08.02.22 | [9 empty] | 404-10-627696-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Model Basti, New Delhi | Mr Sanjay Goel ,House Number - 32A,Model Basti,Police Station - Shidipura,Post Office - Manakpura,New Delhi - 110005 | 20108 | 20108 | 20108 | 20108 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PTIPL69 | New | New_Built | RTP | 14 | 9 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6571 | 77.2029 | 20108 | 2021-05-21 | 2021-09-24 | 2021-09-27 | 111-2865-70772029 | 2022-01-31 | 2022-02-01 |  |  |  |  | 2022-01-29 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-08 | 2022-03-10 |  |  |  | 2021-10-04 | ST202110547597 | S20210030891 |  |  | 2021-10-08 | P/FVC/DEL/1043113/2021 | 2022-03-10 | 2022-03-11 | DL/01/5433/00003/0031/03/01/10428/NS/11032022 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-20 | 2022-03-11 | 2022-03-13 | 2022-03-11 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1544 | [5 empty] | 2022-02-08 | 2022-03-10 | Hold due to Parsawa,Owner Issue & Material deliver by toco,Public issue/Infra power issue as on 03.03.22,Issue closed on 10.03.22 | [9 empty] | 404-10-620108-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SECTOR 49,faridabad | Government Land,Municipal Corporation of Faridabad(MCF),GBM Location,Green Belt,Near House Number - A-249, Sainik Colony, Sector- 49, Faridabad,Post Office - NIFM,Police Station - badkhal pali,Faridabad Haryana 121012 | 17380 | 17380 | 17380 | 17380 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3046424 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.4029 | 77.2768 | R/NN-632001 | 2021-08-27 | 2021-09-30 | 2021-10-07 | 11106-2840-29772767 | 2022-01-20 | 2022-01-20 |  |  |  |  | 2022-01-21 | 2022-01-21 | 2022-01-23 | 2022-01-24 | 2022-01-24 | 2022-01-24 |  |  |  | 2021-10-08 | ST202110554407 | S20210031332 |  |  | 2021-10-22 | P/FVC/DEL/1043933/2021 | 2022-01-24 | 2022-01-25 | DL/02/5177/05077/0031/03/01/10383/NS/25012022 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-31 | 2022-01-25 | 2022-01-27 | 2022-01-25 | 2022-02-04 | 2022-02-05 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1931 | [17 empty] | 404-10-617380-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Ganesh nagar(Relocation of 4748) | Mr.Krishan Kumar Gupta S/O Late Goverdhan Dass Gupta,House Number - S 220,Pandav Nagar,Mandawali,Police Station - Pandav Nagar,Post Office - Shakarpur,East Delhi-110092 | 21897 | 21897 | 21897 | 21897 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3064961 | Relocation | New_Built | RTP | 6 | 13.4+2(Mumti) |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.618 | 77.2812 | R/NN-628137 | 2021-08-28 | 2021-11-14 | 2021-11-23 | 111-2861-80772811 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-21 |  |  | 2022-01-18 | 2022-01-21 | 2022-01-23 | 2022-01-24 | 2022-01-24 | 2022-01-25 |  |  |  | 2021-12-07 | ST202112604797 | S20210034198 |  |  | 2021-12-15 | P/FVC/DEL/1046208/2021 | 2022-01-25 | 2022-01-25 | DL/01/5177/06522/0031/03/01/10381/NS/25012022 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 2022-01-31 | 2022-02-02 | 2022-01-31 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8042 | [5 empty] | 2022-01-20 | 2022-01-25 | Survey Rejected; Technology deviation found & TND awaited_Issue closed on 21.01.22,Partial Installed_Farend 8042 MW Mount req as on 24.01.22,Issue closed on 25.01.22,GSM Faulty on 25.01.22 | [9 empty] | 404-10-621897-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | Omega IV, Greater Noida | Mrs. Snehlata SinghW/O Mr.Vaibhav Singh,Plot Number - CC-247,Builders Area (Golf Link-I),Pocket Number- P-8, Greater Noida,Police Station - Old Kasna Road,Post Office - Kasna,Gautam Buddha Nagar-201310 | 19760 | 19760 | 19760 | 19760 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1884434 | New | New_Built | RTP | 6 | 13+3(Mumti) |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4552 | 77.5072 | R/NN-569836 | 2021-04-03 | 2021-10-20 | 2021-10-29 | 11109-2845-52775072 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-03-04 |  |  | 2022-01-22 | 2022-03-08 | 2022-03-10 | [6 empty] | 2021-11-03 | ST202111581275 | S20210032784 |  |  | 2021-11-19 | P/FVC/DEL/1044824/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Public Issue-material delivered by TOCO(SRN Done on 24.03.22) | Indus | PRI_Without Material |  |  | Indus |  | M1 | 4411 |  |  | 1042279 | 2022-03-24 |  | 2022-01-20 |  | Public Issue Hold by Ashwani K,Issue closed on 27.01.22,Public Issue_Material return on 01.02.22,Public Issue_Material return on 01.02.22,Night Delivery and Installation required,Public Issue-material delivered by TOCO as on 11.03.22 | [14 empty] | Public Issue-material delivered by TOCO(SRN Done on 24.03.22) | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Teekli, Gurgaon | Mr. Ram Avtar S/O Sh. Jagat Singh,House Number - 231,Near Husawali Gali,Police Station - Badshahpur,Post Office - Teekli ,Gurugram Haryana 122103 | 21865 | 21865 | 21865 | 21865 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032311 | New | New_Built | RTT | 15 | 7 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.3546 | 77.0292 | R/NN-628359 | 2021-09-03 | 2021-09-14 | 2021-09-24 | 11106-2835-46770292 | 2022-01-20 | 2022-01-20 |  |  |  |  | 2022-01-17 | 2022-01-20 | 2022-01-22 | 2022-01-23 | 2022-01-23 | 2022-01-24 |  |  |  | 2021-09-27 | ST202109535770 | S20210030452 |  |  | 2021-09-30 | P/FVC/DEL/1042614/2021 | 2022-01-24 | 2022-01-25 | DL/05/5177/05317/0031/06/05/13090/NS/25012022 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-02-03 | 2022-01-25 | 2022-01-28 | 2022-01-25 | 2022-02-09 | 2022-02-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5712 | [17 empty] | 404-10-621865-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SGT University | Mr Girish ji (Vice Pesident),Nilgiri Hostel,SGT University,Gurgaon Badli Road Chandu,Village Budhera,Post Office - Village Budhera,Gurugram,Police Station - SGT Gurugram Badli, Haryana 122505 | 27684 | 27684 | 27684 | 27684 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27684 | New | New_Built | RTP | 6 | 19 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4809 | 76.9066 | 27684 | 2021-09-21 | 2021-12-29 | 2022-01-05 | 11106-2848-09769066 | 2022-01-31 | 2022-01-31 |  |  |  |  | 2022-01-30 | 2022-02-02 | 2022-02-04 | 2022-02-05 | 2022-02-05 | 2022-02-07 |  |  |  | 2022-01-20 | ST202201014382 | S20220000841 |  |  | 2022-01-24 | P/FVC/DEL/1048483/2022 | 2022-02-07 | 2022-02-09 | DL/05/0031/00620/0031/345/04/08740/NS/09022022 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-14 | 2022-02-09 | 2022-02-10 | 2022-02-09 | 2022-02-15 | 2022-02-19 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 10016 | [7 empty] | Hold due to Parsawa,Hold due to 20 Mtr OFC | [9 empty] | 404-10-627684-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Between cargo Gate No. 2 & 3 | GBM Location,Cargo Car Parking,Between Cargo Gate No. 2 & 3,And Behind Dalao,T3 International Airport,Terminal 2B Road New Delhi-110037 | 21713 | 21713 | 21713 | 21713 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3074302 | New | New_Built | GBM | 24 | 0 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.5557 | 77.0989 | R/NN-635401 | 2021-11-12 | 2021-11-13 | 2021-11-23 | 111-2855-56770989 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-02-21 |  |  | 2022-01-20 | 2022-02-22 | 2022-02-22 | 2022-02-23 | 2022-02-23 | 2022-02-24 |  |  |  | 2021-12-13 | ST202112614869 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046019/2021 | 2022-02-24 | 2022-02-26 | DL/01/5177/06558/0031/03/01/10412/NS/26022022 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 2022-03-10 | 2022-02-26 | 2022-03-02 | 2022-02-26 | 2022-03-12 | 2022-03-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4164 | [5 empty] | 2022-01-18 | 2022-02-24 | Access Not avl on 18.01.22,Survey Plan 0n 19.01.22,Survey Rejected; Mains or DG supply not available as on 19.1.22,Survey Rejected; Mains or DG supply not available,Documents for passes will be submit on Monday (21st-Feb-2022) as per Indus, material will be request post passes,Issue closed 21.02.22,Partially Installed_Media Issue as on 23.02.22 | [9 empty] | 404-10-621713-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Mawai | Mr. Pardeep Tyagi S/O Prahlad Tyagi, House Number-25, Mouja Mavai Village, Post Office-Amarnagar, Police Station- Khedi Pul, Faridabad, Haryana 121008 | 21984 | 21984 | 21984 | 21984 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVI | RJHAZFD0434 | New | Sharing | GBT | 30 | 0 |  | Sharing |  |  | YES | >18HRS | NO | 28.4373 | 77.3335 | 21984 | 2021-09-22 | 2021-09-22 | 2022-01-06 | 11106-2843-73773334 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-02-07 |  |  | 2022-01-23 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-09 | 2022-02-10 |  |  |  | 2022-01-20 | ST202201014381 | S20220000841 |  |  | 2022-01-24 | P/FVC/DEL/1048482/2022 | 2022-02-10 | 2022-02-11 | DL/02/5113/0071/0031/345/04/08742/NS/11022022 | 2022-02-11 | 2022-02-12 | 2022-02-12 | 2022-02-12 | 2022-02-12 | 2022-02-16 | 2022-02-12 | 2022-02-14 | 2022-02-12 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 14175 | [5 empty] | 2022-01-31 | 2022-02-10 | Hold due to Parsawa,As Per Toco Material dispatch Hold due to Parsawa,Partially Installed_2G Media Issue as on 09.02.22,Media Issue closed on 10.02.22 | [9 empty] | 404-10-621984-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector 7A, Rohini | Dr. Raj Kohli W/O Mr. Vijay Kumar Kohli,Plot Number - 175-176, Block - F, Pocket - 17, Sector 8 Rohini, Landmark Near 24*7 Showroom , Post Office - Sector 8 Rohini, Police Station - Rohini South, Delhi - 110085, | 21820 | 21820 | 21820 | 21820 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016715 | New | New_Built | RTP | 6 | 15 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.702 | 77.1192 | R/NN-627079 | 2021-11-08 | 2021-11-18 | 2021-11-30 | 111-2870-19771192 | 2022-01-19 | 2022-01-19 |  |  |  |  | 2022-01-21 | 2022-01-20 | 2022-01-20 | 2022-01-21 | 2022-01-21 | 2022-01-23 |  |  |  | 2021-12-20 | ST202112622912 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046892/2021 | 2022-01-23 | 2022-01-24 | DL/01/5177/06520/0031/345/04/08725/NS/24012022 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-29 | 2022-01-24 | 2022-01-26 | 2022-01-24 | 2022-02-09 | 2022-02-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 663 | [17 empty] | 404-10-621820-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Pandav Nagar( Relocation of 771 ) | Mr. Surrender Kapoor,House Number - A-28,Pandav Nagar,Police Station - Mandawali,Post Office - Shakarpur,New Delhi 110092 | 22156 | 22156 | 22156 | 22156 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1011024 | New | New_Built | RTT | 15 | 10 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6199 | 77.2849 | R/RES-508829 | 2021-12-24 | 2021-12-30 | 2022-01-18 | 111-2861-99772849 | 2022-01-28 | 2022-01-29 |  |  |  |  | 2022-01-23 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-05 | 2022-02-05 |  |  |  | 2022-01-18 | ST202201012958 | S20220000788 |  |  | 2022-01-25 | P/FVC/DEL/1048518/2022 | 2022-02-05 | 2022-02-07 | DL/01/5177/1080/0031/345/04/08736/NS/07022022 | 2022-02-08 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-19 | 2022-02-15 | 2022-02-19 | 2022-02-15 | 2022-02-25 | 2022-03-05 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8042 | [7 empty] | Hold due to Parsawa,2.5 Sqmm Reserved IUT to store kitty,SCFT Delay due to 2G HW Faulty,MO stuck in CATS | [9 empty] | 404-10-622156-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | Sector 26, M.G Road, Gurgaon | Government Land,North Delhi Municipal Corporation(Parking),MBTS Location,Opposite Ghandhi Park A-6, Near Municipal corporation Department Dhalo, and Right side is Delhi Development Authority ( DDA) flate number - 203( A,B,C ) to 212(A,B,C),Paschim Vihar, Police Station - Paschim Vihar,Post Office - Paschim Vihar,Delhi-110063 | 21188 | 21188 | 21188 | 21188 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1923297 | New | New_Built | Cow | 30 | 0 |  | COW |  |  | YES | >18HRS | NO | 28.6726 | 77.106 | R/NN-617417 | 2021-04-13 | 2021-07-17 | 2021-08-31 | 111-2867-25771059 | 2022-01-28 | 2022-01-29 |  |  |  |  | 2022-01-27 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-01-31 | 2022-02-01 |  |  |  | 2021-09-02 | ST202109505868 | S20210029004 |  |  | 2021-09-19 | P/FVC/DEL/1040614/2021 | 2022-02-01 | 2022-02-02 | DL/01/5177/06526/0031/03/01/10386/NS/02022022 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-07 | 2022-02-02 | 2022-02-03 | 2022-02-02 | 2022-02-09 | 2022-02-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4430 | [17 empty] | 404-10-621188-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418
Del | FY20_21 | Q4 | Block Z, New Gopal Nagar, Khaira | Mr. Krishan Sharma S/O Sh. Ram Swaroop Sharma,House Number-40-C,Khasra No. 8/1,Gopal Nagar Extension Dhansa Road,Near Rail Factory,Police Station - Baba Haridas Nagar ,Post Office - Mitrou,New Delhi 110043 | 21838 | 21838 | 21838 | 21838 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016754 | New | New_Built | RTT | 12 | 8.4 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6034 | 76.9642 | R/NN-627099 | 2021-08-09 | 2021-08-24 | 2021-09-07 | 111-2860-33769642 | 2022-01-28 | 2022-01-29 |  |  |  |  | 2022-01-26 | 2022-02-19 | 2022-02-21 | 2022-02-22 | 2022-02-22 | 2022-02-26 |  |  |  | 2022-03-16 | ST202203073509 | S20220003475 |  | 2022-03-24 | 2021-09-19 | P/FVC/DEL/1040667/2021 | 2022-03-24 | 2022-03-24 | DL/01/5177/06563/0031/03/01/10459/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-30 | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5449 | [5 empty] | 2022-01-31 | 2022-03-24 | Material return on 31.01.22,Issue closed on 19.02.22,Public Issue_Farend installed,Issue closed on 23.02.22,Partial Installed-3rd sector material shifting pending-public issue/Farend installed as on 24.02.22,Power Issue-Installed-Public Issue impacted,Power Issue-Installed-Public Issue impacted as pn 25.02.22,SACFA Pending as on 26.02.22,SACFA Issue reslved on 24.03.22 | [9 empty] | 404-10-621838-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Pilli Kothi NathuPura | Mr. Suresh Kumar S/O Sh. Dhanu Ram, Khasra number - 1078, Gali number - 1, Block - D, Swaroop Vihar, Village Nathupura , Post Office - Swaroop Vihar, Police Station - Swaroop Vihar, Delhi - 110084 | 21978 | 21978 | 21978 | 21978 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3044099 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.766 | 77.1714 | R/NN-630186 | 2021-09-22 | 2021-10-05 | 2021-10-16 | 111-2876-60771713 | 2022-01-28 | 2022-01-29 | 2022-01-29 | 2022-01-31 |  |  | 2022-01-26 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-03 |  |  |  | 2021-10-20 | ST202110564521 | S20210031884 |  |  | 2021-11-13 | P/FVC/DEL/1044435/2021 | 2022-02-19 | 2022-02-20 | DL/01/5177/06546/0031/345/04/08751/NS/20022022 | 2022-02-20 | 2022-02-20 | 2022-02-20 | 2022-02-20 | 2022-02-20 | 2022-02-28 | 2022-02-20 | 2022-02-23 | 2022-02-20 | 2022-02-25 | 2022-03-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4505 | [5 empty] | 2022-01-29 | 2022-02-19 | Pole Mount req at Farend,Issue closed on 31.01.22,Partial Installed_Mains not available & Farend-Nearend MW Pole Req as on 02.02.22,Installed_MW link done & Media Issue as on 03.02.22,Media issue closed on 19.02.22 | [9 empty] | 404-10-621978-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | EMCD_65_Block-16 Geeta Colony (Relocation of 9939) | Mr.Subhash Chand,House Number - 26/1,Khureji Khas,Police Station - Jagatpuri,Post Office - Krishna Nagar,Delhi-110051 | 20895 | 20895 | 20895 | 20895 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3053231 | New | New_Built | RTP | 12 | 12.6 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6475 | 77.2793 | R/NN-632829 | 2021-11-08 | 2021-11-18 | 2021-11-30 | 111-2864-75772793 | 2022-01-28 | 2022-01-29 |  |  |  |  | 2022-01-24 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-03 |  |  |  | 2021-12-15 | ST202112617456 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046941/2021 | 2022-02-04 | 2022-02-05 | DL/01/5177/06528/0031/03/01/10388/NS/05022022 | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-02-09 | 2022-02-05 | 2022-02-08 | 2022-02-05 | 2022-02-15 | 2022-02-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 720 | [5 empty] | 2022-02-02 | 2022-02-03 | INCOMPLETE DUE TO 20 MTR OPTICAL & 5216 NOT IN STOCK,Partial Installed_MW alignment Pending,BBU 5216 Faulty & Media Issue as on 02.02.22,Media Issue closed on 03.02.22 and Installed_link done & BBU 5216 Faulty as on 03.02.22 | [9 empty] | 404-10-620895-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | Meet Nagar | Mr.Arun Kumar Kasana S/O Shri Rajesh Kumar,House Number - A-1/91/1,Khasra Number - 1030,Gali Number - 1,East Gokulpur,Police Station - Meet Nagar,Post Office -Gokulpuri,Delhi-110094 | 21177 | 21177 | 21177 | 21177 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3082666 | New | New_Built | RTP | 9 | 11 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.7057 | 77.2933 | R/NN-636286 | 2021-11-19 | 2021-12-16 | 2022-01-18 | 111-2870-57772932 | 2022-01-28 | 2022-01-29 |  |  |  |  | 2022-01-24 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-03 |  |  |  | 2022-01-14 | ST202201010595 | S20220000629 |  |  | 2022-01-20 | P/FVC/DEL/1048372/2022 | 2022-02-03 | 2022-02-04 | DL/01/5177/06527/0031/345/04/08733/NS/04022022 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-07 | 2022-02-04 | 2022-02-08 | 2022-02-04 | 2022-02-15 | 2022-02-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 535 | [5 empty] | 2022-02-02 | 2022-02-03 | INCOMPLETE DUE TO 20 MTR OPTICAL,Partial Installed_MW aligment pending & Media issue as on 02.02.22,Issue closed as on 03.02.22 | [9 empty] | 404-10-621177-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | J COLONY MADIPUR(Relocation of 17215) | Mr. Vijay Kumar S/O Shri Om Prakash,House Number - B-42, JJ Colony,Madipur,Police Station - Punjabi Bagh,Post Office - Paschimpuri, New Delhi-110063 | 21232 | 21232 | 21232 | 21232 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/8871 | Relocation | New_Built | RTP | 6 | 20 |  | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | NO | 28.6739 | 77.1182 | T21DL02473 | 2021-10-10 | 2021-10-20 | 2021-11-11 | 111-2867-38771181 | 2022-02-17 | 2022-02-18 | 2022-02-18 | 2022-02-19 |  |  | 2022-02-15 | 2022-02-20 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-22 |  |  |  | 2021-11-12 | ST202111588374 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045809/2021 | 2022-03-07 | 2022-03-08 | DL/01/5126/01565/0031/06/05/13378/NS/08032022 | 2022-03-08 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-04-01 | 2022-03-24 | 2022-03-26 | 2022-03-24 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 228 | [5 empty] | 2022-02-18 | 2022-03-07 | ,Access Issue_Partial Installed & MW alignment pending as on 06.03.22 | [9 empty] | 404-10-621232-11 |  |  |  |  | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q4 | New Colony Gurgaon | Mr. Kishan Chand ,Jhumb Guest House,Shop Number 1,Bheem Nagar,Sector 6,Police Station - New Colony,Post office - New Colony, Gurugram, Haryana 122006 | 19833 | 19833 | 19833 | 19833 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19833_DEL | New | New_Built | RTM | 6 | 17.1 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4708 | 77.0189 | 19833 | 2021-02-11 | 2021-07-21 | 2021-08-11 | 11106-2847-07770189 | 2022-02-08 | 2022-02-09 |  |  |  |  | 2022-02-06 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-11 | 2022-02-11 |  |  |  | 2022-03-01 | ST202203058376 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051265/2022 | 2022-03-13 | 2022-03-14 | DL/05/0031/00622/0031/03/01/10441/NS/14032022 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-22 | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4723 | [5 empty] | 2022-02-11 | 2022-03-12 | Releasing address mismatch with applied SACFA Address | [9 empty] | 404-10-619833-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sec-37 by pass(Relocation of 15182) | Government Land,Faridabad Authority GBM Location,Green Belt,in Front of Electric Pole Number 33776,Faridabad Bypass Rd,Block F, Molar band Extension, Sector 37,Post Office - Molarband,Police Station - Molarband Faridabad, Haryana 121009 | 17580 | 17580 | 17580 | 17580 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL124 | Relocation | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4841 | 77.3127 | 17580 | 2021-08-27 | 2021-10-20 | 2021-11-15 | 11106-2848-40773127 | 2022-02-08 | 2022-02-09 |  |  |  |  | 2022-02-10 | 2022-02-09 | 2022-02-11 | [6 empty] | 2021-11-19 | ST202111595353 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045397/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 12.02.22 due to Public Issue | 3rd Party PRI | PRI_Without Material |  | PRI | Indus |  | M1 | 9855 | [5 empty] | 2022-02-12 |  | Material return on 12.02.22 due to Public Issue | [14 empty] | Material return on 12.02.22 due to Public Issue | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | BALDEV NAGAR | Mr. Kapil House Number-743/26 Baldev Nagar,Police Station - New Colony,Post Office - New Colony Sub,Gurugram Haryana 122001 | 20412 | 20412 | 20412 | 20412 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20412_DEL | New | New_Built | RTT | 15 | 7 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4592 | 77.0101 | 20412 | 2021-08-27 | 2021-11-28 | 2022-01-17 | 11106-2845-91770101 | 2022-02-17 | 2022-02-18 |  |  |  |  | 2022-02-15 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-21 |  |  |  | 2022-03-01 | ST202203058377 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051266/2022 | 2022-03-13 | 2022-03-14 | DL/05/0031/00628/0031/03/01/10438/NS/13032022 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-03-14 | 2022-02-25 | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 706 | [5 empty] | 2022-02-21 | 2022-03-12 | Releasing address mismatch with applied SACFA Address | [9 empty] | 404-10-620412-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Block C, Vishal Enclave, Tagore Garden Extension | Shop number - 202, Shivaji Market Tegore Garden , Post Office - Tegore Garden, Police Station - Tegore Garden, Delhi 110027 | 19631 | 19631 | 19631 | 19631 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | PJDL052 | New | New_Built | RTT | 9 | 13 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.651 | 77.1129 | 19631 | 2021-11-10 | 2021-12-02 | 2021-12-13 | 111-2865-12771138 | 2022-02-08 | 2022-02-09 |  |  |  |  | 2022-02-06 | 2022-02-09 | 2022-02-11 | 2022-02-12 | 2022-02-12 | 2022-02-15 |  |  |  | 2021-12-15 | ST202112617422 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046924/2021 | 2022-02-15 | 2022-02-16 | DL/01/0031/03120/0031/345/04/08747/NS/16022022 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-02-22 | 2022-02-16 | 2022-02-19 | 2022-02-16 | 2022-02-25 | 2022-03-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 957 | [5 empty] | 2022-02-12 | 2022-02-15 | Material Delivery by Toco_Public Issue Impacted | [9 empty] | 404-10-619631-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | DC Residence, Sec-15A, Faridabad | Residence of Deputy Commisioner,GBM Location,In Front Of Pole Number - 78,of Faridabad,Urban Estate, Sector 15A,Post Office - Sector 15,Police Station - Sector 15, Faridabad, Haryana 121007 | 22054 | 22054 | 22054 | 22054 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Olympians | G/04/F | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.3985 | 77.3189 | 22054 | 2021-11-08 | 2021-11-13 | 2021-11-23 | 11106-2839-85773188 | 2022-02-08 | 2022-02-09 | 2022-02-09 | 2022-02-10 |  |  | 2022-02-06 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-12 | 2022-02-14 |  |  |  | 2021-12-07 | ST202112604804 | S20210034198 |  |  | 2021-12-15 | P/FVC/DEL/1046211/2021 | 2022-02-14 | 2022-02-15 | DL/02/0031/00263/0031/03/01/10397/NS/15022022 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-18 | 2022-02-15 | 2022-02-19 | 2022-02-15 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4009 | [5 empty] | 2022-02-09 | 2022-02-10 | Pole Mount req at Farend,Issue closed on 10.02.22 | [9 empty] | 404-10-622054-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | KURALI | Mrs. Bimla W/o Late Jugal Kishor,Village Junhera Near Panchayat Bhawan, Junhera (87),In Front Of Pole Number.35,Post Office - Tihgao,Police Station - Tigao,Faridabad, Haryana 121101 | 21956 | 21956 | 21956 | 21956 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-BLBG-ENB-9005 | New | New_Built | RTT | 12 | 7 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.317 | 77.4067 |  | 2021-09-22 | 2021-10-22 | 2021-10-25 | 11106-2831-70774067 | 2022-02-01 | 2022-02-02 |  |  |  |  | 2022-01-30 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-04 | 2022-02-05 |  |  |  | 2021-11-15 | ST202111589879 | S20210033274 |  |  | 2021-12-08 | P/FVC/DEL/1045898/2021 | 2022-03-07 | 2022-03-08 | DL/02/5428/0208/0031/03/01/10425/NS/08032022 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-13 | 2022-03-08 | 2022-03-10 | 2022-03-08 | [6 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | Less Payload | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 9624 | [5 empty] | 2022-02-05 | 2022-03-07 | Installed_2G Media Issue,as on 05.02.22 | [9 empty] | 404-10-621956-11 |  |  |  |  | Power Issue | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SHIV DURGA VIHAR | Mr. Naresh Kumar S/O Deepak Kumar,House Number - D2-559,Lakarpur,Shiv Durga Vihar,Faridabad,Post Office - Badarpur,Police Station - Badarpur, Haryana 121010 | 21949 | 21949 | 21949 | 21949 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-FDBD-ENB-3909 | New | New_Built | RTT | 12 | 7 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.4874 | 77.2974 |  | 2021-09-22 | 2021-09-30 12:42 | 2021-11-16 | 11106-2848-74772973 | 2022-02-01 | 2022-02-02 |  |  |  |  | 2022-01-04 | 2022-02-02 | 2022-02-04 | 2022-02-05 | 2022-02-05 | 2022-02-08 |  |  |  | 2021-11-19 | ST202111595369 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045399/2021 | 2022-02-08 | 2022-02-09 | DL/02/5428/0312/0031/345/04/08739/NS/09022022 | 2022-02-09 | 2022-02-14 | 2022-02-14 | 2022-02-14 | 2022-02-14 | 2022-02-17 | 2022-02-14 | 2022-02-15 | 2022-02-14 | 2022-02-21 | 2022-02-28 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 979 | [7 empty] | Partially Installed_VSWR Issue as on 08.02.22,RSSI High | [9 empty] | 404-10-621949-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | BAKOLI BAKHTWAR PUR ROAD | Mr. Sakhil Singh,Khasra number - 78/68,Near UMA Dharam Kanta,Village Bakoli,Post Office - Village Bakoli,Police Station - Ali Pur,Delhi - 110036 | 20326 | 20326 | 20326 | 20326 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3964 | New | New_Built | RTT | 15 | 8 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.8113 | 77.1428 | SR-DL000158 | 2021-08-22 | 2021-09-01 | 2021-11-30 | 111-2881-13771427 | 2022-02-01 | 2022-02-02 |  |  |  |  | 2022-01-08 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-04 | 2022-02-04 |  |  |  | 2021-12-20 | ST202112623013 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046900/2021 | 2022-02-04 | 2022-02-05 | DL/01/5428/1632/0031/06/05/13131/NS/05022022 | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-02-15 | 2022-02-05 | 2022-02-07 | 2022-02-05 | 2022-02-15 | 2022-02-19 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4502 | [17 empty] | 404-10-620326-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Kamla Nehru Nagar | Mr. Gajender Yadav S/o Mr. Vijay Pal, House, Plot Number - 202 ,Harsaon,Kamla Nehru Nagar,Near By Shanti Farm House, Police Station - Kavi Nagar,Post Office - Police Line Harsaon ,Ghaziabad,Uttar Pradesh-201001. | 21953 | 21953 | 21953 | 21953 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GZBD-ENB-4142 | New | New_Built | RTT | 12 | 8 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6804 | 77.4743 | NA | 2021-09-22 | 2021-09-30 12:42 | 2021-11-01 | 11109-2868-04774742 | 2022-02-01 | 2022-02-02 |  |  |  |  | 2022-01-20 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-04 | 2022-02-04 |  |  |  | 2021-11-12 | ST202111588362 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045798/2021 | 2022-02-07 | 2022-02-08 | DL/04/5428/0372/0031/345/04/08737/NS/08022022 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-16 | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 619 | [5 empty] | 2022-02-04 | 2022-02-07 | Installed_MW link Done & Media Issue as on 04.02.22,Media Issue closed on 07.02.22 | [9 empty] | 404-10-621953-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Atmadpur Village, Faridabad | Mr. Suraj S/O Mahender,Khewat Number - 44 // 41,Khatoni Number - 46,Khasra Number - 5// 17/1 (3-15),in Front Of Pole Number T2 ,Colony,Atmadpur Village,Post Ofice - Sec 28,Police Station - Sec 28,Faridabad, Haryana 121003 | 22022 | 22022 | 22022 | 22022 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-FDBD-ENB-9018 | New | New_Built | GBT | 25 | 0 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.443 | 77.3331 | NA | 2021-10-18 | 2021-12-03 | 2022-01-24 | 11106-2844-29773331 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-06 |  |  | 2022-01-27 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-08 | 2022-02-08 |  |  |  | 2021-12-13 | ST202112614864 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046017/2021 | 2022-02-09 | 2022-02-10 | DL/02/5428/0287/0031/345/04/08741/NS/10022022 | 2022-02-10 | 2022-02-12 | 2022-02-12 | 2022-02-12 | 2022-02-12 | 2022-02-16 | 2022-02-12 | 2022-02-19 | 2022-02-12 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 14175 | [5 empty] | 2022-02-02 | 2022-02-06 | Height deviation 18M | [9 empty] | 404-10-622022-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sec 6 Sultanpuri | Mrs. Kiran Modi W/O Mr. Mahesh Modi,Plot Number - 37, Block F-6, JJ Colony, Sultanpuri, Landmark Noori Masjid, Post Office - Sultanpuri, Police Station - Sultanpuri, New Delhi - 110041, | 21824 | 21824 | 21824 | 21824 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016734 | New | New_Built | RTP | 9 | 13.6 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6879 | 77.0681 | R/NN-627091 | 2021-08-09 | 2021-12-07 | 2022-01-18 | 111.2868.78770681.CWIP-CL | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-03 |  |  | 2022-01-31 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-05 | 2022-02-05 |  |  |  | 2022-01-14 | ST202201010591 | S20220000629 |  |  | 2022-01-20 | P/FVC/DEL/1048370/2022 | 2022-02-07 | 2022-02-08 | DL/01/5177/06530/0031/345/04/08738/NS/08022022 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-14 | 2022-02-08 | 2022-02-10 | 2022-02-08 | 2022-02-15 | 2022-02-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1154 | [5 empty] | 2022-02-02 | 2022-02-07 | MW Farend Pole Mount Required_1154,Issue will closed parallel,Installed & Farend MW Pole req & Media Not Provisioned as on 05.02.22,Media Issue closed on 07.02.22 | [9 empty] | 404-10-621824-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | C Park in Sec-23 Rohini | Mr. Sunil Solanki S/O Khehar Singh, House number - WZ-697, Khasra number - 62/21/1, Badiyal Village Palam, Post Office - Palam ,Police Station - Palam, New Delhi - 110045 | 21587 | 21587 | 21587 | 21587 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3071660 | New | New_Built | RTT | 15 | 10 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5859 | 77.0794 | R/NN-634770 | 2021-11-08 | 2021-11-13 | 2021-11-23 | 111.2858.59770794.CWIP-CL | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-03 |  |  | 2022-02-03 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-05 | 2022-03-03 |  |  |  | 2021-12-07 | ST202112604798 | S20210034198 |  |  | 2021-12-15 | P/FVC/DEL/1046209/2021 | 2022-03-03 | [16 empty] | PRI_Closed | PRI_BEFORE_MS1 | EMF Failed | Indus | PRI_With Material |  | PRI | Indus |  | M1 | 1364 | [5 empty] | 2022-02-02 |  | MW Farend Pole Mount Required_1364,Issue will closed parallel,Material Delivered_Installation Hold by Toco due to 10 Port Antenna as on 07.02.22,Partially Installed_Power Issue as on 09.02.22,Issue closed on 02.03.22,EMF failed as on 02.03.22 | [9 empty] | 404-10-621587-11 |  |  |  |  | EMF Failed | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | DLF The Ultima Gurugram | DLF The Ultima sec-81 Gurugram Haryana-122004 | 27697 | 27697 | 27697 | 27697 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1366148 | New | New_Built | IBS |  | 15 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.3888 | 76.954 | IBSR/RES-822 | 2021-04-21 | 2021-08-04 | 2021-08-31 | 11106-2838-87769539 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-22 |  |  | 2022-01-30 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-03-08 | [10 empty] | 2022-03-21 |  |  | 2022-03-21 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-31 | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11260 | [5 empty] | 2022-02-02 | 2022-03-21 | Survey Rejected; FMS not Available,Material to be dispatch after discussion With Ankur Sir as on 22.02.22,Partial installed/FMS issue/Media Issue as on 24.02.22,N(M) to N(M) Jumper to be dispatch as on 07.03.22,Installed FMS Connectivity Issue as on 08.03.22,Issue closed on 21.03.22 | [9 empty] | 404-10-627697-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | DLF The Ultima Gurugram-2 | DLF The Ultima sec-81 Gurugram Haryana-122004 | 27698 | 27698 | 27698 | 27698 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1366148 | New | New_Built | IBS |  |  |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.3888 | 76.954 | IBSR/RES-822 | 2021-04-21 | 2021-08-04 | 2021-08-31 | 11106-2838-87769539 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-02-22 |  |  | 2022-01-30 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-03-08 | [10 empty] | 2022-03-24 |  |  | 2022-03-24 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-30 | 2022-03-25 | 2022-03-28 | 2022-03-25 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5358 | [5 empty] | 2022-02-02 | 2022-03-24 | Survey Rejected; FMS not Available,Material to be dispatch after discussion With Ankur Sir as on 22.02.22,Partial installed/FMS issue/Media Issue as on 24.02.22,N(M) to N(M) Jumper to be dispatch as on 07.03.22,Installed FMS Connectivity Issue as on 08.03.22,Installed_FMS Connectivity Issue_Fiber Team timing at 12:00 PM_24.03.22 | [9 empty] | 404-10-627698-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Saad Nagar-II Palam (Relocation of 11210) | Mr. Jitendra Bharadwaj, House Number - RZ F-87D,Plot Number - 7/1,Khasra Number - 91/25, 93/21 Min,Saadh Nagar,Palam colony,Post Office - Saadh Nagar,Police station - Palam, New Delhi 110045 | 22058 | 22058 | 22058 | 22058 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3079320 | Relocation | New_Built | RTT | 15 | 9 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.5913 | 77.089 | R/NN-635944 | 2021-11-17 | 2021-11-26 | 2022-01-24 | 111-2859-13770889 | 2022-02-01 | 2022-02-02 |  |  |  |  | 2022-01-30 | 2022-02-04 | 2022-02-06 | 2022-02-07 | 2022-02-07 | 2022-02-08 |  |  |  | 2021-12-20 | ST202112622909 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046891/2021 | 2022-02-14 | 2022-02-15 | DL/01/5177/06537/0031/03/01/10398/NS/15022022 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-25 | 2022-02-19 | 2022-02-21 | 2022-02-19 | 2022-02-25 | 2022-03-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 14193 | [5 empty] | 2022-02-08 | 2022-02-14 | 2.5 Sqmm Reserved IUT to store kitty & MIMO Not in Stock,Installed_Link Done Power Issue as on 08.02.22,Issue closed on 14.02.22,GSM Faulty | [9 empty] | 404-10-622058-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD RRUS14B3,L_2100 RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q4 | TPDDL Bawana 7 Grid. ( Relocation of 19707 ) | Government Land,GBM Location,Tata Power Delhi Distribution Limited,66Kv Grid Substation Building,Opposite Pragati Power,Infront of house Number - B-86, & B-87,Bawana Industrial Area,Post office - Bawana,Police Station - Bawana,New Delhi - 110039 | 22173 | 22173 | 22173 | 22173 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1359490 | Relocation | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.795 | 77.0766 | R/RES-508931 | 2022-01-02 | 2022-01-04 | 2022-01-18 | 111-2879-49770765 | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-03-22 |  |  | 2022-01-30 | 2022-03-23 | 2022-03-23 | 2022-03-24 | 2022-03-24 | 2022-03-25 |  |  |  | 2022-01-18 | ST202201012969 | S20220000788 |  |  | 2022-01-25 | P/FVC/DEL/1048519/2022 | 2022-03-25 | 2022-03-26 | DL/01/5177/5785/0031/03/01/10469/NS/26032022 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-04-02 | 2022-03-26 | 2022-03-28 | 2022-03-26 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-16 |  | Indus |  | M1 | 333 | [5 empty] | 2022-02-02 | 2022-03-22 | Survey Rejected; Access Issue (Details to be share for Access),MW Farend Pole Mount Required_333,Nearend Access Issue | [9 empty] | 404-10-622173-11 |  |  |  |  | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 Available on Parent SIte
Del | FY20_21 | Q4 | M3M Urbana Business Park | M3M Urbana Business Park,Tower A& BGolf Course Ext Rd Ramgarh, Sector 67 Gurugram, Haryana 122002 | 27769 | 27769 | 27769 | 27769 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | SIPLHR016 | New | New_Built | IBS |  | 20 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.39 | 77.0649 |  | 2022-01-03 | 2022-01-07 | 2022-01-24 | 11106-2838-99770649 | 2022-02-02 | 2022-02-03 |  |  |  |  | 2022-01-31 | 2022-02-06 | 2022-02-08 | 2022-02-09 | 2022-02-09 | 2022-02-12 | [10 empty] | 2022-02-12 |  |  | 2022-02-12 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-02-24 | 2022-02-15 | 2022-02-19 | 2022-02-15 | 2022-02-21 | 2022-02-28 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11110 | [7 empty] | Hold due to Parsawa | [9 empty] | 404-10-627769-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Magic Bricks | B-20, Block B, Sector 3, Noida, Uttar Pradesh 201301 | 27778 | 27778 | 27778 | 27778 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | IBS |  | 32 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.5793 | 77.3192 |  | 2022-01-03 | 2022-01-07 | 2022-01-24 | 11109-2857-91773193 | 2022-02-08 | 2022-02-09 |  |  |  |  | 2022-02-05 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-24 | [10 empty] | 2022-02-24 |  |  | 2022-02-24 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-03-03 | 2022-02-25 | 2022-03-02 | 2022-02-25 | 2022-03-12 | 2022-03-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 903 | [7 empty] | FDD Jumper Not in Stock,partial Installed/POP Team req.-DAS 890 mtr-IBS jumper short 8 nos/Link Done-BBU ping ok as on 23.02.22 | [9 empty] | 404-10-627778-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800) | 2G RRU 2219
Del | FY20_21 | Q4 | Near DND Flyover | Government Land,GBM Location,In Front of Pole Number - PD-58,Delhi Noida Direct Flyway,New Friends Colony,Post Office - New Friends Colony,Police Station - New Friends Colony, New Delhi, Delhi 110024 | 22236 | 22236 | 22236 | 22236 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | NTGA_25654 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | NO | 28.5779 | 77.2786 | NA | 2022-01-28 | 2022-01-28 | 2022-01-28 | 111-2857-79772785 | 2022-02-11 | 2022-02-11 |  |  |  |  | 2022-02-08 | 2022-02-11 | 2022-02-13 | 2022-02-14 | 2022-02-14 | 2022-02-15 |  |  |  | 2022-01-31 | ST202202026017 | S20220001291 |  |  | 2022-02-09 | P/FBW/DEL/1049159/2022 | 2022-02-16 | 2022-02-17 | DL/01/9037/00002/0031/03/01/10402/NS/17022022 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-21 | 2022-02-17 | 2022-02-19 | 2022-02-17 | 2022-03-12 | 2022-03-12 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 184 | [5 empty] | 2022-02-15 | 2022-02-16 | Partial Installed - Site ID change from 25654 to 22236,Installed_2G Media Issue as on 15.02.22,Issue closed on 16.02.22 | [9 empty] | 404-10-622236-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Bawana(Relocation of 13458) | Mr. Vikas Dahiya S/O Sh. Dharambir Dahiya, House number - 34, Near Shiv Mandir , Vijay Nagar Main Road, Bawana , Post Office - Bawana , Police Station - Bawana , Delhi - 110039 | 19926 | 19926 | 19926 | 19926 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | ALICE | AT-DL-0031 | New | New_Built | RTP | 6 | 17 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.7994 | 77.0401 | NA | 2021-01-10 | 2021-11-30 | 2021-11-30 | 111-2879-93770401 | 2022-02-11 | 2022-02-11 |  |  |  |  | 2022-02-08 | 2022-02-11 | 2022-02-13 | 2022-02-14 | 2022-02-14 | 2022-02-14 |  |  |  | 2021-12-15 | ST202112617445 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046932/2021 | 2022-02-14 | 2022-02-15 | DL/01/0031/03115/0031/03/01/10399/NS/15022022 | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2022-02-23 | 2022-02-18 | 2022-02-21 | 2022-02-18 | 2022-02-25 | 2022-03-05 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9063 | [7 empty] | BBU Faulty | [9 empty] | 404-10-619926-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Chhelera | Mr Jitender Kumar S/o Sh Chattar Singh, Khasra No.- 513,Near Royal Residency, Plot Number-D 11, Block-C ,Village-Chhelera, Sector-44, Police Station - Sector 37, Post Office - Sector 45 ,Noida,Uttar Pradesh - 201301 | 11473 | 11473 | 11473 | 11473 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-NOID-ENB-4099 | New | New_Built | RTT | 12 | 16 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.5544 | 77.3369 | SO-DL000030 | 2021-07-18 | 2021-08-26 | 2021-09-21 | 11109-2855-44773368 | 2022-02-11 | 2022-02-11 |  |  |  |  | 2022-02-08 | 2022-02-11 | 2022-02-13 | 2022-02-14 | 2022-02-14 | 2022-02-16 |  |  |  | 2021-09-16 | ST202109522335 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041982/2021 | 2022-02-18 | 2022-02-19 | DL/03/5428/0451/0031/345/04/08750/NS/19022022 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-24 | 2022-02-19 | 2022-02-21 | 2022-02-19 | 2022-02-25 | 2022-03-05 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 639 | [5 empty] | 2022-02-14 | 2022-02-15 | Partially Installed_Farend Access Issue 639,Installed_Link Done/BBU 6630 used at Rasid Gate as on 16.02.22 | [9 empty] | 404-10-611473-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | EMCD_24_BLOCK NO. 05 GEETA COLONY | Property Bearing No. 5/7/17, Block No. 5, Lane No. 7, Qtr. No. 17, Geeta Colony, Jheel Kurenja, Delhi-110031 | 20860 | 20860 | 20860 | 20860 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3033714 | New | New_Built | GBT | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6513 | 77.2713 | R/NN-627536 | 2021-08-17 | 2021-09-13 | 2021-11-11 | 111-2865-12772712 | 2022-02-11 | 2022-02-11 | 2022-02-11 | 2022-02-13 |  |  | 2022-02-13 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-15 | 2022-02-16 |  |  |  | 2021-11-15 | ST202111589872 | S20210033274 |  |  | 2021-12-08 | P/FVC/DEL/1045891/2021 | 2022-02-16 | 2022-02-17 | DL/01/5177/06543/0031/06/05/13224/NS/17022022 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-19 | 2022-02-17 | 2022-02-19 | 2022-02-17 | 2022-02-21 | 2022-02-28 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 720 | [5 empty] | 2022-02-11 | 2022-02-15 | Locator Pending,Partially Installed_Farend Owner 720 as on 15.02.22 | [9 empty] | 404-10-620860-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | EMCD_54_Khureji Khas | Mohd. Ashraf S/O Sh. Akhtar Ali, House numbe -17, Arampark,Gali number - 4D, Khureji Khas , Post Office - Aram Park , Police Station - Geeta Colony, New Delhi - 110031 | 17988 | 17988 | 17988 | 17988 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Protel Telepower Infrastructure Pvt Ltd. | PTIPL105 | New | New_Built | RTP | 9 | 18 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6433 | 77.2779 | NA | 2021-10-14 | 2021-10-20 | 2021-11-11 | 111-2864-32772778 | 2022-02-14 | 2022-02-14 | 2022-02-14 | 2022-02-28 |  |  | 2022-02-16 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-03 |  |  |  | 2021-11-12 | ST202111588381 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045811/2021 | 2022-03-03 | 2022-03-04 | DL/01/5433/00002/0031/03/01/10414/NS/04032022 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-10 | 2022-03-05 | 2022-03-08 | 2022-03-05 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1020 | [5 empty] | 2022-02-14 | 2022-02-28 | Survey Rejected; Safety railing required, EB power is on Sub-meter, PARSWA Base required, Cable tray from BTS PAD to Tower required, Public issue,Farend Pole Mount reuired on 25.02.22,Issue closed on 28.02.22,Partial Installed-BBU Faulty-6630(new kitty)/Mains connetion pending cable req./MW installed-TND Issue as on 02.03.22,RSSI High as on 04.03.22 | [9 empty] | 404-10-617988-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | ACME CLEANTECH SOLUTIONS PRIVATE LIMITED | Plot No. 152, sector -44, Gurgaon - 122002 | 27765 | 27765 | 27765 | 27765 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | DELR4435 | New | New_Built | IBS |  | 20 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.4472 | 77.0785 | NA | 2021-11-20 | 2021-12-03 | 2021-12-16 | 11106-2844-72770784 | 2022-02-14 | 2022-02-15 |  |  |  |  | 2022-02-11 | 2022-02-18 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-22 | [10 empty] | 2022-02-22 |  |  | 2022-02-22 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-28 | 2022-02-23 | 2022-02-25 | 2022-02-23 | 2022-03-21 | 2022-03-29 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4732 | [7 empty] | FDD Jumper Not in Stock,Installed-combining pending(IBS jumper short 7 nos)/cable tray req.-BBU Ping ok as on 21.02.22 | [9 empty] | 404-10-627765-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 ,TD RRU 4418
Del | FY20_21 | Q4 | Punjab explorer compound | Plat No 2/3,Saraswati metal works,gali no 7 punjab explorer compound gzb-201003 | 20997 | 20997 | 20997 | 20997 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | GTL | DEL/RTT/K/20280 | New | New_Built | RTT | 15 | 10 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6811 | 77.4291 | NA | 2021-10-10 | 2021-04-20 | 2021-11-22 | 11109-2868-10774291 | 2022-02-15 | 2022-02-16 | 2022-02-16 | 2022-02-17 |  |  | 2022-02-12 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-19 | 2022-02-24 |  |  |  | 2021-04-22 | ST202104166421 | S20210007457 |  |  | 2021-07-22 | P/FVC/DEL/1036054/2021 | 2022-02-24 | 2022-02-25 | DL/04/5297/0072/0031/03/01/10410/NS/25022022 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-03-10 | 2022-02-25 | 2022-03-08 | 2022-02-25 | 2022-03-12 | 2022-03-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 290 | [5 empty] | 2022-02-16 | 2022-02-24 | 8U Space required for BBU installation and GSM pole mount movement required for planned degree achievement,Issue closed on 17.02.22,Media Issue reoprted on 19.02.22 | [9 empty] | 404-10-620997-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Modeltown-Gaziabad (Relocation of 141) | Sri Vaishno Mandir Sewa Samiti,Infront Of Plot Number-105,Arya Nagar,Dharampura,G.T.Road,Police Station-Kotwali Ghantaghar,Post Office-Arya Nagar,Ghaziabad,Uttar Pradesh-201009 | 22213 | 22213 | 22213 | 22213 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1075425 | New | New_Built | RTT | 15 | 8 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6571 | 77.4316 | R/RES-509128 | 2022-01-21 | 2022-01-25 | 2022-02-01 | 11109.2865.70774315.CWIP-CL | 2022-02-15 | 2022-02-16 | 2022-02-16 | 2022-02-18 |  |  | 2022-02-12 | 2022-02-19 | 2022-02-21 | 2022-02-22 | 2022-02-22 | 2022-02-23 |  |  |  | 2022-02-02 | ST202202027665 | S20220001393 |  |  | 2022-02-15 | P/FVC/DEL/1049402/2022 | 2022-02-24 | 2022-02-25 | DL/04/5177/0087/0031/345/04/08755/NS/25022022 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-03-08 | 2022-02-25 | 2022-02-26 | 2022-02-25 | 2022-03-12 | 2022-03-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4413 | [5 empty] | 2022-02-16 | 2022-02-24 | Space to be punch by planning for Indus PARSWA canopy, Available GSM pole mounts height is not as per plan,3rd sector installed/GSM pole blockage, 1st 2nd, canopy not installed/Link Done as on 21.02.22,Installed_User Plane Not reachable as on 23.02.22 | [9 empty] | 404-10-622213-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q4 | Radha Krishana Temple, Noida Ext. | Plot No.5,Khasra No.8,Village-Haibatpur,Tehsil Dadri,Gautam buddha Nagar,Uttar Pradesh-201009 | 20274 | 20274 | 20274 | 20274 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1476081 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6178 | 77.4166 | R/NN-512028 | 2020-10-29 | 2020-11-06 | 2020-11-21 | 11109-2861-78774165 | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-02-18 |  |  | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-22 |  |  |  | 2020-11-27 | ST202011158379 | S20200008804 |  |  | 2020-12-16 | P/FVC/DEL/1012730/2020 | 2022-02-22 | 2022-02-23 | DL/04/5177/00807/0031/03/01/10406/NS/23022022 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-03-07 | 2022-02-25 | 2022-02-26 | 2022-02-25 | 2022-03-12 | 2022-03-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1443 | [5 empty] | 2022-02-16 | 2022-02-22 | Survey Rejected; Mains supply not available,Partial Installed/Mains not availabe-DG not working as on 21.02.22 | [9 empty] | 404-10-620274-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Dr. Lal path lab rohini | Dr. Lal path lab rohini sec-18,new delhi | 27753 | 27753 | 27753 | 27753 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27753 | New | New_Built | IBS |  | 17 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.7387 | 77.1365 | NA | 2021-10-05 | 2021-12-27 | 2022-01-21 | 111.2873.86771364.CWIP-CL | 2022-02-16 | 2022-02-16 |  |  |  |  | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-24 | [10 empty] | 2022-02-25 |  |  | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-03-07 | 2022-02-25 | 2022-02-27 | 2022-02-25 | 2022-03-18 | 2022-03-19 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8164 | [7 empty] | Hold due to IBS feeder 7/8"(1930 mtr) & FDD Jumper,Installed/-DAS 2130 mtr night permission 4 floor done 1 and half floor pending-combining pending/Link done-BBU ping ok as on 24.02.22 | [9 empty] | 404-10-627753-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 ,TD RRU 4418
Del | FY20_21 | Q4 | Superon Group | Plot No-551, Pace City-2, sector-37, Gurgaon | 27773 | 27773 | 27773 | 27773 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27773 | New | New_Built | IBS |  | 13 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.436 | 76.9948 | NA | 2022-01-03 | 2022-01-07 | 2022-01-24 | 11106-2843-59769943 | 2022-02-16 | 2022-02-16 |  |  |  |  | 2022-02-18 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-24 | [10 empty] | 2022-03-24 |  |  | 2022-03-24 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-31 | 2022-03-25 | 2022-03-29 | 2022-03-25 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 219 | [5 empty] | 2022-03-17 | 2022-03-20 | Hold due to IBS feeder 7/8"(1540 mtr) & FDD Jumper,N-male connector 1/2 & FDD Jumper not in stock as on 08.03.22,Partial Installed-DAS 2540 mtr/Farend Installed as on 11.03.22,Installed-Ping ok/2 floor complete DAS 2540 mtr cabling wip/Short 150 mtr/Access issue 18,19,20 as on 17.03.22 | [9 empty] | 404-10-627773-11 |  |  |  |  | KPI Accepted/Infra AT pending | MAPA_&_ON_AIR_(MS2)_PENDING | 2G(1800)+TD | 2G RRU 2219 ,TD RRU 4418
Del | FY20_21 | Q4 | Baprola(Relocation of 9482) | Mr. Ajit Singh S/O Suraj Bhan,Plot Number - 174,175,Khasra Number - 65/21,Village Baprola,Nangli Vihar,Baprola Vihar,Police Station - Kakrola,Post Office - Baprola,New Delhi-110043 | 22176 | 22176 | 22176 | 22176 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | NA | Relocation | New_Built | RTT | 18 | 5 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6301 | 77.019 | R/NN-640922 | 2022-01-05 | 2022-01-13 | 2022-01-24 | 111-2863-05770187 | 2022-02-18 | 2022-02-19 |  |  |  |  | 2022-02-15 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-22 |  |  |  | 2022-01-31 | ST202202025973 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049200/2022 | 2022-02-22 | 2022-02-23 | DL/01/5177/06555/0031/345/04/08753/NS/23022022 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-02 | 2022-02-23 | 2022-02-25 | 2022-02-23 | 2022-03-12 | 2022-03-12 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4498 | [5 empty] | 2022-02-21 | 2022-02-22 | Partial Installed/Link done-Mains not connected as on 21.02.22 | [9 empty] | 404-10-622176-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4412 available on Parent site
Del | FY20_21 | Q4 | Ambedkarnagar(Relocation Of 52) | House no- E-133 NEHRU NAGAR Krishna Nagar, Christian Nagar, Nai Basti Dundahera, Ghaziabad, Uttar Pradesh 201009 | 22208 | 22208 | 22208 | 22208 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1007419 | New | New_Built | GBT | 30 | 0 |  | INDUS_30M_GBT_OD_2T |  |  | YES | >18HRS | NO | 28.6397 | 77.4206 | R/RES-509127/R/RL-5319321 | 2022-01-21 | 2022-01-13 | 2022-02-02 | 11109-2863-97774206 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-03-01 |  |  | 2022-02-20 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-06 |  |  |  | 2022-02-16 | ST202202047107 | S20220002142 |  |  | 2022-03-11 | P/FBW/DEL/1051271/2022 | 2022-03-15 | 2022-03-16 | DL/04/5177/0462/0031/03/01/10443/NS/16032022 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-24 | 2022-03-16 | 2022-03-17 | 2022-03-16 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1443 | [5 empty] | 2022-02-24 | 2022-03-12 | Survey Rejected; U space required, Available Tower and GSM height is greater than Planned height (Technology Deviation),Survey Rejected; Indus PARSWA required, TDD_TB & L2100_TB to be released as on 28.02.22,Partial Installed_MW Pending-Parswa Req_Sacfa pending & Power Issue as on 04.03.22,Installed_Link done & Power Issue-DCDB Req & SACFA Req as on 06.03.22,Installed_FDD 2nd Sector RRU & Antenna Faulty(Site Fluctuate) as on 13.03.22 | [9 empty] | 404-10-622208-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | MBTS Green Corner of parking area | Near Security Guard Room,Behind Flat Number P-289/08,DLC_DC_IAFS_Green Crn prking area main gt CVD, Near security room ,Police Station Delhi Cant,Post Office- Delhi Cant,Delhi Cant New Delhi-110010 | 21186 | 21186 | 21186 | 21186 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/VI/8329 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6029 | 77.1184 | T22DL00203 | 2021-07-15 | 2022-01-08 | 2022-01-28 | 111-2860-28771184 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-02-28 |  |  | 2022-02-20 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-02 |  |  |  | 2022-02-21 | ST202202050940 | S20220002363 |  |  | 2022-02-25 | P/FBW/DEL/1050353/2022 | 2022-03-10 | 2022-03-11 | DL/01/5126/1444/0031/03/01/10427/NS/11032022 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-14 | 2022-03-11 | 2022-03-13 | 2022-03-11 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4388 | [5 empty] | 2022-02-24 | 2022-03-10 | ATC PARSWA Canopy Required,Issue closed on 28.02.22,Installed_SACFA Pending as on 02.03.22,SACFA Received on 10.03.22 | [9 empty] | 404-10-621956-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | DLF Ph-I, GGN(Relocation of 325) | Deepak Chaudhary,A-1/3, Dlf Qutub Enclave-I, Gurgaon | 22197 | 22197 | 22197 | 22197 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1011433 | New | New_Built | RTT | 12 | 10 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.4728 | 77.101 | R/RES-509125 | 2022-01-21 | 2022-02-02 | 2022-02-17 | 11106-2847-27771009 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-02-28 |  |  | 2022-02-20 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-03 | 2022-03-03 |  |  |  | 2022-03-01 | ST202203058305 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051254/2022 | 2022-03-12 | 2022-03-12 | DL/05/5177/0579/0031/03/01/10433/NS/12032022 | 2022-03-12 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-16 | 2022-03-13 | 2022-03-15 | 2022-03-13 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 940 | [5 empty] | 2022-02-24 | 2022-03-12 | Indus PARSWA Canopy Required (Technology deviation),Issue closed on 28.02.22,Hold Due to Kinia to Din Jumper Not in stock as on 28.02.22,Installed_SACFA Pending as on 03.03.22 | [9 empty] | 404-10-622197-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | Mahanpuri | Mr Nathan Singh S/o Sh Mai Lal,House Number - C 88,Vijay Park,Shahdara,Police station - Bhajanpura,Post Office - Yamuna Vihar,New Delhi-110053 | 21943 | 21943 | 21943 | 21943 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-2838 | New | New_Built | RTT | 12 | 14 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6943 | 77.2744 | NA | 2021-09-22 | 2021-10-18 | 2021-10-21 | 111-2869-43772744 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-03-01 |  |  | 2022-02-20 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-03 | 2022-03-03 |  |  |  | 2021-10-23 | ST202110568684 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044622/2021 | 2022-03-07 | 2022-03-08 | DL/01/5428/1878/0031/03/01/10424/NS/08032022 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-11 | 2022-03-08 | 2022-03-10 | 2022-03-08 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 611 | [5 empty] | 2022-02-24 | 2022-03-05 | Survey Rejected; Safety railing required, Eagle nest issue, GSM movement issue in 2nd & 3rd Sector,Safety railing required, Eagle nest issue, GSM movement issue in 2nd & 3rd Sector as on 28.02.22,Installed_2G Media Issue as on 03.03.22,Issue closed on 05.03.22,Antenna faulty as on 05.03.22 | [9 empty] | 404-10-621943-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Dnd Noida Link Road,Toll Plaza(Relocation of 2562) | Mayur Vihar Toll Plaza,Mayur Vihar Link Road,Police Station - Mayur Vihar Ph 1,Post Office - Trilok Puri,New Delhi-110091 | 20728 | 20728 | 20728 | 20728 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | VELDEL202729 | New | New_Built | RTP | 6 | 7 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.5842 | 77.2944 | NA | 2021-09-06 | 2022-01-24 | 2022-01-25 | 111-2858-42772944 | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-02-28 |  |  | 2022-02-20 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-03 | 2022-03-04 |  |  |  | 2022-01-31 | ST202202026023 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049214/2022 | 2022-03-04 | 2022-03-05 | DL/01/5126/01563/0031/03/01/10417/NS/05032022 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-10 | 2022-03-05 | 2022-03-09 | 2022-03-05 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 7192 | [5 empty] | 2022-02-24 | 2022-02-28 | Survey Rejected; 02 GSM pole mounts and ATC Parswa canopy required, Cable tray from tower to canopy required, Mains meter installation WIP (Tchnology Deviation),Issue closed on 28.02.22,RRUS-2219 B3 NOT IN STOCK as on 28.02.22 | [9 empty] | 404-10-620728-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 available on parent site
Del | FY20_21 | Q4 | DLF PHASE- I | Mr.Bigien Berry,Plot Number - A-12/12,Block - A,Sector - 26A,Police Station - DLF Phase-1,Post Office - DLF Phase-1,Gurugram,Haryana-122002 | 17058 | 17058 | 17058 | 17058 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3102999 | New | New_Built | RTP | 9 | 10.4 |  | Indus_Lite+ | Indus_Lite+ | Other than Indus & ATC | YES | >18HRS | NO | 28.473 | 77.0962 | R/NN-638983 | 2021-11-10 | 2021-12-22 | 2022-01-24 | 11106-2847-29770962 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-04-21 |  |  | 2022-03-06 | 2022-04-21 | [7 empty] | 2022-01-31 | ST202202025990 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049205/2022 | [17 empty] | PRI_Closed | WH_To_Dispatch | 18558801 | Ericsson/SCM | X | 2022-04-21 |  | Indus |  | M1 | 17226 |  |  | 18417994 | 2022-03-26 |  | 2022-03-05 | 2022-04-21 | Survey done_Material requested but MW TND awaited,Material Delivered Owner Issue as on 22.03.22_Site on Sub meter | [14 empty] | Owner Issue_SRN Done on 26.03.22) | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Daulatpura,Ghaziabad(relocation of 11783) | Ravider S/O Ramlalla,House Number.211,Khasra No.40,Post Office.Ghantaghar Gzb,Thana.Bazariya Gzb,Lohar Pura, Panchvati Colony, Sector 5, Daulatpura, Ghaziabad, Uttar Pradesh 201009 | 21674 | 21674 | 21674 | 21674 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTS011 | Relocation | New_Built | RTP | 6 | 17 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.647 | 77.443 | NA | 2021-11-01 | 2021-12-22 | 2022-02-08 | 11109-2864-69774430 | 2022-03-10 | 2022-03-10 |  |  |  |  | 2022-03-12 | 2022-03-11 | 2022-03-13 | 2022-03-14 | 2022-03-14 | 2022-03-16 |  |  |  | 2022-02-21 | ST202202050913 | S20220002363 |  |  | 2022-02-25 | P/FBW/DEL/1050343/2022 | 2022-03-16 | 2022-03-17 | DL/04/5414/00004/0031/03/01/10445/NS/17032022 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-25 | 2022-03-17 | 2022-03-22 | 2022-03-17 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 536 | [5 empty] | 2022-03-15 | 2022-03-16 | Relocation Site; Survey done, RRU 2279 approval awaited as on 11.03.22,Installed - Power Issue as on 15.03.22,Issue closed on 16.03.22 | [9 empty] | 404-10-621674-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 availabe on parent site
Del | FY20_21 | Q4 | Raghubir Nagar(Relocation of 11245) | Mr. Amar Nath Arora C/O Sh. Nihal Chand Arora,House Number - 588 2nd Floor , Pocket - 1, Pashchim Puri, Post Office - Pashchim Puri, Police Station - Pashchim Puri, New Delhi - 110063, | 19799 | 19799 | 19799 | 19799 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVIL | ATDLPSV0829 | Relocation | New_Built | RTP | 9 | 17 |  | STANDARD_PRODUCT |  | Other than Indus & ATC | YES | >18HRS | NO | 28.6639 | 77.1134 | NA | 2021-11-19 | 2021-11-30 | 2022-01-07 | 111-2866-39771134 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-03-01 |  |  | 2022-02-25 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-04 |  |  |  | 2022-01-20 | ST202201014387 | S20220000841 |  |  | 2022-01-24 | P/FVC/DEL/1048486/2022 | 2022-03-04 | 2022-03-05 | DL/01/5113/00226/0031/03/01/10416/NS/05032022 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-10 | 2022-03-05 | 2022-03-08 | 2022-03-05 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 11667 | [5 empty] | 2022-02-28 | 2022-03-01 | Survey Rejected; Pole mounts required and site is on Sub-Meter | [9 empty] | 404-10-619799-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 available on parent site
Del | FY20_21 | Q4 | Greater Kailash, Kalkaji | Rahul S/O Dinesh,House Number.I-46,Mehrauli - Badarpur Rd, Vishwakarma Colony, Pul Pehlad Pur,Post Office.Badarpuur,Police Station.Badarpur,New Delhi, Delhi 110044 | 20298 | 20298 | 20298 | 20298 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-201 | New | New_Built | RTP | 9 | 10 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.503 | 77.2812 | NA | 2021-11-19 | 2021-11-30 | 2022-01-07 | 111-2850-27772808 | 2022-02-28 | 2022-02-28 |  |  |  |  | 2022-02-25 | 2022-03-01 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-05 |  |  |  | 2022-02-16 | ST202202047094 | S20220002142 |  |  | 2022-02-24 | P/FBW/DEL/1050006/2022 | 2022-03-10 | 2022-03-11 | DL/01/0031/03152/0031/345/04/08778/NS/11032022 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-15 | 2022-03-11 | 2022-03-17 | 2022-03-11 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8061 | [5 empty] | 2022-03-05 | 2022-03-10 | Hold Due to Kinia to Din Jumper Not in stock as on 28.02.22,Installed_SACFA Pending as on 05.03.22,SACFA Received on 10.03.22 | [9 empty] | 404-10-620298-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Patel Nagar, Nehru Nagar | Man singh Timber Store,H No-50,F Block,Near Ramjas Park,Gali No 4,Baljeet Nagar, New Delhi 110008 | 21287 | 21287 | 21287 | 21287 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1550109 | New | New_Built | RTT | 12 | 11.5 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6603 | 77.168 | R/NN-560206/R/RL-5329284/R/RL-5329300 | 2021-08-27 | 2021-12-23 | 2021-01-23 | 111-2866-02771679 | 2022-02-28 | 2022-02-28 |  |  |  |  | 2022-02-25 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-03 | 2022-03-04 |  |  |  | 2021-01-08 | ST202101005482 | S20210000384 |  |  | 2021-01-16 | P/FVC/DEL/1016301/2021 | 2022-03-04 | 2022-03-05 | DL/01/5177/06570/0031/03/01/10415/NS/05032022 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-05 | 2022-03-10 | 2022-03-05 | 2022-03-08 | 2022-03-05 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9658 | [5 empty] | 2022-03-03 | 2022-03-04 | Partial Installed_Link done-Media Issue | [9 empty] | 404-10-621287-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Village-Nor Nagar, Raj Nagar Extn. | Mr.Praveen Gupta,Khasra Number - 03 & 04,Aggarwal Plaza,Raj Nagar Extension,Near By SVP Gulmohar Garden,Police Station - Sihani Gate,Post Office - Raj Nagar Ext.,Ghaziabad,Uttar Pradesh- 201003. | 17285 | 17285 | 17285 | 17285 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Tower | STTSPL019 | New | New_Built | RTM | 9 | 13 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.7046 | 77.4346 | NA | 2021-10-14 | 2021-09-12 | 2022-01-18 | 11109-2870-54774326 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-12 |  |  | 2022-03-07 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-14 | 2022-03-15 |  |  |  | 2022-02-21 | ST202202050941 | S20220002363 |  |  | 2022-02-25 | P/FBW/DEL/1050354/2022 | 2022-03-15 | 2022-03-16 | DL/04/5414/00003/0031/03/01/10444/NS/16032022 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-25 | 2022-03-16 | 2022-03-17 | 2022-03-16 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4087 | [5 empty] | 2022-03-10 | 2022-03-12 | Survey done; Material requested but Locator Required_Loactor Issue resolved oon 12.03.22 | [9 empty] | 404-10-617285-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sector-08, IMT Manesar(Relocation of 7164) | Government Land,Green Belt,GBM Location,Opposite HCL,CP-03, Sector- 08, IMT Manesar,Post Office - Bhangrola,Police Station - Sector- 08, IMT Manesar,Gurgaon, Haryana 122051 | 20479 | 20479 | 20479 | 20479 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032292 | Relocation | New_Built | GBM | 30 | 0 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.3766 | 76.902 | R/NN-628353 | 2021-09-03 | 2021-09-28 | 2021-11-11 | 11106-2837-65769020 | 2022-02-28 | 2022-02-28 |  |  |  |  | 2022-02-25 | 2022-03-01 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2021-11-12 | ST202111588383 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045813/2021 | 2022-03-06 | 2022-03-07 | DL/05/5177/05326/0031/03/01/10420/NS/07032022 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-03-12 | 2022-03-07 | 2022-03-08 | 2022-03-07 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5325 | [5 empty] | 2022-03-05 | 2022-03-06 | Installed_Link Done & Media Issue as on 05.03.22 | [9 empty] | 404-10-620479-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418
Del | FY20_21 | Q4 | Supertech Romano sector -118 | Mr. Vikash Jain(Manager),Tower Number-B4, Supertech The Romano ,Post Office - Sector 66,Police station - Sector 66, Sector 118, Noida, Uttar Pradesh-201301 | 21789 | 21789 | 21789 | 21789 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Fine bunch | FB0026 | New | New_Built | RTP | 6 | 76 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5826 | 77.4052 | - | 2021-08-10 | 2021-10-11 | 2022-01-18 | 11109-2858-25774051 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-04-11 |  |  | 2022-03-12 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-13 | 2022-04-15 |  |  |  | 2022-01-31 | ST202202026009 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049210/2022 | 2022-04-21 | [16 empty] | PRI_Closed | EMF_Pending |  | EMF_Pending | X | 2022-04-11 |  | Indus |  | M1 | 25649 | [5 empty] | 2022-03-10 | 2022-04-21 | Survey done_Material requested but MW TND awaited,Issue resloved on 11.03.22,Material Submitted by WH 15.03.22,Installed_LOS Issue at 4482 as on 15.04.22 | [14 empty] | Installed_LOS Issue at 4482 | Farend PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Church Road, Kashmiri Gate(Relocation of 5561) | Mr. Kishore Kumar,Shop Number 1582,Church Road, Kashmiri Gate,Police Station - Kashmiri Gate,Post Office - Kashmiri Gate,Delhi-110006 | 20846 | 20846 | 20846 | 20846 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL061 | Relocation | New_Built | RTP | 12 | 8 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6668 | 77.2311 | NA | 2021-11-19 | 2022-02-08 | 2022-02-08 | 111-2866-68772310 | 2022-03-04 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-03-06 | [8 empty] | 2022-02-21 | ST202202050899 | S20220002363 |  |  | 2022-02-25 | P/FBW/DEL/1050338/2022 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Relocation Site Hold By Praveen & trilok | Bharti Planning | PRI_Without Material |  |  | Indus |  | M1 | 208 | [5 empty] | 2022-03-05 |  | Survey Rejected; 03M height deviation, Technology deviation b/w new and parent site | [14 empty] | Relocation Site Hold By Praveen & trilok | Bharti Planning | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2271 TD RRU 4412 availabe on parent site
Del | FY20_21 | Q4 | VILL KAREHARA | Mr Virender Singh S/o Sh Suraj Bhan Singh, Khatoni No.-343, Khasra No.-2904, Village- Karhera, Mohan Nagar, Near Bharat Petrol Pump Loni, Ghaziabad, UP-201007 | 22101 | 22101 | 22101 | 22101 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-GZBD-ENB-3864 | New | New_Built | RTT | 12 | 7 |  | Sharing |  |  | YES | >18HRS | NO | 28.6842 | 77.389 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 11109-2868-42773889 | 2022-02-28 | 2022-03-01 |  |  |  |  | 2022-02-24 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-05 |  |  |  | 2022-03-03 | ST202203061540 | S20220002825 |  |  | 2022-03-14 | P/FBW/DEL/1051309/2022 | 2022-03-17 | 2022-03-17 | DL/04/5428/0309/0031/03/01/10446/NS/17032022 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-24 | 2022-03-17 | 2022-03-22 | 2022-03-17 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 551 | [5 empty] | 2022-03-05 | 2022-03-17 | Installed_SACFA Pending as on 05.03.22,Installed_SACFA Pending(SACFA Address Mismatch with Releasing Address),Mail received on 17.03.22 | [9 empty] | 404-10-622101-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | RAJEEV NAGAR EXTN | Mr. Aman Mathur S/O Sh. Balwan Singh, Plot Number - 204, 204/1, 205, & 205/1, Khasra Number - 49/22/2, Block - H, Rajeev Nagar Extension , Village Karala , Post Office - Karala, Police Station - Karala, Delhi - 110081. | 22107 | 22107 | 22107 | 22107 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-8631 | New | New_Built | GBM | 25 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.7385 | 77.0591 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 111-2873-85770590 | 2022-02-28 | 2022-03-01 | 2022-03-01 | 2022-04-12 |  |  | 2022-03-02 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-14 | 2022-04-14 |  |  |  | 2022-03-01 | ST202203058234 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051244/2022 | 2022-04-14 | 2022-04-16 | DL/01/5428/2023/0031/03/01/10482/NS/16042022 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-19 | 2022-04-16 | 2022-04-18 | 2022-04-16 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-12 |  | Indus |  | M1 | 4989 | [5 empty] | 2022-03-01 | 2022-04-12 | MW Pole Mount & MCB required at Farend_4989,Nearend Owner Issue_Farend installed as on 04.03.22,Nearend Owner Issue_Farend installed_SRN Done on 17.03.22,Issue closed on 12.04.22 | [9 empty] | 404-10-622107-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SULTANFARM_3941(Relocation of 4525) | Property Bearing no:-30, Kharsa no-216/217/219, Village-Fatehpur Beri, Tehsil-Mehrauli, Delhi-110074 | 22235 | 22235 | 22235 | 22235 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1311449 | Relocation | sharing | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.4615 | 77.1725 | R/RES-509350 | 2022-02-12 | 2022-02-17 | 2022-02-22 | 111-2846-14771725 | 2022-02-28 | 2022-03-01 | 2022-03-01 | 2022-03-02 |  |  | 2022-02-24 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-03-01 | ST202203058337 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051257/2022 | 2022-03-12 | 2022-03-13 | DL/01/5177/4612/0031/06/05/13426/NS/13032022 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-20 | 2022-03-13 | 2022-03-15 | 2022-03-13 | 2022-03-21 | 2022-03-29 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5595 | [5 empty] | 2022-03-01 | 2022-03-12 | Pole mount not free in 2nd Sector and Indus PARSWA Canopy required,Installed_SACFA Pending as on 05.03.22 | [9 empty] | 404-10-622235-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 available on parent site
Del | FY20_21 | Q4 | Pandav Nagar(Relocation Of 1308) | Mr. Rajpal Chauhan,House Number - 18,Samspur Village,Pandav Nagar,Police Station - Mayur Vihar Phase 2,Post Office - Laxmi Nagar,Delhi-110091 | 22241 | 22241 | 22241 | 22241 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1306992 | Relocation | sharing | RTP | 6 | 15 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6139 | 77.2852 | IN-1306992 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 111-2861-39772852 | 2022-02-28 | 2022-03-01 | 2022-03-01 | 2022-03-03 |  |  | 2022-02-24 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-03-01 | ST202203058338 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051258/2022 | 2022-03-12 | 2022-03-12 | DL/01/5177/4367/0031/03/01/10432/NS/12032022 | 2022-03-12 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-17 | 2022-03-13 | 2022-03-15 | 2022-03-13 | 2022-03-21 | 2022-03-29 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8042 | [5 empty] | 2022-03-01 | 2022-03-12 | Survey Rejected; Pole mount degree need to change in 1st and 2nd Sector and Indus PARSWA Canopy required,Alternate TND Required,Pole Rquired at Farend as on 02.03.22,Installed_SACFA Pending as on 05.03.22 | [9 empty] | 404-10-622241-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418 available on parent site
Del | FY20_21 | Q4 | NEW PHIRNI ROAD, BAKOLI | Mr. Satya Kumar , Shri Ganesh Dharam Kanta, Khasra Number - 46/20, Outer Phirni Road, Bakoli, Post Office - Alipur, Police Station - Alipur, Delhi - 110036. | 22113 | 22113 | 22113 | 22113 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9913 | New | New_Built | GBM | 25 | 0 |  | Sharing |  | 3RD_PARTY | YES | >18HRS | NO | 28.8085 | 77.1417 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 111-2880-85771416 | 2022-03-01 | 2022-03-01 |  |  |  |  | 2022-02-26 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-03-01 | ST202203058172 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051234/2022 | 2022-03-12 | 2022-03-13 | DL/01/0031/03157/0031/345/04/08786/NS/13032022 | 2022-03-13 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-23 | 2022-03-15 | 2022-03-16 | 2022-03-15 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4502 | [5 empty] | 2022-03-06 | 2022-03-15 | Locator Pending,Installed_Ping Ok & GPS Req as on 05.03.22,Installed_SACFA Pending as on 06.03.22,SCFT Owner Issue 13.03.22 | [9 empty] | 404-10-622113-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418
Del | FY20_21 | Q4 | LADPUR | Mr. Jagbir Singh S/o Sh Sohan Lal,Property Number -220, Vill Ladpur,Police Station - Kanjhawala,Post Office - Kanjhawala,New Delhi-110081 | 22106 | 22106 | 22106 | 22106 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-4342 | New | New_Built | GBM | 25 | 0 |  | Sharing |  | 3RD_PARTY | YES | >18HRS | NO | 28.7371 | 76.9942 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 111-2873-70769941 | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-03-15 |  |  | 2022-02-26 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-17 | 2022-03-19 |  |  |  | 2022-03-01 | ST202203058181 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051238/2022 | 2022-03-19 | 2022-03-21 | DL/01/5428/2083/0031/03/01/10448/NS/21032022 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-28 | 2022-03-21 | 2022-03-22 | 2022-03-21 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 585 | [5 empty] | 2022-03-01 | 2022-03-15 | Locator Pending,Material return on 05.03.22 | [9 empty] | 404-10-622106-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4418
Del | FY20_21 | Q4 | Juneja Tele Point Parvatiya Colony | Mr.Ajay Yadav,Plot Number - 3,Khasra Number - 8/2,Village Gauchhi, Parvatiya Colony, Police Station - Parvatiya Colony,Post Office - Sanjay Colony,Faridabad,Haryana-121001 | 21248 | 21248 | 21248 | 21248 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3009233 | New | New_Built | RTT | 15 | 5 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.3605 | 77.2835 | R/NN-626350 | 2021-07-27 | 2021-09-30 | 2021-10-07 | 11106-2836-05772834 | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-03-02 |  |  | 2022-02-26 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-05 |  |  |  | 2021-10-08 | ST202110554417 | S20210031332 |  |  | 2021-10-22 | P/FVC/DEL/1043937/2021 | 2022-03-06 | 2022-03-07 | DL/02/5177/05086/0031/03/01/10421/NS/07032022 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-03-11 | 2022-03-07 | 2022-03-09 | 2022-03-07 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 542 | [5 empty] | 2022-03-01 | 2022-03-05 | MW Pole Mount required at Farend,Installed_Farend Mount required(542) as on 04.03.22,Installed_Farend Mount required(542) as on 05.03.22 | [9 empty] | 404-10-621248-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Patparganj1 (Relocation of 317) | Plot no-420 Oriental Aparment ,Patparganj Industrial Area, Patparganj, Ghaziabad, Delhi 110092 | 22207 | 22207 | 22207 | 22207 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1002135 | Relocation | sharing | RTT | 12 | 10 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6384 | 77.3071 | R/RES-509126 | 2022-01-21 | 2022-02-02 | 2022-02-18 | 111-2863-84773070 | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-03-02 |  |  | 2022-02-26 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-02-21 | ST202202050955 | S20220002363 |  |  | 2022-02-25 | P/FBW/DEL/1050359/2022 | 2022-03-10 | 2022-03-11 | DL/01/5177/3696/0031/03/01/10426/NS/11032022 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-15 | 2022-03-11 | 2022-03-13 | 2022-03-11 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 317 | [5 empty] | 2022-03-01 | 2022-03-10 | Survey Rejected; Indus PARSWA required and Eagle Issue_Alternate TND Required,Installed_MW Installed-DCDB req & Media Issue as on 05.03.22,Access Issue_Installed-DCDB req & Media Issue as on 06.03.22,Installed_Link done-Media Issue & SACFA Req as on 07.03.22,SACFA Received on 10.03.22 | [9 empty] | 404-10-622207-11 |  |  |  |  | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,FD RRU 2219 ,L_2100 RRU RRUS12B1 TD RRU 4412 Available on Parent SIte
Del | FY20_21 | Q4 | Shahid Nagar 2 (Relocation of 9895) | Mr.Kiswar Jahan,House Number- G-125,Shaheed Nagar,Police Station-Shaheed Nagar,Post Office-Chikambarpur,Ghaziabad,Uttar Pradesh-201001 | 21261 | 21261 | 21261 | 21261 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/9034 | Relocation | sharing | RTP | 6 | 15 |  | STANDARD_PRODUCT |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.6799 | 77.3358 | NA | 2021-11-01 | 2022-02-08 | 2022-02-08 | 11109-2867-99773357 | 2022-03-01 | 2022-03-01 |  |  |  |  | 2022-02-26 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-04 |  |  |  | 2022-02-16 | ST202202047100 | S20220002142 |  |  | 2022-02-24 | P/FBW/DEL/1050012/2022 | 2022-03-10 | 2022-03-11 | DL/04/5126/00261/0031/06/05/13409/NS/11032022 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-16 | 2022-03-11 | 2022-03-13 | 2022-03-11 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5817 | [5 empty] | 2022-03-04 | 2022-03-10 | ATC Parswa to be reach on 3rd March,Installed_2G Media/SACFA Issue as on 04.03.22,Installed_SACFA Pending as on 05.03.22,SACFA Received on 10.03.22 | [9 empty] | 404-10-621261-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Chatterpur Farms Outdoor (Relocation of 7082) | Mr. yashpal,Khasra Number - 652,Near Gate No- 05 and Water Tank ,Radha Swami Satsang Vyas, Village Bhati,Post Office - Fatehpur,Police Station - Fatehpur Beri,New Delhi-110074 | 21855 | 21855 | 21855 | 21855 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3035714 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.4413 | 77.2072 | R/NN-628337 | 2021-09-03 | 2022-01-14 | 2022-01-24 | 111-2844-12772071 | 2022-03-01 | 2022-03-02 |  |  |  |  | 2022-02-25 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-04 | 2022-03-05 |  |  |  | 2022-01-31 | ST202202025975 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049201/2022 | 2022-03-07 | 2022-03-08 | DL/01/5177/06571/0031/03/01/10422/NS/08032022 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-14 | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-18 | 2022-03-19 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4248 | [5 empty] | 2022-03-05 | 2022-03-07 | Partial Installed_Farend Mount Required(4248) as on 04.03.22,Installed_Farend Mount Required(4248) as on 05.03.22 | [9 empty] | 404-10-621855-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 Available on Parent SIte TD RRU 4418
Del | FY20_21 | Q4 | Vill Neemka | Mrs. Girraji Dei, W/O Jai Karan, Khasra No. 14/1786 Vill Neemka,Sec-72Fariidabad-121002 | 21331 | 21331 | 21331 | 21331 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVIL | RJHAZFD0435 | New | New_Built | GBT | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.352 | 77.3679 | NA | 2020-12-09 | 2022-02-22 | 2022-02-24 | 11106-2835-19773678 | 2022-03-01 | 2022-03-01 |  |  |  |  | 2022-02-26 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-03-01 | ST202203058130 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051229/2022 | 2022-03-12 | 2022-03-12 | DL/02/5113/0072/0031/03/01/10431/NS/12032022 | 2022-03-12 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-23 | 2022-03-13 | 2022-03-16 | 2022-03-13 | 2022-03-21 | 2022-03-29 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9621 | [5 empty] | 2022-03-06 | 2022-03-12 | Locator Pending,Installed_MW Pending as on 05.03.22,Installed_SACFA Pending & Power Issue as on 06.03.22 | [9 empty] | 404-10-621331-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | AGRAULA | Neelam Packaging Industries,Plot Number- B1-C58,Sector-D1,Agraula,Tronica City,Police Station-Tronica City,Post Office-Tronica City,Ghaziabad,Uttar Pradesh-201103 | 22112 | 22112 | 22112 | 22112 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-LONI-ENB-3357 | New | New_Built | RTT | 12 | 7 |  | Sharing |  | RTT/RTP_HT_ISSUES | YES | >18HRS | NO | 28.7893 | 77.2787 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 11109-2878-93772787 | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-03-02 |  |  | 2022-02-26 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-05 |  |  |  | 2022-03-01 | ST202203058229 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051242/2022 | 2022-03-12 | 2022-03-13 | DL/04/0031/00316/0031/06/05/13429/NS/13032022 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-17 | 2022-03-13 | 2022-03-16 | 2022-03-13 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 20812 | [5 empty] | 2022-03-01 | 2022-03-12 | Survey Rejected; GSM pole mounts are not available at planned height,Installed_Media Issue as on 05.03.22,Installed-Media issue MDU Lan Cable req/SACFA Req as on 07.03.22 | [9 empty] | 404-10-622112-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Village Kulesara, Gautam Buddha Nagar | Mr. Liley Ram S/o Sh. Tariph Singh, Khasra Number - 634/1, Village-Kulesara, Near House number - 19, Gali number -1, Sanjay Vihar , Village-Kulesara, Post Office - Kulesara, Police Station - Kulesara, Gautam Buddha Nagar, Greater Noida - 201306. | 22090 | 22090 | 22090 | 22090 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-NOID-ENB-9061 | New | New_Built | GBM | 25 | 0 |  | Sharing |  |  | YES | >18HRS | NO | 28.5204 | 77.4416 | NA | 2021-12-06 | 2021-12-23 | 2022-02-07 | 11109-2852-04774415 | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-03-02 |  |  | 2022-02-26 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-06 |  |  |  | 2022-03-01 | ST202203058246 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051249/2022 | 2022-03-12 | 2022-03-12 | DL/03/5428/0404/0031/06/05/13424/NS/12032022 | 2022-03-12 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-20 | 2022-03-13 | 2022-03-25 | 2022-03-13 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 8079 | [5 empty] | 2022-03-01 | 2022-03-12 | MW Pole Mount & Owner Issue at Farend 8079,Installed_SACFA Pending as on 06.03.22 | [9 empty] | 404-10-622090-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Noida Ext,Sec-4 | Mr.NA S/o Mr.NA.House Number NA,Choti Milak(Backside Of Himalya Legend),Near By Primary School,Police Station Bisrakh,Post Office Bisrakh,Greater Noida,Uttar Pradesh- 201009. | 22092 | 22092 | 22092 | 22092 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-NOID-ENB-9032 | New | New_Built | GBM | 30 | 0 |  | Sharing |  |  | YES | >18HRS | NO | 28.5977 | 77.4495 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 11109-2859-77774494 | 2022-03-07 | 2022-03-08 |  |  |  |  | 2022-03-03 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-10 | 2022-03-13 |  |  |  | 2022-03-01 | ST202203058180 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051237/2022 | 2022-03-14 | 2022-03-21 | DL/03/5428/0281/0031/03/01/10447/NS/21032022 | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-31 | 2022-03-22 | 2022-03-26 | 2022-03-22 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 10157 | [5 empty] | 2022-03-10 | 2022-03-21 | Installed_MW LOS Issue-Farend changed as on 10.03.22,Installed_Link Done_Owner issue as on 11.03.22,Installed_Link Done_Owner/Power Issue & 2G Media Issue as on 12.03.22,EMF/SCFT Power Issue as on 14.03.22,issue closed on 21.03.22 | [9 empty] | 404-10-622092-11 |  |  |  |  | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VILLAGE - BADSHAHPUR | Ms.Sarita Yadav W/O Mr.Manoj Kumar,House Number-21,Gali Number-2,Neelkanth Enclave,Badshahpur,Police Station-Badshahpur,Post Office-Badshahpur,Gurgaon,Haryana-122101 | 22086 | 22086 | 22086 | 22086 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GRGN-ENB-0628 | New | New_Built | RTT | 15 | 14 |  | Sharing |  |  | YES | >18HRS | NO | 28.3987 | 77.044 | NA | 2021-12-06 | 2021-12-28 | 2022-02-05 | 11106-2839-86770440 | 2022-03-07 | 2022-03-08 |  |  |  |  | 2022-03-03 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-10 | 2022-03-10 |  |  |  | 2022-03-01 | ST202203058235 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051245/2022 | 2022-03-12 | 2022-03-12 | DL/05/5428/0486/0031/06/05/13416/NS/12032022 | 2022-03-12 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-26 | 2022-03-15 | 2022-03-16 | 2022-03-15 | 2022-03-21 | 2022-03-29 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4265 | [5 empty] | 2022-03-11 | 2022-03-12 | Installed_Link Interference as on 10.03.22,Installed_SACFA Pending as on 11.03.22,2G BSC issue_13.03.22 | [9 empty] | 404-10-622086-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | SEC-78, GURGAON | aveen Prakash S/o Janak Raj Yadav; Khasra No. / Kita No. 14/3; Village Naurangpur; Teshsil Manesar; Gurgaon; Haryana 122004 | 22085 | 22085 | 22085 | 22085 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-MESR-ENB-0059 | New | New_Built | GBM | 25 | 0 |  | Sharing |  |  | YES | >18HRS | NO | 28.3785 | 76.9622 | NA | 2021-12-06 | 2021-12-28 | 2022-02-05 | 11106-2837-84769622 | 2022-03-07 | 2022-03-08 |  |  |  |  | 2022-03-03 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-10 | 2022-03-11 |  |  |  | 2022-03-01 | ST202203058236 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051246/2022 | 2022-03-12 | 2022-03-12 | DL/05/5428/0229/0031/345/04/08781/NS/12032022 | 2022-03-12 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-13 | 2022-03-17 | 2022-03-13 | 2022-03-15 | 2022-03-13 | 2022-04-01 | 2022-04-07 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 23871 | [5 empty] | 2022-03-11 | 2022-03-12 | Installed_SACFA Pending as on 11.03.22 | [9 empty] | 404-10-622085-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | NTH | National Trust for Handicapped (NTH)- A2,Shaheed Jeet Singh Marg, Block- A,Qutab Institutional Area, New Delhi-110067 | 27775 | 27775 | 27775 | 27775 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | SIS | DLNT12012022 | New | New_Built | IBS |  | 20 |  | PURE_IBS |  |  | YES | >18HRS | NO | 28.5435 | 77.1789 | NA | 2022-01-21 | 2022-02-12 | 2022-02-27 | 111-2854-35771789 | 2022-03-07 | 2022-03-08 | 2022-03-08 | 2022-03-20 |  |  | 2022-03-03 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-22 | [10 empty] | 2022-03-23 |  |  | 2022-03-23 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-30 | 2022-03-24 | 2022-03-30 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 999 | [5 empty] | 2022-03-08 | 2022-03-23 | Access Issue at Farend_999,Installed_Farend Access Issue -999(Timeline 23.03.22) as on 22.03.22 | [9 empty] | 404-10-627775-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Institut Francais En Inde | 2, APJ Abdul Kalam Road, ND-110011 | 27723 | 27723 | 27723 | 27723 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27723_DEL | New | New_Built | IBS |  | 13 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.6029 | 77.2214 | 27723 | 2021-07-31 | 2022-03-07 | 2022-03-07 | 111-2860-28772213 | 2022-03-07 | 2022-03-07 | 2022-03-07 | 2022-04-21 |  |  | 2022-04-21 | 2022-04-21 | [31 empty] | PRI_Closed | WH_To_Dispatch | 75228 | Ericsson/SCM | X | 2022-04-21 |  |  |  | M1 | [6 empty] | 2022-03-07 | 2022-04-21 | Hold By Shashank | [14 empty] | Hold By Shashank | Shashank | TD | TD RRU 4418
Del | FY20_21 | Q4 | Delhi Metro Rail Corporation Ltd,lajpat nagar | Delhi Metro Rail Corporation Ltd,Office of Chief Project Manager-8 Opposite Frank Anthony Public School Near Metro Pillar No -40 Lajpat Rai Marg , Lajpat Nagar-IV New Delhi -110024 | 27771 | 27771 | 27771 | 27771 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27771 | New | New_Built | IBS |  | 13 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5601 | 77.235 | NA | 2021-12-12 | 2021-12-13 | 2022-01-18 | 111-2856-12772349 | 2022-03-07 | 2022-03-08 |  |  |  |  | 2022-03-09 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-11 | [10 empty] | 2022-03-30 |  |  | 2022-03-30 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-04-04 | 2022-03-31 | 2022-04-02 | 2022-03-31 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-30 |  |  |  | M1 | [6 empty] | 2022-03-11 | 2022-03-30 | N-male connector 1/2 & FDD Jumper not in stock as on 08.03.22,Media Issue FTTH Required as on 11.03.22,Issue closed on 25.03.22,Installed Media Pending as on 26.03.22 | [9 empty] | 404-10-627771-11 |  |  |  |  | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G(1800)+TD | 2G RRU 2219 , TD RRU 4418
Del | FY20_21 | Q4 | Nandgram Ghukna Ghaziabad | Plot No.D-17, Nandgram, Ghukna, Ghaziabad 201003 | 19677 | 19677 | 19677 | 19677 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Communication | STTSPL012 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6892 | 77.4136 | 19677 | 2021-10-10 | 2021-08-26 | 2022-02-11 | 11109-2868-92774135 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-29 |  |  | 2022-03-14 | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 |  |  |  |  | 2022-02-21 | ST202202050043 | S20220002311 |  |  | 2022-02-25 | P/FBW/DEL/1050351/2022 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Public Issue | 3rd Party PRI | PRI_With Material | 2022-03-29 | PRI | Indus |  | M1 | 171 | [5 empty] | 2022-03-12 |  | Pole Mount required at farend,Hold by Toco_20.03.22,Survey done; Material request hold (CWIP Issue),Public Issue as on 30.03.22 | [14 empty] | Punlic Issue | 3rd Party PRI
Del | FY20_21 | Q4 | Alipur X (Relocation of 41) | Mr. Praveen,House Number - B-117,Dayal Market,Main Narela Road,Alipur Village,Police Station - Alipur,Post Office - Alipur, Delhi, 110036 | 22218 | 22218 | 22218 | 22218 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | 451932 | New | New_Built | RTT | 6 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.7971 | 77.1329 | 13759344 | 2022-02-16 | 2022-02-22 | 2022-03-10 | 111-2879-71771328 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-24 |  |  | 2022-03-14 | 2022-03-30 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-01 |  |  |  | 2022-03-01 | ST202203058126 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051227/2022 | 2022-04-01 | 2022-04-01 | DL/01/5126/0524/0031/06/05/13602/NS/01042022 | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-08 | 2022-04-04 | 2022-04-08 | 2022-04-04 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-12 |  | Indus |  | M1 | 177 | [5 empty] | 2022-03-12 | 2022-03-24 | Survey Rejected; ATC PARSWA Required & Technology deviation,Pole Mount required at farend_4472,Survey done; Material request hold (CWIP Issue),Planning change by Bharti on 01.04.22 | [9 empty] | 404-10-622218-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Amrit Nagar Ghaziabad | Mr,Sanjay Goyal S/O Kamal Prasad Goyal,Plot ,no, 301, Loha Mandi,Ghaziabad,Site Plan of plot ,Kh,No,405/1, in Vellage,Shahapur ,Bhamheta,Pargna ,Dasna,Ghaziabad uttar Pradesh,201009 | 21379 | 21379 | 21379 | 21379 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/9030 | New | New_Built | RTP | 9 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6463 | 77.4493 | T21DL03261 | 2021-11-01 | - | 2022-02-08 | 11109-2864-63774493 | 2022-03-15 | 2022-03-15 |  |  |  |  | 2022-03-12 | 2022-03-17 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-02-16 | ST202202046866 | S20220002133 |  |  | 2022-02-24 | P/FBW/DEL/1050011/2022 | 2022-03-22 | 2022-03-23 | DL/04/5126/00262/0031/03/01/10454/NS/23032022 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-31 | 2022-03-23 | 2022-03-25 | 2022-03-23 | 2022-04-01 | 2022-04-07 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 536 | [17 empty] | 404-10-621379-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | EMCD_73_Geeta Colony(Relocation of 13109) | Mrs Kamal Makkar W/O Mr. A.S Makkar, House Number - 529/1, Jheel Khurenja , Post Office - Geeta Colony , Police Station - Geeta Colony, Delhi - 110031 | 20903 | 20903 | 20903 | 20903 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL056 | Relocation | New_Built | RTT | 12 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6554 | 77.2745 | NA | 2021-11-19 | 2021-12-08 | 2022-02-08 | 111-2865-53772744 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 |  |  | 2022-03-11 | 2022-03-17 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-02-21 | ST202202050027 | S20220002311 |  |  | 2022-02-25 | P/FBW/DEL/1050337/2022 | 2022-03-24 | 2022-03-24 | DL/01/0031/03188/0031/03/01/10457/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-31 | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 675 | [5 empty] | 2022-03-16 | 2022-03-24 | Access Issue at farend_720,Partial Installed_Farend changed -675(Material Need to shift & Media Issue) as on 21.03.22,Installed_Link done-Media Issue as on 22.03.22,Installed_Link done-Media Issue as on 23.03.22,Media Issue resolved on 24.03.22 | [9 empty] | 404-10-620903-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Palamfarm-Ii(Relocation of 4513) | Shri Ram Narayan S/o Munshi Ram, palam farms near dhundhera road,Police chauki- Palam farm , Post office-Bijwasan, new delhi,110061. | 22008 | 22008 | 22008 | 22008 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/9145 | Relocation | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5256 | 77.0595 | T22DL00175 | 2021-11-01 | 2022-01-08 | 2022-02-08 | 111-2852-55770594 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-16 |  |  | 2022-03-12 | 2022-03-17 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-02-16 | ST202202046872 | S20220002133 |  |  | 2022-02-24 | P/FBW/DEL/1050014/2022 | 2022-03-22 | 2022-03-24 | DL/01/5126/01566/0031/03/01/10460/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-30 | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 334 | [5 empty] | 2022-03-15 | 2022-03-22 | ATC Parswa Required,Partial Installed_Mains not available(Timeline_24 & 25 March 22) as on 21.03.22,Integrated_Temp Power as on 22.03.22 | [9 empty] | 404-10-622008-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | A-Block Lajpat Nagar | Mr.NA W/o Mr. NA.Plot Number NA,Om Nagar Mohan Nagar,L Block,Sector 4,Lajpat Nagar,Police Station Sahibabad,Post Office Mohan Nagar,Rajender Nagar,Ghaziabad,Uttar Pradesh- 201007. | 22019 | 22019 | 22019 | 22019 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-GZBD-ENB-3365 | New | Sharing | RTT | 9 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.53 | 77.3883 | SR-DL000219 | 2021-10-18 | 2021-12-03 | 2022-02-07 | 11109-2853-00773882 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-16 |  |  | 2022-03-12 | 2022-03-17 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-03-01 | ST202203058249 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051250/2022 | 2022-03-22 | 2022-03-23 | DL/04/5428/0174/0031/03/01/10453/NS/23032022 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-04-01 | 2022-03-23 | 2022-03-29 | 2022-03-23 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 9753 | [5 empty] | 2022-03-15 | 2022-03-22 | Survey Rejected; Safety Railing Required (OHS Issue),Installed_Media issue as on 21.03.22 | [9 empty] | 404-10-622019-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | INDRA COMPLEX, MAWAI ROAD | Mr Aadesh Kumar S/O Sh Vijay Singh, Khatoni No.-473, Khasra No.-1820, 8/2, New Baselwa Colony, Mawai Road, Old Faridabad,Post Office. Naharpur,Police Station. Naharpur,Faridabad, Haryana-121003 FARIDABAD | 22087 | 22087 | 22087 | 22087 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-FDBD-ENB-3995 | New | sharing | RTT | 12 | 7 |  | Sharing |  |  | YES | >18HRS | NO | 28.4301 | 77.3307 | NA | 2021-12-06 | 2021-12-30 | 2022-02-05 | 11106-2843-01773306 | 2022-03-14 | 2022-03-15 | 2022-03-15 | 2022-03-16 |  |  | 2022-03-10 | 2022-03-17 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-03-01 | ST202203058244 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051247/2022 | 2022-03-22 | 2022-03-23 | DL/02/5428/0193/0031/03/01/10450/NS/23032022 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-31 | 2022-03-23 | 2022-03-25 | 2022-03-23 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 15208 | [5 empty] | 2022-03-15 | 2022-03-22 | Pole Mount required at farend,Partial Installed_Farend MW mount req at 15208(Timeline 22.03.22) as on 21.03.22 | [9 empty] | 404-10-622087-11 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | I-DL-DLHI-ENB-2135 | Mr. Dharm Dutt, Plot No. 10, Khesra No. 361, 362 & 363, Asola, Post Office- Fatehpur Beri, Police Station- Maidan Garhi, New Delhi 110074 | 22088 | 22088 | 22088 | 22088 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-2135 | New | sharing | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.4594 | 77.1926 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 111-2845-93771926 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-16 |  |  | 2022-03-17 | 2022-03-17 | 2022-03-20 | [6 empty] | 2022-03-01 | ST202203058214 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051241/2022 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 21.03.22 | 3rd Party PRI | PRI_Without Material |  |  | Indus |  | M1 | 5595 | [5 empty] | 2022-03-15 |  | Pole mount required at Farend_5595,Material return on 21.03.22 | [14 empty] | Material return on 21.03.22 | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | LAKSHMI PARK | SHAKUNTLA DEVI; KH. NO. 74/19; PLOT NO. 45; BLOCK-H; LAKSHMI PARK; NANGLOI; NEW DELHI 110041 | 22099 | 22099 | 22099 | 22099 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3284 | New | sharing | RTT | 12 | 7 |  | Sharing |  |  | YES | >18HRS | NO | 28.671 | 77.0648 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 111-2867-09770647 | 2022-03-14 | 2022-03-15 |  |  |  |  | 2022-03-10 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-17 | 2022-03-17 |  |  |  | 2022-03-01 | ST202203058182 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051239/2022 | 2022-03-19 | 2022-03-21 | DL/01/5428/1657/0031/03/01/10449/NS/21032022 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-26 | 2022-03-21 | 2022-03-22 | 2022-03-21 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4912 | [5 empty] | 2022-03-17 | 2022-03-19 | Installed/MCB req at far End-Media issue as on 17.03.22,Issue closed on 19.03.22 | [9 empty] | 404-10-622099-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | shalimar Garden | H.no-95,vikram enclave ext,shalimar garden,ghaziabad,Up-201005 | 17526 | 17526 | 17526 | 17526 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | 17526 | New | New_Built | RTP | 9 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6893 | 77.3328 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11109-MGBD-2101229 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-03-16 |  |  | 2022-03-12 | 2022-03-16 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2021-03-24 | ST202103102874 | S20210005414 |  |  | 2021-07-08 | P/FBW/DEL/1033678/2021 | 2022-03-22 | 2022-03-23 | DL/04/0031/00322/0031/03/01/10452/NS/23032022 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-31 | 2022-03-23 | 2022-03-25 | 2022-03-23 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 5817 | [5 empty] | 2022-03-15 | 2022-03-22 | Survey Rejected; Planned GSM height not available, Climbing ladder required at Mumty, Mains supply not available,Partial Installed_Mains not connected-Temporary Power/Climbing ladder req(Timeline 22.03.22) as on 21.03.22,Integrated_Temp Power as on 22.03.22 | [9 empty] | 404-10-617526-11 |  |  |  |  | KPI Accepted/Infra AT pending | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Lal Kuan MB Road(Relocation of 2925) | Ms. Droopati W/O Mr.Kapil,House Number - 50, J Blcok Lal Kaun Prem Nagar,Post Office - Badarpuur,Police Station - Badarpur,New Delhi - 110044 | 22174 | 22174 | 22174 | 22174 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/7475 | New | New_Built | RTT | 15 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5031 | 77.2778 | NA | 2022-02-16 | 2022-02-26 | 2022-03-08 | 111-2850-31772777 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-03-21 |  |  | 2022-03-13 | 2022-03-21 | 2022-03-23 | 2022-03-23 | 2022-03-24 | 2022-03-25 |  |  |  | 2022-03-15 | ST202203072370 | S20220003354 |  |  | 2022-03-22 | P/FVC/DEL/1051681/2022 | 2022-03-25 | 2022-03-26 | DL/01/5126/0982/0031/03/01/10470/NS/26032022 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-04-02 | 2022-03-26 | 2022-03-28 | 2022-03-26 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-16 |  | Indus |  | M1 | 8061 | [5 empty] | 2022-03-16 | 2022-03-25 | Survey Rejected; GSM Pole mounts and ATC PARSWA not available,Partially Installed_Power Issue as on 24.03.22,Issue closed on 25.03.22 | [9 empty] | 404-10-622174-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2219 TD RRU 4412 available on parent site
Del | FY20_21 | Q4 | Rajkumari Amrit Kaur OPD_AIIMS_Delhi | Rajkumari Amrit Kaur OPD,AIIMS,Gautam Nagar, New Delhi | 27657 | 27657 | 27657 | 27657 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | IBUS | IbusDL005 | New | New_Built | IBS |  | 22 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5646 | 77.2151 | 27657 | 2021-08-27 | 2021-08-30 | 2021-08-30 | 111-2856-46772151 | 2022-03-16 | 2022-03-17 |  |  |  |  | 2022-03-12 | 2022-03-17 | 2022-03-20 | 2022-03-22 | 2022-03-22 | 2022-03-25 | [10 empty] | 2022-03-25 |  |  | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-04-04 | 2022-03-26 | 2022-03-30 | 2022-03-26 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-16 |  | Indus |  | M1 | 630 | [5 empty] | 2022-03-24 | 2022-03-25 | Delivered-Combiner 2X2 6 nos short, N2N male connector 4 nos short, cabinet and LDF 20 mtr req as on 22.03.22,Partially Installed_Link Done,Access avl at 10:30 AM | [9 empty] | 404-10-627657-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G(1800)+TD | 2G RRU 2279 , TD RRU 4418
Del | FY20_21 | Q4 | Village-Daultabad | Mr. Amit S/o Mr. Vijendra Kumar,Khasra Number - 74//2/2,Village- Daulatabad,Sector 103,Post Office- Daulatabad,Police Station - Rajendra Park,District- Gurgaon,Haryana 122006 | 21828 | 21828 | 21828 | 21828 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3017238 | New | New_Built | RTT | 15 | 7 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.4967 | 76.9899 | R/NN-627133 | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11106-2849-67769898 | 2022-03-17 | 2022-03-19 |  |  |  |  | 2022-03-12 | 2022-03-20 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-03-03 | ST202203061536 | S20220002825 |  |  | 2022-03-14 | P/FBW/DEL/1051305/2022 | 2022-03-22 | 2022-03-23 | DL/05/5177/05329/0031/03/01/10451/NS/23032022 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-30 | 2022-03-23 | 2022-03-25 | 2022-03-23 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4466 | [5 empty] | 2022-03-21 | 2022-03-22 | Partial Installed_Mains not connected(Timeline_22.03.22),Integrated_Temp Power & Mains Not Connected as on 22.03.22 | [9 empty] | 404-10-621828-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | DM SOUTH M.B Road Saket(Relocation of 19943) | Government Land,SDMC MBTS location,Behind of Swayam Swachhatta Initiative Ltd,Dhallao Number-A-188/67-S,Mehrauli-Badarpur Road,Saket,Police Station - Saket,Post Office - Saket,New Delhi-110017 | 22151 | 22151 | 22151 | 22151 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3095086 | New | New_Built | Cow | 30 |  |  | COW |  |  | YES | >18HRS | NO | 28.5189 | 77.2108 | R/NN-637484 | 2021-11-01 | 2022-01-08 | 2022-02-08 | 111-2851-88772108 | 2022-03-17 | 2022-03-19 | 2022-03-19 | 2022-03-21 |  |  | 2022-03-12 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-24 | 2022-03-24 |  |  |  | 2022-03-01 | ST202203058357 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051262/2022 | 2022-03-24 | 2022-03-25 | DL/01/5177/06596/0031/03/01/10468/NS/25032022 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-04-01 | 2022-03-25 | 2022-03-31 | 2022-03-25 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING |  |  |  | Indus |  | M1 | 5978 | [5 empty] | 2022-03-19 | 2022-03-24 | Survey done; Material requested/TND awaited,TND Received on 21.03.22,Integrated_DG Connection Pending/Power Issue resolved at 12:45 PM,Alarm in 1 TDD sector & 2 L2100 Sector as on 24.03.22 | [9 empty] | 404-10-622151-11 |  |  |  |  | Less Payload/Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | BPTP Princess Park (Relocation of 11583) | Mr. TejVeer Singh,Khasra Number - 9/17,Sector 86,Budhena Village,Behind BTP Princess Park,Post Office - Sector 15,Police Station - Sector-14,Faridabad, Haryana 121002 | 22026 | 22026 | 22026 | 22026 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3052600 | New | New_Built | Cow | 30 |  |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4043 | 77.3424 | R/NN-632783 | 2021-10-04 | 2022-02-14 | 2022-03-17 | 11106-2840-42773424 | 2022-03-17 | 2022-03-19 | 2022-03-19 | 2022-04-20 |  |  | 2022-03-19 | 2022-04-20 | [7 empty] | 2022-03-01 | ST202203058324 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051255/2022 | [17 empty] | PRI_Closed | Material_In_Transit | 18553551 | Ericsson/SCM | X | 2022-04-20 |  | Indus |  | M1 | 661 | [5 empty] | 2022-03-19 | 2022-04-20 | Survey Rejected; 65M Lat-Long Deviation found and Access Issue at Parent site 11583,SACFA Reappled_WPC Confirmation Awaited as on 18.04.22 | [14 empty] | Survey Rejected; 65M Lat-Long Deviation found and Access Issue at Parent site 11583_SACFA Reappled_WPC Confirmation Awaited | Bharti Planning | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Nanakpura, Moti Bagh(Relocation of 16527) | house no 76 A motibagh village behind nanak pio gurudwara Delhi 21 | 20922 | 20922 | 20922 | 20922 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Protel Telepower Infrastructure Pvt Ltd. | PTIPL146 | New | New_Built | RTP | 6 | 19 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.586 | 77.1709 | NA | 2022-02-22 | 2022-03-17 | 2022-03-17 | 111-2858-60771709 | 2022-03-17 | 2022-03-19 | 2022-03-19 | 2022-03-29 |  |  | 2022-03-19 | 2022-03-30 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-01 |  |  |  | 2022-03-15 | ST202203072146 | S20220003354 |  |  | 2022-03-22 | P/FVC/DEL/1051664/2022 | 2022-04-12 | 2022-04-13 | DL/01/5433/00004/0031/03/01/10477/NS/13042022 | 2022-04-13 | 2022-04-13 | 2022-04-13 | 2022-04-13 | 2022-04-13 |  | 2022-04-13 | 2022-04-16 | 2022-04-13 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-29 |  | Indus |  | M1 | 4036 | [5 empty] | 2022-03-19 | 2022-04-12 | Survey Rejected; 04M height deviation,EB or DG supply not available and Blockage issue at 90 degree,Survey done; Material request hold (CWIP Issue),Partial Installed-Power Issue/Link done as on 31.03.22 | [9 empty] | 404-10-620922-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | East Model Town, Ghaziabad | Mr. Charan Singh Yadav S/o Mr.Ram Babu Yadav,House Number-8A, Plot Number. 121 (Old No.-104), Model Town,Tehsil Road, Opp. Yadav Sweets,Police Station - Sihani Gate,Post Office - Navyug Market Paragana-Loni, Ghaziabad, UP-201001. | 20732 | 20732 | 20732 | 20732 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GZBD-ENB-3879 | New | New_Built | RTT | 12 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6538 | 77.4388 | SR-DL000148 | 2021-07-18 | 2021-07-27 | 2021-08-05 | 11109-2865-37774388 | 2022-03-17 | 2022-03-19 | 2022-03-19 | 2022-04-12 |  |  | 2022-03-19 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-16 | 2022-04-16 |  |  |  | 2021-09-20 | ST202109525327 | S20210030000 |  |  | 2021-09-27 | P/FBW/DEL/1042131/2021 | 2022-04-16 | 2022-04-18 |  | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18 |  | 2022-04-18 |  | 2022-04-18 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-12 |  | Indus |  | M1 | 141 | [5 empty] | 2022-03-21 | 2022-04-12 | Material return on 21.03.22,Issue closed on 12.04.22,MO Punching Required on 14 Apr 22_Delivery Plan required on 16 Apr 22 | [9 empty] | 404-10-620732-11 | [5 empty] | EMF_Pending | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VILLAGE - BAJGHERA | Mr.Nain Singh S/O Shri Pyare Lal,House Number-238,Village-Bajghera,Police Station-Bajghera Road,Post Office-Palam Vihar,Gurgaon,Haryana-122017 | 22091 | 22091 | 22091 | 22091 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GRGN-ENB-5123 | New | New_Built | RTT | 9 | 10 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.5274 | 77.0209 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11106-2852-73770209 | 2022-03-17 | 2022-03-19 |  |  |  |  | 2022-03-12 | 2022-03-20 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-03-01 | ST202203058173 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051235/2022 | 2022-03-22 | 2022-03-23 | DL/05/5428/0334/0031/03/01/10455/NS/23032022 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-31 | 2022-03-23 | 2022-03-25 | 2022-03-23 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4468 | [5 empty] | 2022-03-21 | 2022-03-22 | Partial installed_MW alignment Pending/Cable tray not installed(Timeline 22.03.22) | [9 empty] | 404-10-622091-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | VISHNU ENCLAVE | SUDHANSU YADAV; KRISHNA MARRIAGE HOME; 151; VISHNU ENCLAVE; OPP. ANAAJ MANDI GOVINDPURAM; GZB,Police Station Kavi Nagar Office Plice line Harsaogao,Ghaziabad,Uttar Pradesh- 201013. | 22100 | 22100 | 22100 | 22100 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GZBD-ENB-4137 | New | New_Built | RTT | 15 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6785 | 77.4847 | NA | 2021-12-06 | 2021-12-30 | 2022-02-05 | 11109-2867-85774846 | 2022-03-17 | 2022-03-19 |  |  |  |  | 2022-03-12 | 2022-03-20 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-22 |  |  |  | 2022-03-01 | ST202203058245 | S20220002739 |  |  | 2022-03-11 | P/FBW/DEL/1051248/2022 | 2022-03-25 | 2022-03-25 | DL/04/5428/0363/0031/03/01/10467/NS/25032022 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-03-26 | 2022-04-02 | 2022-03-26 | 2022-04-01 | 2022-03-26 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-17 |  | Indus |  | M1 | 289 | [5 empty] | 2022-03-21 | 2022-03-24 | Partial Installed_Farend Owner issue -599(Timeline 22.03.22),Installed_Farend Owner issue -599(Timeline 23.03.22) as on 22.03.22,Installed_Link done-Media Issue as on 23.03.22 | [9 empty] | 404-10-622100-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | AWHO Gurjinder Vihar | Mr. Uday Veer Sing-, Tower- GVAI Club, AWHO Township, Residents Welfare Association, Pocket No- P5,Sec-CHI-1, Gurjinder Vihar,Greater Noida, Gautam Buddha Nagar, Uttar Pradesh-201310 | 13250 | 13250 | 13250 | 13250 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Saral Communication | STTSPL042 | New | New_Built | RTP | 9 | 15 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.4471 | 77.5107 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11109-2844-71775106 | 2022-03-21 | 2022-03-21 |  |  |  |  | 2022-03-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-23 |  |  |  | 2021-10-27 | ST202110572261 | S20210032268 |  |  | 2021-11-19 | P/FVC/DEL/1044879/2021 | 2022-03-23 | 2022-03-24 | DL/03/5414/00006/0031/03/01/10464/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-04-01 | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 27129 | [5 empty] | 2022-03-22 | 2022-03-23 | Partial Installed_Farend Access issue 13268 | [9 empty] | 404-10-613250-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | New Industrial Twp2 | Mrs. Geeta Bhateja W/O Mr.Desraj Bhateja,Plot Number - 2G-17,Block-2G,New Industrial Twp2,Police Station - New Industrial Twp2,Post Office - New Industrial Twp1,Faridabad,Haryana-121001 | 21808 | 21808 | 21808 | 21808 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | 597734 | New | New_Built | RTP | 9 | 14 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.3828 | 77.287 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11106-2838-27772870 | 2022-03-21 | 2022-03-21 |  |  |  |  | 2022-03-18 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-23 | 2022-03-23 |  |  |  | 2021-12-20 | ST202112622964 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046894/2021 | 2022-03-23 | 2022-03-24 | DL/02/5126/00214/0031/03/01/10463/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-04-01 | 2022-03-24 | 2022-03-26 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 562 | [17 empty] | 404-10-621808-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Village-Nacholi(Relocation of 8096) | Mr. Ramesh S/O Sri Chand,House Number - 95,Village Nacholi,Post Office - Badsahpur,Police Station - Badsahpur,Faridabad Haryana 121002 | 22007 | 22007 | 22007 | 22007 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | 598042 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.4118 | 77.4018 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11106-2841-18774017 | 2022-03-21 | 2022-03-21 |  |  |  |  | 2022-03-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-23 |  |  |  | 2022-03-03 | ST202203061167 | S20220002821 |  |  | 2022-03-14 | P/FVC/DEL/1051365/2022 | 2022-03-23 | 2022-03-24 | DL/02/5126/00213/0031/03/01/10458/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-31 | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-04-08 | 2022-04-16 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 4528 | [5 empty] | 2022-03-22 | 2022-03-23 | Partial Installed/Farend Installed-Power temporary-mains not available-DCDB Req. as on 22.03.22,Integrated_Temp Power as on 23.03.22 | [9 empty] | 404-10-622007-11 |  |  |  |  | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | KHERA DHAMPURA¦ CHAPRAULA | .Mahender Singh S/O Late Shri Narayan Singh,Khasra No.744,Khata Number-00381,Khera Dharampura,Chhapraula,Police Station-Chhapraula,Post Office-Chhapraula,Gautam Buddha Naga,Uttar Pradesh-201308 | 20280 | 20280 | 20280 | 20280 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/9143 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6147 | 77.4888 | T21DL03273 | 2021-11-01 | 2021-12-08 | 2022-02-08 | 11109-2861-46774888 | 2022-03-21 | 2022-03-21 | 2022-03-21 |  |  |  | 2022-03-23 | [8 empty] | 2022-02-16 | ST202202047101 | S20220002142 |  |  | 2022-02-24 | P/FVC/DEL/1050150/2022 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; EB supply, PARSWA and Infra material not available | ATC | PRI_Without Material |  |  | Indus |  | M1 | 8009 | [5 empty] | 2022-03-21 |  | Survey Rejected; EB supply, PARSWA and Infra material not available | [14 empty] | Survey Rejected; EB supply, PARSWA and Infra material not available | ATC | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | Sec 51 Noida | Government Land,Noida Authority,GBM Location,in Front Of House Number - B-179,B- Block,Sector 50, Noida,Post Office - Sec 51,Police Station - Sector 51,Uttar Pradesh 201304 | 20566 | 20566 | 20566 | 20566 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3096778 | New | New_Built | GBM | 30 | 0 |  | COW |  |  | YES | >18HRS | NO | 28.5762 | 77.3662 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11109-2857-61773662 | 2022-03-21 | 2022-03-21 |  |  |  |  | 2022-03-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-23 |  |  |  | 2021-03-18 | ST202103094625 | S20210004928 |  |  | 2021-08-04 | P/FVC/DEL/1036716/2021 | 2022-03-23 | 2022-03-24 | DL/03/5177/00931/0031/03/01/10461/NS/24032022 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-30 | 2022-03-24 | 2022-03-30 | 2022-03-24 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) |  |  |  | Indus |  | M1 | 1116 | [5 empty] | 2022-03-22 | 2022-03-23 | Partial Installed_Pole Mount Required at 1116 as on 22.03.22,Site on DG & Fuel issue as on 23.03.22 | [9 empty] | 404-10-620566-11 | [5 empty] | MAPA_&_On_Air_(MS2) | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q4 | PCI Limited | P NO-287-288 PH-2 U/VIHAR GURUGRAM GURGAON, Dundahera 122016 | 27739 | 27739 | 27739 | 27739 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27739 | New | New_Built | IBS |  |  |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5069 | 77.0891 | NA | 2021-09-20 | 2022-02-10 | 2022-03-02 | 11106-2850-69770890 | 2022-03-22 | 2022-03-22 |  |  |  |  | 2022-03-24 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | [10 empty] | 2022-04-02 |  |  | 2022-04-02 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-09 | 2022-04-04 | 2022-04-08 | 2022-04-04 | [6 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | KPI Accepted | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-22 |  | Indus |  | M1 | 119 | [7 empty] | Survey done; Material request hold (CWIP Issue),Installation WIP-BBU Ping ok/GPS LDF 200 mtr req./combining wip as on 01.04.22 | [9 empty] | 404-10-627739-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | YMCA office | YMCA Connaught placeGround Floor,1, Jai Singh Road, New Delhi – 110001 .,DELHI | 27783 | 27783 | 27783 | 27783 |  |  |  | L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27783 | New | New_Built | IBS |  |  |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.6261 | 77.2113 | NA | 2022-03-08 | 2022-03-09 | 2022-03-18 | 111-2862-61772113 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-29 |  |  | 2022-03-24 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-01 | [27 empty] | ACCESS_Far_END | PRI_BEFORE_MS1 | Installed/Farned Partial installed-LDF 260 mtr req/LDF Routing Permission req for routing_21070/LDF Requested | Farend PRI | PRI_With Material | 2022-03-29 |  | Indus |  | M1 | 21070 | [5 empty] | 2022-03-31 |  | Survey done; Material request hold (CWIP Issue),Partial Installled-300 Mtr DAS Cabling,Farend Access Issue_345 as on 31.03.22,Installed/Farned Partial installed-LDF 260 mtr req./LDF Routing Permission req for routing_21070 as on 18.04.22 | [14 empty] | Installled With DAS,Farend Access Issue_27111 | Farend PRI
Del | FY20_21 | Q4 | Khirki Extn(Relocation of 5977) | House No. J-1/14, Gupta Colony, Khirki Extension, Post Office- Malviya Nagar, Police Station- Malviya Nagar, New Delhi-110017 | 21727 | 21727 | 21727 | 21727 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL141 | New | New_Built | RTP | 9 | 18 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5353 | 77.2167 | 21727 | 2021-08-27 | 2021-10-20 | 2021-11-11 | 111-2853-53772166 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-04-11 |  |  | 2022-03-27 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-13 | 2022-04-13 |  |  |  | 2022-02-21 | ST202202050924 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050296/2022 | 2022-04-19 | 2022-04-20 |  | 2022-04-20 | 2022-04-20 | 2022-04-20 | [11 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING |  | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-11 |  | Indus |  | M1 | 356 | [5 empty] | 2022-03-26 | 2022-04-19 | Survey Rejected; EB supply not available, Climbing ladder at Mumty not available,Approval received on 11.04.22,Partial Installed_Farend Access Issue_356 as on 13.04.22,Installed_Farend Access Issue_356 as on 13 Apr 22 | [14 empty] | Installed_Farend Access Issue_356 | Farend PRI
Del | FY20_21 | Q4 | DDA Okhla State(Relocation of 2731) | Government land -Shri Shiv Shakti Hanuman Vidya Mandir Charitable Trust,Infront of A-371,N J Camp,Govindpuri,Post Office - Alaknanda,Police Station - Govindpuri,Kalkaji,New Delhi 110019 | 21256 | 21256 | 21256 | 21256 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1503179 | New | New_Built | Cow | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5299 | 77.2595 | R/NN-558657 | 2020-11-11 | 2021-12-26 | 2022-01-24 | 111-2852-99772595 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-04-08 |  |  | 2022-03-27 | 2022-04-08 | 2022-04-10 | 2022-04-11 | 2022-04-11 | 2022-04-13 |  |  |  | 2022-01-31 | ST202202025984 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049203/2022 | 2022-04-13 | 2022-04-14 | DL/01/5177/06616/0031/03/01/10479/NS/14042022 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-17 | 2022-04-14 | 2022-04-16 | 2022-04-14 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-08 |  | Indus |  | M1 | 71 | [5 empty] | 2022-03-26 | 2022-04-12 | Survey Rejected; EB supply not available_Site On DG EB Timeline 14.04.22,Assembled/Farend Installed/DG down/Mains not available-Supporting wire theft_Infra issue | [9 empty] | 404-10-621256-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Saraswati Vihar(Relocation of 14374) | Property No. 288, out of Khasra no. 502-503/348,situated in the Lal Dora abadi deh 1908-09 of Village Pritampura Delhi-11034 | 22178 | 22178 | 22178 | 22178 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3119830 | New | New_Built | RTP | 6 | 22 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.699 | 77.1293 | R/NN-640924 | 2021-11-01 | 2022-01-08 | 2022-02-08 | 111-2869-89771293 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-04-11 |  |  | 2022-03-27 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-14 | 2022-04-14 |  |  |  | 2022-02-26 | ST202202056406 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1051027/2022 | 2022-04-14 | 2022-04-16 | DL/01/5177/06619/0031/03/01/10483/NS/16042022 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-16 |  | 2022-04-16 | 2022-04-18 | 2022-04-16 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-11 |  | Indus |  | M1 | 218 | [5 empty] | 2022-03-26 | 2022-04-11 | Survey Rejected; EB supply not available,Approval received on 11.04.22 | [9 empty] | 404-10-622178-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | GBD_Nyay_Khand(Relocation of 192) | Mr. Deepak Hans,Plot Number C-4,Nyay Khand I,Indirapuram,Near By Sai Mandir,Police Station Indirapuram,Post Office Indirapuram,Ghaziabad,Uttar Pradesh- 201014. | 22266 | 22266 | 22266 | 22266 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1275384 | New | New_Built | RTT | 9 | 13 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.6338 | 77.35 | R/RES-509713 | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11109-2863-38773499 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-04-16 |  |  | 2022-03-27 | 2022-04-16 | 2022-04-17 | [6 empty] | 2022-03-16 | ST202203073794 | S20220003485 |  |  | 2022-03-28 | P/FVC/DEL/1051938/2022 | [17 empty] | INFRA_Far_END | PRI_BEFORE_MS1 | Material return on 18.04.22 due to Access Issue & Farend Mount req | Farend PRI | PRI_Without Material | 2022-04-16 |  | Indus |  | M1 | 1312 | [5 empty] | 2022-03-26 |  | Survey Rejected; 06 pole mounts required_SO shared with Indus Team,Pole Mount reuired at Farend 1312,Material return on 18.04.22 | [14 empty] | 1027043 | Ericsson/SCM
Del | FY20_21 | Q4 | PVR Saket(Relocation of 604) | Mr. Mohd. Rafi, Plot Number 9, Community Centre, Ashok Vihar, Saket, Post Office- Saket, Police Station- Saket, New Delhi 110017 | 22265 | 22265 | 22265 | 22265 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1010399 | New | New_Built | GBM | 12 | 14 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.523 | 77.2077 | R/RES-509712 | 2022-03-04 | 2022-03-07 | 2022-03-17 | 111-2852-29772077 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-03-29 |  |  | 2022-03-27 | 2022-03-30 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-01 |  |  |  | 2022-03-16 | ST202203073795 | S20220003485 |  |  | 2022-03-28 | P/FVC/DEL/1051939/2022 | 2022-04-01 | 2022-04-04 | DL/01/5177/3256/0031/03/01/10475/NS/04042022 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-07 | 2022-04-04 | 2022-04-08 | 2022-04-04 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-29 |  | Indus |  | M1 | 5978 | [5 empty] | 2022-03-26 | 2022-03-29 | Survey Rejected; Technology deviation found,SACFA awaited | [9 empty] | 404-10-622265-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Global Heights 33 | Mr.Satendra.Tower-19,Breez Global Height,Sector-33,Dhonela Sohna Road,Police Station - Bhondsi,Post Office - Baluda,Gurugram Haryana 122102. | 20725 | 20725 | 20725 | 20725 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-GRGN-194 | New | New_Built | RTP | 6 | 39 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.2858 | 77.0697 | 20725 | 2021-08-27 | 2021-08-31 | 2022-01-13 | 11106-2828-58770697 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-04-11 |  |  | 2022-03-27 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-13 |  |  |  |  | 2022-01-31 | ST202202026014 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049212/2022 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Partial Installed_Public/Police Issue - Material with Toco | 3rd Party PRI | PRI_With Material | 2022-03-25 |  | Indus |  | M1 | 10120 | [5 empty] | 2022-03-26 |  | Survey done; Material request hold (CWIP Issue),Site on Sub Meter and Approval received on 11.04.22,Partial Installed_Public/Police Issue - Material with Toco 13.04.22 | [14 empty] | Partial Installed_Public/Police Issue - Material with Toco | 3rd Party PRI
Del | FY20_21 | Q4 | Ektagarden(Relocation of 863) | Dr.Anurag Jain,Plot no-18, Link Apartment, IP Extension Padpadganj, Delhi-110092 | 15749 | 15749 | 15749 | 15749 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-211 | New | New_Built | RTT | 6 | 25 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6202 | 77.2916 | 15749 | 2021-08-27 | 2022-02-07 | 2022-02-22 | 111-2862-02772915 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-04-11 |  |  | 2022-03-27 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-13 | 2022-04-13 |  |  |  | 2022-02-26 | ST202202055939 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050992/2022 | 2022-04-13 | 2022-04-14 | DL/01/0031/03210/0031/03/01/10481/NS/14042022 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 |  | 2022-04-14 | 2022-04-16 | 2022-04-14 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-25 |  | Indus |  | M1 | 8042 | [5 empty] | 2022-03-26 | 2022-04-11 | Survey done; Material request hold (CWIP Issue),Site on Sub Meter and Approval received on 11.04.22 | [9 empty] | 404-10-615749-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Surajkund International Craft Mela | Land of Paryatan wibhag,besides food court,North east gate, opp bharat petrolium, Suraj Kund, Lakewood city, Surajkund, Faridabad, Haryana 121010 | 22277 | 22277 | 22277 | 22277 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 22277 | New | New_Built | Cow | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4848 | 77.2867 | NA | 2022-03-25 | 2022-03-25 | 2022-03-25 | 11106-2848-47772867 | 2022-03-25 | 2022-03-26 | 2022-03-26 | 2022-03-27 |  |  | 2022-03-27 | 2022-03-27 | 2022-03-27 | 2022-03-27 | 2022-03-28 | 2022-03-29 | [10 empty] | 2022-03-29 | 2022-03-29 | DL/02/0031/00276/0031/345/04/08824/NS/29032022 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-04-01 | 2022-04-07 | NO |  |  | PRI_Closed | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-25 |  | Indus |  | M1 | 4994 | [5 empty] | 2022-03-26 | 2022-03-27 | MBTS not erected yet | [9 empty] | 404-10-622277-11 | [5 empty] | MAPA_&_On_Air_(MS2)
Del | FY20_21 | Q4 | Pacific Mall Dwarka -21 | PACIFIC MALL, Metro Station, Sect-21 Dwarka, New Delhi, 110077 | 27787 | 27787 | 27787 | 27787 |  |  |  | G1800_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Space Telelink | STIPL-DEL-1157 | New | New_Built | IBS |  |  |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5525 | 77.0584 | NA | 2022-03-14 | 2022-03-24 | 2022-03-24 | 111-2855-25770584 | 2022-03-29 | 2022-03-30 | 2022-03-30 | 2022-04-15 |  |  | 2022-03-31 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-18 | 2022-04-19 | [10 empty] | 2022-04-21 |  |  | 2022-04-21 | 2022-04-21 | 2022-04-21 | [11 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING |  | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-03-29 |  | Indus |  | M1 | 238 | [5 empty] | 2022-03-30 | 2022-04-20 | MW Mount required at Farend_238,Issue closed on 15.04.22,Partial installed-earthing pit req./climbing ladder req/N2N male jumper req. 9 nos due to planning/mcb req. 120 Amps/Link Done as on 18.04.22,Media Issue as on 18.04.22,Installed/climbing ladder req/mcb 63 Amps installed/Link done-BBU ping ok/SMPS faulty as on 19.04.22 | [14 empty] | 75112 | Ericsson/SCM
Del | FY20_21 | Q4 | Prem Nagar 2, Nagloi | Hno.346,old no.135,kh no.1356,kirari suleman nagar delhi-110086 | 21129 | 21129 | 21129 | 21129 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1441368 | New | New_Built | RTT | 12 |  |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.689 | 77.0544 | R/NN-469896 | 2020-10-02 | 2020-10-31 | 2020-11-09 | 111-2868-89770544 | 2022-03-29 | 2022-03-29 |  |  |  |  | 2022-03-31 | 2022-03-30 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-01 |  |  |  | 2020-11-12 | ST202011145365 | S20200008117 |  |  | 2020-12-25 | P/FVC/DEL/1013822/2020 | 2022-04-01 | 2022-04-01 | DL/01/5177/06597/0031/345/04/08826/NS/01042022 | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-08 | 2022-04-16 | NO |  |  |  | MAPA_&_On_Air_(MS2) |  | MAPA_&_On_Air_(MS2) | X | 2022-03-29 |  | Indus |  | M1 | 4913 | [17 empty] | 404-10-621129-11 |  |  |  |  | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Sainik Colony | Government Land,MCF Green Belt,GBM Location,Near A.S. Motors,A Block Road,Pocket A, Sainik Colony, Sector - 49,Post Office - SGM Nagar,Police Station - SGM Nagar, Faridabad, Haryana 121012 | 17348 | 17348 | 17348 | 17348 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3103110 | New | New_Built | GBM | 30 |  |  | Indus_Lite+ | Indus_Lite+ | Other than Indus & ATC | YES | >18HRS | NO | 28.4016 | 77.2725 | R/NN-639009 | 2021-10-10 | 2021-12-17 | 2022-01-18 | 11106-2840-15772725 | 2022-03-29 | 2022-03-30 | 2022-03-30 | 2022-04-20 |  |  | 2022-03-31 | 2022-04-20 | [7 empty] | 2022-01-18 | ST202201012948 | S20220000788 |  |  | 2022-01-25 | P/FVC/DEL/1048517/2022 | [17 empty] | PRI_Closed | Material_In_Transit | 18552656 | Ericsson/SCM | X | 2022-03-29 |  | Indus |  | M1 | 1931 | [5 empty] | 2022-03-30 | 2022-04-20 | Survey Rejected; 186M Lat-Long deviation found | [14 empty] | Survey Rejected; 186M Lat-Long deviation found_Site Need to Re RFAI by Indus Discussed with Tarun on 12.04.22 | Indus
Del | FY20_21 | Q4 | Khanpur Japti | Mr. Bharat Sharma S/O Sh. Surender Pal Sharma,Plot Number -E-6, Sector A-7, (P),Tronica City, Loni Ghaziabad,Police Station - Tronica City,Post Office - Tronica City, Ghaziabad Uttar Pradesh - 201102. | 21274 | 21274 | 21274 | 21274 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Tvil | TV_21274_DEL | New | New_Built | RTT | 15 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.7858 | 77.2404 | 21274 | 2020-12-28 | 2022-01-04 | 2022-03-09 | 11109-2878-58772403 | 2022-04-06 | 2022-04-06 |  |  |  |  | 2022-04-08 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-08 | 2022-04-09 |  |  |  | 2022-03-14 | ST202203071693 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051677/2022 | 2022-04-11 | 2022-04-12 | DL/04/5113/00080/0031/03/01/10476/NS/12042022 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-14 | 2022-04-12 | 2022-04-14 | 2022-04-12 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | MS Submitted | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-06 |  | Indus |  | M1 | 4503 | [5 empty] | 2022-04-09 | 2022-04-11 | Partial Installed/Wrong GSM deliverd/signage board req_Link done-BBU Ping ok,Installed_Link Done Media Issue as on 09.04.22_Media Issue closed on 11.04 | [9 empty] | 404-10-621274-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Raj Nagar Extension, Ghaziabad | Mr.Vishal Kumar,Khasra Number-1007,Windsor Paradise-2,Tower-H,Noor Nagar,Raj Nagar Extention,Police Station-Raj Nagar Extention,Post Office-Raj Nagar Extention,Ghaziabad,Uttar Pradesh-201008 | 21836 | 21836 | 21836 | 21836 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3017385 | New | New_Built | RTP | 6 | 65 |  | Indus_Lite+ |  |  | YES | >18HRS | NO | 28.7074 | 77.424 | R/NN-627178 | 2021-11-01 | 2022-01-08 | 2022-02-08 | 11109-2870-74774240 | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-04-11 |  |  | 2022-04-08 | 2022-04-11 | [7 empty] | 2022-02-26 | ST202202056377 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1051026/2022 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Hold By Juber on 13.04.22 for Material Dispatch due RWA Issue | Indus | PRI_Without Material | 2022-04-06 |  | Indus |  | M1 | 290 | [5 empty] | 2022-04-06 |  | Survey Rejected; Sub_Meter available for Power Supply,Approval received on 11.04.22,Hold By Juber on 13.04.22 for Material Dispatch due RWA Issue | [14 empty] | Hold By Juber on 13.04.22 for Material Dispatch due RWA Issue | Indus
Del | FY20_21 | Q4 | Nasbandi Colony, Ghaziabad | MR. SAVITA DEVI; KH NO 346/1 PLOT NO 78 ASE 2 SADALA BAD COLONY LONI GZBD,Uttar Pradesh-201102 | 21842 | 21842 | 21842 | 21842 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-LONI-ENB-3399 | New | New_Built | GBM | 25 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7387 | 77.2729 | NA | 2021-12-06 | 2021-12-22 | 2022-02-05 | 11109-2873-87772729 | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-04-09 |  |  | 2022-04-08 | 2022-04-09 | 2022-04-11 | 2022-04-12 | 2022-04-12 | 2022-04-13 |  |  |  | 2022-02-26 | ST202202056015 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1051009/2022 | 2022-04-13 | 2022-04-14 | DL/04/5428/0364/0031/03/01/10478/NS/14042022 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-19 | 2022-04-14 | 2022-04-18 | 2022-04-14 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-06 |  | Indus |  | M1 | 1705 | [5 empty] | 2022-04-06 | 2022-04-09 | Survey Rejected; Eagle Issue | [9 empty] | 404-10-621842-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Mayur Vihar | Government Land,Budhha Park Adjacent To Public Toilet, Opposite Metro Piller Number 25 And Mayur Vihar Metro Gate Number 1,Mayur Vihar,Police Station - Mayur Vihar Phase 1,Post Office - Trilokpuri Pocket 3,New Delhi-110091 | 13973 | 13973 | 13973 | 13973 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nettel Infrastructure Private Limited | NBGC_13973 | New | New_Built | Cow | 30 | 0 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.6057 | 77.2975 | NA | 2021-11-01 | 2022-01-08 | 2022-02-08 | 111-2860-57772974 | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-04-20 |  |  | 2022-04-08 | 2022-04-20 | [7 empty] | 2022-02-26 | ST202202055938 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050991/2022 | [17 empty] | PRI_Closed | Material_In_Transit | 75203 | Ericsson/SCM | X | 2022-04-06 |  | Indus |  | M1 | 1047 | [5 empty] | 2022-04-06 | 2022-04-20 | Survey Rejected; 46M lat-Long deviation found, GSM pole mounts not available in any sector, Cable tray & tower earthing not available and EB supply not available_Ok For Drift Location As Per Manoj approval on 11.04.22 & Infra Issue Closed as per Prince on 11.04.22,Site on DG_Approval awaited | [14 empty] | Site on DG_Approval awaited | 3rd Party PRI
Del | FY20_21 | Q4 | Gautam Nagar | Government Land,South Delhi Municipal Corporation(Park),MBTS Location,Infront of Gulmohar Enclave Gate Number - 4,and House Number 135B Gautam Nagar,and Left Side House Number -183A Gautam Nagar,Right Side House Number F-9 Gautam Nagar,Police Station - Hauz khas,Post office - Gautam Nagar,New Delhi -110049 | 21059 | 21059 | 21059 | 21059 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1806603 | New | New_Built | Cow | 30 | 0 |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.5599 | 77.2106 | R/NN-567850 | 2021-03-12 | 2021-05-03 | 2021-07-28 | 111-2855-98772105 | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-04-08 |  |  | 2022-04-08 | 2022-04-08 | 2022-04-10 | 2022-04-11 | 2022-04-11 | 2022-04-11 |  |  |  | 2021-07-29 | ST202107401859 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037088/2021 | 2022-04-13 | 2022-04-14 | DL/01/5177/06615/0031/03/01/10480/NS/14042022 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 |  | 2022-04-14 | 2022-04-16 | 2022-04-14 | [6 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-08 |  | Indus |  | M1 | 4740 | [5 empty] | 2022-04-06 | 2022-04-13 | Survey Rejected; EB supply not available_Site On DG EB Timeline 14.04.22,Installed_2G Media Issue as on 11.04.22,Media Issue closed on 13.04.22 | [9 empty] | 404-10-621059-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | Amar Colony | Mr. Ajay Kumar S/O Mr.Bhopal Singh,House Number - D -134,Gali Number - 26,Amar Colony,Gokulpur,Police Station - Gokulpur,Post Office - Gokulpuri,East Delhi-110094 | 21178 | 21178 | 21178 | 21178 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nettel Infrastructure Private Limited | NTPA_21178 | New | New_Built | RTP | 10 | 11 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.7061 | 77.2975 | NA |  |  |  | 111-2870-61772974 | 2022-04-12 | 2022-04-12 | [5 empty] | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-14 | 2022-04-15 |  |  |  | 2021-12-15 | ST202112617438 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046930/2021 | 2022-04-15 | 2022-04-16 | DL/01/9037/00003/0031/03/01/10484/NS/16042022 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-16 | 2022-04-19 | 2022-04-16 | 2022-04-18 | 2022-04-16 | [6 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-12 |  | Indus |  | M1 | 1647 | [17 empty] | 404-10-621178-11 | [5 empty] | MAPA_&_ON_AIR_(MS2)_PENDING
Del | FY20_21 | Q4 | VILLAGE DHORKHA | Mr. Ramphal Yadav,Plot Number - 18/23,Village Dhorka Pataudi Road,Police Station - Farrukhnagar,Post Office - Farrukhnagar,Gurugram, Haryana 122051 | 22230 | 22230 | 22230 | 22230 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6752 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.4122 | 76.8948 | NA |  |  |  | 11106-2841-21768947 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-13 |  |  |  | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-16 | 2022-04-17 |  |  |  | 2022-03-22 | ST202203078561 | S20220003797 |  |  |  |  | 2022-04-18 | 2022-04-19 |  | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-19 |  | 2022-04-19 |  | 2022-04-19 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING |  | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-12 |  | Indus |  | M1 | 21171 | [5 empty] | 2022-04-12 | 2022-04-13 | Survey Rejected; Cable Tray required and Parswa canopy power need to route properly,Issue closed on 13.04.22 | [14 empty] | Installed_Link Done | Jitender
Del | FY20_21 | Q4 | Racketroad-Oldsecretariat(Relocation of 23357) | Mrs. Nirmala Bhargav W/O Mr. Suresh Bhargav, House number - 4/5, Racquet Court Road, Khyber Pass, Civil Lines, Police Station - Civil lines,Post Office - Civil Lines,Delhi-110054 | 18359 | 18359 | 18359 | 18359 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Infinite Telecom | ITSPL-DL-DLHI-168 | New | New_Built | RTP | 6 | 15 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.685 | 77.2212 | NA |  |  |  | 111-2868-50772212 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-20 |  |  | 2022-04-20 | 2022-04-20 | [7 empty] | 2020-03-04 | 2020397626 | 2020397626 |  |  | 2020-05-30 | P/FVC/DEL/6072239/2020 | [17 empty] | PRI_Closed | Material_In_Transit | 75208 | Ericsson/SCM | X | 2022-04-12 |  | Indus |  | M1 | 10855 | [5 empty] | 2022-04-12 | 2022-04-20 | Sub_meter available for Power supply | [14 empty] | Sub_meter available for Power supply | 3rd Party PRI
Del | FY20_21 | Q4 | EMCD_50_Shivam Enclave | Mr. Mahinder Singh S/O Devi Dayal,House Number 28/17/4,Kasturba Nagar, Shahdara, Police Station - Vivek Vihar,Post Office - Shahdara ,Delhi-110032 | 20886 | 20886 | 20886 | 20886 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVIL | ATDLSHA0832 | New | New_Built | RTP | 9 | 13 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.6685 | 77.3016 | NB_SR1638941514670 |  |  |  | 111-2866-85773015 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-20 |  |  | 2022-04-20 | 2022-04-20 | [7 empty] | 2020-10-09 | ST202010102176 | S20200005874 |  |  | 2020-10-20 | P/FVC/DEL/1009263/2020 | [17 empty] | PRI_Closed | Material_In_Transit | 75199 | Ericsson/SCM | X | 2022-04-12 |  | Indus |  | M1 | 283 | [5 empty] | 2022-04-15 | 2022-04-20 | Locator Issue resolved on 13.04.22,Material return on 15.04.22 | [14 empty] | Material return on 15.04.22 | 3rd Party PRI
Del | FY20_21 | Q4 | NAND NAGARI | MRS. SUSHMA,Mr. Rakesh Ji,SHOP NO- B-1/39,Near House Number A-4/425, Behind Mother Dairy,Nand Nagari,Post Office - Nand Nagari,Police Station - Nand Nagari, Delhi - 110093 | 21948 | 21948 | 21948 | 21948 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-9822 | New | New_Built | RTT | 12 | 8 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6929 | 77.3095 | SR-DL000193 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-15 | 111-2869-28773094 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-13 |  |  |  | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-15 | 2022-04-15 | [28 empty] | SACFA_Pending |  | SACFA_Pending | SACFA_Pending | 2022-04-12 |  | Indus |  | M1 | 1394 | [5 empty] | 2022-04-15 |  | Locator Issue resolved on 13.04.22_SACFA Pending as on 15.04.22 | [15 empty] | SACFA_Pending
Del | FY20_21 | Q4 | Karawal Nagar | Mrs. Warisa Jaha W/O Ahmed Hasan,House Number C-83,Gali Number 1,Old Mustafabad,Karawal Nagar, Police Station - Shiv vihar,Post Office -Karawal Nagar,Delhi-110094 | 18186 | 18186 | 18186 | 18186 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL91 | New | New_Built | RTP | 6 | 15 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7161 | 77.2745 | 18186 | 2021-08-27 | 2022-03-01 | 2022-03-01 | 111-2871-60772745 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-20 |  |  | 2022-04-20 | 2022-04-20 | [7 empty] | 2022-03-03 | ST202203061176 | S20220002821 |  |  | 2022-03-14 | P/FVC/DEL/1051367/2022 | [17 empty] | PRI_Closed | Material_In_Transit | 75209 | Ericsson/SCM | X | 2022-04-12 |  | Indus |  | M1 | 1738 | [5 empty] | 2022-04-12 | 2022-04-20 | Survey Rejected; Sub_meter available for Power, Cable tray required Tower to BTS PAD, Tower earthing not available,Infra Issue closed on 13.04.22,Site on Sub Meter | [14 empty] | Sub_meter available for Power supply | 3rd Party PRI
Del | FY20_21 | Q4 | RCC(Roof top billet 7D) Air Force A-1 | Airforce RCC, Air Force Station, 412, Lok Kalyan Marg, Race Course, New Delhi. 110011 | 20533 | 20533 | 20533 | 20533 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVIL | VIDLLKM0820 | New | New_Built | RTT | 12 | 10 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.5942 | 77.2052 | NT_SR1648026510883 |  |  |  | 111-2859-42772051 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-19 |  |  | 2022-04-19 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-21 | 2022-04-21 | [27 empty] | PRI_Closed | Integration_Pending | Installed_Farend Mount req. | Jitender | X | 2022-04-14 |  | Indus |  | M1 | 21742 | [5 empty] | 2022-04-14 | 2022-04-19 | Survey Rejected; TVIL PARSWA Canopy and DCDB required,Pole Mount required at farend as on 16.04.22 | [14 empty] | Pole Mount required at farend | Farend PRI
Del | FY20_21 | Q4 | Alahawas (Relocation of 18613) | Smt. Rajesh W/O Rohtas Behrampur,Mushtil No 45,Vill-Alahawas,Police Station - Sec 65,Post Office - kardarur,Tehsil- Sohna, District-Gurgaon, Haryana-122001 | 22243 | 22243 | 22243 | 22243 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVIL | RJHAZSH0273 | New | New_Built | GBT | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.4012 | 77.1101 | NA | 2022-02-14 | 2022-02-22 | 2022-03-09 | 11106-2840-12771100 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-18 |  |  | 2022-04-18 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-20 | 2022-04-21 |  |  |  | 2022-03-14 | ST202203071692 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051676/2022 | [17 empty] | PRI_Closed | Integration_Pending | Installed_BBU Faulty | Jitender | X | 2022-04-14 |  | Indus |  | M1 | 4539 | [5 empty] | 2022-04-14 | 2022-04-18 | Approval required to use Parent site EB meter and height deviation approval received on 29 Mtr,Issue closed on 18.04.22 | [14 empty] | Approval required to use Parent site EB meter and height deviation approval received on 29 Mtr | 3rd Party PRI
Del | FY20_21 | Q4 | Sec63,Noida(Relocation of 5847) | Mr. Suchet Singh S/o Atar Singh & Mr. Upender Chauhan S/o Suchet Singh .Sharmik Kunj,Village Mamura,Near By Electric Substation,Sector 66,Police Station - Phase 3,Post Office - Franchise Post Office Sec 51 Noida ,Noida,Uttar Pradesh- 201307 | 22074 | 22074 | 22074 | 22074 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVIL | RJUPZNO0237 | New | New_Built | RTT | 12 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6093 | 77.3785 | NT_SR1648541932861 | 2021-11-19 | 2022-03-24 | 2022-03-25 | 11109-2860-93773784 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-21 |  |  | 2022-04-21 | 2022-04-21 | [31 empty] | PRI_Closed | WH_To_Dispatch | 1027098 | Ericsson/SCM | X | 2022-04-14 |  | Indus |  | M1 | 5522 | [5 empty] | 2022-04-14 | 2022-04-21 | Survey Rejected; Infra not ready, Technology deviation_TB Plan on 240 Degree,Issue closed on 18.04.22,Pole Mount required at farend as on 18.04.22 | [14 empty] | Survey Rejected; Infra not ready, Technology deviation_TB Plan on 240 Degree | 3rd Party PRI
Del | FY20_21 | Q4 | Asola, Fatehpur | khasra no. 443-444 , Rajkumar Colony Asola Bandh Road ,New Delhi 110074 | 20994 | 20994 | 20994 | 20994 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20994_DEL | New | New_Built | RTT | 12 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4556 | 77.1888 | 20994 | 2020-08-27 | 2021-01-13 | 2021-01-15 | 11106-2832-19768994 | 2022-04-14 | 2022-04-14 | [5 empty] | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-16 | 2022-04-16 |  |  |  | 2021-01-08 | ST202101005485 | S20210000384 |  |  | 2021-01-16 | P/FVC/DEL/1016305/2021 | 2022-04-18 | 2022-04-19 |  | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-19 |  | 2022-04-19 |  | 2022-04-19 | [5 empty] | PRI_Closed | MAPA_&_ON_AIR_(MS2)_PENDING |  | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-14 |  | Indus |  | M1 | 5595 | [5 empty] | 2022-04-16 | 2022-04-18 | Installed_2G Media Issue as on 16.04.22 | [14 empty] | Installed_2G Media Issue | Shashank
Del | FY20_21 | Q4 | Panchgaon-Proudly Desi, kukhrola | Mr.Sarab Singh Yadav S/O Shri Lakhmi Chand,Near Panchgaon Hotel,Village-Panchgaon,Fazalwas(149),Police Station-Manesar,Post Office-Manesar,,Gurgaon,Haryana-122015 | 22194 | 22194 | 22194 | 22194 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 22194 | New | New_Built | RTT | 12 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.3219 | 76.8995 | NA | 2022-03-03 | 2022-03-07 | 2022-03-08 | 111-2845-55771888 | 2022-04-14 | 2022-04-14 | [5 empty] | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-16 | 2022-04-17 |  |  |  | 2022-03-14 | ST202203071700 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051684/2022 | 2022-04-17 | 2022-04-18 |  | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18 |  | 2022-04-18 |  | 2022-04-18 | [6 empty] | MAPA_&_ON_AIR_(MS2)_PENDING | Under KPI | MAPA_&_ON_AIR_(MS2)_PENDING | X | 2022-04-14 |  | Indus |  | M1 | 9193 | [17 empty] | 404-10-622194-11 | [5 empty] | EMF_Pending
Del | FY20_21 | Q4 | South Extension I | H No-A-3, Ground Floor, N.D.S.E-1,Mr.Vijay Kumar Jindal, S/o- Sri Satpal Vir,New Delhi-110049 | 14459 | 14459 | 14459 | 14459 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Fine bunch | FB0014 | New | New_Built | RTP | 9 | 15 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5723 | 77.2186 | 14459 | 2020-09-25 | 2020-10-05 | 2020-10-20 | [16 empty] | 2020-10-22 | ST202010118681 | S20200006620 |  |  | 2020-11-30 | P/FVC/DEL/1010497/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC on-air | RFAI_Pending
Del | FY20_21 | Q4 | Trilokpuri(Relocation of 2832) | - | 21746 | 21746 | 21746 | 21746 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001520 | Relocation | New_Built | RTT | - | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6005 | 77.3045 | R/NN-620818 | 2021-06-24 | 2021-06-28 | 2021-07-05 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Agar Nagar Ugna Chowk | - | 21266 | 21266 | 21266 | 21266 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001888 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6985 | 77.0383 | R/NN-621212 | 2021-11-01 | 2022-02-01 | 2022-02-08 | [16 empty] | 2022-02-16 | ST202202047097 | S20220002142 |  |  | 2022-02-24 | P/FVC/DEL/1050146/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | ASHOK VIHAR, LONI | Mr.Abid S/O Mr.Altmuddin,House Number - 120,Khasra Number - 321,Ahmed Nagar,Ashok Vihar,Loni,Police Station - Loni,Post Office - Loni,Ghaziabad,Uttar Pradesh-201102 | 21278 | 21278 | 21278 | 21278 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3055780 | New | New_Built | RTT | 12 | 8 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7582 | 77.2891 | R/NN-633109 | 2021-10-12 | 2021-10-15 | 2021-10-22 | [16 empty] | 2021-10-27 | ST202110572264 | S20210032268 |  |  | 2021-11-19 | P/FVC/DEL/1044873/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Molar Band | House No.1332/E,Gali no.51, molarband ext. badarpur New delhi 110044 | 21269 | 21269 | 21269 | 21269 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21269_DEL | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4908 | 77.314 | 21269 | 2021-03-22 | 2021-05-24 | 2021-05-26 | [16 empty] | 2021-05-28 | ST202105303940 | S20210010398 |  |  | 2021-07-22 | P/FVC/DEL/1036081/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Indra Park(Relocation of 13759) | Mr. Sochitra W/O LT Ram Chandra Prashad,Plot No. RZ-26P/184-A_1, Khasra No. 305,Village Nasirpur, Indra Park, Palam Colony,New Delhi | 21607 | 21607 | 21607 | 21607 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1734111 | Relocation | New_Built | RTP | 9 | 13 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5995 | 77.0984 | R/NN-565738 | 2021-02-15 | 2021-04-10 | 2021-04-15 | [16 empty] | 2021-04-21 | ST202104161242 | S20210007316 |  |  | 2021-07-22 | P/FVC/DEL/1036298/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Mahipalpur(Relocation of 23153) | Mr. Jai parkash S/o Mangal singh,House Number -867,Gali Number -6G,Block -k-2,Near Mata Chowk Mahipalpur Ext,Police station - Mahipalpur,Post office - mahipalpur,District - south west,Delhi -110037 | 21848 | 21848 | 21848 | 21848 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21848_DEL | Relocation | New_Built | RTP | 9 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5399 | 77.1282 | 21848 | 2021-08-13 | 2021-09-17 | 2021-09-29 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SEC-17/A,GURGAON | Mr.Vijay yadav, House Number-681, Sector 17/A , Police station-Sector 17, Post Office-Sector 17, Gurgaon,Haryana-122101, | 19704 | 19704 | 19704 | 19704 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/AT/8911 | New | New_Built | RTP | 9 | 12 |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.4799 | 77.0636 | T21DL02800 | 2021-09-06 | 2021-09-27 | 2021-11-24 | [16 empty] | 2021-12-13 | ST202112614876 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046024/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Laxman Vihar, Ph-2 | Mr. Bijender Singh, House number- 15G, Khatoni No. 448, Khasra No.11001/2959, Gali No. - 4, Laxman Vihar, Phase II, Gurgaon, Haaryana - 122101 | 18707 | 18707 | 18707 | 18707 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/AT/8757 | New | New_Built | RTT | 9 | 13 |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.4807 | 77.0077 | T21DL00666 | 2021-03-08 | 2021-03-16 | 2021-05-08 | [16 empty] | 2021-03-18 | ST202103095673 | S20210004955 |  |  | 2021-06-06 | P/FVC/DEL/1027946/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Village Pillangi,Kotla Mubarakpur, | Mr. Mahesh S/O Udayveer,House Number - 2037,Pilanji kotla mubarakpur,Uday Chand Marg, South Extension,Trilok Colony,South Extension I,Post Office - Kotla,Police Station - Kotla,New Delhi 110003 | 19948 | 19948 | 19948 | 19948 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19948_DEL | New | New_Built | RTM | 12 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5755 | 77.2202 | 19948 | 2021-09-14 | 2021-09-17 | 2021-09-24 | [16 empty] | 2021-09-27 | ST202109535768 | S20210030452 |  |  | 2021-09-30 | P/FVC/DEL/1042612/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | SDMC_Kalindi Colony(Relocation of 705) | Kalindi colony near by meerabai polytechnic staff campus delhi-110014 | 9851 | 9851 | 9851 | 9851 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/9109 | Relocation | New_Built | Cow | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5756 | 77.2681 | T22DL00022 | 2020-06-15 | 2020-09-10 | 2020-09-24 | [16 empty] | 2020-09-29 | ST202009092462 | S20200005308 |  |  | 2020-10-06 | P/FVC/DEL/1007774/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Vivek Vihar Gr.Noida(Relocation of 13235) | Noida Authority(Green Belt),GBM Location Near Service Ln,In Front of Electricity Pole No.196,Purvanchal Silver City - 2, Pi I & II, Pi I & Ii,Greater Noida,Uttar Pradesh 201310 | 21702 | 21702 | 21702 | 21702 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1843012 | Relocation | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4756 | 77.536 | R/NN-568942 | 2021-03-22 | 2021-04-16 | 2021-04-26 | [16 empty] | 2021-04-27 | ST202104194582 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028807/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Gaur Global Village Society, Crossing republic ghaziabad | - | 21740 | 21740 | 21740 | 21740 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | STTSPL02 | New | New_Built | RTP | 6 | 71 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6305 | 77.4366 | 21740 | 2021-08-27 | - | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050910 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050291/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SECTOR 46,GURGAON(Relocation of 7799) | Mr. Vijay Aggarwal S/O Sh. Satay Narain,Plot Number - 41P,Sector- 45,Police Station - Sector-40,Post Office - Kanhai ,Gurugram Haryana 122003 | 20891 | 20891 | 20891 | 20891 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GRG/AT/8755 | Relocation | New_Built | RTP | 9 | 16 |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.4383 | 77.0659 | T21DL00664 | 2021-03-09 | 2021-10-20 | 2021-10-28 | [16 empty] | 2021-11-03 | ST202111581272 | S20210032784 |  |  | 2021-11-19 | P/FVC/DEL/1044821/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sainik Enclave | Plot No-121 Khasra No-5/19,Block B,Sainik Enclave,Part III,New Delhi 110072 | 20357 | 20357 | 20357 | 20357 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6311 | 76.9577 | 20357 | 2019-10-09 | 2020-02-11 | 2020-02-14 | [16 empty] | 2021-12-20 | ST202112622974 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046899/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Taj Vivanta hotel | - | 23189 | 23189 | 23189 | 23189 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 23189 | New | New_Built | RTP | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.558 | 77.0626 | 23189 | 2021-09-06 | 2021-12-06 | 2021-12-06 | [16 empty] | 2021-11-19 | ST202111595354 | S20210033636 |  |  | 2021-11-26 | P/FVC/DEL/1045398/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Main Road Jaitpur(Relocation of 199) | A-2/A, Hari Nagar Extension, Saurabh Vihar, Badarpur, ND-110044 | 20747 | 20747 | 20747 | 20747 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20747_DEL | Relocation | New_Built | RTM | 15 | 11 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5059 | 77.3252 | 20747 | 2020-08-29 | 2020-09-25 | 2020-10-14 | [16 empty] | 2020-07-21 | ST202007026848 | S20200001913 |  |  | 2020-07-25 | P/FVC/DEL/1002758/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SAMTAPUR,MUKANDPUR | A-307,Samta Vihar,Mukundpur,Delhi-42 | 19888 | 19888 | 19888 | 19888 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19888_DEL | New | New_Built | RTT | 12 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7424 | 77.1859 | 19888 | 2019-09-20 | 2020-08-30 | 2020-09-04 | [16 empty] | 2020-10-29 | ST202010125954 | S20200007048 |  |  | 2020-12-08 | P/FVC/DEL/1011453/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec 9, Gurgaon | Hno. 1029/9 Sec-9 Gurgaon Haryana-122001 | 18244 | 18244 | 18244 | 18244 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | AM_18244_Del | New | New_Built | RTP | 9 | 12 |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.4632 | 77.0006 | T21DL03673 | 2021-09-06 | 2021-12-02 | 2021-12-07 | [16 empty] | 2021-12-20 | ST202112622968 | S20210035261 |  |  | 2021-12-24 | P/FVC/DEL/1046895/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Sector 7 Faridabad | H.No. 2199, New White Drycleaners, Sector- 7A, Faridabad, Haryana, 121006 | 17899 | 17899 | 17899 | 17899 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Space_Telelink | SC_17899_DEL | New | New_Built | RTP | 9 | 12 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.3663 | 77.3285 | 17899 | 2021-02-08 | 2021-02-18 | 2021-03-22 | [16 empty] | 2021-02-23 | ST202102066899 | S20210003586 |  |  | 2021-07-08 | P/FVC/DEL/1033741/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SDMC_J BLOCK,SARITA VIHAR | G Pocket Parking Back side of Gurudwara, Sarita Vihar, New Delhi-110044 | 19572 | 19572 | 19572 | 19572 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388105 | New | New_Built | Cow | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5335 | 77.2938 | R/NN-464518 | 2020-08-07 | 2020-08-10 | 2020-08-14 | [16 empty] | 2020-08-21 | ST202008049427 | S20200003305 |  |  | 2020-08-27 | P/FVC/DEL/1004492/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | DJB CA Blk Shalimar Bagh | Mr. Sushil Kumar S/O Sh. Ved Prakash,Khasra number - 23/14, 100 futa road,Infront of Transformer number - Zone 414,DT-400KVA, P/M-S/S. Jharoda Dairy,Serial Number - OP-11/400KVA/183,Himgiri Enclave ,Sant Nagar,Village Burari, Post Office - Burari,Police Station - Burari, Delhi - 110084, | 20157 | 20157 | 20157 | 20157 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1893932 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.735 | 77.1972 | R/NN-569960 | 2021-04-05 | 2021-08-05 | 2021-08-20 | [16 empty] | 2021-08-17 | ST202108430891 | S20210018854 |  |  | 2021-08-26 | P/FVC/DEL/1038089/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | The Aranya | Government Land,Noida Authority,GBM Location,Green Belt Noida Authority,Pradhan Jaipal singh Rd,Opposite Tower 2 The Aranya, Sector 122, Noida,Police Station - Bisrakh, Post Office- Sector 122 Noida,Uttar Pradesh-201304. | 21779 | 21779 | 21779 | 21779 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3017297 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5904 | 77.4033 | R/NN-627143 | 2021-08-10 | 2021-10-02 | 2021-10-16 | [16 empty] | 2021-10-20 | ST202110564526 | S20210031884 |  |  | 2021-11-13 | P/FVC/DEL/1044424/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-21 Rohini | Ms. Baljeet Kaur S/O S. Karnail Singh,Plot Number - 18,Pocket - 1, Sector 21 Rohini,Near MCD Primary School,Post Office - Sector 23 Rohini,Police Station - Old Aman Vihar, Delhi - 110066 | 21825 | 21825 | 21825 | 21825 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3107674 | New | New_Built | RTP | 9 | 14 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7111 | 77.0669 | R/NN-639602 | 2021-08-09 | 2021-12-21 | 2022-01-18 | [16 empty] | 2022-02-21 | ST202202050949 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050307/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sector 3, IMT Manesar(Relocation of 17624) | GBM Location In Front Of Sunrays Engineers Pvt.Ltd., Plot No.111,Sector-3,IMT Manesar,Gurugram ,Haryana-122051 | 21724 | 21724 | 21724 | 21724 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1954002 | Relocation | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.3635 | 76.912 | R/NN-618366 | 2021-04-23 | 2021-05-05 | 2021-06-21 | [16 empty] | 2021-06-26 | ST202106362837 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034611/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Jahangirpuri | Municipal corporation of delhi (MCD) community hall,GBM Location,G block and infront of electric pole no HT-505-31/19A,Transformer no - S.No-865132,bhalswa jahangirpuri, New delhi 110033 | 19857 | 19857 | 19857 | 19857 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001974 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7252 | 77.1748 | R/NN-625346 | 2021-07-05 | 2021-07-14 | 2021-07-27 | [16 empty] | 2021-07-30 | ST202107402578 | S20210013993 |  |  | 2021-08-04 | P/FVC/DEL/1037093/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Winsorcourt(Relocation of 4210) | Mr.Yadav,Khasha Number - 417,418,419,420,Windsor Court,Tower-T,In Front Of House Number - 6102,DLF Phase IV,Police Station - Sector 53,Post Office - Sector 53,Gurugram,Haryana-122002 | 10375 | 10375 | 10375 | 10375 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_10375_DEL | Relocation | New_Built | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4639 | 77.0855 | 10375 | 2021-08-27 | 2021-12-31 | 2021-12-31 | [16 empty] | 2020-03-21 | 2020524771 | 2020524771 |  |  | 2020-07-01 | P/FVC/DEL/6104001/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Loni | F-A/173, Lajpat Nagar, Sahibabad, Ghaziabad-201005 | 20369 | 20369 | 20369 | 20369 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL142 | New | New_Built | RTT | 12 | 11 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6831 | 77.3673 | 20369 | 2021-11-10 | - | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050918 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050294/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | crossing rebublic club | Crossing Rebublic Club,Crossings Republik, Ghaziabad, Uttar Pradesh 201016 | 10115 | 10115 | 10115 | 10115 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | STTSPL043 | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6275 | 77.4371 | 10115 | 2021-05-20 | 2021-06-30 | 2021-06-30 | [16 empty] | 2022-03-14 | ST202203071678 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051662/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Ashok Vihar | Mr. Ashok ji,H.No. C-98,DDA Flats,Block C,Ashok Vihar Phase IV,Nimri Colony,New Delhi-110052 | 17753 | 17753 | 17753 | 17753 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NI_17753_DEL | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6836 | 77.172 | 17753 | 2021-04-02 | 2021-06-22 | 2021-06-22 | [16 empty] | 2021-06-26 | ST202106362826 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034605/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Shivaji Enclave | Property No- B-112-A, Khasra No- 1930, Janta Colony, Shivaji Vihar, New Delhi-110027 | 19847 | 19847 | 19847 | 19847 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.657 | 77.1174 | 19847 | 2019-10-17 | 2020-08-30 | 2020-09-04 | [16 empty] | 2020-09-19 | ST202009081771 | S20200004801 |  |  | 2020-09-29 | P/FVC/DEL/1007060/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SEC56, BALLABHGARH | Mr Satish Kumar S/o Sh Samer Singh,House Number- 103/56,Sector-56,Police Station Sector 58,Post Office Sector 56A, Ballabgarh, Faridabad, Haryana-121004 | 20314 | 20314 | 20314 | 20314 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-FDBD-ENB-3771 | New | Sharing | RTT | 9 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.3295 | 77.2892 | SR-DL000073 | 2021-01-12 | 2021-06-17 | 2021-07-29 | [16 empty] | 2021-07-29 | ST202107401847 | S20210013962 |  |  | 2021-08-04 | P/FVC/DEL/1037080/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Punjabi Mohalla(Relocation of 17450) | House No. – 880 Punjabi Mohalla Ballabgarh, Faridabad 121004 | 18053 | 18053 | 18053 | 18053 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_18053_DEL | Relocation | New_Built | RTM | 15 | 7 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.3336 | 77.3264 | 18053 | 2019-01-15 | 2019-01-25 | 2019-01-26 | [16 empty] | 2019-06-11 | 2019970252 | 2019970252 |  |  | 2019-07-15 | P/FVC/DEL/5713746/2019 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Shastri Nagar B Block | MANJEET KAUR,Hno. B-1878,Shastri Nagar,DELHI-110052 | 19933 | 19933 | 19933 | 19933 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/9062 | New | New_Built | RTP | 6 | 15 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6767 | 77.1789 | T21DL03349 | 2021-11-19 | - | 2022-02-08 | [16 empty] | 2022-02-26 | ST202202055937 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050990/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | lock B, Gamma 1, Greater Noida | Noida Authority GBM Location,Near 8th Cross St,in Front of Electricity Pole No.91,Jagat Farm, Block E,Chandila, Gamma 1,Greater Noida, Uttar Pradesh 201308 | 19684 | 19684 | 19684 | 19684 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1884393 | New | New_Built | GBM | 30 | - |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.4842 | 77.5008 | R/NN-569834 | 2021-04-03 | 2021-04-16 | 2021-04-26 | [16 empty] | 2021-05-01 | ST202105213665 | S20210008457 |  |  | 2021-06-12 | P/FVC/DEL/1031142/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | sec-10 raj nagar | - | 19652 | 19652 | 19652 | 19652 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Front Infratel | FIT_026 | New | New_Built | RTP | 9 | 10.3 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6846 | 77.4398 | 19652 | 2021-08-27 | - | 2022-02-08 | [16 empty] | 2022-02-16 | ST202202047103 | S20220002142 |  |  | 2022-02-24 | P/FVC/DEL/1050152/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Shatri Nagar,Lalita Block | Hno. D-2763,Shatri Nagar,Lalita Block,New Delhi-110052 | 20051 | 20051 | 20051 | 20051 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | DL/20051/DL/NT | New | Sharing | RTP | 6 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.6758 | 77.1751 | 12709963 | 2019-10-10 | 2019-10-18 | 2019-10-24 | [16 empty] | 2019-12-06 | 2019422078 | 2019422078 |  |  | 2020-03-09 | P/FVC/DEL/5987187/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | PRI | RFAI_Pending
Del | FY20_21 | Q4 | Tulsi Nagar(Relocation of 16852) | Hno. 313/82,Khasra No. 490, Gali no. 4, Tulsi Nagar, Inderlok, Delhi 110035 | 20677 | 20677 | 20677 | 20677 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20677_DEL | Relocation | New_Built | RTT | 15 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6707 | 77.1651 | 20677 | 2020-10-29 | 2020-11-04 | 2020-11-06 | [16 empty] | 2020-11-07 | ST202011139515 | S20200007786 |  |  | 2020-12-22 | P/FVC/DEL/1012901/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | J BLOCK,SARITA VIHAR | Government Land,South Delhi Municipal Corporation(SDMC)Park,GBM Location,Durga Park,Pocket B,Sarita Vihar,Near by ResidentWelfare Association Pocket B, Opposite side - Children Park(GYM Park),Police Station - Sarita Vihar,Post Office - Sarita Vihar Pocket H,New delhi-110076 | 20378 | 20378 | 20378 | 20378 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1884462 | New | New_Built | GBM | 30 | 0 |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.5317 | 77.2911 | R/NN-569838 | 2021-04-03 | 2021-07-27 | 2021-08-02 | [16 empty] | 2021-08-03 | ST202108406436 | S20210014164 |  |  | 2021-08-12 | P/FVC/DEL/1037555/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Uniworld garden | Government Land,Municipal Corporation Gurugram(MCG)Park,GBM Location,Opposite Plot No. 945P,Sadar Police Station Sec 38,South city 2 post office,Sector-47, Gurgaon-122003 | 23680 | 23680 | 23680 | 23680 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3000657 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4281 | 77.0415 | R/NN-619881 | 2021-06-02 | 2021-06-23 | 2021-06-29 | [16 empty] | 2021-07-05 | ST202107374642 | S20210012735 |  |  | 2021-07-15 | P/FVC/DEL/1035188/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Mahavir Enclave(Relocation of 9400) | - | 21388 | 21388 | 21388 | 21388 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3022942 | Relocation | New_Built | RTP | 9 | 13.7 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6025 | 77.0746 | R/NN-627596 | 2021-08-18 | 2021-09-03 | 2021-09-16 | [16 empty] | 2021-09-16 | ST202109522339 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041985/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SECTOR 18 GURGAON | Government Land,Municipal Corporation Gurugram(MCG),Opposite Plot No. 70, Beside Plot No-54A,Police Station Sector 17/18,Post office Sec 17A,Sector-18, Gurgaon-122022 | 19969 | 19969 | 19969 | 19969 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1901893 | New | New_Built | GBM | 30 | - |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.488 | 77.0652 | R/NN-570079 | 2021-04-07 | 2021-06-23 | 2021-06-29 | [16 empty] | 2021-07-02 | ST202107370640 | S20210012660 |  |  | 2021-07-15 | P/FVC/DEL/1035090/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SUPERTECH-3 | Mrs. Puja (Estate Manager),Building Name-CGD-1,Plot no. GH - 01,Supertech Capetown,Sector-74 ,Noida,Uttar Pradesh-201306 | 25199 | 25199 | 25199 | 25199 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Fine bunch | FI_25199_DEL | New | New_Built | RTP | 6 | 76 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5763 | 77.3882 | 25199 | 2020-08-07 | 2021-02-26 | 2021-03-14 | [16 empty] | 2021-03-13 | ST202103089553 | S20210004658 |  |  | 2021-07-08 | P/FVC/DEL/1033709/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | INDRAPRASTHA,GHAZIABAD | Mrs.Poonam Mavi W/o Mr. Prakash Veer Mavi,Plot Number -- D 409,Indarprasth Colony,Near By Pani Ki Tanki,Police Station - Tila Mod,Post Office - Loni,Loni,Ghaziabad,Uttar Pradesh- 201102. | 21888 | 21888 | 21888 | 21888 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3085678 | New | New_Built | RTP | 9 | 15.5 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7314 | 77.3305 | R/NN-636530 | 2021-09-03 | 2021-11-29 | 2022-01-18 | [16 empty] | 2022-02-21 | ST202202050953 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050308/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI | RFAI_Pending
Del | FY20_21 | Q4 | Noor Nagar Jamia(Relocation of 1507) | South Delhi Municipal Corporation(SDMC),MBTS Location,In Front of Hno.259A,Near of Noor Nagar Jamia Extension,Okhla, New Delhi, Delhi 110025 | 16522 | 16522 | 16522 | 16522 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1382603 | Relocation | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5585 | 77.287 | R/NN-418971 | 2020-03-31 | 2021-04-15 | 2021-04-26 | [16 empty] | 2021-04-27 | ST202104194461 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028802/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-9, Dwarka | Government Land,Delhi Develoment Athourity(DDA) Park,GBM Location Infront of Sarve Sanjhi Apartments,Plot number - 8, Sector - 9,Dwarka South Police Station,Post Office Harijan Basti,sector 7,Dwarka,Dwarka,New Delhi - 110077, | 17387 | 17387 | 17387 | 17387 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL040 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.581 | 77.0678 | 17387 | 2021-05-12 | 2021-06-29 | 2021-09-09 | [16 empty] | 2021-09-16 | ST202109522333 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041983/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Makhanpur Colony | Ms.Pooja Kumari W/O Mr.Mukul Kumar Singh,Khasra Number - 15,Bharat Nagar,Khora,Police Station - Sector-62 Noida,Post Office - Khora,Noida,Uttar Pradesh-201309 | 21310 | 21310 | 21310 | 21310 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | TVIL | NA | New | New_Built | RTP | 6 | 17 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6265 | 77.3436 | 21310 | 2021-10-25 | 2021-11-30 | 2022-01-07 | [16 empty] | 2022-01-20 | ST202201014386 | S20220000841 |  |  | 2022-01-24 | P/FVC/DEL/1048485/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | KHANPUR VILLAGE | Ostello P.G,H.No-A-107,Khanpur Village, Beech ki chopaad, New Delhi, Pin-110062 | 19576 | 19576 | 19576 | 19576 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19576_DEL | New | New_Built | RTP | 6 | 21 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5133 | 77.2313 | 19576 | 2019-11-25 | 2020-08-18 | 2020-08-19 | [16 empty] | 2020-01-30 | 2020349090 | 2020349090 |  |  | 2020-04-28 | P/FVC/DEL/6011071/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Dwarka Sec 22(Relocation of 5656) | Jai dada dev transport sector 22 dwarka near by H.P petrol pump delhi-110045 | 11136 | 11136 | 11136 | 11136 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1382604 | Relocation | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5558 | 77.0544 | R/NN-418975 | 2020-03-31 | 2020-12-29 | 2021-02-16 | [16 empty] | 2021-01-11 | ST202101007922 | S20210000477 |  |  | 2021-01-18 | P/FVC/DEL/1016512/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | EMCD_76_Vivek Vihar(Relocation of 13146) | Mrs. Beenu Mehra W/O Biharilal Mehra,House Number - 118-E,Block E,Jhilmil Colony, Shahdara,Police Station - Vivek Vihar,Post Office - Jhilmil,Delhi-110095 | 20906 | 20906 | 20906 | 20906 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1388170 | Relocation | New_Built | RTP | 9 | 13 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6674 | 77.3064 | R/NN-464246 | 2020-07-22 | 2021-08-20 | 2021-09-06 | [16 empty] | 2021-09-27 | ST202109535769 | S20210030452 |  |  | 2021-09-30 | P/FVC/DEL/1042622/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Amarpali Zodiac 2(Relocation of 23976) | Noida Authority,GBM Location near Amarpali Zodiac Temple, Amarpali zodiac market, infront of the millennium school & Gaur Grandeur Block-4,Sector 119, Noida, Uttar Pradesh 201307 | 25049 | 25049 | 25049 | 25049 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL42 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.586 | 77.3995 | 25049 | 2021-02-19 | 2021-03-16 | 2021-03-19 | [16 empty] | 2021-03-18 | ST202103094629 | S20210004928 |  |  | 2021-08-04 | P/FVC/DEL/1036717/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Raj Nagar | Mr Birender Singh S/o Shri Dukhti Singh,House number - RZF-766/20C,Street number - 7 ,Khasra number-44/1/2/2,Village Palam,Raj Nagar-II,Palam Colony,New Delhi-110045 | 21145 | 21145 | 21145 | 21145 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1765549 | New | New_Built | RTP | 9 | 14 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5741 | 77.081 | R/NN-566741 | 2021-02-24 | 2021-04-21 | 2021-04-29 | [16 empty] | 2021-05-01 | ST202105213662 | S20210008457 |  |  | 2021-06-12 | P/FVC/DEL/1031145/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Shardanand Market(Relocation of 2430) | House Number - 578,ShardaNand Market,Police Station - Kamla Market,Post Office - Prahllad Market ,Delhi-110006 | 21236 | 21236 | 21236 | 21236 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL054 | Relocation | New_Built | RTP | 12 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6534 | 77.2193 | NA | 2021-11-19 | 2021-12-08 | 2022-02-08 | [16 empty] | 2022-03-14 | ST202203071695 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051679/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Pankaj Community Center Kondli(Relocation of 5701) | EDMC PROPERTY BESIDES HOUSE NO-42-C,PKT B-8,MAYUR VIHAR PHASE-III,delhi 110096 | 16008 | 16008 | 16008 | 16008 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL008 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6153 | 77.338 | 16008 | 2020-05-02 | 2020-06-28 | 2021-01-25 | [16 empty] | 2021-01-19 | ST202101017281 | S20210001143 |  |  | 2021-02-25 | P/FVC/DEL/1017924/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Green Velley Apartment | Government Land,Municipal Corporation of Delhi (MCD) Park,GBM Location,Infront of Green Valley Apartments Plot number - 18,and Near Jagaran Apartment Plot number 17,Sector 22 Dwarka,Police Station - Dwarka Sector 23,Post Office - Dwarka Sector 23,New Delhi - 110077 | 20490 | 20490 | 20490 | 20490 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL044 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5577 | 77.0574 | 20490 | 2021-08-27 | 2021-08-25 | 2021-08-31 | [16 empty] | 2021-09-09 | ST202109513789 | S20210029381 |  |  | 2021-09-19 | P/FVC/DEL/1040657/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Push Vihar (Relocation of 8072) | - | 17012 | 17012 | 17012 | 17012 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL157 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5242 | 77.2276 | NA | 2021-12-06 | 2022-03-01 | 2022-03-01 | [16 empty] | 2022-03-14 | ST202203071689 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051673/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Gulmohar Garden | Mr. Rakesh Jha( Manager),Gulmohar Garden,Tower - 13(D1),Phase 2,Block 29,Raj Nagar Extension,Police Station - Sihani Gate,Post Office - Raj Nagar Extension,Noida,Uttar Pradesh-201017 | 21787 | 21787 | 21787 | 21787 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3017349 | New | New_Built | RTP | 9 | 49 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7021 | 77.4357 | R/NN-627166 | 2021-08-10 | 2021-11-10 | 2021-11-23 | [16 empty] | 2021-12-07 | ST202112604808 | S20210034198 |  |  | 2021-12-15 | P/FVC/DEL/1046212/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Unitech Horizon | Gbm Near Unitech Horizon Appartment, Green BeltSec-46, Noida-201303 | 20518 | 20518 | 20518 | 20518 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1380834 | New | New_Built | GBM | 30 | - |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.4777 | 77.5478 | R/NN-404241 | 2020-03-09 | 2020-03-12 | 2020-05-15 | [16 empty] | 2020-10-09 | ST202010102095 | S20200005874 |  |  | 2020-10-20 | P/FVC/DEL/1009234/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Amarpark(Relocation of 2387) | Mr. Roshan Khichi , House number - B1, Amar Park Zakhira,Old Rohtak Road , Near Zakhira Fly Over,Post Office - Rampura,Police Station - Inder lok,Delhi - 110035 | 21708 | 21708 | 21708 | 21708 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-9415 | Relocation | Sharing | RTT | 9 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6706 | 77.1612 | SR-DL000141 | 2021-07-18 | 2021-10-24 | 2021-10-27 | [16 empty] | 2021-11-10 | ST202111586345 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045115/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Mohalla Charbisa, Village-Dasna | Mr.Navi Mohammad S/o Mr. Shamashad Ali ,Khasra Number 2143, Yasin Garhi, Near By Masjid, Dasna, Police Station Massorie, Post Office Dasna , Ghaziabad,Uttar Pradesh- 201015. | 21292 | 21292 | 21292 | 21292 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3092277 | New | New_Built | - | - | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6809 | 77.519 | R/NN-637354 | 2021-11-01 | 2021-11-23 | 2022-01-24 | [16 empty] | 2021-12-15 | ST202112617432 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046927/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Udyog Vihar Sec 82 Noida | Green Belt,RWA Udyog Vihar Sec 82,Udyog Vihar,Block D4,Swarnim Vihar,Sec 82,Police Station - Phase 2,Post Office - Maharishi Nagar,Noida,Uttar Pradesh - 201304. | 19654 | 19654 | 19654 | 19654 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | TVIL | NA | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.53 | 77.3883 | 19654 | 2021-05-11 | 2021-11-30 | 2022-01-07 | [16 empty] | 2022-01-31 | ST202202026002 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049208/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Inder Enclave | Smt. Savitri Mandal W/O Sh. Umesh Prasad, House number - B-275/A , Khasra number - 18/9, Village Mukbarakpur Dabas, B-Block, Vidhyapati Nagar, Inder Enclave , Phase - II, Post Office - Sultanpuri , Police Station - Prem Nagar, Delhi - 110081 | 21212 | 21212 | 21212 | 21212 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | TVIL | NA | New | New_Built | RTP | 9 | 11 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7105 | 77.0453 | 21212 | 2021-08-27 | 2021-09-15 | 2021-10-16 | [16 empty] | 2021-10-16 | ST202110561374 | S20210031698 |  |  | 2021-10-28 | P/FVC/DEL/1044033/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Summer Palms,Sector 86, Faridabad | Mr. Sanjiv(Estate Manager),Tower Number - A1,Summer Palms Block - C,Sector 86,Post Office - Sector 86,Police Station - Amolik Chowk,Faridabad,Haryana 121002 | 19621 | 19621 | 19621 | 19621 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Olympians | R/21/F | New | New_Built | RTP | 6 | 70 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.4095 | 77.346 | NA | 2021-12-06 | 2022-03-03 | 2022-03-03 | [16 empty] | 2022-03-03 | ST202203061180 | S20220002821 |  |  | 2022-03-14 | P/FVC/DEL/1051368/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sector 2, Dwarka | - | 21827 | 21827 | 21827 | 21827 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016746 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5967 | 77.0725 | R/NN-627095 | 2021-08-09 | 2022-01-13 | 2022-02-02 | [16 empty] | 2022-03-14 | ST202203071488 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051655/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | DDA_sec-18 | Government Land,GBM Location,Property of Municipal Corporation of Delhi,Infront of Flate Number 31 to 48, Block - A,Pocket - 6,Rohini Sector 18,Police Station - Rohini Sector 18,Post Office - Rohini Sector 18, New Delhi - 110085. | 13137 | 13137 | 13137 | 13137 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3105044 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ | Other than Indus & ATC | YES | >18HRS | NO | 28.7381 | 77.1329 | R/NN-638883 | 2021-11-10 | 2021-12-23 | 2022-01-24 | [16 empty] | 2022-01-31 | ST202202025979 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049202/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-12 Faridabad(Relocation of 68) | Government Land,MCF Green Belt,GBM Location,Infront of Airtel Office, Near SRS Cinema, Sector-12, Post Office - Sec-12,Police Sattion - 15A,Faridabad,Haryana 121007 | 21896 | 21896 | 21896 | 21896 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3103104 | Relocation | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.3869 | 77.3177 | R/NN-639004 | 2021-09-06 | 2021-12-17 | 2022-01-18 | [16 empty] | 2022-01-14 | ST202201010597 | S20220000629 |  |  | 2022-01-20 | P/FVC/DEL/1048373/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Noida Sec-62 | Government Land,Green Belt,GBM Location,Near-PMO Apartment,Plot Number-C-58/20,C-Block,Sector-62 Noida,Police Station - Sector-62 Noida,Post Office - Sector-62 Noida,Noida,Uttar Pradesh-201307 | 25123 | 25123 | 25123 | 25123 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | TVIL | NA | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6116 | 77.3688 | 25123 | 2021-02-01 | 2021-12-17 | 2022-01-18 | [16 empty] | 2022-02-16 | ST202202047095 | S20220002142 |  |  | 2022-02-24 | P/FVC/DEL/1050144/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | H-Block, Rajiv Garden | - | 21885 | 21885 | 21885 | 21885 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032768 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7351 | 77.2986 | R/NN-628391 | 2021-09-03 | 2021-09-13 | 2021-09-17 | [16 empty] | 2021-09-23 | ST202109528782 | S20210030186 |  |  | 2021-09-27 | P/FVC/DEL/1042239/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Jalvayu Towers(Relocation of 27386) | Sector 56 Road, Opposite, Jalvayu Towers, Sector 56, Gurugram, Haryana 122011 | 13703 | 13703 | 13703 | 13703 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | FCM | FC_13703_DEL | Relocation | New_Built | RTT | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4312 | 77.0953 | 13703 | 2020-08-25 | 2020-08-28 | 2020-08-28 | [16 empty] | 2020-09-03 | ST202009059156 | S20200003909 |  |  | 2020-09-08 | P/FVC/DEL/1005235/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SEC-120, NOIDA | - | 19678 | 19678 | 19678 | 19678 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVIL | RJUPZNO0755 | New | New_Built | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5798 | 77.3985 | 19678 | 2020-05-26 | 2021-12-02 | 2021-12-13 | [16 empty] | 2021-12-15 | ST202112617416 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046922/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SECTOR 55/56, NOIDA | In Front Of B-26,B-Block,Sector-56 Noida,Uttar Pradesh-201307 | 23414 | 23414 | 23414 | 23414 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | TVIL | ATUPZNO0094 | New | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6026 | 77.3432 | 23414 | 2020-05-26 | 2020-06-20 | 2021-01-25 | [16 empty] | 2021-01-22 | ST202101020422 | S20210001323 |  |  | 2021-02-25 | P/FVC/DEL/1017945/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Shahi Export Private Limited | C-35/36, Block C, Sector -58, Noida uttar pradesh-201301 | 27680 | 27680 | 27680 | 27680 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27680_DEL | New | New_Built | IBS | IBS | 16 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.6088 | 77.3611 | 27680 | 2021-02-10 | 2021-02-24 | 2021-02-24 | [41 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | Indus |  | M1 | 719 | [22 empty] | RFAI | RFAI_Pending
Del | FY20_21 | Q4 | VILLAGE RITHALA, VIJAY VIHAR | House No. F-61,Gali No. 7,Near kali mandir near shankar hardware,Vijay vihar Phase 2,New Delhi,Pin-110085 | 20327 | 20327 | 20327 | 20327 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20327_DEL | New | New_Built | RTM | 12 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7089 | 77.097 | 20327 | 2019-10-09 | 2020-02-21 | 2020-02-21 | [16 empty] | 2020-11-11 | ST202011143644 | S20200008077 |  |  | 2020-12-25 | P/FVC/DEL/1013786/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec 9, Vaishali | Mr.Subhash Singh, Khasra Number 308,313&318, (Building T-5)Civitech Florencia Park Sapphire,Sector-9,Vaishali,Police Station-Ramprastha Vaishali, Post Office-Kaushambi,Ghaziabad,Uttar Pradesh-201010 | 10934 | 10934 | 10934 | 10934 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | NA | New | New_Built | RTP | 6 | 49 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6526 | 77.3488 | 10934 | 2021-08-27 | 2022-01-27 | 2022-01-18 | [16 empty] | 2022-01-31 | ST202202026027 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049215/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Kalyan Vihar Rana Pratap Bagh | Government Land,GBM Location,Green Belt of Municipal Corporation of Delhi,Kalyan Vihar, Rana Pratap Bagh,Infront of House Number - C-33,Chief Commissioner Colony, Main GT Karnal Road,Post Office - Model Town,Police Station - Model Town,Delhi - 110009 | 18026 | 18026 | 18026 | 18026 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3107705 | New | New_Built | MBTS | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ | Other than Indus & ATC | YES | >18HRS | NO | 28.69 | 77.1927 | R/NN-639622 | 2021-08-27 | 2022-01-02 | 2022-01-27 | [16 empty] | 2022-01-31 | ST202202025995 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049206/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Mahagun Mansion | Plot Number - 3,Aditya Gold Crest,Indirapuram,Police Station - Indirapuram,Post Office - Shipra Sun City,Ghaziabad,Uttar Pradesh-201014 | 20489 | 20489 | 20489 | 20489 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3121550 | New | New_Built | RTP | 9 | 24 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6361 | 77.3606 | R/NN-642848 | 2021-11-18 | 2021-12-14 | 2022-01-24 | [16 empty] | 2022-01-31 | ST202202025988 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049204/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Nehru Nagar(Relocation of 7113) | Government Land,SDMC Park,MBTS Location,Block-2 Park,Opposite Sanatan Dharm Mandir,Nearby Shop No.3, Nehru Nagar Main Market,Nehru Nagar, Lajpat Nagar,Post Office - Nehru Nagar,Police Station - Shrinivaspuri,New Delhi 110065 | 21606 | 21606 | 21606 | 21606 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3048256 | Relocation | New_Built | MBTS | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5704 | 77.2538 | R/NN-565707 | 2021-02-15 | 2021-10-06 | 2021-10-27 | [16 empty] | 2021-11-10 | ST202111586363 | S20210033073 |  |  | 2021-11-20 | P/FVC/DEL/1045112/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Ajronda, Faridabad | Hno. 247A,Ajronda,Sector 15A,Faridabad,Haryana 121007 | 20472 | 20472 | 20472 | 20472 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20472_DEL | New | New_Built | RTP | 9 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.3962 | 77.3171 | 20472 | 2019-11-14 | 2020-01-16 | 2020-01-16 | [16 empty] | 2020-01-30 | 2020349055 | 2020349055 |  |  | 2020-04-28 | P/FVC/DEL/6011036/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | EMCD_51_Khichripur Colony | Mrs.Nareshwari w/o Mr.Karan singh,Property Bearing No. 8/301,Resettlement Colony,Khichripur Colony,Police Station kalyanpuri,Post office khichripur,Delhi 110091 | 20887 | 20887 | 20887 | 20887 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001801 | New | New_Built | RTP | 9 | 16 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6255 | 77.3166 | R/NN-621222 | 2021-06-30 | 2021-07-12 | 2021-07-14 | [16 empty] | 2021-07-19 | ST202107388709 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036223/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | EMCD_68_Surya Niketan(Relocation of 13110) | Park Of EDMC,Near h.no-204,Block B,Surya niketan,Anand Vihar,Delhi-110092 | 20898 | 20898 | 20898 | 20898 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001984 | Relocation | New_Built | GBM | 12 | 14 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6562 | 77.3074 | R/NN-625357 | 2021-07-05 | 2021-07-14 | 2021-07-25 | [16 empty] | 2020-09-29 | ST202009092445 | S20200005308 |  |  | 2020-10-06 | P/FVC/DEL/1007757/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Shahberi, Greater Noida | Plot No 50 ,Taj Palce , Main Sain Garden, Noida Extension ShahBeri,G.B Nagar, 201009 | 19680 | 19680 | 19680 | 19680 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | STTSPL022 | New | New_Built | RTP | 6 | 19 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6203 | 77.4385 | 19680 | 2021-08-27 | - | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050906 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050290/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Nagarro | Plot 17 Opposite Passport Office , Maruti Industrial Area , Gurgaon | 27368 | 27368 | 27368 | 27368 |  |  |  | G1800_L2100_L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_27368_DEL | New | New_Built | IBS | IBS | 20 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.4907 | 77.0762 | 27368 | 2019-11-24 | 2019-11-29 | 2019-12-06 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI | RFAI_Pending
Del | FY20_21 | Q4 | SDMC_Sector-19 Phase-I Dwarka | Open Terrace No 1, (Above 2nd Floor of Unit No 243 to 250), Vardhaman Crown Plaza, LSC, Sector 19, Dwarka, New Delhi 110077 | 20381 | 20381 | 20381 | 20381 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20381_DEL | New | New_Built | RTP | 15 | 11 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5753 | 77.0508 | 20381 | 2021-01-25 | 2021-02-02 | 2021-02-09 | [16 empty] | 2021-02-10 | ST202102048371 | S20210002677 |  |  | 2021-03-05 | P/FVC/DEL/1019254/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | EMCD_37_Park Q-Pocket,Dilshad Garden | Government Land, Dhalao Number 25 B,Near House Number. Q 211,& Opposite Param Dham Temple,Q Pocket,New Seemapuri,Police Station - New Seemapuri Post Office - New Seemapuri,Delhi 110093 | 20873 | 20873 | 20873 | 20873 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3065534 | New | New_Built | RTT | 18 | 4 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6856 | 77.3194 | R/NN-634421 | 2021-10-29 | 2021-12-18 | 2022-01-18 | [16 empty] | 2022-02-21 | ST202202050946 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050306/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Beta I Gr. Noida | Noida Authority Park(Green Belt),GBM Location,Opp Plot No. 4,IEC College Of Engineering & Technlogy,Surajpur kasana Rd,Knowledge Park 1,Greater Noida-201310 | 21284 | 21284 | 21284 | 21284 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1550066 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4761 | 77.5018 | R/NN-560203 | 2020-12-04 | 2021-04-16 | 2021-04-22 | [16 empty] | 2021-04-27 | ST202104194460 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028806/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Udyog nagar,Mangolpuri(Relocation of 23071) | Mr.Pawan, SS Industrial Corporation,Plot Number - G-10,Udyag Nagar,Police Station - Peeragarhi,Post Office - Jwalapuri,New Delhi-110041 | 20702 | 20702 | 20702 | 20702 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-DLHI-204 | Relocation | New_Built | RTP | 6 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6824 | 77.0933 | NA | 2021-11-19 | 2022-01-27 | 2022-01-27 | [16 empty] | 2022-02-16 | ST202202047096 | S20220002142 |  |  | 2022-02-24 | P/FVC/DEL/1050145/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | 122_DDA_SEC-13 ROHINI | Government Land,North Delhi Municipal Corporation (MCD) Park,MBTS Location,Infront of Venkateshwar Global School and Near Shanti Appartment ,Plot number 7/1, Sector 13, Rohini, Police Station Prashant Vihar , Sector 9 Rohini, Post Office Rohini Sector 13, Delhi - 110085, | 13054 | 13054 | 13054 | 13054 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001890 | New | New_Built | Cow | 24 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.719 | 77.1302 | R/NN-621219 | 2021-06-30 | 2021-07-12 | 2021-07-15 | [16 empty] | 2021-07-19 | ST202107388726 | S20210013356 |  |  | 2021-07-22 | P/FVC/DEL/1036220/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | viilage -Nilothi, Bharat Vihar ,Nilothi(Relocation of 11440) | Mr. Lakhvinder Singh S/O Santokh Singh, House Numar- A-3, Nihal Vihar, Police Station - Nihal Vihar, Post Office - Nangloi, Delhi-110087 | 21676 | 21676 | 21676 | 21676 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | Relocation | Sharing | GBT | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6529 | 77.0632 | NA | 2021-12-06 | 2021-12-07 | 2021-12-07 | [16 empty] | 2021-12-15 | ST202112617447 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046934/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Near Indira Gandhi International Airport | Government Land of (GMR ),MBTS Location,Near Electric Light Pole Number - HM/12, Infront of Dats Complex IGI Airports Authorty of India, Post Office - Gate 8 Departure T3, Police Station - Indira Gandhi International Airport New Delhi-110037 | 21754 | 21754 | 21754 | 21754 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3098559 | New | New_Built | MBTS | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5548 | 77.0919 | R/NN-638028 | 2021-12-06 | 2021-12-16 | 2022-02-02 | [16 empty] | 2022-02-26 | ST202202055990 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050998/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SDMC_Sainik Farms | Mr. Ashok Kumar S/o Mr. Balbir Singh,House Number - E-22 G/FLOOR LANE NO.W-4, Khasra Number - 2289/469 479, 480,Western Avenue,Sainik Farms,Khirki,Post Office - Khanpur,Police Station - Neb Sarai,New Delhi 110062 | 13155 | 13155 | 13155 | 13155 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NA | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5103 | 77.2181 | 13155 | 2022-02-18 | 2022-02-28 | 2022-03-10 | [16 empty] | 2022-03-14 | ST202203071696 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051680/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Bhuya Chowk, Mehrauli | Mr.Praveen Kumar Sharma S/o Mr NA,H.No. 277,Ward No.2 ,Roopam wala Kunwa,Mehrauli New Delhi, Delhi 110030 | 21245 | 21245 | 21245 | 21245 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Front Infratel | FI_21245_DEL | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5218 | 77.1763 | 21245 | 2021-05-13 | 2021-06-02 | 2021-06-15 | [16 empty] | 2021-06-18 | ST202106351960 | S20210011842 |  |  | 2021-07-22 | P/FVC/DEL/1036139/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | KALYAN VIHAR(Relocation of 25349) | Kalyan Vihar ,A-29 New Gupta Colony ,Model Town,North West , Delhi-110009 | 17453 | 17453 | 17453 | 17453 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1381373 | Relocation | New_Built | RTP | 9 | 12 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.692 | 77.1966 | R/NN-403545 | 2020-03-06 | 2020-06-14 | 2020-06-19 | [16 empty] | 2020-06-23 | ST202007018556 | S20200001310 |  |  | 2020-07-10 | P/FVC/DEL/1001734/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Sector 13, Rohini 3 | Government Land,North Delhi Municipal Corporation(NDMC)Park,GBM Location,Sector 13,Rohini 3,Opposite Backgate of Canara Appartments and Near Tree Number - 164,and Near Flat Number- 232,Sector-13,Police Station - Prashant Vihar,Post Office - Rohini Rohini,Delhi-110085 | 21818 | 21818 | 21818 | 21818 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016704 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7223 | 77.1293 | R/NN-627073 | 2021-08-09 | 2021-09-08 | 2021-09-24 | [16 empty] | 2021-09-29 | ST202109540886 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042805/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Rohini Sec 05 | Mr. Ishwar Singh,Plot Number - C-6/8, Sector - 5 Rohini,Post Office - Sector 7 Rohini,Police Station - Budh Vihar,Delhi - 110085 | 21813 | 21813 | 21813 | 21813 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3016685 | New | New_Built | RTP | 6 | 16 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7177 | 77.1065 | R/NN-627066 | 2021-08-09 | 2022-01-14 | 2022-01-27 | [16 empty] | 2022-01-31 | ST202202025999 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049207/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | VikasPuri(Relocation of 4987) | Flat no-42,R.P.S. Janta Flats,Block E,Vikaspuri,New Delhi-110018 | 13145 | 13145 | 13145 | 13145 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_13145_DEL | Relocation | New_Built | RTT | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6397 | 77.0689 | 13145 | 2020-11-21 | 2021-01-16 | 2021-03-19 | [16 empty] | 2022-02-16 | ST202202047105 | S20220002142 |  |  | 2022-02-24 | P/FVC/DEL/1050154/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Indirapuram_6(Relocation of 1373) | Amrapali Village Resident Welfare Association AH- 801 , Amrapali Village Gyan Khand-2 , Indirapuram , Ghaziabad UP – Pin Code – 201014 | 16251 | 16251 | 16251 | 16251 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | ATC | 452381 | Relocation | Sharing | RTP | 6 | 60 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.6346 | 77.3575 | 13734922 | 2021-08-19 | 2021-10-20 | 2021-10-22 | [16 empty] | 2021-10-27 | ST202110572265 | S20210032268 |  |  | 2021-11-19 | P/FVC/DEL/1044881/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Shipra Suncity | Mr. Monit,GBM/MBTS Location,Plot No-10,Vaibhav Khand,Near of Gate No.5,Shipra Suncity, Indirapuram,Police Station Vasundhara,Post Office Shipra Sun City,Ghaziabad, Uttar Pradesh 201014 | 9849 | 9849 | 9849 | 9849 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | NA | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6355 | 77.3726 | 9849 | 2021-04-17 | 2021-06-30 | 2021-07-08 | [16 empty] | 2021-07-09 | ST202107379591 | S20210012929 |  |  | 2021-07-16 | P/FVC/DEL/1035539/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | SAFDARJUNG HOSPITAL(Relocation of 10945) | Government Land,South Delhi Municipal Corporation(SDMC),GBM Location,Opposite Electric Pole Number 9,Near Jai Prakash Narayan Apex Trauma Centre,Road Side Area Adjacent to Safdarjung Hospital, New Delhi-110023 | 21752 | 21752 | 21752 | 21752 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3009198 | Relocation | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.567 | 77.2023 | R/NN-626358 | 2021-07-27 | 2021-09-10 | 2021-11-11 | [16 empty] | 2021-11-12 | ST202111588385 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045815/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Sushant Lok I | Varun Alambayan, House Number-C-1118 Sushant Lok Phase-1 Sector-43, Police station-Shushant lok , Post office- Sector 27 Gurugram,122002 | 13697 | 13697 | 13697 | 13697 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3045078 | New | New_Built | RTP | 9 | 13 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4533 | 77.0786 | R/NN-630148 | 2021-09-22 | 2022-01-13 | 2022-02-02 | [16 empty] | 2022-02-26 | ST202202055991 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050999/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sector-40, Noida | Government Land,Greater Noida Authority,Green Belt (Area),GBM Location,in Front Of Electricity Pole Number - 675,C Block, Sector 40, Noida,Post Office - Sec 40,Police Station - Noida Sec 40, Uttar Pradesh 201303 | 21864 | 21864 | 21864 | 21864 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3042720 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5618 | 77.3566 | R/NN-629816 | 2021-09-21 | 2021-09-23 | 2021-10-01 | [16 empty] | 2021-10-04 | ST202110547619 | S20210030891 |  |  | 2021-10-08 | P/FVC/DEL/1043112/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Amrapali Leisure Valley, Greater Noida | Greater Noida Authority Green Belt,GBM Location,In Front Of Light Pole No.16 And Apex Golf Avenue A-Block,Amrapali Leisure Valley,Greater Noida,Uttar Pradesh-201009 | 21139 | 21139 | 21139 | 21139 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1762749 | New | New_Built | GBM | 30 | - |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.5837 | 77.4332 | R/NN-566644 | 2021-02-24 | 2021-04-16 | 2021-04-22 | [16 empty] | 2021-04-27 | ST202104194457 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028800/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Nanak Pura, Hari Nagar | Mr. Amarjeeet Kaur,House Number - BE -140, Khasra Number - 2007,Village Tihar,Hari Nagar,Post Office - Hari Nagar,Police Station - Hari Nagar,New Delhi-110064, | 21867 | 21867 | 21867 | 21867 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032215 | New | New_Built | RTP | 9 | 14 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6283 | 77.1197 | R/NN-628328 | 2021-09-03 | 2021-10-30 | 2021-11-23 | [16 empty] | 2021-12-07 | ST202112604809 | S20210034198 |  |  | 2021-12-15 | P/FVC/DEL/1046213/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Push Vihar Sec 3 (Relocation of 9241) | - | 16080 | 16080 | 16080 | 16080 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL156 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5186 | 77.221 | NA | 2021-12-06 | 2022-03-01 | 2022-03-01 | [16 empty] | 2022-03-14 | ST202203071688 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051672/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Indigo Hanger | Government Land ,Delhi International Airport Limited (DIAL) is a consortium of the GMR (Grandhi Mallikarjuna Rao) Group, Roof of Indgo Warehouse , Dwarka Link Road , IGI , Post Office - Gate 8 Departure ,T3 Indira Gandhi International Airport, Police Station - Indira Gandhi International Airport, New Delhi, Delhi 110037 | 27729 | 27729 | 27729 | 27729 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | IBS+Macro | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3032232 | New | New_Built | IBS+OD | 6 | 12 |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5569 | 77.1111 | R/NN-628334 IBSR/NN-2550/IBSSO/NN-625 | 2021-09-03 | 2021-08-11 | 2021-09-13 | [16 empty] | 2022-02-26 | ST202202056441 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1051034/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Karampura | Mr. Raj Kumar S/o Mr. Arumugam,House Number - E-278, F/F,Karampura Complex, Post Office - Karampura,Police Station - Moti Nagar,New Delhi 110015 | 18166 | 18166 | 18166 | 18166 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_18166_DEL | New | New_Built | RTM | 12 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6664 | 77.1448 | 18166 | 2019-03-26 | 2021-12-07 | 2021-12-07 | [16 empty] | 2021-12-15 | ST202112617449 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046935/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | B-Block Sector-62,noida | Government Land,Noida Authority,GBM Location Back of Plot Number - B9/15,Rasoolpur Nawada, Industrial Area, Sector 62, Noida,Post Office - Sector 63,Police Station - Setor 62,Noida Uttar Pradesh 201309 | 16787 | 16787 | 16787 | 16787 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL119 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6228 | 77.3722 | 16787 | 2021-08-27 | 2021-10-20 | 2021-11-13 | [16 empty] | 2021-11-15 | ST202111589876 | S20210033274 |  |  | 2021-12-08 | P/FVC/DEL/1045895/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MCF Sec-15 fbd | H.No. 264, Sector 15, Faridabad, Haryana 121007 | 15202 | 15202 | 15202 | 15202 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Olympians | OL_15202_Del | New | New_Built | RTP | 9 | 11 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4001 | 77.321 | 15202 | 2020-07-13 | 2020-08-04 | 2020-08-11 | [16 empty] | 2020-08-26 | ST202008053145 | S20200003535 |  |  | 2020-08-29 | P/FVC/DEL/1004847/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-4 &6 , Vasundhara | Mr.V.K.Singh,Plot Number-GH-06,Vasudha Apartment,Block-12,Sector-6,Vasundhara,Police Station-Indirapuram,Post Office-Vasundhara,Ghaziabad,Uttar Pradesh-201012 | 20253 | 20253 | 20253 | 20253 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Saral communication | I-DL-GZBD-ENB-3865 | New | Sharing | RTP | 9 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6631 | 77.3742 | SR-DL000145 | 2021-07-18 | 2022-01-11 | 2022-02-11 | [16 empty] | 2022-02-21 | ST202202050937 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050302/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Central Ridge Reserve Forest (Relocation of 27392) | - | 20977 | 20977 | 20977 | 20977 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL155 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6048 | 77.1312 | NA | 2021-11-19 | 2022-03-01 | 2022-03-01 | [16 empty] | 2022-03-14 | ST202203071687 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051671/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | EMCD_86_Khichripur | Khichripur Block-1,East Delhi,Delhi-110091 | 20917 | 20917 | 20917 | 20917 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1995483 | New | New_Built | Cow | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6168 | 77.3192 | R/NN-619069 | 2021-05-05 | 2021-05-07 | 2021-06-26 | [16 empty] | 2021-07-02 | ST202107370639 | S20210012660 |  |  | 2021-07-15 | P/FVC/DEL/1035096/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Aditya Urban Homes | Green Belt,GBM Location,Agarwal Associates (Promoters) Limited .In Front Of City Apartment(Near By Mother booth No.15888),Aditya World City,Police Station - Kavi Nagar,Post Office - Kavi Nagar,Ghaziabad,Uttar Pradesh- 201002. | 21906 | 21906 | 21906 | 21906 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3098578 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6456 | 77.4901 | R/NN-638043 | 2021-12-06 | 2021-12-17 | 2022-02-02 | [16 empty] | 2022-02-02 | ST202202027680 | S20220001393 |  |  | 2022-02-15 | P/FVC/DEL/1049404/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | C Block Vasant kunj(Relocation of 27404) | Block-C,Pocket-09,Near-Gate No. 10,Vasant Kunj,New Delhi-110070 | 20806 | 20806 | 20806 | 20806 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1386857 | Relocation | New_Built | Cow | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5403 | 77.1466 | R/NN-456555 | 2020-06-15 | 2020-07-28 | 2020-08-10 | [16 empty] | 2020-09-29 | ST202009092442 | S20200005308 |  |  | 2020-10-06 | P/FVC/DEL/1007754/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Sector 28, FBD(Relocation of 9737) | Mr. Balbir Singh S/O Harkirath Singh,Plot Number - 70,HBH Colony,Sector 27/A,Post Office - Sector 27,Police Station - Sector 27,Faridabad, Haryana 121003 | 21730 | 21730 | 21730 | 21730 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3098587 | Relocation | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4402 | 77.3061 | R/NN-638044 | 2021-12-06 | 2021-12-29 | 2022-02-02 | [16 empty] | 2022-02-02 | ST202202027671 | S20220001393 |  |  | 2022-02-15 | P/FVC/DEL/1049403/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Subash Nagar(Relocation of 9873) | Kuljeet Singh -9999937132,Maninderjot Singh- 9990090089Hno. 6/12, Subhash Nagar, Delhi -27 | 21396 | 21396 | 21396 | 21396 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_21396_DEL | Relocation | New_Built | RTT | 12 | 13.7 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6387 | 77.1137 | 21396 | 2020-12-08 | 2021-10-20 | 2021-11-20 | [16 empty] | 2021-12-13 | ST202112614881 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046025/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | acaranda Estate, Eta Iacaranda Estate, Eta I Greater Noida, | Gbm Near Plot No-C-148 Eta-1 Grather Noida UP-201301 | 16068 | 16068 | 16068 | 16068 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1368368 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4906 | 77.5283 | R/NN-363029 | 2019-08-09 | 2019-09-06 | 2019-09-27 | [16 empty] | 2019-11-28 | 2019402534 | 2019402534 |  |  | 2020-05-30 | P/FVC/DEL/6074074/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SEC-93 , NOIDA | Infront Of Mother's Pride Building,Sampark Marg,Sector-93B Noida,Police Station- Sector-108 Noida,Post Office- Sector-110 Noida,Gautam Buddha Nagar,Uttar Pradesh-201304 | 19591 | 19591 | 19591 | 19591 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL138 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5156 | 77.3873 | 19591 | 2021-10-25 | 2022-03-03 | 2022-03-03 | [16 empty] | 2022-03-14 | ST202203071691 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051675/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Nirala State Tower 4,.G.noida(Relocation of 13017) | - | 21116 | 21116 | 21116 | 21116 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3008980 | Relocation | New_Built | RTT | - | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5867 | 77.4426 | R/NN-626270 | 2021-07-29 | 2021-07-30 | 2021-08-10 | [16 empty] | 2021-08-16 | ST202108428701 | S20210018615 |  |  | 2021-09-02 | P/FVC/DEL/1038906/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | ODSC planned | RFAI_Pending
Del | FY20_21 | Q4 | Airlines Society | Noida Authority (Green Belt)GBM Location,in Front of Electricity Pole No.59134,Near Senior Citizen Apartment,Phi II, Greater Noida, Uttar Pradesh 201310 | 11373 | 11373 | 11373 | 11373 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1900823 | New | New_Built | GBM | 30 | - |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.4521 | 77.5152 | R/NN-569827 | 2021-04-02 | 2021-04-16 | 2021-04-22 | [16 empty] | 2021-04-27 | ST202104194458 | S20210007960 |  |  | 2021-06-10 | P/FVC/DEL/1028805/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Roja village 2, Ghaziabad | Mr. CP Gupta,Plot No.GH-07B,Sector-16B,Noida Extention,French Apartment Tower-G,Greater Noida,Police Station Parthala Khanjarpur,Roza Post office Yakubpur,Uttar Pradesh-201009 | 19478 | 19478 | 19478 | 19478 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | NA | New | New_Built | RTT | 12 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6057 | 77.4501 | 19478 | 2021-05-11 | 2021-06-17 | 2021-06-21 | [16 empty] | 2021-06-26 | ST202106362825 | S20210012285 |  |  | 2021-07-13 | P/FVC/DEL/1034600/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Tihar Village(Relocation of 2841) | H No-WZ-265, Khasra No. 1575,Tihar Village, New Delhi-110018 | 21233 | 21233 | 21233 | 21233 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1503195 | Relocation | New_Built | RTP | 9 | 13.5 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6331 | 77.1069 | R/NN-558660 | 2020-11-11 | 2020-11-30 | 2020-12-10 | [16 empty] | 2020-12-11 | ST202012170927 | S20200009484 |  |  | 2020-12-25 | P/FVC/DEL/1013859/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Delhi University(Relocation of 9765) | In Front of University Of Delhi,International Guest House,7,University Road,Vishwavidyalaya Marg,Delhi-110007 | 16089 | 16089 | 16089 | 16089 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | CO_16089_DEL | Relocation | New_Built | Cow | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6915 | 77.2166 | 16089 | 2020-09-01 | 2020-09-10 | 2020-09-10 | [16 empty] | 2020-09-12 | ST202009066048 | S20200004361 |  |  | 2020-09-19 | P/FVC/DEL/1005953/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Ace Aspire | Mr.Hemant Rathi,Plot Number - GH0-02A, ACE Aspire,Tower D1(Liftroom),Tech Zone 4,Greater Noida West,Police Station - Bisrakh,Post Office - Bisrakh,Greater Noida,Uttar Pradesh-201301. | 21904 | 21904 | 21904 | 21904 |  |  |  | G900_L900_L2100_L1800_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Saral Tower telecommunication Service Private Limited | STTSPL01 | New | New_Built | RTP | 6 | 81 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5883 | 77.4306 | - | 2021-08-31 | 2022-03-03 | 2022-03-03 | [16 empty] | 2022-03-03 | ST202203061270 | S20220002821 |  |  | 2022-03-14 | P/FVC/DEL/1051369/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sector 1,Manesar | Mr. Prashant Tripathi(Estate Manager),Roof of flat number - 201,202,203,204,Tower - B, Express Greens Sector-M1 ,Manesar Delhi Jaipur Expy,Post Office - Manesar,Police Station - Manesar,Gurgaon-122052 | 21683 | 21683 | 21683 | 21683 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1776856 | New | New_Built | RTP | 6 | 70 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.3591 | 76.9452 | R/NN-566961 | 2021-02-24 | 2021-12-03 | 2022-01-18 | [16 empty] | 2022-01-14 | ST202201010589 | S20220000629 |  |  | 2022-01-20 | P/FVC/DEL/1048369/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Safdarjung Enclave, New Delhi | South Delhi Municipal Corporation(SDMC),MBTS Location,Near House No.B-7/111B,& In Front Of JRD Luxury Bonquit Hotel,Safdarjung Enclave,New Delhi-110029 | 19655 | 19655 | 19655 | 19655 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1898323 | New | New_Built | Cow | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5581 | 77.2002 | R/NN-569998 | 2021-04-06 | 2021-04-16 | 2021-04-26 | [16 empty] | 2021-01-11 | ST202101007920 | S20210000477 |  |  | 2021-01-18 | P/FVC/DEL/1016511/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Daulat Ram College | - | 15139 | 15139 | 15139 | 15139 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL47 | New | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6877 | 77.2091 | 15139 | 2021-08-27 | 2022-03-01 | 2022-03-01 | [16 empty] | 2022-03-14 | ST202203071686 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051670/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Govindpuri(Relocation of 2839) | Ms. Mohini W/O Mr. Dinesh,House Number - 1139B,Gali Number - 11,Govindpuri,Post Office - Kalka Ji,Police Station - Govvindpuri, New Delhi, Delhi 110019 | 20639 | 20639 | 20639 | 20639 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20639_DEL | Relocation | New_Built | RTT | 9 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5348 | 77.2617 | 20639 | 2021-09-06 | 2021-09-17 | 2021-09-24 | [16 empty] | 2021-09-24 | ST202109531878 | S20210030334 |  |  | 2021-09-28 | P/FVC/DEL/1042300/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Model Town Delhi | Municipal Corporation of Delhi (MCD),GBM Location,Infront of tree no - 166, and near Indraprastha Gas Limited (IGL) piler no - 155216, behind side gate no - 1, of vallabhbhai patel chest institute (VPCI), delhi university , vijay nagar marg, art faculty, university enclave, delhi 110007 | 21181 | 21181 | 21181 | 21181 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3001992 | New | New_Built | Cow | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6916 | 77.2084 | R/NN-625366 | 2021-07-05 | 2021-07-21 | 2021-07-27 | [16 empty] | 2021-07-30 | ST202107402574 | S20210013993 |  |  | 2021-08-04 | P/FVC/DEL/1037092/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-3,Gr. Noida | - | 21399 | 21399 | 21399 | 21399 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | STTSPL026 | New | New_Built | RTP | 6 | 15 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5766 | 77.4628 | 21399 | 2021-08-27 | - | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050912 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050292/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Gangaram Hospital New Block | House No 23/12. Old Rajinder nagar New Delhi-110060 | 19559 | 19559 | 19559 | 19559 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Infinite | NA | New | New_Built | RTT | 6 | 19 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6383 | 77.1867 | 19559 | 2021-01-20 | 2021-02-06 | 2021-02-09 | [16 empty] | 2021-01-01 | ST202101000202 | S20210000003 |  |  | 2021-01-13 | P/FVC/DEL/1015686/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Tikona Park (Relocation of 9247) | Shri Ram Janki Mandir Trust ,Plot No 112 ,Vijay Ghat ,Raj Gaht ,Chandni Chowk,New Delhi 110002 | 16077 | 16077 | 16077 | 16077 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | - | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6579 | 77.2455 | 16077 | 2021-01-11 | 2021-01-14 | 2021-04-12 | [16 empty] | 2021-01-22 | ST202101020420 | S20210001323 |  |  | 2021-02-25 | P/FVC/DEL/1017943/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Dream Valley | Green Belt area,Infront of Amrapali Dream Valley, Greater Noida, Uttar Pradesh 201009 | 16159 | 16159 | 16159 | 16159 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1368375 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5979 | 77.4529 | R/NN-363011 | 2019-08-09 | 2019-09-06 | 2019-09-11 | [16 empty] | 2019-10-22 | 2019665340 | 2019665340 |  |  | 2019-12-18 | P/FVC/DEL/5909898/2019 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | SENIOR CIVIL SERVENT HOUSING SOEICTY | - | 15759 | 15759 | 15759 | 15759 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3098756 | New | New_Built | MBTS | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6354 | 77.2257 | R/NN-638046 | 2021-12-06 | 2021-12-21 | 2022-02-02 | [16 empty] | 2022-02-26 | ST202202055985 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050996/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | LNJP Hospital | Surgical block 7th floor LNJP HOSPITAL , New Delhi Gate ,JN Merg New Delhi, New Delhi-110002 | 16755 | 16755 | 16755 | 16755 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL117 | New | New_Built | RTP | 6 | 29 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6379 | 77.2385 | 16755 | 2021-08-27 | 2022-03-17 | 2022-03-17 | [16 empty] | 2022-03-22 | ST202203078551 | S20220003797 | [22 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Khatna Village(Relocation of 9324) | Veerpal Singh S/O Mahavir Singh,House Number 195,Near By Electricity Pole No.D1/22,Village Khatana Dhirkhera,Post Office - Jarcha,Police Station - Dadri,Uttar Pradesh 203207 | 21709 | 21709 | 21709 | 21709 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/8874 | Relocation | New_Built | GBM | 30 | 0 |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.5594 | 77.6022 | T21DL02476 | 2021-03-22 | 2021-09-06 | 2021-09-09 | [16 empty] | 2021-09-16 | ST202109522332 | S20210029835 |  |  | 2021-09-24 | P/FVC/DEL/1041980/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | KRISHNA MENON MARG | - | 19388 | 19388 | 19388 | 19388 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL143 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6092 | 77.2093 | 19388 | 2021-08-27 | - | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050920 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050295/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | R.K.PURAM-II, GRID SSTN | government land-BSES Rajdhani Power Limited,Customer care center/ Bigili Digi seva kendra , R.K. Puram Sector-I, Post Office-R K Puram, Police Station- R K Puram, New Delhi 110022 | 19915 | 19915 | 19915 | 19915 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | 0 | New | New_Built | MBTS | 6 | 30 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5679 | 77.1817 | - | 2022-02-08 | 2022-02-08 | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050930 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050298/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | suraj kund road(Relocation of 25571) | Government Land,Faridabad Authority,GBM Location,Pali road ,surajkund road,Police Station - Pali,Post Office - Pali,fariadabad-Gurgaon highway faridabad Haryana-121003 | 17269 | 17269 | 17269 | 17269 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NTGA-17269 | Relocation | New_Built | GBM | 0 | 30 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.427 | 77.2517 | 17269 | 2021-09-06 | 2021-09-24 | 2021-09-24 | [16 empty] | 2021-09-29 | ST202109538516 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042801/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Kaveri Hostel JNU campus | - | 15145 | 15145 | 15145 | 15145 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | 0 | New | New_Built | MBTS | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5461 | 77.1667 | - | 2022-02-10 | 2022-02-08 | 2022-02-08 | [16 empty] | 2022-02-21 | ST202202050931 | S20220002363 |  |  | 2022-02-25 | P/FVC/DEL/1050299/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Dasaborder(Relocation of 588) | Kiran w/o Mr.Ashok Dagar VPO Dhansa Village South West Delhi -110073 H.no.121 vpo dasa Village near dispensary New Delhi | 17767 | 17767 | 17767 | 17767 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/AT/8401 | Relocation | New_Built | GBM | 30 | - |  | ATC_LITE_POLE_SITE | ATC_LITE_POLE_SITE |  | YES | >18HRS | NO | 28.5561 | 76.8674 | T20DL00851 | 2020-01-30 | 2020-02-24 | 2020-02-24 | [16 empty] | 2020-02-29 | 2020398358 | 2020398358 |  |  | 2020-05-30 | P/FVC/DEL/6072324/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MBTS Rao Tula Marg Foot Over Bridge(Relocation of 27071) | Government Land, South Delhi Municipal Corporation( Foothpath), GBM Location Near Electric Light Pole number - 1/I3-SLl , & Arjun Path Bus Stand, Infront of Subroto Park Gate number - 1, Gurgaon - Delhi Expressway, Delhi Cantonment,Post Office - Rao Tularam Marg, South Campus, Shankar Vihar, Police Station - Vasant Vihar , Delhi - 110010 | 19812 | 19812 | 19812 | 19812 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NE_19812_Del | Relocation | New_Built | GBM | 0 | 30 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.575 | 77.1468 | 19812 | 2021-08-27 | 2021-10-07 | 2021-10-07 | [16 empty] | 2021-10-08 | ST202110554420 | S20210031332 |  |  | 2021-10-22 | P/FVC/DEL/1043936/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Pali (Relocation of 4363) | Sh. Dineshwar Tiwar S/o- Vashisht Tiwar Mobile No- 8447823728 Shiv Sankat Mochan Hanuman Mandir, Faridabad Gurgaon Road, Crusher Zone Pali Chowk Opp Police Chowki Pali Faridabad Haryana 121001 | 16888 | 16888 | 16888 | 16888 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/FRD/AT/9147 | Relocation | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.4101 | 77.2365 | - | 2022-02-25 | 2022-03-07 | 2022-03-17 | [16 empty] | 2022-03-22 | ST202203078545 | S20220003797 | [22 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Village Bishara | Saroj devi,Chakbandi No. 739, Ghata No. 181/P, Village Bishara, Pargana and Tehsil Dadri,Police Station - Jharcha,Post Office -Bisheda,Greater Noida,Uttar Pradesh-203207. | 13772 | 13772 | 13772 | 13772 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3013689 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5914 | 77.5756 | R/NN-626793 | 2021-08-04 | 2021-10-28 | 2021-11-11 | [16 empty] | 2021-11-12 | ST202111588382 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045812/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Spicejet Building_Apron_Airport T1(Relocation of 23904) | Spicejet Engineering, Near Fire Station 4, IGI Airport, New Delhi-110037 | 20716 | 20716 | 20716 | 20716 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1372503 | Relocation | Sharing | RTP | 6 | 8 |  | Indus_Lite+ | Indus_Lite+ | Sharing available | YES | >18HRS | NO | 28.5656 | 77.1138 | R/RES-430834 | 2020-10-14 | 2020-10-15 | 2020-10-17 | [16 empty] | 2020-10-20 | ST202010115956 | S20200006476 |  |  | 2020-12-06 | P/FVC/DEL/1011024/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | Indus |  | M1 | 3070 | [22 empty] | PRI | RFAI_Pending
Del | FY20_21 | Q4 | Block A, XU II, Greater Noida | Greater Noida Authority.Green Belt Greater Noida Authority,A-Block,Sector XU II,Near By Electric Office,Police Station Kasna,Post Office Kasna,Greater Noida,Uttar Pradesh- 203207. | 21922 | 21922 | 21922 | 21922 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3044057 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4721 | 77.5726 | R/NN-630165 | 2021-09-22 | 2022-01-13 | 2022-02-02 | [16 empty] | 2022-03-14 | ST202203071491 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051656/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | NEW_Ajanta Textiles-LNA | Mr. Fakir Chand S/o Late Ram Kishan Chauhan,House Number- 921, At- Gali Number- 1,New Kareda Colony, Near Hindon Airforce Station, Police Station - Hawai Adda, Post Office - Nistauli, Ghaziabad- 201004 | 21929 | 21929 | 21929 | 21929 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/DL/RJ/6268 | New | Sharing | RTP | 9 | 11.3 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.6881 | 77.3779 | T21DL03016 | 2021-09-22 | 2021-09-27 | 2021-10-18 | [16 empty] | 2021-10-23 | ST202110568678 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044614/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-14 Vaishali | Siddharth Niketan,Plot Number - 42,Sector - 14,Kaushambi, Vaishali,Police Station - Kaushambi,Post Office -Kaushambi,Ghaziabad Uttar Pradesh-201012 | 21932 | 21932 | 21932 | 21932 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | 457807 | New | Sharing | RTP | 9 | 9 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.6327 | 77.3291 | 13750432 | 2021-09-22 | 2021-11-23 | 2021-11-24 | [16 empty] | 2021-12-15 | ST202112617437 | S20210034867 |  |  | 2021-12-24 | P/FVC/DEL/1046929/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Harbans Nagar Colony, Ghaziabad | - | 21939 | 21939 | 21939 | 21939 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | GTL | DEL/RTT/K/20363 | New | Sharing | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6796 | 77.4228 | NA | 2021-09-22 | 2021-12-02 | 2021-12-07 | [16 empty] | 2021-12-13 | ST202112614868 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046018/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | BLOCK-C,VIKASPURI | Mr. Praveen Kumar,House Number - C-65,C Block Vikas Puri,Police Station - Vikaspuri,Post Office - Vikaspuri,New Delhi-110018 | 21962 | 21962 | 21962 | 21962 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3321 | New | Sharing | RTT | 12 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6319 | 77.0691 | SR-DL000195 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-11 | [16 empty] | 2021-11-12 | ST202111588369 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045804/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Yamuna Vihar | Mr.Vijay Prakash Gupta S/O Late Shri Ram Gupta,House Number - C-11/9,Block-C,Yamuna Vihar,Police Station - Bhajanpura,Post Office - Yamuna Vihar,Sahadara,Delhi-110053 | 21964 | 21964 | 21964 | 21964 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3684 | New | Sharing | RTT | 12 | 10.2 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.6978 | 77.2769 | SR-DL000207 | 2021-09-22 | 2021-11-20 | 2021-11-30 | [16 empty] | 2021-12-13 | ST202112614872 | S20210034722 |  |  | 2021-12-14 | P/FVC/DEL/1046021/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | ThANA ROAD, BHAJANPURA | Mr Chhatrpal Singh,House Number - C-188,Block C,Infront of House Number - C-9/248,Gali Number - 9,Thana Marg , Post Office - Bhajanpura,Police Station - Bhajanpura,Delhi - 110053 | 21965 | 21965 | 21965 | 21965 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-DLHI-ENB-3744 | New | Sharing | RTT | 15 | 8 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7002 | 77.2637 | SR-DL000197 | 2021-09-22 | 2021-09-30 12:42 | 2021-11-11 | [16 empty] | 2021-11-12 | ST202111588366 | S20210033187 |  |  | 2021-12-08 | P/FVC/DEL/1045802/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | D, Block D, Omicron III, Greater Noida | Greater Noida Authority.Green Belt Greater Noida Authority,D-Block,Sector Omnicorn III,Opposite D Block,Police Station Kasna,Post Office Kasna,Greater Noida,Uttar Pradesh- 203207. | 21976 | 21976 | 21976 | 21976 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3044087 | New | New_Built | GBM | 30 | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4818 | 77.5542 | R/NN-630182 | 2021-09-22 | 2022-01-13 | 2022-02-02 | [16 empty] | 2022-03-14 | ST202203071492 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051657/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Malviya Nagar(Relocation of 2846) | Mr. Jagbeer Chaudhary, House Number - B-1/4,Malviya Nagar Police station - Malviya Nagar,Post office- Malvia Nagar, New Delhi 110017 | 21981 | 21981 | 21981 | 21981 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | 451923 | Relocation | Sharing | RTP | 9 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Sharing available | YES | >18HRS | NO | 28.5366 | 77.2171 | 13750437 | 2021-09-22 | 2021-09-27 | 2021-10-18 | [16 empty] | 2021-10-23 | ST202110568679 | S20210032152 |  |  | 2021-11-14 | P/FVC/DEL/1044621/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Chattisgarh Bhawan(Relocation of 10058) | - | 21995 | 21995 | 21995 | 21995 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Protel Telepower Infrastructure Pvt LTd | PTIPL148 | Relocation | New_Built | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6024 | 77.1881 | - | 2021-09-22 | 2022-02-28 | 2022-02-28 | [16 empty] | 2022-03-14 | ST202203071682 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051666/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | GHATA MOREGGN-FBD LINK ROAD(Relocation of 25558) | - | 21996 | 21996 | 21996 | 21996 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL154 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.4367 | 77.1221 | - | 2021-09-22 | 2022-03-01 | 2022-03-01 | [16 empty] | 2022-03-14 | ST202203071685 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051669/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec 15 Fbd(Relocation of 18727) | Government Land,Faridabad Authority GBM Location,in Front of Pole Number - 73,Sector 15,Faridabad,Post Office - Sector 14,Police Station - Sector 14 Faridabad, Haryana 121007 | 27744 | 27744 | 27744 | 27744 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Olympians | R/18/F | Relocation | New_Built | GBM | 0 | 27 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.3984 | 77.3271 | 27744 | 2021-09-21 | 2021-09-24 | 2021-09-24 | [16 empty] | 2021-09-29 | ST202109538514 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042803/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Mohabbatabad Chungi(Relocation OF 25573) | Government Land,Faridabad Authority,GBM Location,Near Mohabaatabad Chungi,In Front Of NH 8,Police Station - Mangar,Post Office - Pali, Gurgaon-Faridabad Highway Faridabad Haryana 122003 | 27746 | 27746 | 27746 | 27746 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NTGA-27746 | Relocation | New_Built | GBM | 0 | 30 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.4085 | 77.2108 | 27746 | 2021-09-21 | 2021-09-24 | 2021-09-24 | [16 empty] | 2021-09-29 | ST202109538517 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042828/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MB Road(Relocation of 8098) | Government Land,GBM Location,Faridabad Authority,Nardan Basti,MST Marg,MB Road,Post Office - Hamdard Nagar,Police Station- Pul Pehladpur,District- South Delhi, New Delhi 110044 | 27748 | 27748 | 27748 | 27748 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Nibar/Nettel | NTGA-27748 | Relocation | New_Built | GBM | 0 | 30 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5061 | 77.2739 | 27748 | 2021-09-21 | 2021-09-24 | 2021-09-26 | [16 empty] | 2021-09-29 | ST202109540884 | S20210030587 |  |  | 2021-10-04 | P/FVC/DEL/1042802/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Logix Blossom Greens | Mrs.Jayvati W/o Mr.Deepchand,Khasra Number - 591,Village Garhi Shahdara,Sector 141,Near By Logix Blossom Greens,Police Station - Surajpur,Post Office - Mahrishi Nagar,Goutam Buddh Nagar,Noida,Uttar Pradesh- 201305. | 22013 | 22013 | 22013 | 22013 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3052586 | New | New_Built | RTT | 7 | 15 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.4986 | 77.4218 | R/NN-632772 | 2021-10-01 | 2021-10-01 | 2022-03-22 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Indira Gandhi Stadium(Relocation of 9655) | - | 22066 | 22066 | 22066 | 22066 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL158 | Relocation | New_Built | GBM | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6309 | 77.2523 | - | 2022-03-12 | 2022-03-12 | 2022-03-12 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MBTS DHOULA KUA(Relocation of 9845) | - | 22067 | 22067 | 22067 | 22067 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Protel Telepower Infrastructure Pvt LTd | PTIPL148 | Relocation | New_Built | RTT | - | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5973 | 77.1664 | - | 2021-11-18 | 2022-02-28 | 2022-02-28 | [16 empty] | 2022-03-14 | ST202203071683 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051667/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MBTS ISBT Kasmiri Gate(Relocation of 23879) | Government Land,GBM Location,Near House No.8/2-A,Jamna Road,Qudsiabag Park,ISBT Kasmiri Gate,Ward No.83-N,Police Station - Kasmiri Gate,Post Office - Kasmiri Gate,Delhi-110006 | 22069 | 22069 | 22069 | 22069 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | PTIPL43 | Relocation | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.671 | 77.231 | - | 2021-11-18 | 2022-02-03 | 2022-02-23 | [16 empty] | 2022-03-14 | ST202203071487 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051654/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MBTS Jor Bagh(Relocation of 25661) | Government Land,GBM Location,Near-Plot Number- J-1,Infront of Karbala Gate Jor Bagh Road, Civil Colony, Jorbagh,Police Station - Lodhi Colony,Post Office - Lodhi Road, New Delhi-110004 | 22070 | 22070 | 22070 | 22070 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept/Protel | NA | Relocation | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5857 | 77.2161 | - | 2021-11-18 | 2021-12-24 | 2022-01-13 | [16 empty] | 2022-01-31 | ST202202026006 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049209/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | MBTS Gujranwala town(Relocation of 27395) | Government Land,Property of Municipal Corporation of Delhi, GBM Location Behind side House Number - B-53, G.T Karnal Road, Ashok Vihar Flyover, Dilkhush Bagh Industrial Area, Ashok Vihar, Post Office - Ashok Vihar, Police Station - Ashok Vihar, Delhi - 110009 | 22071 | 22071 | 22071 | 22071 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3083660 | Relocation | New_Built | RTT | - | - |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6977 | 77.1839 | R/NN-636389 | 2021-11-18 | 2022-01-13 | 2022-02-02 | [16 empty] | 2022-02-26 | ST202202055989 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1050997/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | InterGlobe Aviation Ltd.("IndiGo") | InterGlobe Aviation Ltd.("IndiGo") C/O OBEROI FLIGHT SERVICES, INDIRA GANDHI INTERNATIONAL AIRPORT COMPLEX, Near Centaur Hotel, New Delhi- 110037 | 27762 | 27762 | 27762 | 27762 |  |  |  | L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | NA | New | New_Built | IBS | IBS | IBS |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5495 | 77.1076 | NA | 2021-11-08 | 2021-11-18 | 2021-11-30 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Bits N Bytes Soft Private Limited | First Floor, Plot No 11, Udyog Vihar, Phase 1, Gurgaon Haryana 122016. | 27766 | 27766 | 27766 | 27766 |  |  |  | G900_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | AIRTEL_27766_DEL_NT | New | New_Built | IBS | IBS | IBS |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5156 | 77.0798 | NA | 2021-11-29 | 2021-11-29 | 2021-11-29 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Chandani Mahal(Relocation of 1953) | Mrs. Shahina Begum W/o Mr. Mohd. Akhlaq,House Number - 468, GF,Gali Bahar Wali,Chhatta Lal Mian,Daryaganj,Post Office - Daryaganj,Police Station - Daryaganj,New Delhi 110002 | 22082 | 22082 | 22082 | 22082 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3104633 | Relocation | New_Built | RTP | 6 | 19 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6429 | 77.2368 | R/NN-639150 | 2021-12-06 | 2021-12-30 | 2022-01-18 | [16 empty] | 2022-01-18 | ST202201012975 | S20220000788 |  |  | 2022-01-25 | P/FVC/DEL/1048520/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Village.Haibaitpur | Mr Raj Kumar S/o Sh Kishan Lal, Khasra No.-172, Village-Haibatpur, Near Gaurcity, Dadari, Gautam Buddha Nagar,Post Office. Dadari,Police Station. Dadari,UP-201301 NOIDA | 22094 | 22094 | 22094 | 22094 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Brookfield | I-DL-NOID-ENB-4076 | New | sharing | GBM | 25 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6104 | 77.4185 | - | 2021-12-06 | 2021-12-23 | 2022-02-07 | [16 empty] | 2022-02-26 | ST202202056369 | S20220002616 |  |  | 2022-03-09 | P/FVC/DEL/1051025/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sector71 Noida(Relocation of9340) | Government Land Noida Authority,GBM Location,in Front of Pole Number - 05,Sector 71 A,Post Office - Sector 70,Police Station - Sector 70,Noida,Uttar Pradesh 201307 | 22166 | 22166 | 22166 | 22166 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3119107 | Relocation | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5922 | 77.3802 | R/NN-640651 | 2022-01-03 | 2022-01-07 | 2022-01-24 | [16 empty] | 2022-01-31 | ST202202025969 | S20220001291 |  |  | 2022-02-09 | P/FVC/DEL/1049199/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sector 126 Noida(Relocation of 21443) | Green Belt Adjoining Main Road, Raipur Khadar, Sector-126,Noida,Up- 201303 | 22186 | 22186 | 22186 | 22186 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3119774 | Relocation | sharing | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.5422 | 77.34 | R/RES-510023 | 2022-04-01 | 2022-04-01 | 2022-04-01 | [16 empty] | 2022-03-14 | ST202203071677 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051661/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI | RFAI_Pending
Del | FY20_21 | Q4 | Sehrwal Village Gurgaon X (Relocation of 5540) | Kh. No. 13/24/31, NH-8, Vill. Sarhaul, Gurgaon | 22219 | 22219 | 22219 | 22219 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | GTL | DEL/RTT/K/20133 | Relocation | sharing | RTT | 15 | 15 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.4878 | 77.0752 | NA | 2022-02-15 | 2022-03-17 | 2022-03-17 | [16 empty] | 2022-03-14 | ST202203071699 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051683/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Umang Winter Hills Sector-77 | Mr. Sandeep , Umang Winter Hills Sector-77 Gurugram, police station-Kherki Daula, Post office- Vatika, Gurugram, Haryana, 122004 | 22220 | 22220 | 22220 | 22220 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | infinite | ITSPL-DL-GRGN-206 | New | New_Built | RTP | 6 | 40.7 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.3813 | 76.9793 | - | 2022-01-29 | 2022-03-03 | 2022-03-03 | [16 empty] | 2022-03-03 | ST202203061272 | S20220002821 |  |  | 2022-03-14 | P/FVC/DEL/1051370/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Bhagirathi Vihar(Relocation of 20761) | Mohd. Yakub S/O Deen Mohd,Khasra Number - 1/1 Main Brijpuri Road,Mansingh Nagar,Old Mustafabad,Near Hans Bhawan,Police Station - Dayalpur,Post Office - Karawal Nagar,Delhi-110094 | 22239 | 22239 | 22239 | 22239 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3124430 | New | New_Built | RTT | 12 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.7104 | 77.2768 | R/NN-645690 | 2022-02-12 | 2022-03-22 | 2022-03-22 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Sec-75, Gardenia Gateway,Noida | Noida Authority,GBM Location,in Front Of Pole Number-5,Gardenia Gateway, Sector 75, Noida,Post office - Sector 50,Police Station - Sector 50 Noida Uttar Pradesh 201304 | 19255 | 19255 | 19255 | 19255 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Saral communication | STTSPL042 | New | New_Built | GBM | 30 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5746 | 77.3848 | 19255 | 2021-06-08 | 2022-03-03 | 2022-03-03 | [16 empty] | 2022-03-14 | ST202203071690 | S20220003350 |  |  | 2022-03-22 | P/FVC/DEL/1051674/2022 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Lotus Boulevard Espacia | NEAR-SBI REGIONAL BUSINESS OFFICE-6 SECTOR-100,BLOCK-C, NOIDA UTTAR PRADESH-201301 | 16829 | 16829 | 16829 | 16829 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Concept/Protel | 16829 | New | New_Built | Cow | 30 | - |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5417 | 77.366 | 16829 | 2021-05-30 | 2021-06-04 | 2021-07-04 | [16 empty] | 2021-07-09 | ST202107379589 | S20210012929 |  |  | 2021-07-16 | P/FVC/DEL/1035541/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Kapas Hera Estate (Relocation of 15089) | Green Area,GBM Location,Near Plot Number 889, Phase-I,Udyog Vihar, Sec-20,Post Office - Sec-19,Police Station - Udyog Vihar,Gurgaon, Haryana 122022 | 22242 | 22242 | 22242 | 22242 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3125375 | Relocation | New_Built | GBM | 0 | 30 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5178 | 77.0806 | R/NN-646222 | 2022-02-21 | 2022-03-22 | 2022-03-22 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | LIG Flats Sec 16B Dwarka | Mr. Anil Yadav S/O Sh. S.S Yadav,Roof of Flat number - 14,Studio Apartment,Aashirwad Residents Welfare Association (RWA), Sector 16 B, Pocket - B,Phase II,Dwarka ,Police Station - Sector 17 Dwarka,Post Office - Sector 16 Kakrola,Dwarka,New Delhi - 110078 | 17856 | 17856 | 17856 | 17856 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 17856 | New | New_Built | RTT | 9 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT | Other than Indus & ATC | YES | >18HRS | NO | 28.5993 | 77.0182 | 17856 | 2021-09-22 | 2021-10-05 | 2021-10-05 | [16 empty] | 2020-02-06 | 2020360465 | 2020360465 |  |  | 2020-03-04 | P/FVC/DEL/5984354/2020 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Rohini Sec-20 | Smt Asha Gola S/h. Ram Babu, Plot number - 3, Khasra number 669 & 670, Village Kirari Suleman Nagar, Karan Vihar, Post Office - Suleman Nagar, Police Station - Suleman Nagar, Delhi-110086, | 21205 | 21205 | 21205 | 21205 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3053155 | New | New_Built | GBM | 30 | 0 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7086 | 77.0656 | R/NN-618378 | 2021-03-23 | 2021-10-11 | 2021-10-16 | [16 empty] | 2021-10-20 | ST202110564524 | S20210031884 |  |  | 2021-11-13 | P/FVC/DEL/1044420/2021 | [18 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | Kajaria Ceramics Limited | J1/B1 EXT. MOHAN COOPEARTIVE IND. AREA MATHURA ROAD | 27784 | 27784 | 27784 | 27784 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | Airtel | New | NEW_BUILT | IBS | 0 | - |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5055 | 77.3001 | NA | 2022-03-08 | 2022-03-16 | 2022-03-26 | 111-2850-55773000 | 2022-04-15 | 2022-04-15 | 2022-04-15 | 2022-04-18 | [36 empty] | MO_Pending | IBS/N-male connector 7/8",IBS/Combiner-Combining 2 TRX for 2 Feed,Adapter Din(m)-N(F) | Ericsson/SCM | X | 2022-04-15 |  | Indus |  | M1 | 27423 | [5 empty] | 2022-04-15 | 2022-04-18 | Access Issue cleared on 18.04.22 | [14 empty] | RFAI | Saurav P
Del | FY20_21 | Q4 | MANKIND PHARMA PVT LTD | Plot No. 262, Okhla Phase - 3, New Delhi – 110020 | 27786 | 27786 | 27786 | 27786 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | AIRTEL | Airtel | New | New_Built | IBS | IBS | IBS |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5473 | 77.2692 | - | 2022-03-10 | 2022-03-16 | 2022-03-26 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI | RFAI_Pending
Del | FY20_21 | Q4 | THINK AND LEARN PRIVATE LIMITED | d 1 sec 3 NOIDA | 27789 | 27789 | 27789 | 27789 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | Airtel | New | New_Built | IBS | IBS | IBS |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.5819 | 77.3167 | - | 2022-03-16 | 2022-03-23 | 2022-03-23 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI_Pending | RFAI_Pending
Del | FY20_21 | Q4 | adardh nagar ram parkash kapoor | Mr.Ram Prakash Kapoor S/O Ram Swaroop Kapoor, House No.C-33,Block-C,Shankara Charya Road,Adarsh Nagar,Adarsh Nagar Police Station,Adarsh Nagar(Majlis Park)Post Office,Delhi-110033 | 20709 | 20709 | 20709 | 20709 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | front infratel | FIT_034 | New | New_Built | RTP | 9 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.7179 | 77.1744 | NA |  |  |  | 111-2871-79771744 | 2022-04-18 | 2022-04-18 | 2022-04-18 | [36 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Site wrong RFAIed by TOCO, Tower not installed | 3rd Party PRI | PRI_Without Material | 2022-04-18 |  | Indus |  | M1 | 901 | [5 empty] | 2022-04-18 |  | Survey Rejected; Site wrong RFAIed by TOCO, Tower not installed
Del | FY20_21 | Q4 | Dasna Village | Mr.Chand Mohmmad S/O Mr.Akhlak,Khasra Number - 3475,Ward Number - 12,Dasna,Police Station - Dasna,Post Office - Dasna,Ghaziabad,Uttar Pradesh-201001 | 22075 | 22075 | 22075 | 22075 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-3082767 | New | New_Built | RTT | 12 | 12 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6752 | 77.5193 | R/NN-636306 |  |  |  |  | 2022-04-18 | 2022-04-18 | 2022-04-18 | [36 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Access issue (GDA Notice) | Indus | PRI_Without Material | 2022-04-18 |  | Indus |  | M1 | 5742 | [5 empty] | 2022-04-18 |  | Survey Rejected; Access issue (GDA Notice)
Del | FY20_21 | Q4 | KASIYAM SIDDHARTHA VIHAR | Sh Nasir Ali, Plot No.-7A/26, Sector-7A, Siddharth Vihar, Ghaziabad,UP-201009 | 22097 | 22097 | 22097 | 22097 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-GZBD-ENB-9017 | New | New_Built | GBM | 25 | 0 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6543 | 77.4003 | NA |  |  |  | 11109.2865.43774002.CWIP-CL | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18 |  |  | 2022-04-19 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-21 | [28 empty] | PRI_Closed | I&C_Pending | Partial Installed | Jitender | X | 2022-04-18 |  | Indus |  | M1 | 9044 | [5 empty] | 2022-04-18 | 2022-04-18 | Survey Rejected; 03M climbing ladder at Tower required, Cable tray 2M required, Pole mounts need to shift
Del | FY20_21 | Q4 | Shiv Mandir Colony | Mr. Vrijvallabh Kaushik S/O Sh. Kanhiya Lal, Khasra Number - 14/3, Shiv Mandir Colony, Street Number - 7, Narela, Post Office - Narela, Police Station - Narela, Delhi - 110040. | 22115 | 22115 | 22115 | 22115 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | brookfield | I-DL-DLHI-ENB-9087 | New | New_Built | RTT | 15 | 7 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.8739 | 77.0796 | NA |  |  |  | 111.2887.39770796.CWIP-CL | 2022-04-18 | 2022-04-18 |  |  |  |  | 2022-04-19 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-21 | 2022-04-21 | [10 empty] | 2022-04-21 | [17 empty] | EMF_Pending |  | EMF_Pending | X | 2022-04-18 |  | Indus |  | M1 | 9972
Del | FY20_21 | Q4 | Chander Gar¦1¦ Link Road | Shri Pankaj Jain, 14/14 , Site-IV, Sahibabad, Vasundhara, Ghaziabad-201010, U.P | 21767 | 21767 | 21767 | 21767 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/9100 | New | New_Built | RTT | 9 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6632 | 77.3335 | NA |  |  |  | 11109-2866-31773334 | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-20 |  |  | 2022-04-20 | 2022-04-20 | [31 empty] | PRI_Closed | Material_In_Transit | 1027094 | Ericsson/SCM | X | 2022-04-19 |  |  |  | M1 | [6 empty] | 2022-04-19 | 2022-04-20 | Survey Rejected; 03M height deviation, Sub_Meter available for Power Supply
Del | FY20_21 | Q4 | Sector-62 Ballabgarh | Mr.Arvind Patel S/O Shri Gango Patel,House Number - 1694,Sector 62,Housing Board Colony,Ballabgarh,Police Station - Adarsh Nagar,Post Office - Faridabad,Faridabad,Haryana- 121004 | 21172 | 21172 | 21172 | 21172 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3021111 | New | New_Built | RTT | 15 | 6 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.3145 | 77.332 | R/NN-627485 |  |  |  | 11106-2831-44773320 | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-20 |  |  | 2022-04-20 | 2022-04-20 | [31 empty] | PRI_Closed | Material_In_Transit | 18557833 | Ericsson/SCM | X | 2022-04-19 |  |  |  | M1 | [6 empty] | 2022-04-19 | 2022-04-20 | Survey Rejected; 01M height deviation, Sub_Meter available for Power Supply
Del | FY20_21 | Q4 | Sangam vihar najafgarh | Hno.11,Khasra no 588,40 futta road sangam vihar najafgarh delhi-110043 | 19687 | 19687 | 19687 | 19687 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 19687 | New | New_Built | RTP | 9 | 12 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6026 | 76.9982 | NA |  |  |  | 111-2860-26769981 | 2022-04-19 | 2022-04-19 |  |  |  |  | 2022-04-19 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-21 | 2022-04-21 | [10 empty] | 2022-04-21 | [17 empty] | EMF_Pending |  | EMF_Pending | X | 2022-04-19 |  |  |  | M1
Del | FY20_21 | Q4 | Padam Nagar(Relocation of14369) | Mr. Muksad Khan ( Maneger), Roof of Water tank in Tower Number - 9A, Unity the Amaryllis, Gaushala Road Kishan Ganj, Karol Bagh, Post Office - Kishan Ganj, Police Station - Kishan Ganj, Delhi, 110006 | 22162 | 22162 | 22162 | 22162 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 22162 | New | New_Built | RTP | 6 | 45 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6615 | 77.1971 | NA |  |  |  | 111-2866-15771970 | 2022-04-19 | 2022-04-20 | 2022-04-20 | [36 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected @ 60M Lat-Long deviation, EB or DG Supply not available & Blockage issue at 150 degree | Airtel | PRI_Without Material | 2022-04-19 |  |  |  | M1 | [6 empty] | 2022-04-20 |  | Survey Rejected @ 60M Lat-Long deviation, EB or DG Supply not available & Blockage issue at 150 degree
Del | FY20_21 | Q4 | BLACKBOARD EDUCATION | B 136 sector 2 Noida | 27788 | 27788 | 27788 | 27788 |  |  |  | LPSC+DAS | New_Tower |  |  | LPSC+DAS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | Airtel | New | New_Built | IBS | IBS | IBS |  | PURE_IBS | PURE_IBS | IBS Site | YES | >18HRS | NO | 28.584 | 77.3134 | - | 2022-03-17 | 2022-03-24 | 2022-03-26 | [41 empty] | RFAI_Pending |  | RFAI_Pending | [5 empty] | M1 | [23 empty] | RFAI | RFAI_Pending

## Sheet3
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details | Resposibility |  | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
Del | FY20_21 | Q1 | JAWAHAR COLONY | 665/33,JAWAHAR COLONY,NEAR GURUDWARA ROAD,NIT,FARIDABAD-121005 | 23473 | 23473 | 23473 | 23473 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Nibar | 23473 | New | New_Built | RTM | 6 | 10 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.3617 | 77.2876 | 23473 | 2019-05-28 | 2019-12-24 | 2020-01-13 | [16 empty] | 2020-01-16 | 2020331387 | 2020331387 |  |  | 2020-05-11 | P/FVC/DEL/6030318/2020 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | Mukherjeepark(Relocation of 4121) | Hno. A-55, Khayala Road, Vishnu Garden, New Delhi 110018 | 21689 | 21689 | 21689 | 21689 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1364589 | New | New_Built | RTM | 10 | 12 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.6484 | 77.1035 | R/NN-339653 | 2019-06-01 | 2019-06-17 | 2019-06-26 | 111-2864-86771031 | [15 empty] | 2019-07-01 | 2019998099 | 2019998099 |  |  | 2019-07-19 | P/FVC/DEL/5722714/2019 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | ASHOK VIHAR PHASE 3 | Mr. Manoj Kumar S/O Inder Singh ,House No.161, Gali No-6, Block J, Ashok Vihar, Phase-3, Gurgaon-122001 | 19782 | 19782 | 19782 | 19782 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II_19782_DEL | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.4953 | 77.0268 | 19782 | 2021-05-13 | 2021-06-02 | 2021-06-13 | [16 empty] | 2021-06-16 | ST202106346577 | S20210011619 |  | 2021-07-08 | 2021-07-10 | P/FVC/DEL/1034034/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q2 | Park at 7.5 MGD Capacity UGR pumping station Sec-23 Rohini | GBM Green Belt opposite Abhilasha Appartment Rohini Sec-23 Delhi-110085 | 20238 | 20238 | 20238 | 20238 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-3000551 | New | New_Built | GBM | 25 |  |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.7199 | 77.0802 | R/NN-619742 | 2021-05-25 | 2021-06-03 | 2021-06-11 | [16 empty] | 2021-04-17 | ST202104151769 | S20210007098 |  |  | 2021-06-09 | P/FVC/DEL/1028603/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | DDA_sec-18 | D block Rohini sec 18 front of mcd barat ghar delhi-110089 | 13137 | 13137 | 13137 | 13137 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1383075 | New | New_Built | GBM | 30 |  |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.7383 | 77.1329 | R/NN-420815 | 2020-04-08 | 2020-06-24 | 2020-07-08 | [16 empty] | 2019-10-24 | 2019664981 | 2019664981 |  |  | 2019-12-18 | P/FVC/DEL/5910191/2019 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q2 | Loni | F-A/173, Lajpat Nagar, Sahibabad, Ghaziabad-201005 | 20369 | 20369 | 20369 | 20369 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1405488 | New | New_Built | RTM | 15 | 7 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.683 | 77.3666 | R/NN-467238 | 2020-09-21 | 2020-10-20 | 2020-10-23 | [16 empty] | 2020-06-23 | ST202007018550 | S20200001310 |  |  | 2020-07-10 | P/FVC/DEL/1001728/2020 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | Marium Nagar Gbd(Relocation of 5057) | House No.209,Subhash Nagar,Ghookna, Ghaziabad,Uttar Pradesh-201001 | 19259 | 19259 | 19259 | 19259 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-GZBD-149 | New | New_Built | RTP | 9 | 9.7 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6847 | 77.4177 | 19259 | 2020-11-19 | 2020-11-29 | 2021-02-09 | [16 empty] | 2021-02-05 | ST202102039762 | S20210002332 |  |  | 2021-02-28 | P/FVC/DEL/1018785/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | Hari Nagar-2 | Mr Amar Singh S/o Sh Harkesh Meena ,House number - B-40,Gali number - 8,Hari nagar,Part 2, Jaitpur,South Delhi - 110044, | 19668 | 19668 | 19668 | 19668 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | II_19668_DEL | New | New_Built | RTP | 6 | 14 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.5024 | 77.3174 | 19668 | 2021-05-13 | 2021-06-02 | 2021-06-05 | [16 empty] | 2021-06-04 | ST202106322611 | S20210010900 |  |  | 2021-06-27 | P/FVC/DEL/1032888/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q4 | Site 4, Sahibabad, Ghaziabad | Branch.13/1&15/1,site iv the times of india press sahibabad U.P-201010 | 19666 | 19666 | 19666 | 19666 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | No | Ericsson | Ericsson | Ericsson | Airtel | AI_19666_DEL | New | New_Built | RTP | 9 | 12 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6604 | 77.3315 | 19666 | 2019-09-03 | 2021-06-14 | 2021-06-14 | [16 empty] | 2021-06-16 | ST202106346570 | S20210011619 |  | 2021-07-08 | 2021-07-29 | P/FVC/DEL/1036560/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | Nandgram, Ghukna, Ghaziabad | Plot No.D-17, Nandgram, Ghukna, Ghaziabad 201003 | 19677 | 19677 | 19677 | 19677 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1368296 | New | New_Built | GBM | 30 |  |  | INDUS_30M_GBT_OD_2T | INDUS_30M_GBT_OD_2T |  | YES | >18HRS | NO | 28.6893 | 77.4143 | R/NN-363051 | 2019-08-09 | 2019-08-23 | 2019-08-26 | [16 empty] | 2020-01-30 | 2020349095 | 2020349095 |  |  | 2020-04-28 | P/FVC/DEL/6011076/2020 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | Raj nagar Sec-20(Relocation of 10452) | H No-4/114,Saroj Rajora W/o M.C Rajora ,r,Ghaziabad ,UP,201002 | 13009 | 13009 | 13009 | 13009 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Infinite | ITSPL-DL-GZBD-166 | New | New_Built | RTP | 9 | 13 |  | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | NO | 28.6834 | 77.4434 | 13009 | 2020-11-19 | 2020-11-29 | 2020-12-13 | [16 empty] | 2020-12-09 | ST202012169528 | S20200009357 |  |  | 2020-12-13 | P/FVC/DEL/1012315/2020 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | SDMC_INFRONT OFYAMUNA COLONY,RANGPURI | NA | 13046 | 13046 | 13046 | 13046 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1375873 | New | New_Built | Cow | 30 |  |  | COW | COW |  | YES | >18HRS | NO | 28.5237 | 77.1454 | R/NN-383484 | 2020-01-14 | 2020-03-06 | 2020-03-17 | [16 empty] | 2020-03-21 | 2020524789 | 2020524789 |  |  | 2020-07-01 | P/FVC/DEL/6104019/2020 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q1 | Village-Nor Nagar, Raj Nagar Extn. | Khata No. 00744, Khasra No. 1181 Min., Village Noor Nagar, Near-SD Public School,Pargana Loni, Tehsil and District Ghaziabad-20100 | 17285 | 17285 | 17285 | 17285 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | No | Ericsson | Ericsson | Ericsson | Indus | IN-1377587 | New | New_Built | RTM | 12 | 8 |  | Indus_Lite+ | Indus_Lite+ |  | YES | >18HRS | NO | 28.7046 | 77.4346 | R/NN-396275 | 2020-02-12 | 2020-06-19 | 2020-06-22 | [16 empty] | 2020-07-10 | ST202007022382 | S20200001608 |  |  | 2020-07-18 | P/FVC/DEL/1002215/2020 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  | M1 | [24 empty] | RFAI_Pending
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details | Resposibility |  | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
Del | FY20_21 | Q1 | IP Marg, Near ITO | Near ITOFootpath, Near ITO Bus stop and Indian Institute of Public Administration, New Delhi-110002 | 20824 | 20824 | 20824 | 20824 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_Capacity | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1432970 | New | New_Built | Cow | 30 |  | 0/170/240 | COW | COW |  | YES | >18HRS | No | 28.63 | 77.2467 | R/NN-469465 | 2020-10-01 | 2020-10-20 | 2020-10-26 | 111.MDEL.2168598 | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2021-01-08 |  |  |  | 2021-01-10 | 2021-01-11 | [6 empty] | 2020-11-05 | ST202011135750 | S20200007597 |  |  | 2020-12-25 | P/FVC/DEL/1013727/2020 | [16 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Lat Long Shift_SR Drooped as per Indus_SRN Done | SR SP Dropped |  | Indus |  | M1 | 75 | [5 empty] | 2020-12-05 |  | Lat Long Shift_SR Drooped as per Indus_SRN Done | [14 empty] | Lat Long Shift_SR Drooped as per Indus_SRN Done | Indus | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRUS 4418
Del | FY20_21 | Q1 | Spicejet Building_Airport T1(Relocation of 23904) | Spicejet Engineering, Near Fire Station 4, IGI Airport, New Delhi-110037 | 20716 | 20716 | 20716 | 20716 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1372503 | Relocation | Sharing | RTP | 6 | 8 | 20/90/180/260 | STANDARD_PRODUCT | STANDARD_PRODUCT |  | YES | >18HRS | No | 28.5656 | 77.1138 | R/RES-430834 | 2020-10-14 | 2020-10-15 | 2020-10-17 | 111.MDEL.56771138 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-04 |  |  |  | 2021-02-04 | 2021-02-07 | [6 empty] | 2020-10-20 | ST202010115956 | S20200006476 |  |  | 2020-12-06 | P/FVC/DEL/1011024/2020 | [16 empty] | ACCESS_FAR_END | PRI_BEFORE_MS1 | Access Issue at Farend_3070 & Material removed by Frogcell_Site SRN Done | SR SP Dropped |  | Non INDUS |  | M1 | 3070 | [5 empty] | 2021-02-02 |  | Access Issue at Farend_3070 & Material removed by Frogcell | [14 empty] | Access Issue at Farend_3070 & Material removed by Frogcell_Site SRN Done | Farend PRI | 2G+FD+TD+L_2100 | 2G RRU 2219B0A FD RRU 2219B3 L-2100 RRU 12B1 TD RRUS 4418 Available on Parent site
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details | Resposibility |  | CTA | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
Del | FY20_21 | Q1 | MBTSDefence Colony | Chetna Marg, Opposite C-Block, Near C-327, Dabra Park, Defence Colony, New Delhi-110024 | 27432 | 27432 | 27432 | 27432 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Indus | IN-1382617 | New | New_Built | Cow | 30 |  | 0/120/250 | COW | COW |  | YES | >18HRS | No | 28.5694 | 77.2328 | R/NN-419365 | 2020-04-02 | 2020-09-14 | 2020-09-22 | 111.MDEL.2168600 | 2020-12-01 | 2020-12-02 | 2020-12-02 | 2020-12-16 |  |  |  | 2020-12-16 | 2020-12-16 | [6 empty] | 2020-09-29 | ST202009092452 | S20200005308 |  |  | 2020-10-06 | P/FVC/DEL/1007764/2020 | [16 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material Return_17.12.20,Site rejected by Toco_Planning has to Update SR SP tracker | Indus/Planning |  |  | Indus |  | M1 | 862 | [5 empty] | 2020-12-02 |  | Material Return_17.12.20 | [14 empty] | Material Return_17.12.20,Site rejected by Toco_Planning has to Update SR SP tracker | Indus/Planning | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRUS 4418
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details | Resposibility |  | CTA | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
Del | FY20_21 | Q4 | Sector 149, Noida | Mr. Nitin Lehra(Estate Manager),Golfshire Ace Group,Small Pole Location Opp Tower 1 (Flat No.1015 ),Plot No. SC - 01/A-5, Sector 150, Noida, Uttar Pradesh 201310 | 21294 | 21294 | 21294 | 21294 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | SC_21294_DEL | New | Sharing | RTP | 7 | 0 | 04 Sector | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.4387 | 77.4827 | 21294 | 2021-04-14 | 2021-07-06 | 2021-07-07 | 11109-2843-87774827 | 2021-09-06 | 2021-09-07 | 2021-09-07 | [12 empty] | 2021-07-09 | ST202107379566 | S20210012929 |  |  | 2021-07-16 | P/FVC/DEL/1035533/2021 | [16 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | VBW Antenna Not in Stock_Hold by Trilok and Ritesh | Trilok/Ritesh |  |  |  |  | M1 | [6 empty] | 2021-09-07 |  | Survey Rejected; OHS Issue and Cable tray required b/w 1-2 and 3-4 pole location, RRU and GSM pole mounts required,Issue closed on 24 Sep 21,HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 sep 21HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock & VBW Antenna Not in Stock,Hold by Trilonk on call 7th Oct 21 with Gaurav A | [14 empty] | VBW Antenna Not in Stock_Hold by Trilok and Ritesh | Trilok/Ritesh
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) |  | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details remarks | Resposibility |  | CTA | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
Del | FY20_21 | Q1 | Shahbad mohmmadpur | Khasra NO. 338/2, Village shahabad mohammadpur,New delhi,Pin-110061 | 20373 | 20373 | 20373 | 20373 | As On 18 Oct SR SP |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | #N/A | No | Ericsson | Ericsson | Ericsson | Indus | IN-1371615 | NEW | NEW_BUILT | RTP | 9 | 15 | 0/100/270 | Indus_Lite+ |  |  | YES | >18HRS | No | 28.5551 | 77.0752 | R/NN-372386 | 2019-10-18 | 2019-12-27 | 2020-01-15 | 111.MDEL.2072088 | 2020-06-29 | 2021-02-17 | 2020-06-30 | 2021-02-15 |  |  |  | 2021-02-17 | 2021-02-19 | [6 empty] | 2020-01-16 | 2020331372 | 2020331372 |  |  | 2020-05-11 | P/FVC/DEL/6030303/2020 | [16 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Public Issue/L2100 SACFA Rejected(Airport Area Site) | Indus/Planning |  | PRI | Indus |  | M1 | 238 | [5 empty] | 2020-06-30 |  | Public Issue(SRN Done) | [14 empty] | Public Issue/L2100 SACFA Rejected(Airport Area Site) | Indus/Planning | 2G+FD+TD+L_2100 | 2G RRU 2219 FD RRU 2219 TD RRUS 4418
Del | FY20_21 | Q4 | Gaur City -6 | Saya zion Tower No G Block E gaur city 1,sector 4 Gzb U.P-201009 | 17399 | 17399 | 17399 | 17399 | As On 18 Oct SR SP |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | #N/A | No | Ericsson | Ericsson | Ericsson | Airtel | AI_17399_DEL | New | New_Built | RTP | 6 | 61 | 60/130/240/300 | STANDARD_PRODUCT |  |  | YES | >18HRS | No | 28.6114 | 77.4241 | 17399 | 2021-01-25 | 2021-02-18 | 2021-02-26 | 11109-2861-13774240 | 2021-07-05 | 2021-07-06 | 2021-07-06 | [12 empty] | 2021-03-02 | ST202103075339 | S20210004046 |  |  | 2021-03-21 | P/FVC/DEL/1020368/2021 | [16 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Access Issue_Hold by Kushabh | Airtel |  | PRI | Indus |  | M1 | 1695 | [5 empty] | 2021-07-06 |  | Access Issue_Hold by Kushabh | [14 empty] | Access Issue_Hold by Kushabh | Airtel | 2G+FD+TD+L_2100 | 2G RRU 2219 ,(FD+L_2100) RRU 2279 TD RRU 4418
Del | FY20_21 | Q2 | Sangam Vihar-2 | Hno.C-297,Gali no 5,Sangam vihar,New delhi,110080 | 20144 | 20144 | 20144 | 20144 | As On 18 Oct SR SP |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | Yes | #N/A | No | Ericsson | Ericsson | Ericsson | Indus | IN-1010503 | New | Sharing | RTT | 15 | 10 | 90/250/340 | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.5022 | 77.2372 | R/RES-430511 | 2020-10-05 | 2020-10-15 | 2020-10-21 | 111-2850-21772372 | 2021-08-10 | 2021-08-11 | 2021-08-11 | [12 empty] | 2020-11-04 | ST202011134634 | S20200007565 |  |  | 2020-12-13 | P/FVC/DEL/1012173/2020 | [16 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | Survey Rejected; Pole mounts required | Indus |  | PRI | Indus |  | M1 | 5125 | [5 empty] | 2021-08-11 |  | Pole Mount required in all 3 sector | [14 empty] | Survey Rejected; Pole mounts required | Indus
Del | FY20_21 | Q2 | Vikaspuri | FG 1/67-C SF,Vikaspuri,New Delhi-110018 | 20213 | 20213 | 20213 | 20213 | As On 18 Oct SR SP |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | #N/A | No | Ericsson | Ericsson | Ericsson | Airtel | AI_20213_DEL | New | New_Built | RTT | 12 | 13 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.6427 | 77.0707 | 20213 | 2019-12-19 | 2021-02-02 | 2021-02-09 | [16 empty] | 2021-02-10 | ST202102048369 | S20210002677 |  |  | 2021-03-05 | P/FVC/DEL/1019252/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q2 | DDA_Akshardham Appt. Dwarka , Sec-19 | Mr. Deepak Guliya S/O Anup Guliya,House Number 1168, Akshardham Apartment,Dwarka Sec 19,Pocket 3,Dwarka South Police Station,Raj Nagar - II Post Office Delhi-110078 | 17099 | 17099 | 17099 | 17099 | As On 18 Oct SR SP |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | #N/A | No | Ericsson | Ericsson | Ericsson | Protel | PTIPL64 | New | New_Built | RTP | 6 | 16 |  | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.5847 | 77.0448 | 17099 | 2021-04-06 | 2021-06-30 | 2021-06-30 | [16 empty] | 2021-07-02 | ST202107370628 | S20210012660 |  |  | 2021-07-15 | P/FVC/DEL/1035089/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  |  | M1 | [24 empty] | RFAI_Pending
Del | FY20_21 | Q2 | EMCD_Mayur Vihar Phase 1 | EDMC GREEN BELT OPP 302 -A BLOCK MAVILLA APARTMENT GATE NO 2 BESIDES CHATAN JAIN MARG NEAR DELHI POLICE Apartment A-BLOCK PARKING MAYUR VIHAR Plot No 9,Mayur Vihar PH 1,Delhi-110091 | 27048 | 27048 | 27048 | 27048 | As On 18 Oct SR SP |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | Yes | #N/A | No | Ericsson | Ericsson | Ericsson | Prabhjass | PJDL010 | New | New_Built | GBT | 30 | 0 | 20/90/150 | STANDARD_PRODUCT |  |  | YES | >18HRS | NO | 28.6107 | 77.2861 | 27048 | 2020-05-02 | 2020-06-28 | 2021-01-25 | [16 empty] | 2021-01-22 | ST202101020421 | S20210001323 |  |  | 2021-02-25 | P/FVC/DEL/1017944/2021 | [17 empty] | RFAI_Pending |  | RFAI_Pending |  |  |  |  | M1 | [24 empty] | RFAI_Pending
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MS_ACCEPTED_WITH_EXCLUSION | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details remarks | Resposibility |  |  | Opening RFAI | List o 43 | CTA | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1 | SR_REJECTION_BY_TOCO_DATE | SP_REJECTION_BY_AIRTEL_DATE | SO_WITHDRAWN_BY_AIRTEL_DATE | SO_REJECTION_BY_TOCO_DATE | CGI_ID | TOTAL_NO_OF_PRI_DAYS_PRE_MS1 | TOTAL_NO_OF_PRI_DAYS_POST_MS1 | Site_Status_History | SITE_STATUS_UPDATE_DATE | Circle Remark 1 | Circle Remark 2 | Released technology | RRU
Del | FY20_21 | Q2 | Bhopura,Ghaziabad | HARENDER SINGH MAVI S/O BALJEET SINGH MAVI KHASRA NO. 631 PLOT NO E14-C/2 KRISHNA VIHAR BHOUPURA GHAZIABAD UTTAR PRADESH-201005 | 17164 | 17164 | 17164 | 17164 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/8240 | NEW | NEW_BUILT | GBT | 30 | 0 | 0/90/180/270 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | No | 28.7046 | 77.3381 | T20DL00091 | 2020-01-13 | 2020-05-03 | 2020-06-01 | 11109.MGBD.2065393 | 2020-06-11 | 2020-07-13 | 2020-06-12 | 2020-07-13 |  |  |  | 2020-07-14 | 2020-07-15 | [6 empty] | 2020-06-18 | ST202007018116 | S20200001291 |  |  | 2020-07-10 | P/FVC/DEL/1001584/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material SRN Done_21.06.21 after 7th times PRI attempt | ATC | #N/A |  |  |  |  | Indus |  | M1 | 4942 | [5 empty] | 2020-06-12 |  | Material SRN Done_21.06.21 after 7th times PRI attempt | [14 empty] | Material SRN Done_21.06.21 after 7th times PRI attempt | ATC | 2G+FD+TD_Ericsson | 2G RRU 2219 FD RRU 2219 TD RRUS 4418
Del | FY20_21 | Q2 | GAUR CITY-2 ,16 AVENUE,C-BLOCK | Plot No.B-85,Khasra No.115,Gram ChipyanaKhurd ,Gautam Buddah Nagar,Ghaziabad,Uttar Pradesh-201009 | 27042 | 27042 | 27042 | 27042 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | ATC | DL/GBN/AT/8428 | New | New_Built | RTP | 9 | 12 | 340/100/170 | ATC_LITE_POLE_SITE |  |  | YES | >18HRS | No | 28.6239 | 77.42 | T20DL01287 | 2020-01-30 | 2020-09-21 | 2020-09-22 | 11109.MGBD.2174423 | 2020-11-17 | 2020-11-18 | 2020-11-18 | 2020-12-10 |  |  |  | 2020-12-10 | 2020-12-11 | [6 empty] | 2020-09-23 | ST202009086526 | S20200004981 |  |  | 2020-10-01 | P/FVC/DEL/1007211/2020 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Material return on 12.12.20 | ATC | #N/A |  |  |  |  | Indus |  | M1 | 52 | [5 empty] | 2020-11-18 |  | Material return on 12.12.20 | [14 empty] | Material return on 12.12.20 | ATC | 2G+FD+TD+L_2100 | 2G RRU 2219 (FD+ L-2100 RRU 2279) TD RRUS 4418
Del | FY20_21 | Q3 | Khedi Bhanauta | H.No 303 ,Vill Kheri, Post Tilapta ,Dadri ,G.B Nagar UP 203207 | 19759 | 19759 | 19759 | 19759 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | 3G_INFRA | FIT_01 | New | New_Built | RTP | 9 | 14 | 120/230/300 | STANDARD_PRODUCT |  | 3RD_PARTY | YES | >18HRS | No | 28.5569 | 77.5076 | 19759 | 2019-12-06 | 2021-02-17 | 2021-02-20 | 11109.MGBD.69775076 | 2021-03-17 | 2021-03-18 | 2021-03-18 | 2021-07-13 |  |  |  | 2021-07-13 | 2021-07-14 | [6 empty] | 2021-02-18 | ST202102058250 | S20210003229 |  |  | 2021-03-09 | P/FVC/DEL/1019516/2021 | [17 empty] | ACCESS_NEAR_END | PRI_BEFORE_MS1 | Public Issue_Plan for Saturday & Sunday_again hold on 6th Aug 21(SRN Done on 29th Sep 21) | 3rd Party PRI | #N/A |  |  |  |  | Indus |  | M1 | 4492 | [5 empty] | 2021-03-18 |  | Material return on 05.05.21_Material Delivered with Toco & Public Issue reported on 15.07.21_Public Issue resolved on 04.08.21 as per Deepak Luthra(Plan on Saturday & Sunday) | [14 empty] | Public Issue_Plan for Saturday & Sunday_again hold on 6th Aug 21(SRN Done on 29th Sep 21) | 3rd Party PRI | 2G+FD+TD+L_2100 | 2G RRU 2219,(FD+L_2100) RRU 2279, TD RRU 4418
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE |  | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MS_ACCEPTED_WITH_EXCLUSION | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details remarks | Resposibility |  | Opening RFAI | CTA | FAR_END_TOCO | FAR_END_SR | TXN_CATEGORY(M0,M1,M2,M3) | MW_FAR_END_ID | MW_HOP_ID | MW_FAR_END_TOCO | RMO_NO | RMO_DATE | MATERIAL_RETURNED_DATE | PRE_MS1_PRI_OPENING_DATE | PRE_MS1_PRI_CLOSING_DATE | PRE_MS1_PRI_History | NO_OF_TIME_PRI_PRE_MS1 | POST_MS1_PRI_OPENING_DATE | POST_MS1_PRI_CLOSING_DATE | POST_MS1_PRI_History | NO_OF_TIME_PRI_POST_MS1
DEL | FY20_21 | Q1 | MBTS_Daulat Ram College | MBTS Location Near Front of Gate no 1,Daulat Ram College,Guru Tegh Bahadur Road,Delhi, 110007 | 27394 | 27394 | 27394 | 27394 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P1 | No | No | Ericsson | Ericsson | Ericsson | Concept | CO_27394_DEL | Relocation | NEW_BUILT | COW | 30 | 0 | 40/120/210/300 | COW |  | 3RD_PARTY | YES | >18HRS | No | 28.6886 | 77.2067 | 27394 | 2019-05-20 | 2019-06-17 | 2019-06-19 | 111.MDEL.1915287 | 2019-07-19 | 17 Feb 22 SR SP | 2019-10-04 | 2019-10-05 | [12 empty] | 2019-07-19 | 2019827633 | 2019827633 |  |  | 2019-08-21 | P/FVC/DEL/5767870/2019 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | MBTS Not installed | 3rd Party PRI | PRI_Without Material |  |  | Indus |  | M1 | 362 | [5 empty] | 2019-07-20 |  | MBTS Not installed
Del | FY20_21 | Q4 | Sector 149, Noida | Mr. Nitin Lehra(Estate Manager),Golfshire Ace Group,Small Pole Location Opp Tower 1 (Flat No.1015 ),Plot No. SC - 01/A-5, Sector 150, Noida, Uttar Pradesh 201310 | 21294 | 21294 | 21294 | 21294 |  |  |  | G900_L900_L1800_L2100_L2300 | New_Tower |  |  | MACRO_OUTDOOR | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Space_Telelink | STIPL-DEL-704 | New | Sharing | GBM | 30 | 0 | 04 Sector | SHARING |  | SHARING | YES | >18HRS | NO | 28.4387 | 77.4827 | 21294 | 2021-04-14 | 2021-07-06 | 2021-07-07 | 11109-2843-87774827 | 2021-09-06 | 17 Feb 22 SR SP | 2021-09-07 | 2021-09-07 | 2021-12-10 | [11 empty] | 2021-07-09 | ST202107379566 | S20210012929 |  |  | 2021-07-16 | P/FVC/DEL/1035533/2021 | [17 empty] | INFRA_NEAR_END | PRI_BEFORE_MS1 | TOCO will not provide Infra for 06port GSM so replanning would be done for ODSC instead of NT,Hold by trilok | Bharti Planning | PRI_Without Material |  |  |  |  | M1 | [6 empty] | 2021-09-07 |  | Survey Rejected; OHS Issue and Cable tray required b/w 1-2 and 3-4 pole location, RRU and GSM pole mounts required,Issue closed on 24 Sep 21,HOLD DUE TO MW POWER CONNECTOR NOT IN STOCK,Issue resolved on 28 sep 21HOLD DUE TO Ethernet Cable & U- Bolt & BBU6630 & SFP Not In Stock & VBW Antenna Not in Stock,Hold by Trilonk on call 7th Oct 21 with Gaurav A,Infra Issue as On 24.11.21,Issue closed on 10.12.21,TOCO will not provide Infra for 06port GSM so replanning would be done for ODSC instead of NT,Hold by trilok as on 11.12.21
CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | Site Name | Site Address | Physical Site Id | TECH_ID | 2G_SITE_ID | ENODEB_ID | CELL_ID | SECTOR | CELL_NAME | BAND | PROJECT | TD_CONF | L2100_CONF | BTS_TYPE | TOWN_CATEGORY | TOWN_NAME | SITE_TYPE | BUSINESS_PRIORITY | CTA(YES/NO) | USO(YES/NO) | OEM_NAME | Installation Partner | Integration Partner | TOCO_NAME | TOCO_ID | TYPE_OF_TENANCY | NOMINAL_TYPE | TOWER_TYPE | TOWER_HEIGHT | BUILDING_HEIGHT | SECTOR_AZIMUTH | PRODUCT_TYPE | PRODUCT_TYPE_PUNCHED_AS_PER_SR | REASON_FOR_NORMAL_PRODUCT | EB_AVAILABLE_(YES/NO) | EB_AVAILABILITY_FROM_SP | DG_REQUIRED | LATITUDE | LONGITUDE | SR_NO | SR_DATE | SP_DATE | SO_DATE | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | RFAI_Sign_OFF_Date | MRFAI Signoff Date | E_E_MEDIA_READY_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | SACFA_APPLIED_DATE_CIRCLE | SACFA_APPLIED_DATE_PORTAL | SACFA_APPLICATION_ID | SACFA_APPLICATION_NO | SACFA_HARD_COPY_SUBMISSION_DATE | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | INTEGRATION_DATE | EMF_SUBMISSION_DATE | EMF_Ack_No | SCFT Offered Date | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | SOA_PUSH_DATE | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | SOFT AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Performance AT Offered Date | PERFORMANCE_AT_ACCEPTANCE_DATE | MAPA_INCLUSION_DATE | MS_ACCEPTED_WITH_EXCLUSION | MRFS Signoff Date | TX_MEDIA_ON | PRI_CATEGORY_(ACCESS/INFRA) | CURRENT_STATUS_OF_SITE | Details remarks | Resposibility |  |  | Opening RFAI
Del | FY20_21 | Q4 | Delhi Metro Rail Corporation Ltd,lajpat nagar | Delhi Metro Rail Corporation Ltd,Office of Chief Project Manager-8 Opposite Frank Anthony Public School Near Metro Pillar No -40 Lajpat Rai Marg , Lajpat Nagar-IV New Delhi -110024 | 27771 | 27771 | 27771 | 27771 |  |  |  | L2300 | New_Tower |  |  | IBS | Urban | DELHI | URBAN_INFILL_COVERAGE | P0 | No | No | Ericsson | Ericsson | Ericsson | Airtel | 27771 | New | New_Built | IBS |  | 13 |  | Sharing |  |  | YES | >18HRS | NO | 28.5601 | 77.235 | NA | 2022-01-21 | 2022-02-12 | 2022-02-27 | 111-2856-12772349 | 2022-03-07 | 2022-03-08 | [5 empty] | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-11 | [29 empty] | Media_Pending | Installed/Media Issue | Shashank | #N/A | Media_Pending | 2022-03-07